## Instructions
Single Feature Forecaster or Throughput Forecaster
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
| 2 | 2018-01-17 | Refactored to support Excel 2007+ in all formulas
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). That's the odds of a coin-toss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for converting story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
About me….
I develop and teach how to use data in software development and operations teams for coaching or forecasting.
- Forecasting using Data workshop. Teach how to use these spreadsheets with practical hands-on examples based on your (and my) specific examples. Often run internally, sometimes publically.
- Data Driven Coaching workshop. Teach how to develop data driven approaches to improvement based on balancing multiple competing metrics. Often run internally, sometimes publically.
- Custom Dashboards or giving advice on your current dashboards. Take the next step in customizing our spreadsheets or deploying more advanced versions in Tableau or Power BI.
- Quantitative consulting or advice - give me a chance to answer something you need to know. I'll work with your teams in designing a prediction system or delivering a compelling visual demonstrting the issues.
Interested in chatting? Email me at troy.magennis@focusedobjective.com
Interested in stalking? Follow me on twitter @t_magennis
(best way to hear about new and improved spreadsheets like this)

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2019-01-01 |  |  |  |  | Likelihood | 2 weeks's | Date
[8 empty] | 100% | 11 | 2019-06-04
2. How many stories are remaining to be completed? | [7 empty] | 95% | 11 | 2019-06-04
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 10 | 2019-05-21
| Low guess |  | 108 |  | Highest guess |  | 108 | 85% | 10 | 2019-05-21
[8 empty] | 80% | 10 | 2019-05-21
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 10 | 2019-05-21
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 10 | 2019-05-21
| Low guess |  | 1 |  | Highest guess |  | 1 | 65% | 10 | 2019-05-21
[8 empty] | 60% | 10 | 2019-05-21
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 10 | 2019-05-21
[8 empty] | 50% | 9 | 2019-05-07
Throughput/velocity data or estimate is for |  |  |  | 2 weeks | 14 | days |  | 45% | 9 | 2019-05-07
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | 40% | 9 | 2019-05-07
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 35% | 9 | 2019-05-07
[8 empty] | 30% | 9 | 2019-05-07
[8 empty] | 25% | 9 | 2019-05-07
| Low guess |  | 8 |  | Highest guess |  | 16 | 20% | 9 | 2019-05-07
[8 empty] | 15% | 9 | 2019-05-07
[8 empty] | 10% | 9 | 2019-05-07
[8 empty] | 5% | 8 | 2019-04-23
[8 empty] | 0% | 8 | 2019-04-23
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 2 weekss |  | Result: Total Pre-split Stories in 6 2 weekss
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 61.95
[5 empty] | 85% | 65 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 84
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I16: Author: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks (hidden)
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 2 weeks's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 108
30% | 10 | 15 | Server performance issues | duration at 85th P | 10
15% | 5 | 10 | Layout issues when text localized | count per period | 10.8
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For example, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
3 | 1 | 3
5 | 1 | 5
2 | 2 | 2
1 | 1 | 1
5 | 2 | 6
3 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 6 | 3 | 3 | 0
|  |  | min | 1 | 1 | 2
|  |  | max | 5 | 5 | 5
|  |  | avg | 3.1667 | 3 | 3.3333 | -0.33333
|  |  | median | 3 | 3 | 3 | 0
|  |  | avg error |  |  |  | 0.33333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 8.333% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 3,5,2,1,5,3
|  |  | Data |  | 3 | 5 | 5 | 2 | 1 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="3.16666666666667" median="3">3,5,2,1,5,3</sip>
|  |  | Estimate |  | 12 | 11 | 15 | 12 | 14 | Distribution | <distribution name="dist" shape="fromSamples">3,5,2,1,5,3</distribution>
|  |  | Samples Or Data |  | 8 | 16 | 9 | 10 | 8
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many Samples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was captured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2019-04-23 | 26
[14 empty] | 2019-05-07 | 232
[14 empty] | 2019-05-21 | 215
[14 empty] | 2019-06-04 | 28
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 2 weekss | 8 2 weekss | 12 2 weekss | 16 2 weekss | 20 2 weekss | 24 2 weekss | 28 2 weekss | 32 2 weekss | 36 2 weekss | 40 2 weekss | 44 2 weekss | 48 2 weekss | 52 2 weekss
95% | 39 | 84 | 129 | 175 | 221 | 267 | 313 | 359 | 406 | 452 | 499 | 548 | 593
85% | 42 | 89 | 134 | 181 | 228 | 275 | 321 | 368 | 414.85 | 463 | 510.85 | 556 | 604
5% | 57 | 108 | 160 | 209 | 260 | 309 | 359 | 411 | 459 | 508.05 | 557 | 607 | 656.05
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Remaining Stories Actuals (hidden)
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2019-01-01 | 27
2019-01-15 | 25
2019-01-29 | 20
2019-02-12 | 19
2019-02-26
2019-03-12
2019-03-26
2019-04-09
2019-04-23
2019-05-07
2019-05-21
2019-06-04
2019-06-18
2019-07-02
2019-07-16
2019-07-30
2019-08-13
2019-08-27
2019-09-10
2019-09-24
2019-10-08
2019-10-22
2019-11-05
2019-11-19
2019-12-03
2019-12-17
2019-12-31
2020-01-14
2020-01-28
2020-02-11
2020-02-25
2020-03-10
2020-03-24
2020-04-07
2020-04-21
2020-05-05
2020-05-19
2020-06-02
2020-06-16
2020-06-30
2020-07-14
2020-07-28
2020-08-11
2020-08-25
2020-09-08
2020-09-22
2020-10-06
2020-10-20
2020-11-03
2020-11-17
2020-12-01
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings (hidden)
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2019-01-01 to 2020-12-29
1 | 9 | 2019-05-07 | 108 | 99 | 84 | 69 | 59 | 51 | 39 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 10 | 2019-05-21 | 108 | 93 | 81 | 71 | 61 | 50 | 40 | 32 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 10 | 2019-05-21 | 108 | 97 | 87 | 77 | 62 | 48 | 40 | 26 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 9 | 2019-05-07 | 108 | 93 | 78 | 69 | 57 | 43 | 33 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 9 | 2019-05-07 | 108 | 93 | 83 | 74 | 59 | 43 | 33 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 9 | 2019-05-07 | 108 | 99 | 85 | 70 | 59 | 49 | 41 | 26 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 8 | 2019-04-23 | 108 | 92 | 76 | 64 | 48 | 37 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 9 | 2019-05-07 | 108 | 97 | 84 | 69 | 61 | 53 | 41 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 8 | 2019-04-23 | 108 | 95 | 79 | 65 | 55 | 44 | 29 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 9 | 2019-05-07 | 108 | 96 | 84 | 72 | 59 | 45 | 35 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 10 | 2019-05-21 | 108 | 95 | 83 | 69 | 58 | 43 | 34 | 24 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 9 | 2019-05-07 | 108 | 99 | 87 | 75 | 66 | 56 | 40 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 9 | 2019-05-07 | 108 | 92 | 78 | 63 | 52 | 40 | 31 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 9 | 2019-05-07 | 108 | 95 | 80 | 66 | 52 | 39 | 29 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 10 | 2019-05-21 | 108 | 99 | 90 | 81 | 73 | 58 | 45 | 36 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 11 | 2019-06-04 | 108 | 98 | 90 | 79 | 67 | 59 | 50 | 35 | 19 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 9 | 2019-05-07 | 108 | 96 | 87 | 72 | 60 | 44 | 35 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 10 | 2019-05-21 | 108 | 93 | 82 | 74 | 61 | 53 | 39 | 31 | 16 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 10 | 2019-05-21 | 108 | 92 | 83 | 70 | 58 | 48 | 40 | 26 | 15 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 11 | 2019-06-04 | 108 | 99 | 87 | 76 | 67 | 52 | 39 | 31 | 23 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 9 | 2019-05-07 | 108 | 99 | 83 | 67 | 57 | 48 | 36 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 10 | 2019-05-21 | 108 | 93 | 79 | 66 | 56 | 44 | 35 | 25 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 9 | 2019-05-07 | 108 | 94 | 83 | 71 | 56 | 41 | 27 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 9 | 2019-05-07 | 108 | 95 | 84 | 76 | 65 | 49 | 35 | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 10 | 2019-05-21 | 108 | 96 | 85 | 76 | 61 | 53 | 38 | 30 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 10 | 2019-05-21 | 108 | 92 | 78 | 70 | 62 | 46 | 37 | 26 | 17 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 9 | 2019-05-07 | 108 | 94 | 83 | 67 | 57 | 49 | 35 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 11 | 2019-06-04 | 108 | 99 | 90 | 81 | 68 | 56 | 46 | 37 | 27 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 8 | 2019-04-23 | 108 | 94 | 80 | 65 | 49 | 37 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 10 | 2019-05-21 | 108 | 96 | 87 | 72 | 61 | 51 | 43 | 30 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 10 | 2019-05-21 | 108 | 93 | 83 | 73 | 60 | 51 | 43 | 29 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 10 | 2019-05-21 | 108 | 94 | 86 | 70 | 59 | 51 | 38 | 25 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 10 | 2019-05-21 | 108 | 99 | 88 | 80 | 64 | 53 | 45 | 37 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 10 | 2019-05-21 | 108 | 93 | 83 | 71 | 62 | 47 | 36 | 22 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 8 | 2019-04-23 | 108 | 92 | 76 | 64 | 50 | 38 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 8 | 2019-04-23 | 108 | 92 | 77 | 67 | 51 | 35 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 9 | 2019-05-07 | 108 | 94 | 85 | 77 | 68 | 54 | 39 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 10 | 2019-05-21 | 108 | 95 | 83 | 70 | 57 | 45 | 34 | 24 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 10 | 2019-05-21 | 108 | 94 | 86 | 77 | 64 | 53 | 44 | 28 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 10 | 2019-05-21 | 108 | 97 | 81 | 67 | 58 | 49 | 36 | 28 | 18 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 10 | 2019-05-21 | 108 | 98 | 88 | 72 | 60 | 49 | 40 | 30 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 9 | 2019-05-07 | 108 | 97 | 84 | 73 | 58 | 49 | 34 | 20 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 9 | 2019-05-07 | 108 | 92 | 78 | 64 | 55 | 39 | 27 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 10 | 2019-05-21 | 108 | 92 | 84 | 74 | 65 | 50 | 39 | 24 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 10 | 2019-05-21 | 108 | 99 | 84 | 73 | 59 | 46 | 38 | 29 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 10 | 2019-05-21 | 108 | 92 | 79 | 65 | 57 | 48 | 37 | 22 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 9 | 2019-05-07 | 108 | 96 | 81 | 73 | 64 | 50 | 40 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 9 | 2019-05-07 | 108 | 95 | 86 | 72 | 63 | 50 | 38 | 28 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 9 | 2019-05-07 | 108 | 97 | 82 | 70 | 58 | 46 | 30 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 10 | 2019-05-21 | 108 | 94 | 86 | 71 | 59 | 43 | 32 | 22 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 9 | 2019-05-07 | 108 | 94 | 85 | 74 | 62 | 51 | 37 | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 10 | 2019-05-21 | 108 | 96 | 82 | 74 | 62 | 47 | 39 | 31 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 9 | 2019-05-07 | 108 | 94 | 85 | 73 | 59 | 45 | 32 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 10 | 2019-05-21 | 108 | 95 | 86 | 75 | 62 | 54 | 40 | 24 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 9 | 2019-05-07 | 108 | 94 | 84 | 69 | 53 | 41 | 27 | 16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 10 | 2019-05-21 | 108 | 96 | 84 | 70 | 59 | 43 | 31 | 23 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 11 | 2019-06-04 | 108 | 95 | 86 | 77 | 67 | 58 | 49 | 41 | 30 | 20 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 9 | 2019-05-07 | 108 | 92 | 77 | 66 | 53 | 40 | 32 | 16 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 9 | 2019-05-07 | 108 | 92 | 82 | 70 | 60 | 48 | 39 | 26 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 10 | 2019-05-21 | 108 | 94 | 85 | 76 | 68 | 59 | 50 | 34 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 10 | 2019-05-21 | 108 | 99 | 88 | 76 | 68 | 54 | 45 | 34 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 11 | 2019-06-04 | 108 | 97 | 86 | 77 | 64 | 55 | 45 | 37 | 25 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 10 | 2019-05-21 | 108 | 97 | 86 | 70 | 59 | 51 | 43 | 27 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 10 | 2019-05-21 | 108 | 100 | 91 | 83 | 67 | 51 | 42 | 30 | 22 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 10 | 2019-05-21 | 108 | 100 | 88 | 80 | 66 | 56 | 42 | 29 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 10 | 2019-05-21 | 108 | 94 | 85 | 75 | 67 | 53 | 37 | 21 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 10 | 2019-05-21 | 108 | 93 | 83 | 74 | 61 | 50 | 41 | 32 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 9 | 2019-05-07 | 108 | 94 | 79 | 69 | 55 | 39 | 30 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 10 | 2019-05-21 | 108 | 99 | 89 | 73 | 59 | 51 | 35 | 25 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 8 | 2019-04-23 | 108 | 92 | 82 | 67 | 55 | 41 | 29 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 10 | 2019-05-21 | 108 | 98 | 84 | 73 | 62 | 52 | 41 | 26 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 10 | 2019-05-21 | 108 | 100 | 91 | 82 | 70 | 60 | 44 | 34 | 20 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 10 | 2019-05-21 | 108 | 95 | 85 | 76 | 64 | 55 | 46 | 37 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 11 | 2019-06-04 | 108 | 100 | 89 | 81 | 65 | 57 | 49 | 38 | 26 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 9 | 2019-05-07 | 108 | 92 | 77 | 68 | 53 | 40 | 28 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 9 | 2019-05-07 | 108 | 95 | 83 | 74 | 61 | 47 | 33 | 22 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 10 | 2019-05-21 | 108 | 100 | 89 | 73 | 61 | 48 | 40 | 31 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 9 | 2019-05-07 | 108 | 92 | 81 | 67 | 52 | 39 | 29 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 10 | 2019-05-21 | 108 | 92 | 84 | 74 | 59 | 49 | 36 | 25 | 16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 9 | 2019-05-07 | 108 | 96 | 87 | 75 | 65 | 51 | 35 | 24 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 8 | 2019-04-23 | 108 | 94 | 78 | 64 | 49 | 33 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 9 | 2019-05-07 | 108 | 99 | 91 | 76 | 66 | 53 | 37 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 11 | 2019-06-04 | 108 | 100 | 86 | 73 | 65 | 55 | 43 | 33 | 25 | 16 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 9 | 2019-05-07 | 108 | 93 | 83 | 72 | 63 | 50 | 38 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 10 | 2019-05-21 | 108 | 96 | 83 | 75 | 61 | 53 | 39 | 27 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 10 | 2019-05-21 | 108 | 98 | 88 | 73 | 57 | 42 | 33 | 22 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 11 | 2019-06-04 | 108 | 100 | 89 | 75 | 67 | 55 | 47 | 33 | 25 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 10 | 2019-05-21 | 108 | 100 | 91 | 81 | 73 | 61 | 50 | 40 | 27 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 11 | 2019-06-04 | 108 | 99 | 90 | 77 | 67 | 59 | 48 | 34 | 23 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 10 | 2019-05-21 | 108 | 99 | 89 | 80 | 71 | 63 | 50 | 37 | 28 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 9 | 2019-05-07 | 108 | 96 | 82 | 66 | 57 | 48 | 39 | 23 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 11 | 2019-06-04 | 108 | 98 | 88 | 74 | 66 | 55 | 45 | 36 | 25 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 10 | 2019-05-21 | 108 | 94 | 85 | 73 | 64 | 50 | 42 | 28 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 9 | 2019-05-07 | 108 | 94 | 82 | 70 | 54 | 42 | 34 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 9 | 2019-05-07 | 108 | 95 | 87 | 73 | 62 | 47 | 35 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 9 | 2019-05-07 | 108 | 97 | 82 | 70 | 54 | 43 | 29 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 9 | 2019-05-07 | 108 | 95 | 86 | 75 | 60 | 50 | 37 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 10 | 2019-05-21 | 108 | 99 | 84 | 75 | 67 | 54 | 41 | 32 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 8 | 2019-04-23 | 108 | 92 | 83 | 68 | 53 | 40 | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 8 | 2019-04-23 | 108 | 93 | 82 | 70 | 57 | 42 | 26 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 9 | 2019-05-07 | 108 | 97 | 83 | 72 | 57 | 41 | 30 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 9 | 2019-05-07 | 108 | 94 | 79 | 70 | 55 | 39 | 26 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 9 | 2019-05-07 | 108 | 95 | 86 | 72 | 62 | 49 | 35 | 24 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 9 | 2019-05-07 | 108 | 96 | 85 | 74 | 60 | 45 | 32 | 23 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 10 | 2019-05-21 | 108 | 96 | 80 | 70 | 57 | 45 | 34 | 24 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 10 | 2019-05-21 | 108 | 97 | 83 | 69 | 57 | 44 | 36 | 24 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 10 | 2019-05-21 | 108 | 95 | 79 | 71 | 60 | 51 | 39 | 29 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 9 | 2019-05-07 | 108 | 95 | 80 | 66 | 54 | 38 | 27 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 9 | 2019-05-07 | 108 | 96 | 80 | 64 | 49 | 40 | 30 | 15 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 9 | 2019-05-07 | 108 | 96 | 86 | 72 | 58 | 44 | 32 | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 8 | 2019-04-23 | 108 | 95 | 79 | 65 | 53 | 38 | 23 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 10 | 2019-05-21 | 108 | 94 | 79 | 70 | 58 | 48 | 35 | 27 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 10 | 2019-05-21 | 108 | 94 | 85 | 74 | 65 | 52 | 44 | 31 | 15 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 9 | 2019-05-07 | 108 | 100 | 85 | 69 | 60 | 51 | 36 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 9 | 2019-05-07 | 108 | 95 | 79 | 69 | 58 | 46 | 32 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 10 | 2019-05-21 | 108 | 98 | 86 | 72 | 63 | 55 | 47 | 36 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 9 | 2019-05-07 | 108 | 94 | 86 | 75 | 61 | 48 | 34 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 9 | 2019-05-07 | 108 | 95 | 81 | 68 | 55 | 47 | 34 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 9 | 2019-05-07 | 108 | 99 | 85 | 71 | 61 | 47 | 31 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 9 | 2019-05-07 | 108 | 92 | 81 | 67 | 54 | 42 | 32 | 16 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 10 | 2019-05-21 | 108 | 94 | 86 | 71 | 62 | 54 | 45 | 37 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 9 | 2019-05-07 | 108 | 94 | 78 | 70 | 61 | 47 | 39 | 26 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 9 | 2019-05-07 | 108 | 92 | 80 | 64 | 48 | 39 | 26 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 10 | 2019-05-21 | 108 | 92 | 80 | 70 | 60 | 50 | 39 | 31 | 22 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 9 | 2019-05-07 | 108 | 99 | 89 | 77 | 65 | 51 | 36 | 26 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 9 | 2019-05-07 | 108 | 95 | 86 | 72 | 56 | 46 | 32 | 20 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 10 | 2019-05-21 | 108 | 93 | 79 | 69 | 55 | 47 | 37 | 26 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 9 | 2019-05-07 | 108 | 98 | 84 | 70 | 61 | 45 | 31 | 22 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 10 | 2019-05-21 | 108 | 100 | 88 | 78 | 62 | 47 | 31 | 20 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 9 | 2019-05-07 | 108 | 96 | 83 | 75 | 59 | 48 | 34 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 9 | 2019-05-07 | 108 | 93 | 81 | 72 | 57 | 43 | 27 | 15 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 9 | 2019-05-07 | 108 | 97 | 83 | 67 | 59 | 45 | 34 | 21 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 10 | 2019-05-21 | 108 | 98 | 89 | 74 | 63 | 51 | 36 | 28 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 10 | 2019-05-21 | 108 | 94 | 84 | 76 | 61 | 48 | 34 | 24 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 9 | 2019-05-07 | 108 | 92 | 76 | 68 | 56 | 46 | 30 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 10 | 2019-05-21 | 108 | 100 | 87 | 71 | 62 | 51 | 38 | 29 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 10 | 2019-05-21 | 108 | 100 | 87 | 74 | 65 | 49 | 33 | 23 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 10 | 2019-05-21 | 108 | 98 | 87 | 73 | 59 | 47 | 38 | 27 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 10 | 2019-05-21 | 108 | 96 | 85 | 69 | 59 | 48 | 40 | 32 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 10 | 2019-05-21 | 108 | 100 | 90 | 78 | 62 | 49 | 38 | 24 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 9 | 2019-05-07 | 108 | 92 | 78 | 69 | 53 | 44 | 33 | 22 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 10 | 2019-05-21 | 108 | 97 | 86 | 77 | 61 | 51 | 39 | 29 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 9 | 2019-05-07 | 108 | 92 | 81 | 73 | 63 | 47 | 31 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 9 | 2019-05-07 | 108 | 96 | 84 | 73 | 62 | 46 | 34 | 23 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 9 | 2019-05-07 | 108 | 100 | 84 | 68 | 60 | 45 | 36 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 9 | 2019-05-07 | 108 | 95 | 82 | 70 | 56 | 40 | 31 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 10 | 2019-05-21 | 108 | 99 | 90 | 82 | 72 | 60 | 47 | 38 | 25 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 9 | 2019-05-07 | 108 | 97 | 84 | 71 | 57 | 49 | 34 | 22 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 10 | 2019-05-21 | 108 | 97 | 89 | 81 | 67 | 59 | 50 | 34 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 10 | 2019-05-21 | 108 | 92 | 83 | 73 | 63 | 54 | 44 | 32 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 10 | 2019-05-21 | 108 | 99 | 86 | 72 | 64 | 51 | 35 | 20 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 10 | 2019-05-21 | 108 | 95 | 82 | 69 | 56 | 46 | 36 | 28 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 9 | 2019-05-07 | 108 | 98 | 85 | 75 | 63 | 49 | 36 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 10 | 2019-05-21 | 108 | 93 | 84 | 74 | 58 | 46 | 35 | 22 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 8 | 2019-04-23 | 108 | 96 | 82 | 70 | 55 | 40 | 29 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 10 | 2019-05-21 | 108 | 92 | 84 | 73 | 62 | 48 | 40 | 25 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 10 | 2019-05-21 | 108 | 98 | 89 | 80 | 69 | 59 | 44 | 30 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 9 | 2019-05-07 | 108 | 100 | 91 | 82 | 71 | 56 | 45 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 10 | 2019-05-21 | 108 | 99 | 90 | 80 | 64 | 56 | 41 | 25 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 9 | 2019-05-07 | 108 | 96 | 85 | 76 | 65 | 51 | 38 | 24 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 9 | 2019-05-07 | 108 | 98 | 88 | 72 | 59 | 48 | 32 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 10 | 2019-05-21 | 108 | 96 | 85 | 77 | 61 | 53 | 38 | 24 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 10 | 2019-05-21 | 108 | 93 | 84 | 70 | 60 | 52 | 44 | 32 | 16 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 10 | 2019-05-21 | 108 | 95 | 84 | 69 | 61 | 50 | 37 | 25 | 16 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 10 | 2019-05-21 | 108 | 96 | 84 | 76 | 64 | 51 | 43 | 34 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 9 | 2019-05-07 | 108 | 94 | 79 | 65 | 53 | 43 | 27 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 9 | 2019-05-07 | 108 | 94 | 85 | 69 | 53 | 38 | 29 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 10 | 2019-05-21 | 108 | 94 | 80 | 65 | 51 | 40 | 30 | 22 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 9 | 2019-05-07 | 108 | 95 | 82 | 69 | 55 | 44 | 30 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 11 | 2019-06-04 | 108 | 97 | 88 | 78 | 63 | 52 | 39 | 30 | 22 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 10 | 2019-05-21 | 108 | 100 | 91 | 83 | 68 | 59 | 50 | 35 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 10 | 2019-05-21 | 108 | 97 | 81 | 72 | 62 | 48 | 38 | 22 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 10 | 2019-05-21 | 108 | 99 | 89 | 73 | 63 | 53 | 43 | 34 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 8 | 2019-04-23 | 108 | 95 | 80 | 66 | 52 | 38 | 27 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 9 | 2019-05-07 | 108 | 96 | 88 | 75 | 60 | 46 | 34 | 23 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 10 | 2019-05-21 | 108 | 98 | 83 | 73 | 65 | 51 | 38 | 30 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 9 | 2019-05-07 | 108 | 95 | 86 | 70 | 57 | 46 | 30 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 9 | 2019-05-07 | 108 | 96 | 88 | 72 | 64 | 52 | 37 | 23 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 10 | 2019-05-21 | 108 | 99 | 90 | 74 | 61 | 51 | 36 | 22 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 9 | 2019-05-07 | 108 | 97 | 88 | 72 | 56 | 43 | 35 | 23 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 11 | 2019-06-04 | 108 | 98 | 90 | 81 | 70 | 61 | 49 | 39 | 29 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 9 | 2019-05-07 | 108 | 93 | 81 | 68 | 60 | 51 | 37 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 11 | 2019-06-04 | 108 | 98 | 82 | 71 | 63 | 54 | 43 | 35 | 25 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 9 | 2019-05-07 | 108 | 92 | 77 | 66 | 52 | 43 | 27 | 19 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 9 | 2019-05-07 | 108 | 98 | 88 | 72 | 58 | 43 | 33 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 9 | 2019-05-07 | 108 | 99 | 86 | 77 | 62 | 47 | 39 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 9 | 2019-05-07 | 108 | 92 | 76 | 64 | 52 | 37 | 24 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 10 | 2019-05-21 | 108 | 100 | 89 | 74 | 65 | 54 | 43 | 35 | 25 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 9 | 2019-05-07 | 108 | 94 | 79 | 71 | 58 | 44 | 30 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 10 | 2019-05-21 | 108 | 93 | 85 | 77 | 64 | 49 | 35 | 24 | 12 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 9 | 2019-05-07 | 108 | 94 | 84 | 68 | 56 | 45 | 29 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 9 | 2019-05-07 | 108 | 93 | 77 | 67 | 52 | 41 | 29 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 8 | 2019-04-23 | 108 | 92 | 76 | 65 | 53 | 44 | 31 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 9 | 2019-05-07 | 108 | 92 | 76 | 67 | 57 | 47 | 34 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 9 | 2019-05-07 | 108 | 99 | 83 | 67 | 57 | 44 | 30 | 16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 10 | 2019-05-21 | 108 | 98 | 85 | 77 | 63 | 50 | 41 | 25 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 9 | 2019-05-07 | 108 | 99 | 86 | 75 | 59 | 43 | 27 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 9 | 2019-05-07 | 108 | 93 | 78 | 64 | 54 | 42 | 26 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 10 | 2019-05-21 | 108 | 92 | 78 | 69 | 60 | 51 | 41 | 30 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 9 | 2019-05-07 | 108 | 98 | 86 | 77 | 67 | 54 | 39 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 10 | 2019-05-21 | 108 | 97 | 86 | 72 | 63 | 54 | 44 | 28 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 9 | 2019-05-07 | 108 | 96 | 84 | 73 | 62 | 48 | 35 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 9 | 2019-05-07 | 108 | 94 | 79 | 64 | 56 | 40 | 25 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 10 | 2019-05-21 | 108 | 97 | 85 | 75 | 59 | 44 | 34 | 26 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 10 | 2019-05-21 | 108 | 100 | 85 | 70 | 59 | 49 | 40 | 31 | 21 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 10 | 2019-05-21 | 108 | 99 | 91 | 77 | 65 | 55 | 41 | 26 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 10 | 2019-05-21 | 108 | 96 | 88 | 79 | 70 | 61 | 53 | 42 | 27 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 9 | 2019-05-07 | 108 | 97 | 86 | 75 | 59 | 48 | 32 | 16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 9 | 2019-05-07 | 108 | 94 | 80 | 70 | 54 | 45 | 29 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 10 | 2019-05-21 | 108 | 99 | 87 | 75 | 59 | 47 | 37 | 26 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 9 | 2019-05-07 | 108 | 97 | 87 | 75 | 65 | 50 | 38 | 23 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 10 | 2019-05-21 | 108 | 97 | 84 | 76 | 66 | 52 | 42 | 30 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 9 | 2019-05-07 | 108 | 93 | 82 | 66 | 52 | 38 | 26 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 9 | 2019-05-07 | 108 | 100 | 86 | 78 | 62 | 51 | 43 | 28 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 10 | 2019-05-21 | 108 | 99 | 90 | 76 | 61 | 45 | 31 | 22 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 11 | 2019-06-04 | 108 | 95 | 87 | 77 | 65 | 53 | 44 | 32 | 21 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 9 | 2019-05-07 | 108 | 94 | 79 | 68 | 55 | 42 | 31 | 16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 10 | 2019-05-21 | 108 | 95 | 84 | 74 | 59 | 47 | 36 | 24 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 10 | 2019-05-21 | 108 | 95 | 82 | 67 | 56 | 48 | 34 | 23 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 9 | 2019-05-07 | 108 | 99 | 88 | 74 | 63 | 49 | 36 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 10 | 2019-05-21 | 108 | 97 | 85 | 72 | 61 | 47 | 33 | 23 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 11 | 2019-06-04 | 108 | 99 | 91 | 81 | 65 | 53 | 45 | 34 | 26 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 9 | 2019-05-07 | 108 | 98 | 83 | 70 | 59 | 43 | 27 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 10 | 2019-05-21 | 108 | 93 | 81 | 71 | 58 | 48 | 33 | 25 | 16 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 10 | 2019-05-21 | 108 | 100 | 86 | 73 | 65 | 57 | 44 | 34 | 23 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 10 | 2019-05-21 | 108 | 100 | 89 | 81 | 67 | 53 | 39 | 24 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 10 | 2019-05-21 | 108 | 97 | 87 | 75 | 64 | 50 | 41 | 26 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 10 | 2019-05-21 | 108 | 98 | 86 | 72 | 57 | 49 | 33 | 25 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 10 | 2019-05-21 | 108 | 98 | 85 | 75 | 64 | 56 | 44 | 33 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 10 | 2019-05-21 | 108 | 97 | 89 | 75 | 63 | 51 | 42 | 33 | 19 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 9 | 2019-05-07 | 108 | 99 | 84 | 69 | 61 | 47 | 34 | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 9 | 2019-05-07 | 108 | 97 | 82 | 71 | 60 | 47 | 33 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 10 | 2019-05-21 | 108 | 99 | 83 | 70 | 56 | 42 | 34 | 22 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 9 | 2019-05-07 | 108 | 95 | 84 | 68 | 56 | 42 | 29 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 9 | 2019-05-07 | 108 | 97 | 84 | 76 | 66 | 52 | 38 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 9 | 2019-05-07 | 108 | 100 | 86 | 72 | 57 | 46 | 31 | 22 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 10 | 2019-05-21 | 108 | 98 | 88 | 78 | 65 | 54 | 43 | 31 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 11 | 2019-06-04 | 108 | 99 | 88 | 78 | 70 | 58 | 47 | 37 | 22 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 9 | 2019-05-07 | 108 | 99 | 83 | 71 | 56 | 40 | 25 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 9 | 2019-05-07 | 108 | 98 | 85 | 72 | 62 | 48 | 33 | 24 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 10 | 2019-05-21 | 108 | 96 | 84 | 76 | 66 | 50 | 36 | 25 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 9 | 2019-05-07 | 108 | 97 | 88 | 73 | 62 | 48 | 35 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 10 | 2019-05-21 | 108 | 100 | 92 | 77 | 61 | 52 | 42 | 29 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 9 | 2019-05-07 | 108 | 96 | 82 | 69 | 54 | 39 | 23 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 10 | 2019-05-21 | 108 | 99 | 83 | 75 | 64 | 55 | 41 | 33 | 24 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 9 | 2019-05-07 | 108 | 97 | 81 | 66 | 54 | 41 | 25 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 10 | 2019-05-21 | 108 | 100 | 92 | 76 | 62 | 52 | 41 | 25 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 9 | 2019-05-07 | 108 | 93 | 84 | 70 | 56 | 42 | 28 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 10 | 2019-05-21 | 108 | 97 | 89 | 78 | 65 | 54 | 42 | 32 | 23 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 10 | 2019-05-21 | 108 | 92 | 80 | 69 | 61 | 52 | 40 | 32 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 9 | 2019-05-07 | 108 | 97 | 87 | 73 | 59 | 43 | 30 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 10 | 2019-05-21 | 108 | 99 | 84 | 70 | 60 | 50 | 37 | 29 | 21 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 11 | 2019-06-04 | 108 | 98 | 88 | 77 | 64 | 56 | 48 | 37 | 29 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 9 | 2019-05-07 | 108 | 99 | 84 | 70 | 57 | 43 | 27 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 8 | 2019-04-23 | 108 | 93 | 79 | 64 | 48 | 32 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 9 | 2019-05-07 | 108 | 94 | 81 | 72 | 56 | 41 | 26 | 18 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 10 | 2019-05-21 | 108 | 98 | 82 | 72 | 63 | 55 | 47 | 38 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 10 | 2019-05-21 | 108 | 98 | 86 | 77 | 62 | 51 | 40 | 32 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 8 | 2019-04-23 | 108 | 96 | 81 | 69 | 53 | 39 | 25 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 9 | 2019-05-07 | 108 | 99 | 88 | 76 | 61 | 49 | 37 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 9 | 2019-05-07 | 108 | 95 | 83 | 73 | 64 | 50 | 38 | 24 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 11 | 2019-06-04 | 108 | 100 | 88 | 76 | 68 | 59 | 51 | 35 | 22 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 10 | 2019-05-21 | 108 | 99 | 88 | 72 | 60 | 47 | 37 | 28 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 9 | 2019-05-07 | 108 | 96 | 84 | 75 | 64 | 49 | 38 | 29 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 10 | 2019-05-21 | 108 | 99 | 83 | 71 | 63 | 51 | 38 | 30 | 22 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 9 | 2019-05-07 | 108 | 92 | 80 | 64 | 53 | 42 | 27 | 13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 9 | 2019-05-07 | 108 | 94 | 81 | 66 | 56 | 42 | 26 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 9 | 2019-05-07 | 108 | 95 | 83 | 69 | 53 | 37 | 24 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 10 | 2019-05-21 | 108 | 92 | 81 | 71 | 60 | 52 | 41 | 26 | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 9 | 2019-05-07 | 108 | 94 | 80 | 66 | 54 | 46 | 38 | 29 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 8 | 2019-04-23 | 108 | 94 | 82 | 67 | 54 | 38 | 24 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 10 | 2019-05-21 | 108 | 97 | 82 | 72 | 63 | 53 | 43 | 32 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 9 | 2019-05-07 | 108 | 98 | 88 | 73 | 62 | 51 | 39 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 10 | 2019-05-21 | 108 | 95 | 85 | 74 | 61 | 47 | 34 | 24 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 9 | 2019-05-07 | 108 | 99 | 85 | 71 | 57 | 48 | 33 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 10 | 2019-05-21 | 108 | 99 | 87 | 72 | 63 | 50 | 39 | 26 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 8 | 2019-04-23 | 108 | 98 | 82 | 72 | 58 | 42 | 26 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 9 | 2019-05-07 | 108 | 95 | 85 | 71 | 59 | 47 | 34 | 22 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 11 | 2019-06-04 | 108 | 97 | 83 | 74 | 59 | 50 | 41 | 33 | 23 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 10 | 2019-05-21 | 108 | 97 | 89 | 74 | 62 | 48 | 39 | 30 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 10 | 2019-05-21 | 108 | 92 | 78 | 63 | 54 | 44 | 34 | 24 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 10 | 2019-05-21 | 108 | 93 | 77 | 67 | 59 | 45 | 34 | 25 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 11 | 2019-06-04 | 108 | 95 | 83 | 73 | 62 | 52 | 43 | 35 | 23 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 11 | 2019-06-04 | 108 | 95 | 87 | 78 | 68 | 54 | 43 | 31 | 21 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 10 | 2019-05-21 | 108 | 95 | 84 | 70 | 59 | 51 | 43 | 32 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 10 | 2019-05-21 | 108 | 100 | 92 | 79 | 68 | 52 | 41 | 26 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 11 | 2019-06-04 | 108 | 99 | 90 | 79 | 71 | 62 | 49 | 40 | 32 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 9 | 2019-05-07 | 108 | 96 | 81 | 72 | 58 | 43 | 35 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 9 | 2019-05-07 | 108 | 92 | 76 | 60 | 52 | 41 | 29 | 16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 10 | 2019-05-21 | 108 | 100 | 89 | 76 | 68 | 60 | 48 | 35 | 21 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 9 | 2019-05-07 | 108 | 98 | 86 | 75 | 62 | 48 | 32 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 9 | 2019-05-07 | 108 | 99 | 86 | 75 | 65 | 50 | 36 | 23 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 10 | 2019-05-21 | 108 | 95 | 79 | 70 | 58 | 47 | 39 | 31 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 10 | 2019-05-21 | 108 | 92 | 80 | 70 | 61 | 53 | 38 | 30 | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 9 | 2019-05-07 | 108 | 98 | 85 | 74 | 65 | 49 | 33 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 10 | 2019-05-21 | 108 | 93 | 79 | 68 | 52 | 43 | 35 | 27 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 10 | 2019-05-21 | 108 | 98 | 86 | 77 | 67 | 59 | 46 | 31 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 9 | 2019-05-07 | 108 | 95 | 79 | 68 | 58 | 42 | 34 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 10 | 2019-05-21 | 108 | 97 | 84 | 74 | 64 | 50 | 41 | 30 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 9 | 2019-05-07 | 108 | 97 | 82 | 70 | 62 | 46 | 37 | 23 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 10 | 2019-05-21 | 108 | 96 | 82 | 69 | 58 | 42 | 33 | 23 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 9 | 2019-05-07 | 108 | 98 | 90 | 77 | 61 | 49 | 38 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 10 | 2019-05-21 | 108 | 99 | 87 | 74 | 65 | 53 | 40 | 32 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 9 | 2019-05-07 | 108 | 94 | 79 | 69 | 53 | 45 | 35 | 22 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 10 | 2019-05-21 | 108 | 99 | 88 | 74 | 65 | 54 | 38 | 26 | 18 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 9 | 2019-05-07 | 108 | 99 | 84 | 70 | 54 | 43 | 35 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 10 | 2019-05-21 | 108 | 93 | 83 | 72 | 60 | 52 | 42 | 28 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 9 | 2019-05-07 | 108 | 99 | 83 | 72 | 58 | 47 | 33 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 9 | 2019-05-07 | 108 | 94 | 86 | 71 | 59 | 45 | 35 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 10 | 2019-05-21 | 108 | 98 | 86 | 78 | 67 | 52 | 43 | 35 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 9 | 2019-05-07 | 108 | 100 | 88 | 74 | 62 | 53 | 42 | 26 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 10 | 2019-05-21 | 108 | 100 | 91 | 82 | 69 | 53 | 38 | 28 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 8 | 2019-04-23 | 108 | 97 | 83 | 67 | 59 | 46 | 31 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 10 | 2019-05-21 | 108 | 100 | 86 | 76 | 64 | 54 | 42 | 32 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 9 | 2019-05-07 | 108 | 93 | 84 | 75 | 59 | 47 | 33 | 17 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 9 | 2019-05-07 | 108 | 95 | 85 | 72 | 58 | 46 | 38 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 9 | 2019-05-07 | 108 | 98 | 84 | 74 | 58 | 44 | 32 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 10 | 2019-05-21 | 108 | 97 | 85 | 72 | 57 | 47 | 33 | 19 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 11 | 2019-06-04 | 108 | 100 | 92 | 83 | 75 | 61 | 50 | 39 | 29 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 9 | 2019-05-07 | 108 | 99 | 89 | 74 | 63 | 49 | 41 | 27 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 10 | 2019-05-21 | 108 | 93 | 84 | 74 | 61 | 51 | 43 | 33 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 9 | 2019-05-07 | 108 | 95 | 79 | 65 | 57 | 42 | 27 | 14 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 9 | 2019-05-07 | 108 | 95 | 79 | 65 | 51 | 41 | 27 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 10 | 2019-05-21 | 108 | 100 | 91 | 75 | 65 | 57 | 41 | 31 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 10 | 2019-05-21 | 108 | 99 | 88 | 80 | 66 | 55 | 45 | 35 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 9 | 2019-05-07 | 108 | 99 | 83 | 74 | 59 | 47 | 31 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 10 | 2019-05-21 | 108 | 92 | 84 | 72 | 60 | 51 | 43 | 35 | 22 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 9 | 2019-05-07 | 108 | 100 | 88 | 72 | 60 | 47 | 34 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 10 | 2019-05-21 | 108 | 95 | 82 | 71 | 60 | 46 | 31 | 23 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 9 | 2019-05-07 | 108 | 100 | 85 | 71 | 57 | 45 | 33 | 23 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 9 | 2019-05-07 | 108 | 93 | 82 | 67 | 52 | 40 | 28 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 9 | 2019-05-07 | 108 | 100 | 84 | 70 | 58 | 43 | 32 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 9 | 2019-05-07 | 108 | 95 | 79 | 71 | 59 | 49 | 36 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 9 | 2019-05-07 | 108 | 96 | 82 | 67 | 55 | 45 | 33 | 22 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 9 | 2019-05-07 | 108 | 98 | 90 | 81 | 65 | 54 | 45 | 29 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 10 | 2019-05-21 | 108 | 93 | 79 | 68 | 59 | 49 | 35 | 26 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 9 | 2019-05-07 | 108 | 96 | 83 | 71 | 56 | 46 | 30 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 10 | 2019-05-21 | 108 | 97 | 86 | 77 | 62 | 54 | 43 | 33 | 17 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 9 | 2019-05-07 | 108 | 100 | 84 | 69 | 61 | 45 | 37 | 23 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 10 | 2019-05-21 | 108 | 95 | 84 | 75 | 67 | 54 | 45 | 33 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 9 | 2019-05-07 | 108 | 93 | 82 | 69 | 56 | 41 | 28 | 17 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 10 | 2019-05-21 | 108 | 93 | 82 | 72 | 63 | 54 | 42 | 29 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 10 | 2019-05-21 | 108 | 99 | 85 | 75 | 62 | 50 | 42 | 32 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 9 | 2019-05-07 | 108 | 99 | 87 | 79 | 65 | 50 | 39 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 10 | 2019-05-21 | 108 | 93 | 80 | 70 | 62 | 47 | 38 | 28 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 8 | 2019-04-23 | 108 | 94 | 83 | 72 | 60 | 45 | 29 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 10 | 2019-05-21 | 108 | 97 | 84 | 74 | 63 | 54 | 45 | 33 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 9 | 2019-05-07 | 108 | 96 | 81 | 71 | 55 | 44 | 36 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 9 | 2019-05-07 | 108 | 99 | 90 | 79 | 69 | 54 | 38 | 23 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 9 | 2019-05-07 | 108 | 100 | 86 | 78 | 62 | 48 | 34 | 18 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 9 | 2019-05-07 | 108 | 98 | 90 | 74 | 58 | 46 | 33 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 10 | 2019-05-21 | 108 | 99 | 90 | 78 | 70 | 62 | 48 | 37 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 9 | 2019-05-07 | 108 | 98 | 86 | 74 | 63 | 48 | 32 | 16 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 8 | 2019-04-23 | 108 | 92 | 79 | 67 | 52 | 36 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 9 | 2019-05-07 | 108 | 96 | 88 | 80 | 69 | 56 | 40 | 29 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 9 | 2019-05-07 | 108 | 97 | 89 | 76 | 63 | 51 | 36 | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 10 | 2019-05-21 | 108 | 94 | 82 | 71 | 59 | 50 | 40 | 27 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 9 | 2019-05-07 | 108 | 96 | 85 | 71 | 60 | 46 | 33 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 10 | 2019-05-21 | 108 | 95 | 81 | 73 | 65 | 53 | 41 | 29 | 20 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 10 | 2019-05-21 | 108 | 98 | 89 | 77 | 68 | 53 | 39 | 26 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 9 | 2019-05-07 | 108 | 97 | 85 | 73 | 63 | 49 | 33 | 17 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 9 | 2019-05-07 | 108 | 92 | 83 | 69 | 56 | 45 | 29 | 20 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 10 | 2019-05-21 | 108 | 95 | 83 | 70 | 61 | 48 | 39 | 24 | 15 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 9 | 2019-05-07 | 108 | 92 | 78 | 63 | 49 | 40 | 31 | 22 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 10 | 2019-05-21 | 108 | 94 | 81 | 71 | 60 | 49 | 33 | 24 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 10 | 2019-05-21 | 108 | 93 | 83 | 72 | 59 | 51 | 35 | 26 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 9 | 2019-05-07 | 108 | 98 | 86 | 70 | 56 | 46 | 33 | 25 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 9 | 2019-05-07 | 108 | 100 | 85 | 69 | 54 | 40 | 28 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 10 | 2019-05-21 | 108 | 98 | 89 | 73 | 61 | 53 | 43 | 35 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 9 | 2019-05-07 | 108 | 100 | 90 | 75 | 59 | 48 | 36 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 8 | 2019-04-23 | 108 | 93 | 78 | 62 | 54 | 43 | 27 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 8 | 2019-04-23 | 108 | 92 | 78 | 65 | 49 | 35 | 25 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 11 | 2019-06-04 | 108 | 97 | 86 | 74 | 60 | 50 | 41 | 27 | 18 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 10 | 2019-05-21 | 108 | 100 | 89 | 81 | 68 | 58 | 43 | 34 | 24 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 9 | 2019-05-07 | 108 | 92 | 76 | 64 | 48 | 38 | 30 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 9 | 2019-05-07 | 108 | 94 | 79 | 70 | 58 | 47 | 35 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 10 | 2019-05-21 | 108 | 94 | 85 | 72 | 60 | 48 | 40 | 27 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 10 | 2019-05-21 | 108 | 100 | 92 | 78 | 65 | 56 | 47 | 36 | 24 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 9 | 2019-05-07 | 108 | 100 | 84 | 68 | 56 | 48 | 37 | 23 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 10 | 2019-05-21 | 108 | 100 | 86 | 77 | 68 | 54 | 44 | 32 | 23 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 9 | 2019-05-07 | 108 | 99 | 87 | 78 | 63 | 55 | 43 | 28 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 10 | 2019-05-21 | 108 | 96 | 87 | 74 | 62 | 47 | 32 | 23 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 10 | 2019-05-21 | 108 | 95 | 83 | 74 | 62 | 54 | 44 | 31 | 21 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 10 | 2019-05-21 | 108 | 94 | 80 | 72 | 64 | 54 | 40 | 31 | 22 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 9 | 2019-05-07 | 108 | 94 | 78 | 67 | 52 | 44 | 35 | 25 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 11 | 2019-06-04 | 108 | 98 | 89 | 73 | 62 | 52 | 43 | 32 | 22 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 9 | 2019-05-07 | 108 | 92 | 78 | 63 | 51 | 40 | 28 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 11 | 2019-06-04 | 108 | 93 | 84 | 76 | 68 | 60 | 50 | 41 | 33 | 22 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 10 | 2019-05-21 | 108 | 98 | 82 | 71 | 62 | 53 | 42 | 34 | 24 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 9 | 2019-05-07 | 108 | 98 | 90 | 82 | 67 | 56 | 42 | 27 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 9 | 2019-05-07 | 108 | 94 | 80 | 64 | 52 | 36 | 28 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 9 | 2019-05-07 | 108 | 95 | 81 | 73 | 58 | 46 | 38 | 27 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 11 | 2019-06-04 | 108 | 100 | 90 | 77 | 67 | 58 | 44 | 32 | 23 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 10 | 2019-05-21 | 108 | 94 | 82 | 69 | 58 | 46 | 35 | 24 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 10 | 2019-05-21 | 108 | 100 | 87 | 73 | 60 | 49 | 34 | 26 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 9 | 2019-05-07 | 108 | 92 | 84 | 70 | 59 | 43 | 27 | 13 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 9 | 2019-05-07 | 108 | 95 | 83 | 72 | 63 | 53 | 39 | 25 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 8 | 2019-04-23 | 108 | 92 | 82 | 68 | 55 | 39 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 9 | 2019-05-07 | 108 | 97 | 87 | 72 | 58 | 47 | 33 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 10 | 2019-05-21 | 108 | 96 | 87 | 78 | 67 | 54 | 46 | 32 | 19 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 10 | 2019-05-21 | 108 | 96 | 83 | 73 | 65 | 51 | 38 | 30 | 21 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 9 | 2019-05-07 | 108 | 94 | 80 | 66 | 57 | 41 | 27 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 10 | 2019-05-21 | 108 | 99 | 84 | 68 | 52 | 39 | 28 | 20 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 9 | 2019-05-07 | 108 | 92 | 80 | 67 | 55 | 46 | 32 | 18 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 9 | 2019-05-07 | 108 | 95 | 86 | 72 | 56 | 40 | 28 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 10 | 2019-05-21 | 108 | 100 | 85 | 72 | 61 | 50 | 38 | 27 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 10 | 2019-05-21 | 108 | 98 | 90 | 79 | 68 | 58 | 49 | 33 | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 10 | 2019-05-21 | 108 | 98 | 86 | 73 | 60 | 47 | 37 | 26 | 17 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 8 | 2019-04-23 | 108 | 92 | 82 | 68 | 56 | 45 | 29 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 9 | 2019-05-07 | 108 | 92 | 78 | 62 | 52 | 36 | 28 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 9 | 2019-05-07 | 108 | 98 | 84 | 76 | 65 | 50 | 36 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 9 | 2019-05-07 | 108 | 100 | 88 | 80 | 65 | 51 | 40 | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 10 | 2019-05-21 | 108 | 99 | 89 | 79 | 64 | 49 | 37 | 22 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 10 | 2019-05-21 | 108 | 95 | 79 | 65 | 57 | 43 | 33 | 23 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 9 | 2019-05-07 | 108 | 94 | 79 | 66 | 58 | 43 | 34 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 10 | 2019-05-21 | 108 | 94 | 84 | 76 | 68 | 56 | 42 | 33 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 10 | 2019-05-21 | 108 | 100 | 91 | 82 | 71 | 55 | 41 | 25 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 10 | 2019-05-21 | 108 | 97 | 89 | 76 | 63 | 48 | 40 | 31 | 23 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 10 | 2019-05-21 | 108 | 100 | 87 | 73 | 57 | 44 | 29 | 21 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 10 | 2019-05-21 | 108 | 99 | 84 | 75 | 66 | 50 | 36 | 27 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 9 | 2019-05-07 | 108 | 95 | 81 | 70 | 56 | 45 | 32 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 10 | 2019-05-21 | 108 | 95 | 82 | 71 | 62 | 54 | 44 | 33 | 18 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 10 | 2019-05-21 | 108 | 96 | 86 | 74 | 61 | 52 | 37 | 24 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 9 | 2019-05-07 | 108 | 93 | 85 | 75 | 61 | 46 | 37 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 9 | 2019-05-07 | 108 | 92 | 79 | 63 | 49 | 38 | 29 | 20 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 10 | 2019-05-21 | 108 | 96 | 87 | 74 | 65 | 57 | 44 | 30 | 21 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 10 | 2019-05-21 | 108 | 100 | 89 | 78 | 63 | 50 | 36 | 22 | 13 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 10 | 2019-05-21 | 108 | 98 | 87 | 78 | 62 | 48 | 33 | 25 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 10 | 2019-05-21 | 108 | 99 | 91 | 75 | 63 | 54 | 41 | 31 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 9 | 2019-05-07 | 108 | 93 | 78 | 67 | 52 | 40 | 25 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 9 | 2019-05-07 | 108 | 96 | 80 | 67 | 54 | 39 | 31 | 23 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 9 | 2019-05-07 | 108 | 100 | 86 | 71 | 58 | 50 | 37 | 25 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 10 | 2019-05-21 | 108 | 96 | 81 | 65 | 55 | 40 | 29 | 21 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 10 | 2019-05-21 | 108 | 100 | 91 | 83 | 74 | 65 | 50 | 35 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 10 | 2019-05-21 | 108 | 92 | 77 | 64 | 56 | 48 | 38 | 26 | 17 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 9 | 2019-05-07 | 108 | 92 | 80 | 70 | 54 | 45 | 35 | 19 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 9 | 2019-05-07 | 108 | 98 | 87 | 78 | 65 | 49 | 33 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 9 | 2019-05-07 | 108 | 96 | 81 | 69 | 53 | 45 | 35 | 21 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 10 | 2019-05-21 | 108 | 100 | 86 | 78 | 65 | 49 | 34 | 23 | 12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 10 | 2019-05-21 | 108 | 100 | 84 | 76 | 64 | 53 | 37 | 27 | 19 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 10 | 2019-05-21 | 108 | 99 | 84 | 68 | 57 | 46 | 36 | 27 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 10 | 2019-05-21 | 108 | 98 | 87 | 73 | 57 | 49 | 35 | 21 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 10 | 2019-05-21 | 108 | 98 | 89 | 80 | 69 | 54 | 45 | 30 | 20 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 9 | 2019-05-07 | 108 | 97 | 83 | 67 | 51 | 43 | 28 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 9 | 2019-05-07 | 108 | 95 | 83 | 68 | 56 | 45 | 37 | 22 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 10 | 2019-05-21 | 108 | 92 | 84 | 76 | 60 | 47 | 35 | 27 | 11 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 9 | 2019-05-07 | 108 | 98 | 84 | 69 | 59 | 47 | 36 | 26 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 10 | 2019-05-21 | 108 | 93 | 84 | 69 | 61 | 49 | 33 | 25 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 10 | 2019-05-21 | 108 | 95 | 82 | 73 | 58 | 48 | 40 | 27 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 10 | 2019-05-21 | 108 | 97 | 89 | 80 | 70 | 59 | 47 | 32 | 17 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 9 | 2019-05-07 | 108 | 94 | 83 | 69 | 57 | 49 | 37 | 27 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 9 | 2019-05-07 | 108 | 95 | 81 | 70 | 54 | 40 | 28 | 19 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 10 | 2019-05-21 | 108 | 98 | 85 | 69 | 61 | 53 | 38 | 26 | 10 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 9 | 2019-05-07 | 108 | 93 | 83 | 71 | 58 | 49 | 33 | 19 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 9 | 2019-05-07 | 108 | 93 | 79 | 65 | 51 | 36 | 26 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 8 | 2019-04-23 | 108 | 97 | 85 | 70 | 54 | 43 | 31 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 8 | 2019-04-23 | 108 | 93 | 80 | 70 | 55 | 39 | 27 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 9 | 2019-05-07 | 108 | 98 | 83 | 73 | 60 | 49 | 34 | 21 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 9 | 2019-05-07 | 108 | 100 | 86 | 70 | 59 | 43 | 29 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 10 | 2019-05-21 | 108 | 92 | 81 | 72 | 56 | 46 | 37 | 23 | 15 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 10 | 2019-05-21 | 108 | 96 | 85 | 74 | 62 | 54 | 42 | 27 | 15 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 10 | 2019-05-21 | 108 | 98 | 90 | 78 | 67 | 51 | 40 | 24 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 9 | 2019-05-07 | 108 | 92 | 83 | 70 | 54 | 41 | 28 | 14 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 9 | 2019-05-07 | 108 | 94 | 86 | 70 | 56 | 44 | 29 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 9 | 2019-05-07 | 108 | 92 | 78 | 70 | 58 | 44 | 30 | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 10 | 2019-05-21 | 108 | 98 | 86 | 78 | 70 | 57 | 44 | 35 | 20 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 9 | 2019-05-07 | 108 | 93 | 85 | 69 | 58 | 48 | 36 | 24 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 10 | 2019-05-21 | 108 | 100 | 91 | 80 | 68 | 52 | 43 | 31 | 18 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 9 | 2019-05-07 | 108 | 94 | 86 | 72 | 58 | 45 | 31 | 23 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 10 | 2019-05-21 | 108 | 96 | 85 | 75 | 66 | 57 | 43 | 29 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 10 | 2019-05-21 | 108 | 96 | 86 | 77 | 61 | 47 | 39 | 31 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 9 | 2019-05-07 | 108 | 100 | 86 | 71 | 56 | 42 | 30 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 10 | 2019-05-21 | 108 | 100 | 85 | 77 | 69 | 61 | 47 | 34 | 24 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 10 | 2019-05-21 | 108 | 100 | 85 | 74 | 58 | 48 | 37 | 23 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 9 | 2019-05-07 | 108 | 95 | 80 | 67 | 54 | 45 | 29 | 20 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 10 | 2019-05-21 | 108 | 94 | 80 | 71 | 61 | 46 | 37 | 29 | 15 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 9 | 2019-05-07 | 108 | 92 | 77 | 67 | 53 | 41 | 31 | 19 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 9 | 2019-05-07 | 108 | 98 | 85 | 77 | 63 | 51 | 42 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 9 | 2019-05-07 | 108 | 98 | 85 | 74 | 61 | 53 | 38 | 23 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 9 | 2019-05-07 | 108 | 94 | 81 | 67 | 57 | 43 | 31 | 22 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 9 | 2019-05-07 | 108 | 94 | 78 | 66 | 58 | 44 | 28 | 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 9 | 2019-05-07 | 108 | 94 | 86 | 75 | 61 | 45 | 30 | 21 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 9 | 2019-05-07 | 108 | 96 | 82 | 73 | 60 | 51 | 41 | 31 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 9 | 2019-05-07 | 108 | 99 | 90 | 82 | 68 | 58 | 42 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 9 | 2019-05-07 | 108 | 97 | 88 | 74 | 59 | 47 | 36 | 21 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 9 | 2019-05-07 | 108 | 98 | 82 | 73 | 61 | 48 | 35 | 22 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 10 | 2019-05-21 | 108 | 98 | 86 | 78 | 62 | 48 | 34 | 23 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 9 | 2019-05-07 | 108 | 99 | 87 | 71 | 57 | 48 | 36 | 23 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 9 | 2019-05-07 | 108 | 93 | 78 | 69 | 60 | 47 | 32 | 16 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 9 | 2019-05-07 | 108 | 95 | 85 | 70 | 57 | 41 | 25 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 11 | 2019-06-04 | 108 | 100 | 85 | 77 | 69 | 61 | 53 | 45 | 35 | 19 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 9 | 2019-05-07 | 108 | 94 | 84 | 68 | 54 | 40 | 26 | 17 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 9 | 2019-05-07 | 108 | 92 | 82 | 66 | 52 | 36 | 27 | 16 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 10 | 2019-05-21 | 108 | 98 | 86 | 71 | 56 | 44 | 30 | 22 | 13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 10 | 2019-05-21 | 108 | 96 | 85 | 71 | 61 | 45 | 33 | 22 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 10 | 2019-05-21 | 108 | 100 | 92 | 80 | 68 | 55 | 40 | 27 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 9 | 2019-05-07 | 108 | 97 | 88 | 80 | 68 | 55 | 42 | 27 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 9 | 2019-05-07 | 108 | 97 | 82 | 68 | 54 | 41 | 31 | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 9 | 2019-05-07 | 108 | 98 | 86 | 71 | 61 | 50 | 34 | 26 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 9 | 2019-05-07 | 108 | 92 | 82 | 69 | 60 | 47 | 35 | 23 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 9 | 2019-05-07 | 108 | 95 | 80 | 68 | 56 | 48 | 32 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 78 | 53 | 97 | 140 | 186 | 236 | 293 | 347 | 401 | 445 | 496 | 541 | 594 | 645 | 16 | 15 | 9 | 13 | 16 | 9 | 10 | 9 | 8 | 12 | 12 | 11 | 13 | 12 | 9 | 12 | 11 | 15 | 11 | 13 | 15 | 16 | 10 | 16 | 15 | 16 | 12 | 11 | 14 | 15 | 9 | 16 | 12 | 14 | 9 | 9 | 15 | 9 | 13 | 14 | 13 | 14 | 9 | 9 | 11 | 14 | 15 | 13 | 11 | 15 | 11 | 14
2 | 73 | 46 | 95 | 142 | 177 | 226 | 270 | 319 | 366 | 406 | 448 | 493 | 549 | 596 | 11 | 11 | 8 | 16 | 13 | 14 | 9 | 13 | 13 | 9 | 15 | 10 | 9 | 10 | 8 | 8 | 12 | 13 | 11 | 13 | 12 | 9 | 11 | 12 | 12 | 15 | 11 | 11 | 10 | 13 | 8 | 16 | 13 | 9 | 9 | 9 | 13 | 8 | 10 | 11 | 11 | 11 | 11 | 12 | 11 | 13 | 16 | 16 | 10 | 9 | 16 | 12
3 | 71 | 49 | 90 | 138 | 191 | 241 | 282 | 330 | 371 | 420 | 466 | 518 | 569 | 622 | 13 | 12 | 16 | 8 | 12 | 10 | 10 | 9 | 14 | 14 | 9 | 11 | 15 | 13 | 12 | 13 | 16 | 12 | 13 | 9 | 10 | 14 | 8 | 9 | 8 | 9 | 16 | 15 | 8 | 9 | 12 | 12 | 9 | 16 | 8 | 16 | 13 | 9 | 8 | 16 | 14 | 13 | 10 | 15 | 14 | 16 | 10 | 11 | 13 | 16 | 10 | 14
4 | 70 | 51 | 100 | 148 | 195 | 241 | 278 | 325 | 371 | 414 | 463 | 519 | 562 | 605 | 15 | 11 | 13 | 12 | 11 | 8 | 16 | 14 | 10 | 16 | 13 | 9 | 14 | 14 | 10 | 9 | 12 | 15 | 11 | 8 | 10 | 8 | 10 | 9 | 10 | 11 | 10 | 16 | 13 | 15 | 10 | 8 | 9 | 8 | 10 | 16 | 13 | 13 | 9 | 14 | 15 | 15 | 11 | 15 | 8 | 12 | 9 | 14 | 8 | 12 | 11 | 12
5 | 80 | 53 | 103 | 144 | 185 | 236 | 280 | 335 | 384 | 429 | 482 | 525 | 568 | 625 | 13 | 16 | 15 | 9 | 14 | 13 | 12 | 11 | 11 | 9 | 13 | 8 | 10 | 12 | 9 | 10 | 12 | 12 | 16 | 11 | 9 | 13 | 11 | 11 | 14 | 10 | 15 | 16 | 16 | 9 | 14 | 10 | 8 | 16 | 8 | 13 | 15 | 11 | 13 | 14 | 10 | 14 | 10 | 9 | 10 | 8 | 10 | 15 | 16 | 16 | 13 | 12
6 | 83 | 56 | 106 | 149 | 197 | 250 | 299 | 349 | 400 | 443 | 490 | 541 | 580 | 627 | 14 | 16 | 11 | 15 | 14 | 13 | 12 | 11 | 8 | 11 | 12 | 12 | 11 | 14 | 15 | 8 | 15 | 13 | 16 | 9 | 16 | 13 | 11 | 9 | 10 | 16 | 14 | 10 | 16 | 11 | 9 | 15 | 15 | 11 | 8 | 9 | 11 | 11 | 14 | 11 | 14 | 12 | 15 | 10 | 11 | 9 | 8 | 11 | 11 | 14 | 14 | 8
7 | 82 | 57 | 109 | 151 | 197 | 242 | 290 | 334 | 381 | 438 | 480 | 532 | 589 | 629 | 11 | 15 | 15 | 16 | 10 | 15 | 15 | 12 | 12 | 11 | 8 | 11 | 11 | 11 | 11 | 13 | 10 | 11 | 11 | 13 | 14 | 9 | 16 | 9 | 9 | 13 | 12 | 10 | 14 | 10 | 14 | 9 | 14 | 16 | 12 | 15 | 9 | 13 | 8 | 12 | 15 | 14 | 12 | 11 | 14 | 14 | 16 | 13 | 9 | 8 | 10 | 13
8 | 79 | 52 | 98 | 140 | 181 | 226 | 270 | 316 | 365 | 418 | 465 | 511 | 559 | 608 | 13 | 16 | 15 | 8 | 14 | 13 | 9 | 10 | 9 | 9 | 9 | 15 | 10 | 13 | 10 | 8 | 11 | 10 | 8 | 16 | 11 | 11 | 11 | 11 | 10 | 12 | 11 | 13 | 9 | 9 | 16 | 15 | 13 | 15 | 13 | 12 | 14 | 10 | 10 | 13 | 16 | 8 | 8 | 14 | 9 | 15 | 16 | 8 | 14 | 12 | 8 | 15
9 | 77 | 51 | 107 | 155 | 201 | 253 | 308 | 361 | 402 | 451 | 492 | 554 | 597 | 651 | 16 | 14 | 12 | 9 | 10 | 16 | 14 | 16 | 15 | 12 | 13 | 8 | 9 | 14 | 8 | 15 | 14 | 14 | 13 | 11 | 16 | 13 | 16 | 10 | 15 | 15 | 15 | 8 | 10 | 11 | 11 | 9 | 11 | 16 | 10 | 12 | 15 | 8 | 8 | 10 | 16 | 15 | 16 | 15 | 14 | 9 | 11 | 9 | 13 | 15 | 13 | 13
10 | 73 | 47 | 96 | 138 | 194 | 249 | 293 | 335 | 389 | 434 | 482 | 523 | 572 | 607 | 14 | 9 | 10 | 14 | 13 | 13 | 8 | 15 | 9 | 9 | 16 | 8 | 16 | 16 | 13 | 11 | 16 | 15 | 14 | 10 | 8 | 15 | 11 | 10 | 10 | 8 | 12 | 12 | 15 | 15 | 12 | 12 | 9 | 11 | 15 | 10 | 9 | 11 | 13 | 15 | 10 | 12 | 8 | 11 | 14 | 13 | 10 | 12 | 10 | 9 | 8 | 8
11 | 72 | 48 | 91 | 145 | 192 | 234 | 280 | 336 | 385 | 441 | 496 | 549 | 601 | 643 | 11 | 11 | 15 | 11 | 13 | 11 | 8 | 11 | 16 | 13 | 9 | 16 | 8 | 8 | 16 | 15 | 12 | 8 | 8 | 14 | 11 | 10 | 10 | 15 | 13 | 16 | 16 | 11 | 9 | 16 | 16 | 8 | 16 | 15 | 12 | 13 | 11 | 12 | 16 | 16 | 10 | 14 | 13 | 16 | 12 | 14 | 13 | 13 | 13 | 9 | 11 | 9
12 | 81 | 51 | 108 | 162 | 216 | 265 | 313 | 363 | 406 | 461 | 516 | 559 | 603 | 651 | 8 | 11 | 16 | 16 | 16 | 14 | 12 | 15 | 16 | 15 | 12 | 11 | 14 | 10 | 15 | 15 | 16 | 15 | 10 | 8 | 14 | 8 | 14 | 12 | 12 | 9 | 14 | 15 | 9 | 12 | 11 | 11 | 16 | 16 | 13 | 10 | 16 | 13 | 11 | 15 | 11 | 15 | 8 | 9 | 8 | 8 | 12 | 16 | 16 | 9 | 9 | 14
13 | 73 | 49 | 94 | 137 | 182 | 229 | 279 | 328 | 377 | 434 | 479 | 527 | 580 | 629 | 12 | 11 | 11 | 15 | 8 | 16 | 8 | 13 | 13 | 9 | 12 | 9 | 12 | 16 | 9 | 8 | 10 | 16 | 9 | 12 | 14 | 16 | 10 | 10 | 15 | 15 | 11 | 8 | 16 | 12 | 10 | 11 | 10 | 16 | 16 | 15 | 15 | 13 | 9 | 8 | 15 | 8 | 16 | 9 | 15 | 13 | 9 | 16 | 13 | 10 | 13 | 13
14 | 63 | 46 | 82 | 117 | 166 | 210 | 262 | 312 | 365 | 415 | 464 | 514 | 557 | 602 | 8 | 12 | 13 | 13 | 8 | 9 | 10 | 9 | 10 | 8 | 9 | 8 | 14 | 11 | 10 | 14 | 11 | 14 | 10 | 9 | 16 | 11 | 12 | 13 | 10 | 11 | 15 | 14 | 14 | 14 | 15 | 10 | 13 | 14 | 12 | 11 | 14 | 8 | 13 | 14 | 8 | 12 | 15 | 15 | 9 | 11 | 15 | 8 | 14 | 14 | 8 | 9
15 | 66 | 39 | 92 | 138 | 190 | 245 | 303 | 362 | 415 | 462 | 505 | 544 | 599 | 659 | 8 | 8 | 11 | 12 | 15 | 12 | 16 | 10 | 11 | 9 | 13 | 13 | 16 | 12 | 13 | 11 | 16 | 14 | 16 | 9 | 16 | 11 | 16 | 15 | 15 | 14 | 14 | 16 | 10 | 16 | 15 | 12 | 12 | 10 | 10 | 15 | 9 | 10 | 15 | 9 | 8 | 10 | 13 | 8 | 14 | 14 | 14 | 13 | 16 | 16 | 12 | 16
16 | 71 | 42 | 95 | 142 | 194 | 253 | 293 | 339 | 382 | 425 | 475 | 510 | 560 | 610 | 9 | 11 | 14 | 8 | 14 | 15 | 13 | 11 | 14 | 8 | 13 | 12 | 9 | 14 | 15 | 14 | 15 | 15 | 15 | 14 | 8 | 9 | 8 | 15 | 10 | 15 | 12 | 9 | 13 | 11 | 9 | 10 | 11 | 14 | 10 | 8 | 16 | 15 | 9 | 10 | 8 | 10 | 9 | 8 | 10 | 13 | 14 | 13 | 13 | 15 | 12 | 10
17 | 70 | 45 | 96 | 146 | 201 | 247 | 299 | 352 | 399 | 441 | 493 | 540 | 592 | 637 | 12 | 10 | 14 | 9 | 9 | 16 | 11 | 15 | 12 | 13 | 10 | 15 | 14 | 15 | 15 | 11 | 8 | 8 | 15 | 15 | 11 | 14 | 12 | 15 | 15 | 11 | 16 | 11 | 14 | 12 | 12 | 9 | 8 | 9 | 10 | 15 | 15 | 9 | 15 | 13 | 8 | 13 | 12 | 14 | 13 | 15 | 15 | 9 | 13 | 12 | 10 | 10
18 | 68 | 41 | 93 | 135 | 187 | 226 | 277 | 330 | 386 | 435 | 485 | 522 | 562 | 610 | 11 | 10 | 11 | 9 | 15 | 12 | 14 | 11 | 12 | 14 | 8 | 8 | 15 | 15 | 13 | 9 | 8 | 12 | 11 | 8 | 8 | 14 | 16 | 13 | 14 | 16 | 11 | 12 | 15 | 16 | 12 | 13 | 9 | 16 | 14 | 10 | 16 | 13 | 12 | 9 | 10 | 8 | 10 | 9 | 9 | 8 | 12 | 11 | 16 | 9 | 12 | 11
19 | 73 | 45 | 101 | 155 | 201 | 256 | 302 | 343 | 388 | 432 | 486 | 531 | 576 | 624 | 8 | 11 | 11 | 15 | 16 | 12 | 16 | 12 | 14 | 14 | 12 | 14 | 15 | 9 | 10 | 12 | 13 | 14 | 14 | 14 | 9 | 13 | 12 | 12 | 10 | 9 | 14 | 8 | 14 | 9 | 10 | 12 | 9 | 11 | 12 | 12 | 12 | 13 | 16 | 13 | 9 | 16 | 8 | 12 | 16 | 8 | 10 | 11 | 11 | 9 | 16 | 12
20 | 92 | 62 | 115 | 157 | 206 | 255 | 304 | 355 | 403 | 452 | 499 | 547 | 586 | 629 | 16 | 14 | 16 | 16 | 15 | 15 | 9 | 14 | 8 | 13 | 12 | 9 | 14 | 12 | 13 | 10 | 10 | 10 | 15 | 14 | 14 | 8 | 16 | 11 | 9 | 12 | 14 | 16 | 11 | 13 | 10 | 14 | 10 | 15 | 9 | 15 | 11 | 11 | 9 | 16 | 12 | 14 | 9 | 13 | 9 | 10 | 10 | 10 | 10 | 9 | 10 | 14
21 | 77 | 50 | 104 | 148 | 198 | 248 | 293 | 348 | 390 | 436 | 488 | 540 | 594 | 650 | 14 | 14 | 12 | 10 | 15 | 12 | 11 | 16 | 10 | 15 | 8 | 11 | 14 | 9 | 15 | 12 | 12 | 12 | 15 | 11 | 9 | 9 | 12 | 15 | 10 | 13 | 16 | 16 | 8 | 11 | 15 | 8 | 14 | 11 | 13 | 8 | 8 | 16 | 15 | 13 | 15 | 13 | 15 | 9 | 11 | 15 | 13 | 15 | 11 | 16 | 13 | 16
22 | 79 | 49 | 100 | 148 | 194 | 243 | 290 | 338 | 391 | 438 | 486 | 544 | 590 | 631 | 16 | 9 | 9 | 15 | 14 | 16 | 13 | 8 | 13 | 11 | 14 | 10 | 14 | 9 | 14 | 9 | 11 | 9 | 14 | 15 | 11 | 9 | 11 | 16 | 9 | 15 | 15 | 9 | 16 | 9 | 15 | 13 | 10 | 16 | 10 | 11 | 12 | 14 | 10 | 12 | 15 | 15 | 13 | 15 | 11 | 8 | 12 | 15 | 8 | 8 | 9 | 16
23 | 76 | 47 | 92 | 131 | 172 | 221 | 272 | 312 | 355 | 398 | 441 | 492 | 536 | 580 | 10 | 10 | 12 | 15 | 16 | 13 | 8 | 8 | 12 | 11 | 8 | 8 | 9 | 13 | 11 | 8 | 9 | 15 | 12 | 13 | 15 | 13 | 13 | 10 | 10 | 11 | 9 | 10 | 11 | 13 | 11 | 8 | 8 | 14 | 8 | 13 | 10 | 11 | 11 | 11 | 14 | 16 | 10 | 11 | 13 | 11 | 8 | 12 | 13 | 9 | 12 | 10
24 | 73 | 51 | 97 | 150 | 193 | 238 | 280 | 334 | 375 | 418 | 460 | 514 | 559 | 608 | 9 | 14 | 13 | 15 | 10 | 12 | 9 | 15 | 10 | 12 | 16 | 15 | 8 | 15 | 11 | 9 | 14 | 11 | 10 | 10 | 10 | 10 | 9 | 13 | 14 | 16 | 8 | 16 | 10 | 13 | 8 | 10 | 15 | 8 | 11 | 9 | 8 | 10 | 13 | 11 | 15 | 15 | 10 | 14 | 10 | 12 | 11 | 12 | 14 | 8 | 11 | 16
25 | 58 | 41 | 83 | 127 | 179 | 228 | 280 | 329 | 365 | 408 | 458 | 501 | 553 | 605 | 11 | 9 | 11 | 10 | 9 | 8 | 10 | 15 | 15 | 10 | 8 | 11 | 13 | 10 | 15 | 14 | 13 | 10 | 15 | 11 | 16 | 16 | 12 | 8 | 14 | 8 | 12 | 15 | 10 | 10 | 8 | 8 | 13 | 14 | 8 | 8 | 16 | 15 | 8 | 11 | 13 | 8 | 10 | 12 | 13 | 16 | 15 | 8 | 12 | 16 | 12 | 12
26 | 72 | 51 | 92 | 147 | 195 | 234 | 286 | 334 | 382 | 440 | 489 | 538 | 581 | 628 | 11 | 13 | 13 | 14 | 8 | 13 | 11 | 9 | 15 | 16 | 16 | 8 | 14 | 8 | 16 | 10 | 9 | 9 | 8 | 13 | 11 | 11 | 16 | 14 | 12 | 12 | 11 | 13 | 11 | 10 | 13 | 14 | 13 | 13 | 16 | 16 | 15 | 12 | 14 | 8 | 12 | 13 | 9 | 15 | 9 | 8 | 13 | 13 | 16 | 12 | 11 | 8
27 | 84 | 53 | 108 | 161 | 209 | 259 | 304 | 352 | 404 | 454 | 507 | 560 | 612 | 663 | 15 | 16 | 8 | 14 | 15 | 16 | 15 | 9 | 8 | 14 | 16 | 15 | 12 | 9 | 16 | 11 | 9 | 13 | 16 | 12 | 14 | 9 | 11 | 11 | 16 | 9 | 10 | 13 | 11 | 11 | 14 | 16 | 11 | 13 | 12 | 14 | 16 | 13 | 13 | 11 | 16 | 9 | 16 | 12 | 15 | 12 | 16 | 9 | 15 | 11 | 15 | 10
28 | 76 | 52 | 92 | 135 | 191 | 235 | 297 | 339 | 389 | 442 | 483 | 535 | 585 | 623 | 14 | 16 | 14 | 8 | 8 | 16 | 8 | 8 | 8 | 16 | 9 | 10 | 14 | 13 | 16 | 13 | 12 | 9 | 15 | 8 | 16 | 16 | 14 | 16 | 11 | 14 | 9 | 8 | 10 | 11 | 15 | 14 | 15 | 14 | 9 | 15 | 10 | 9 | 10 | 12 | 11 | 15 | 13 | 13 | 10 | 14 | 10 | 16 | 8 | 9 | 11 | 10
29 | 75 | 46 | 106 | 151 | 189 | 237 | 288 | 336 | 373 | 420 | 470 | 517 | 560 | 603 | 12 | 11 | 12 | 11 | 16 | 13 | 15 | 16 | 8 | 16 | 8 | 13 | 9 | 13 | 8 | 8 | 10 | 14 | 15 | 9 | 15 | 16 | 8 | 12 | 15 | 11 | 11 | 11 | 8 | 11 | 8 | 10 | 15 | 8 | 8 | 16 | 9 | 16 | 9 | 16 | 11 | 8 | 16 | 12 | 10 | 9 | 16 | 8 | 10 | 10 | 9 | 14
30 | 70 | 46 | 96 | 149 | 202 | 246 | 299 | 341 | 386 | 439 | 494 | 543 | 596 | 640 | 9 | 15 | 8 | 14 | 13 | 11 | 16 | 10 | 13 | 12 | 16 | 12 | 16 | 8 | 14 | 15 | 9 | 9 | 14 | 12 | 15 | 16 | 8 | 14 | 11 | 12 | 8 | 11 | 11 | 8 | 14 | 12 | 14 | 15 | 16 | 8 | 14 | 16 | 13 | 12 | 8 | 13 | 15 | 13 | 13 | 13 | 15 | 12 | 9 | 16 | 11 | 8
31 | 70 | 48 | 92 | 136 | 184 | 225 | 264 | 312 | 364 | 408 | 456 | 504 | 547 | 590 | 13 | 14 | 11 | 10 | 13 | 9 | 13 | 9 | 12 | 9 | 9 | 14 | 9 | 13 | 13 | 13 | 9 | 13 | 9 | 10 | 8 | 10 | 10 | 11 | 11 | 16 | 10 | 11 | 12 | 12 | 12 | 16 | 10 | 8 | 10 | 16 | 15 | 11 | 12 | 10 | 8 | 15 | 11 | 14 | 13 | 8 | 14 | 8 | 11 | 12 | 8 | 12
32 | 67 | 43 | 97 | 149 | 195 | 242 | 294 | 350 | 401 | 455 | 506 | 554 | 606 | 661 | 12 | 9 | 9 | 13 | 16 | 8 | 16 | 14 | 15 | 12 | 16 | 9 | 10 | 14 | 9 | 13 | 15 | 8 | 15 | 9 | 14 | 15 | 12 | 11 | 16 | 16 | 9 | 15 | 14 | 11 | 10 | 16 | 12 | 16 | 16 | 10 | 16 | 12 | 14 | 9 | 9 | 12 | 13 | 14 | 14 | 13 | 10 | 15 | 14 | 12 | 16 | 13
33 | 63 | 40 | 90 | 138 | 193 | 238 | 291 | 344 | 386 | 433 | 477 | 532 | 582 | 632 | 8 | 10 | 12 | 10 | 8 | 15 | 15 | 12 | 13 | 15 | 9 | 11 | 12 | 14 | 16 | 13 | 8 | 13 | 14 | 10 | 15 | 11 | 14 | 13 | 10 | 16 | 11 | 16 | 8 | 11 | 13 | 10 | 9 | 10 | 12 | 16 | 16 | 9 | 10 | 9 | 15 | 10 | 15 | 15 | 12 | 16 | 13 | 9 | 15 | 13 | 8 | 14
34 | 71 | 45 | 96 | 147 | 183 | 230 | 276 | 323 | 360 | 406 | 445 | 489 | 545 | 590 | 13 | 10 | 11 | 11 | 13 | 13 | 15 | 10 | 9 | 16 | 16 | 10 | 8 | 11 | 8 | 9 | 13 | 14 | 9 | 11 | 11 | 11 | 12 | 12 | 12 | 14 | 11 | 10 | 10 | 8 | 11 | 8 | 12 | 13 | 10 | 11 | 10 | 8 | 12 | 9 | 8 | 16 | 10 | 10 | 13 | 15 | 15 | 13 | 13 | 16 | 8 | 8
35 | 69 | 46 | 98 | 148 | 192 | 242 | 281 | 324 | 376 | 417 | 480 | 529 | 581 | 633 | 9 | 10 | 12 | 15 | 12 | 11 | 16 | 13 | 14 | 13 | 13 | 10 | 9 | 15 | 10 | 10 | 8 | 16 | 12 | 14 | 9 | 11 | 11 | 8 | 11 | 13 | 10 | 9 | 15 | 15 | 13 | 9 | 8 | 13 | 9 | 11 | 15 | 16 | 16 | 16 | 9 | 12 | 14 | 14 | 14 | 13 | 16 | 9 | 15 | 10 | 12 | 15
36 | 72 | 54 | 104 | 152 | 198 | 251 | 299 | 338 | 385 | 429 | 475 | 513 | 559 | 621 | 16 | 12 | 15 | 11 | 8 | 10 | 16 | 16 | 12 | 11 | 9 | 16 | 15 | 8 | 12 | 11 | 11 | 16 | 16 | 10 | 11 | 11 | 12 | 14 | 8 | 13 | 9 | 9 | 8 | 14 | 9 | 16 | 12 | 8 | 14 | 10 | 10 | 12 | 14 | 10 | 8 | 9 | 8 | 13 | 8 | 13 | 14 | 11 | 16 | 15 | 15 | 16
37 | 73 | 52 | 97 | 141 | 187 | 240 | 293 | 350 | 398 | 447 | 510 | 554 | 605 | 652 | 13 | 10 | 15 | 14 | 10 | 11 | 9 | 15 | 9 | 10 | 9 | 16 | 8 | 9 | 15 | 14 | 12 | 15 | 14 | 12 | 16 | 10 | 12 | 15 | 10 | 16 | 15 | 16 | 13 | 8 | 15 | 12 | 14 | 13 | 8 | 14 | 16 | 16 | 15 | 16 | 15 | 10 | 10 | 9 | 15 | 9 | 12 | 15 | 14 | 14 | 9 | 10
38 | 66 | 46 | 94 | 143 | 191 | 241 | 285 | 335 | 386 | 434 | 482 | 535 | 582 | 623 | 16 | 8 | 12 | 10 | 8 | 12 | 15 | 13 | 13 | 9 | 11 | 16 | 12 | 9 | 15 | 12 | 10 | 16 | 14 | 10 | 10 | 11 | 11 | 12 | 16 | 15 | 9 | 10 | 9 | 15 | 14 | 13 | 8 | 11 | 16 | 13 | 16 | 8 | 11 | 13 | 10 | 13 | 15 | 15 | 13 | 8 | 15 | 11 | 9 | 16 | 8 | 8
39 | 66 | 42 | 91 | 130 | 167 | 218 | 276 | 329 | 379 | 428 | 480 | 522 | 565 | 613 | 8 | 13 | 13 | 8 | 11 | 13 | 15 | 10 | 8 | 9 | 12 | 10 | 12 | 8 | 8 | 9 | 9 | 16 | 11 | 15 | 12 | 14 | 16 | 16 | 10 | 15 | 12 | 16 | 14 | 11 | 12 | 13 | 16 | 13 | 9 | 11 | 16 | 15 | 13 | 8 | 10 | 8 | 15 | 9 | 10 | 10 | 11 | 12 | 13 | 9 | 13 | 13
40 | 79 | 54 | 103 | 145 | 195 | 248 | 294 | 336 | 387 | 435 | 478 | 519 | 574 | 613 | 11 | 14 | 13 | 16 | 10 | 15 | 16 | 8 | 13 | 8 | 8 | 13 | 11 | 16 | 9 | 14 | 16 | 16 | 12 | 9 | 15 | 15 | 8 | 8 | 9 | 15 | 9 | 9 | 14 | 9 | 12 | 16 | 15 | 11 | 14 | 8 | 8 | 13 | 12 | 10 | 13 | 11 | 9 | 8 | 14 | 15 | 12 | 14 | 9 | 9 | 11 | 10
41 | 66 | 44 | 88 | 134 | 186 | 229 | 287 | 341 | 390 | 441 | 490 | 536 | 583 | 638 | 13 | 9 | 11 | 11 | 13 | 9 | 12 | 10 | 15 | 12 | 9 | 10 | 9 | 16 | 15 | 12 | 8 | 12 | 9 | 14 | 16 | 12 | 14 | 16 | 11 | 16 | 14 | 13 | 10 | 15 | 16 | 8 | 8 | 16 | 11 | 16 | 14 | 14 | 12 | 9 | 9 | 12 | 15 | 10 | 9 | 11 | 14 | 13 | 12 | 16 | 16 | 11
42 | 68 | 43 | 89 | 144 | 188 | 227 | 267 | 321 | 368 | 416 | 466 | 513 | 559 | 597 | 13 | 11 | 9 | 10 | 15 | 10 | 12 | 9 | 15 | 10 | 16 | 14 | 10 | 9 | 13 | 12 | 10 | 13 | 8 | 8 | 8 | 14 | 8 | 10 | 15 | 10 | 16 | 13 | 13 | 10 | 11 | 13 | 15 | 11 | 8 | 14 | 15 | 12 | 15 | 8 | 11 | 12 | 9 | 15 | 12 | 11 | 15 | 8 | 9 | 13 | 8 | 8
43 | 70 | 42 | 95 | 152 | 209 | 266 | 316 | 354 | 404 | 458 | 501 | 555 | 592 | 640 | 10 | 9 | 12 | 11 | 15 | 13 | 14 | 11 | 15 | 14 | 16 | 12 | 14 | 11 | 16 | 16 | 12 | 15 | 16 | 14 | 11 | 14 | 15 | 10 | 10 | 11 | 8 | 9 | 14 | 13 | 13 | 10 | 14 | 11 | 13 | 16 | 11 | 14 | 10 | 8 | 13 | 10 | 15 | 16 | 8 | 10 | 8 | 11 | 9 | 16 | 12 | 11
44 | 78 | 55 | 104 | 141 | 198 | 251 | 302 | 354 | 402 | 451 | 506 | 557 | 605 | 661 | 10 | 14 | 16 | 15 | 15 | 8 | 13 | 13 | 8 | 13 | 8 | 8 | 16 | 14 | 13 | 14 | 15 | 9 | 14 | 15 | 11 | 16 | 13 | 11 | 12 | 13 | 15 | 12 | 15 | 13 | 10 | 10 | 13 | 15 | 11 | 10 | 15 | 15 | 15 | 10 | 13 | 13 | 13 | 12 | 11 | 11 | 14 | 12 | 14 | 15 | 12 | 15
45 | 64 | 41 | 84 | 124 | 170 | 217 | 262 | 310 | 356 | 403 | 439 | 489 | 535 | 584 | 10 | 8 | 9 | 14 | 10 | 13 | 10 | 10 | 10 | 9 | 13 | 8 | 8 | 12 | 12 | 14 | 11 | 12 | 8 | 16 | 13 | 9 | 14 | 9 | 11 | 16 | 8 | 13 | 14 | 8 | 15 | 9 | 10 | 10 | 11 | 16 | 10 | 8 | 9 | 9 | 16 | 9 | 12 | 13 | 15 | 10 | 13 | 8 | 15 | 10 | 10 | 14
46 | 78 | 47 | 102 | 144 | 182 | 222 | 264 | 313 | 355 | 402 | 461 | 514 | 567 | 614 | 11 | 15 | 9 | 12 | 15 | 16 | 8 | 16 | 11 | 11 | 9 | 11 | 9 | 8 | 8 | 13 | 10 | 9 | 11 | 10 | 10 | 11 | 8 | 13 | 9 | 16 | 11 | 13 | 10 | 13 | 8 | 11 | 13 | 8 | 16 | 10 | 14 | 16 | 14 | 15 | 11 | 15 | 13 | 14 | 11 | 10 | 16 | 16 | 10 | 15 | 11 | 11
47 | 77 | 49 | 99 | 146 | 198 | 258 | 311 | 361 | 412 | 467 | 523 | 561 | 608 | 651 | 15 | 11 | 9 | 14 | 13 | 15 | 8 | 14 | 11 | 9 | 13 | 14 | 11 | 11 | 14 | 16 | 15 | 13 | 16 | 16 | 13 | 11 | 14 | 15 | 11 | 14 | 15 | 10 | 10 | 11 | 15 | 15 | 13 | 14 | 16 | 12 | 14 | 12 | 15 | 15 | 9 | 10 | 9 | 10 | 11 | 12 | 16 | 8 | 9 | 12 | 11 | 11
48 | 68 | 41 | 93 | 148 | 197 | 240 | 291 | 342 | 390 | 431 | 473 | 522 | 579 | 635 | 10 | 8 | 14 | 9 | 15 | 12 | 9 | 16 | 14 | 14 | 14 | 13 | 13 | 11 | 12 | 13 | 10 | 10 | 14 | 9 | 11 | 13 | 13 | 14 | 13 | 14 | 11 | 13 | 11 | 14 | 12 | 11 | 10 | 9 | 9 | 13 | 10 | 9 | 13 | 10 | 10 | 15 | 13 | 11 | 16 | 16 | 16 | 9 | 16 | 15 | 10 | 15
49 | 85 | 57 | 110 | 148 | 195 | 243 | 294 | 339 | 394 | 448 | 504 | 557 | 618 | 676 | 12 | 14 | 15 | 16 | 12 | 16 | 16 | 9 | 9 | 8 | 10 | 11 | 9 | 14 | 11 | 13 | 8 | 13 | 15 | 12 | 16 | 9 | 11 | 15 | 14 | 8 | 11 | 12 | 13 | 15 | 14 | 13 | 14 | 14 | 15 | 11 | 14 | 13 | 14 | 15 | 15 | 13 | 14 | 11 | 16 | 14 | 16 | 15 | 15 | 16 | 12 | 15
50 | 75 | 43 | 99 | 157 | 207 | 266 | 306 | 357 | 416 | 464 | 514 | 557 | 598 | 645 | 10 | 13 | 12 | 8 | 16 | 16 | 12 | 12 | 16 | 12 | 16 | 14 | 15 | 13 | 8 | 14 | 14 | 16 | 14 | 15 | 11 | 13 | 8 | 8 | 14 | 8 | 13 | 16 | 14 | 15 | 14 | 16 | 15 | 9 | 8 | 16 | 15 | 14 | 11 | 10 | 13 | 14 | 8 | 8 | 10 | 9 | 12 | 10 | 11 | 12 | 12 | 12
51 | 80 | 48 | 103 | 140 | 187 | 234 | 282 | 327 | 373 | 426 | 470 | 528 | 575 | 621 | 12 | 13 | 12 | 11 | 16 | 16 | 8 | 15 | 9 | 10 | 8 | 10 | 15 | 8 | 14 | 10 | 9 | 14 | 14 | 10 | 14 | 12 | 8 | 14 | 9 | 15 | 13 | 8 | 14 | 8 | 8 | 16 | 12 | 15 | 11 | 15 | 10 | 10 | 10 | 14 | 16 | 14 | 12 | 16 | 12 | 16 | 8 | 11 | 8 | 15 | 14 | 9
52 | 71 | 50 | 93 | 141 | 182 | 227 | 278 | 325 | 369 | 414 | 467 | 512 | 555 | 607 | 9 | 16 | 9 | 16 | 13 | 8 | 11 | 11 | 16 | 11 | 10 | 11 | 10 | 10 | 13 | 8 | 16 | 8 | 10 | 11 | 10 | 10 | 15 | 16 | 8 | 16 | 8 | 15 | 9 | 15 | 9 | 11 | 9 | 16 | 11 | 9 | 14 | 15 | 15 | 9 | 12 | 13 | 10 | 10 | 12 | 10 | 13 | 8 | 8 | 13 | 15 | 16
53 | 83 | 54 | 111 | 155 | 205 | 255 | 306 | 353 | 401 | 453 | 508 | 556 | 600 | 645 | 16 | 14 | 8 | 16 | 16 | 13 | 13 | 15 | 9 | 8 | 13 | 14 | 14 | 10 | 12 | 14 | 12 | 15 | 11 | 12 | 13 | 16 | 9 | 13 | 14 | 8 | 9 | 16 | 9 | 12 | 13 | 14 | 14 | 16 | 14 | 8 | 13 | 16 | 12 | 14 | 12 | 10 | 14 | 12 | 11 | 9 | 10 | 14 | 9 | 14 | 12 | 10
54 | 72 | 49 | 91 | 143 | 191 | 241 | 285 | 323 | 369 | 412 | 463 | 517 | 566 | 609 | 14 | 11 | 9 | 15 | 13 | 10 | 11 | 8 | 11 | 15 | 11 | 15 | 10 | 12 | 16 | 10 | 13 | 15 | 9 | 13 | 12 | 10 | 13 | 9 | 12 | 8 | 10 | 8 | 12 | 10 | 16 | 8 | 8 | 8 | 12 | 15 | 10 | 14 | 16 | 11 | 13 | 13 | 13 | 15 | 14 | 8 | 12 | 15 | 10 | 12 | 13 | 8
55 | 79 | 49 | 104 | 155 | 207 | 252 | 303 | 352 | 410 | 453 | 496 | 551 | 593 | 638 | 11 | 10 | 13 | 15 | 14 | 16 | 15 | 10 | 15 | 9 | 13 | 14 | 13 | 16 | 15 | 8 | 9 | 11 | 11 | 14 | 15 | 12 | 11 | 13 | 14 | 13 | 14 | 8 | 13 | 16 | 16 | 13 | 8 | 12 | 14 | 9 | 9 | 14 | 8 | 12 | 13 | 13 | 14 | 15 | 8 | 13 | 11 | 10 | 10 | 13 | 11 | 11
56 | 69 | 50 | 92 | 142 | 189 | 246 | 285 | 336 | 387 | 432 | 480 | 519 | 569 | 620 | 10 | 13 | 14 | 13 | 8 | 11 | 11 | 12 | 14 | 9 | 11 | 16 | 8 | 15 | 9 | 15 | 16 | 16 | 14 | 11 | 9 | 14 | 8 | 8 | 10 | 14 | 12 | 15 | 16 | 11 | 10 | 14 | 10 | 9 | 16 | 10 | 14 | 14 | 8 | 12 | 11 | 8 | 10 | 10 | 15 | 16 | 9 | 10 | 16 | 11 | 11 | 13
57 | 84 | 58 | 108 | 162 | 207 | 250 | 295 | 339 | 383 | 434 | 489 | 529 | 578 | 627 | 15 | 14 | 16 | 13 | 11 | 15 | 9 | 15 | 13 | 16 | 13 | 12 | 8 | 9 | 12 | 16 | 9 | 15 | 11 | 8 | 9 | 15 | 12 | 9 | 11 | 13 | 11 | 9 | 10 | 11 | 14 | 9 | 8 | 16 | 14 | 13 | 14 | 14 | 13 | 14 | 9 | 11 | 8 | 12 | 11 | 8 | 14 | 16 | 16 | 14 | 8 | 11
58 | 79 | 55 | 111 | 160 | 211 | 258 | 305 | 358 | 402 | 453 | 510 | 554 | 606 | 654 | 12 | 16 | 16 | 11 | 9 | 15 | 16 | 16 | 16 | 13 | 8 | 12 | 15 | 15 | 8 | 13 | 12 | 9 | 13 | 13 | 9 | 14 | 16 | 8 | 15 | 15 | 15 | 8 | 8 | 15 | 12 | 9 | 12 | 12 | 12 | 15 | 12 | 15 | 15 | 15 | 8 | 12 | 8 | 16 | 10 | 14 | 15 | 13 | 11 | 10 | 16 | 11
59 | 74 | 53 | 92 | 144 | 187 | 237 | 288 | 333 | 376 | 425 | 479 | 526 | 574 | 631 | 15 | 9 | 14 | 15 | 9 | 12 | 10 | 8 | 13 | 16 | 15 | 8 | 8 | 13 | 11 | 11 | 8 | 15 | 13 | 14 | 12 | 10 | 16 | 13 | 11 | 12 | 10 | 12 | 13 | 8 | 12 | 10 | 15 | 10 | 16 | 8 | 16 | 15 | 13 | 10 | 11 | 11 | 10 | 15 | 9 | 14 | 15 | 10 | 16 | 14 | 14 | 13
60 | 66 | 43 | 89 | 138 | 182 | 232 | 284 | 326 | 382 | 439 | 485 | 530 | 575 | 623 | 16 | 9 | 9 | 9 | 12 | 11 | 9 | 14 | 9 | 13 | 15 | 12 | 14 | 14 | 8 | 8 | 13 | 15 | 14 | 8 | 11 | 14 | 16 | 11 | 11 | 8 | 11 | 12 | 13 | 14 | 16 | 13 | 15 | 16 | 13 | 13 | 16 | 11 | 10 | 9 | 9 | 14 | 9 | 13 | 10 | 9 | 15 | 11 | 10 | 13 | 16 | 9
61 | 78 | 49 | 102 | 158 | 205 | 252 | 301 | 354 | 403 | 446 | 500 | 544 | 588 | 638 | 16 | 14 | 9 | 10 | 16 | 13 | 12 | 12 | 15 | 12 | 16 | 13 | 11 | 8 | 14 | 14 | 11 | 15 | 11 | 10 | 10 | 16 | 9 | 14 | 16 | 8 | 13 | 16 | 14 | 13 | 8 | 14 | 11 | 8 | 12 | 12 | 12 | 16 | 15 | 11 | 8 | 10 | 10 | 16 | 11 | 9 | 9 | 15 | 15 | 14 | 13 | 8
62 | 69 | 45 | 94 | 142 | 197 | 243 | 295 | 348 | 392 | 439 | 482 | 533 | 584 | 631 | 11 | 14 | 11 | 9 | 13 | 11 | 11 | 14 | 12 | 11 | 9 | 16 | 10 | 15 | 14 | 16 | 8 | 9 | 15 | 14 | 13 | 9 | 14 | 16 | 16 | 8 | 16 | 13 | 9 | 13 | 9 | 13 | 10 | 8 | 13 | 16 | 11 | 14 | 9 | 9 | 15 | 11 | 11 | 14 | 15 | 13 | 9 | 14 | 9 | 13 | 9 | 16
63 | 64 | 45 | 95 | 138 | 186 | 235 | 277 | 316 | 351 | 393 | 443 | 495 | 549 | 597 | 9 | 10 | 10 | 16 | 9 | 10 | 16 | 15 | 11 | 13 | 8 | 11 | 15 | 10 | 15 | 8 | 10 | 10 | 14 | 15 | 12 | 8 | 11 | 11 | 10 | 9 | 10 | 10 | 9 | 8 | 10 | 8 | 8 | 16 | 9 | 9 | 15 | 8 | 12 | 15 | 14 | 16 | 11 | 11 | 14 | 14 | 15 | 11 | 11 | 15 | 14 | 8
64 | 76 | 57 | 104 | 143 | 190 | 229 | 281 | 321 | 376 | 424 | 468 | 528 | 576 | 628 | 16 | 14 | 11 | 16 | 11 | 8 | 16 | 12 | 10 | 11 | 8 | 10 | 16 | 9 | 10 | 12 | 10 | 11 | 9 | 9 | 14 | 14 | 9 | 15 | 14 | 9 | 9 | 8 | 11 | 14 | 15 | 15 | 14 | 15 | 11 | 8 | 11 | 14 | 8 | 11 | 16 | 16 | 13 | 15 | 13 | 15 | 11 | 9 | 14 | 14 | 13 | 11
65 | 64 | 43 | 89 | 138 | 182 | 234 | 281 | 330 | 384 | 420 | 464 | 508 | 563 | 608 | 12 | 9 | 11 | 11 | 8 | 13 | 13 | 12 | 11 | 15 | 13 | 10 | 9 | 13 | 13 | 9 | 16 | 12 | 16 | 8 | 16 | 13 | 8 | 10 | 11 | 8 | 15 | 15 | 12 | 15 | 11 | 16 | 9 | 8 | 8 | 11 | 9 | 10 | 10 | 15 | 12 | 9 | 14 | 9 | 16 | 14 | 10 | 15 | 9 | 10 | 14 | 12
66 | 73 | 46 | 98 | 152 | 207 | 261 | 311 | 370 | 417 | 467 | 516 | 568 | 611 | 658 | 14 | 8 | 10 | 14 | 15 | 12 | 11 | 14 | 14 | 9 | 16 | 15 | 15 | 13 | 11 | 16 | 11 | 13 | 16 | 14 | 12 | 11 | 13 | 14 | 16 | 12 | 15 | 16 | 8 | 14 | 12 | 13 | 13 | 11 | 10 | 16 | 15 | 12 | 13 | 9 | 13 | 14 | 11 | 14 | 9 | 15 | 11 | 8 | 13 | 13 | 11 | 10
67 | 74 | 46 | 92 | 138 | 173 | 221 | 269 | 309 | 361 | 408 | 452 | 495 | 540 | 599 | 16 | 11 | 10 | 9 | 16 | 12 | 10 | 8 | 12 | 9 | 11 | 14 | 9 | 8 | 9 | 9 | 13 | 14 | 8 | 13 | 15 | 8 | 15 | 10 | 8 | 8 | 12 | 12 | 13 | 15 | 14 | 10 | 12 | 16 | 10 | 9 | 8 | 9 | 15 | 12 | 9 | 14 | 12 | 8 | 13 | 8 | 16 | 8 | 15 | 16 | 14 | 14
68 | 76 | 54 | 101 | 150 | 207 | 254 | 296 | 336 | 388 | 437 | 479 | 519 | 563 | 613 | 9 | 15 | 15 | 15 | 9 | 13 | 13 | 12 | 15 | 10 | 9 | 15 | 15 | 13 | 14 | 15 | 11 | 11 | 11 | 14 | 8 | 10 | 9 | 15 | 8 | 12 | 12 | 8 | 14 | 8 | 15 | 15 | 14 | 12 | 10 | 13 | 14 | 8 | 8 | 12 | 10 | 11 | 8 | 11 | 8 | 11 | 13 | 12 | 14 | 11 | 10 | 15
69 | 70 | 40 | 91 | 147 | 201 | 257 | 304 | 354 | 400 | 448 | 488 | 535 | 580 | 627 | 9 | 8 | 10 | 13 | 15 | 15 | 10 | 11 | 14 | 11 | 16 | 15 | 15 | 11 | 14 | 14 | 16 | 11 | 16 | 13 | 12 | 8 | 15 | 12 | 14 | 11 | 9 | 16 | 8 | 9 | 16 | 13 | 14 | 8 | 13 | 13 | 8 | 11 | 8 | 13 | 13 | 9 | 13 | 12 | 9 | 12 | 12 | 12 | 13 | 9 | 16 | 9
70 | 71 | 46 | 97 | 144 | 198 | 246 | 299 | 342 | 390 | 445 | 499 | 541 | 591 | 641 | 10 | 10 | 12 | 14 | 10 | 15 | 14 | 12 | 15 | 11 | 11 | 10 | 10 | 14 | 15 | 15 | 9 | 10 | 16 | 13 | 16 | 15 | 8 | 14 | 12 | 8 | 8 | 15 | 16 | 12 | 10 | 10 | 14 | 15 | 14 | 12 | 14 | 12 | 14 | 14 | 9 | 8 | 14 | 11 | 14 | 16 | 10 | 10 | 12 | 12 | 12 | 14
71 | 77 | 50 | 104 | 154 | 206 | 260 | 307 | 349 | 388 | 433 | 489 | 538 | 591 | 637 | 16 | 15 | 10 | 9 | 13 | 14 | 15 | 12 | 12 | 11 | 12 | 15 | 13 | 13 | 12 | 14 | 15 | 12 | 12 | 15 | 10 | 11 | 12 | 14 | 10 | 10 | 14 | 8 | 11 | 8 | 9 | 11 | 11 | 11 | 14 | 9 | 16 | 16 | 14 | 10 | 16 | 13 | 8 | 12 | 14 | 14 | 15 | 10 | 10 | 11 | 11 | 14
72 | 65 | 43 | 93 | 137 | 175 | 219 | 277 | 332 | 386 | 439 | 489 | 535 | 577 | 638 | 9 | 14 | 12 | 8 | 12 | 10 | 16 | 12 | 13 | 9 | 9 | 13 | 12 | 8 | 8 | 10 | 10 | 9 | 11 | 14 | 15 | 11 | 16 | 16 | 13 | 16 | 16 | 10 | 16 | 11 | 12 | 15 | 15 | 11 | 15 | 12 | 14 | 14 | 14 | 8 | 12 | 10 | 11 | 13 | 9 | 10 | 15 | 8 | 15 | 15 | 16 | 15
73 | 60 | 38 | 87 | 131 | 189 | 233 | 286 | 338 | 380 | 431 | 472 | 517 | 564 | 614 | 10 | 11 | 9 | 8 | 8 | 14 | 14 | 13 | 9 | 11 | 10 | 14 | 15 | 15 | 12 | 16 | 9 | 9 | 12 | 14 | 13 | 15 | 10 | 15 | 14 | 16 | 14 | 8 | 9 | 15 | 10 | 8 | 15 | 13 | 10 | 13 | 9 | 8 | 10 | 14 | 11 | 12 | 11 | 11 | 13 | 8 | 12 | 14 | 8 | 16 | 13 | 13
74 | 70 | 45 | 96 | 144 | 192 | 247 | 302 | 356 | 406 | 442 | 482 | 527 | 580 | 627 | 13 | 9 | 11 | 12 | 12 | 13 | 11 | 15 | 9 | 14 | 9 | 16 | 15 | 11 | 8 | 14 | 12 | 12 | 16 | 15 | 16 | 14 | 14 | 11 | 13 | 16 | 11 | 14 | 16 | 8 | 15 | 11 | 9 | 10 | 9 | 8 | 10 | 9 | 12 | 9 | 9 | 15 | 8 | 13 | 14 | 14 | 13 | 12 | 11 | 12 | 10 | 14
75 | 74 | 57 | 97 | 144 | 194 | 245 | 292 | 343 | 397 | 447 | 492 | 541 | 583 | 634 | 12 | 15 | 16 | 14 | 9 | 8 | 9 | 14 | 11 | 11 | 9 | 16 | 11 | 15 | 12 | 12 | 15 | 11 | 9 | 16 | 12 | 15 | 12 | 8 | 15 | 12 | 10 | 14 | 11 | 15 | 14 | 14 | 14 | 13 | 11 | 12 | 8 | 10 | 16 | 11 | 13 | 13 | 10 | 13 | 11 | 9 | 13 | 9 | 11 | 14 | 10 | 16
76 | 69 | 47 | 98 | 142 | 194 | 244 | 297 | 356 | 411 | 465 | 510 | 568 | 617 | 668 | 13 | 14 | 8 | 12 | 11 | 11 | 14 | 15 | 13 | 10 | 12 | 9 | 16 | 9 | 16 | 11 | 11 | 13 | 14 | 12 | 14 | 14 | 16 | 9 | 14 | 14 | 16 | 15 | 16 | 16 | 12 | 11 | 16 | 16 | 12 | 10 | 11 | 15 | 11 | 8 | 13 | 15 | 15 | 15 | 14 | 14 | 9 | 12 | 13 | 10 | 14 | 14
77 | 56 | 36 | 78 | 123 | 168 | 209 | 252 | 304 | 352 | 396 | 443 | 500 | 547 | 595 | 8 | 10 | 10 | 8 | 11 | 9 | 13 | 9 | 10 | 11 | 15 | 9 | 8 | 12 | 9 | 16 | 8 | 8 | 15 | 10 | 9 | 10 | 15 | 9 | 16 | 10 | 11 | 15 | 8 | 14 | 16 | 10 | 9 | 8 | 11 | 16 | 12 | 12 | 15 | 8 | 12 | 16 | 13 | 16 | 11 | 8 | 12 | 16 | 16 | 9 | 14 | 9
78 | 77 | 49 | 98 | 141 | 193 | 244 | 289 | 334 | 389 | 440 | 491 | 549 | 606 | 659 | 8 | 16 | 9 | 16 | 15 | 13 | 10 | 11 | 14 | 11 | 9 | 9 | 10 | 13 | 13 | 16 | 14 | 8 | 14 | 15 | 10 | 11 | 11 | 13 | 11 | 10 | 16 | 8 | 13 | 15 | 15 | 12 | 11 | 16 | 12 | 12 | 13 | 11 | 14 | 13 | 15 | 16 | 16 | 11 | 15 | 11 | 15 | 16 | 9 | 14 | 15 | 15
79 | 75 | 45 | 92 | 144 | 194 | 239 | 295 | 350 | 395 | 442 | 485 | 535 | 582 | 626 | 8 | 11 | 10 | 16 | 16 | 14 | 9 | 8 | 13 | 11 | 13 | 15 | 11 | 13 | 12 | 14 | 11 | 16 | 9 | 9 | 14 | 15 | 14 | 13 | 15 | 11 | 15 | 14 | 16 | 8 | 8 | 13 | 12 | 15 | 10 | 10 | 8 | 13 | 10 | 12 | 12 | 11 | 13 | 14 | 11 | 13 | 12 | 11 | 9 | 16 | 8 | 11
80 | 64 | 39 | 82 | 132 | 181 | 231 | 285 | 335 | 381 | 424 | 480 | 521 | 564 | 610 | 10 | 11 | 9 | 9 | 11 | 14 | 9 | 9 | 15 | 13 | 10 | 12 | 11 | 14 | 10 | 14 | 11 | 12 | 13 | 14 | 15 | 15 | 8 | 16 | 11 | 9 | 16 | 14 | 16 | 8 | 14 | 8 | 9 | 14 | 12 | 8 | 16 | 10 | 15 | 15 | 16 | 9 | 8 | 8 | 8 | 12 | 8 | 15 | 10 | 14 | 13 | 9
81 | 71 | 48 | 101 | 149 | 195 | 239 | 286 | 337 | 385 | 441 | 493 | 536 | 586 | 633 | 13 | 11 | 14 | 10 | 12 | 11 | 15 | 15 | 9 | 14 | 11 | 14 | 16 | 12 | 9 | 9 | 14 | 9 | 9 | 12 | 11 | 11 | 14 | 11 | 16 | 8 | 12 | 15 | 15 | 10 | 15 | 8 | 11 | 14 | 15 | 16 | 11 | 11 | 15 | 15 | 9 | 9 | 12 | 13 | 16 | 9 | 11 | 14 | 10 | 11 | 13 | 13
82 | 70 | 48 | 98 | 147 | 190 | 241 | 290 | 342 | 398 | 450 | 501 | 549 | 599 | 647 | 11 | 15 | 8 | 14 | 14 | 8 | 15 | 13 | 14 | 12 | 14 | 9 | 9 | 10 | 8 | 16 | 11 | 12 | 16 | 12 | 12 | 13 | 14 | 10 | 13 | 11 | 15 | 13 | 16 | 13 | 11 | 16 | 13 | 13 | 15 | 11 | 10 | 12 | 14 | 15 | 11 | 13 | 16 | 8 | 9 | 12 | 16 | 13 | 14 | 9 | 11 | 14
83 | 74 | 47 | 93 | 138 | 189 | 230 | 283 | 330 | 373 | 411 | 460 | 508 | 551 | 604 | 11 | 15 | 8 | 13 | 11 | 16 | 10 | 9 | 8 | 15 | 13 | 9 | 11 | 13 | 12 | 15 | 14 | 9 | 8 | 10 | 13 | 16 | 14 | 10 | 16 | 9 | 9 | 13 | 11 | 16 | 8 | 8 | 12 | 10 | 8 | 8 | 14 | 8 | 15 | 12 | 15 | 12 | 12 | 9 | 11 | 8 | 10 | 14 | 8 | 13 | 16 | 16
84 | 71 | 46 | 90 | 137 | 185 | 227 | 277 | 316 | 360 | 408 | 455 | 491 | 534 | 588 | 8 | 13 | 14 | 11 | 10 | 15 | 10 | 9 | 8 | 16 | 12 | 11 | 8 | 15 | 15 | 10 | 9 | 10 | 8 | 15 | 13 | 10 | 16 | 11 | 10 | 11 | 10 | 8 | 12 | 8 | 8 | 16 | 13 | 10 | 11 | 14 | 10 | 8 | 15 | 14 | 11 | 9 | 8 | 8 | 8 | 11 | 9 | 15 | 16 | 13 | 10 | 15
85 | 75 | 45 | 99 | 150 | 199 | 252 | 292 | 346 | 392 | 438 | 489 | 532 | 588 | 631 | 14 | 9 | 14 | 8 | 15 | 15 | 14 | 10 | 16 | 14 | 13 | 8 | 10 | 8 | 15 | 16 | 15 | 15 | 8 | 15 | 8 | 11 | 8 | 13 | 11 | 14 | 15 | 14 | 11 | 11 | 11 | 13 | 13 | 9 | 8 | 16 | 15 | 9 | 16 | 11 | 12 | 9 | 8 | 14 | 15 | 14 | 16 | 11 | 8 | 9 | 14 | 12
86 | 76 | 53 | 99 | 141 | 193 | 243 | 291 | 333 | 383 | 435 | 476 | 515 | 564 | 620 | 9 | 15 | 15 | 14 | 8 | 15 | 15 | 8 | 8 | 14 | 11 | 9 | 9 | 11 | 16 | 16 | 8 | 14 | 13 | 15 | 8 | 13 | 16 | 11 | 9 | 12 | 13 | 8 | 14 | 14 | 11 | 11 | 16 | 12 | 9 | 15 | 8 | 8 | 9 | 16 | 10 | 13 | 8 | 8 | 10 | 14 | 13 | 12 | 13 | 14 | 16 | 13
87 | 72 | 48 | 99 | 143 | 195 | 244 | 296 | 346 | 393 | 436 | 478 | 526 | 576 | 616 | 14 | 12 | 8 | 14 | 11 | 13 | 16 | 11 | 11 | 10 | 13 | 10 | 12 | 15 | 16 | 9 | 9 | 14 | 12 | 14 | 12 | 11 | 14 | 15 | 12 | 16 | 12 | 10 | 11 | 11 | 15 | 10 | 11 | 13 | 8 | 11 | 11 | 15 | 8 | 8 | 11 | 15 | 9 | 13 | 15 | 16 | 9 | 10 | 9 | 8 | 14 | 9
88 | 69 | 48 | 95 | 129 | 175 | 219 | 261 | 313 | 357 | 400 | 447 | 492 | 542 | 602 | 11 | 16 | 9 | 12 | 12 | 9 | 13 | 13 | 8 | 8 | 10 | 8 | 14 | 15 | 8 | 9 | 10 | 13 | 11 | 10 | 11 | 14 | 9 | 8 | 16 | 9 | 14 | 13 | 12 | 8 | 12 | 12 | 11 | 9 | 12 | 11 | 8 | 16 | 12 | 11 | 10 | 15 | 12 | 8 | 8 | 16 | 16 | 10 | 14 | 16 | 14 | 16
89 | 67 | 48 | 92 | 142 | 191 | 237 | 284 | 338 | 385 | 435 | 481 | 539 | 582 | 631 | 9 | 15 | 15 | 9 | 9 | 10 | 16 | 9 | 15 | 12 | 9 | 14 | 14 | 12 | 8 | 15 | 15 | 14 | 9 | 8 | 9 | 13 | 15 | 10 | 11 | 16 | 12 | 15 | 12 | 14 | 10 | 11 | 12 | 13 | 14 | 11 | 9 | 10 | 15 | 12 | 13 | 16 | 14 | 15 | 9 | 14 | 10 | 10 | 9 | 12 | 15 | 13
90 | 59 | 40 | 77 | 124 | 178 | 234 | 284 | 331 | 383 | 424 | 468 | 517 | 566 | 613 | 14 | 8 | 9 | 9 | 9 | 10 | 9 | 9 | 12 | 8 | 13 | 14 | 15 | 13 | 13 | 13 | 15 | 15 | 14 | 12 | 16 | 11 | 13 | 10 | 9 | 13 | 10 | 15 | 16 | 10 | 10 | 16 | 11 | 8 | 13 | 9 | 13 | 8 | 14 | 9 | 16 | 9 | 13 | 11 | 15 | 10 | 8 | 16 | 9 | 14 | 13 | 11
91 | 77 | 49 | 100 | 147 | 198 | 246 | 299 | 351 | 392 | 445 | 497 | 539 | 583 | 639 | 11 | 16 | 10 | 12 | 13 | 15 | 13 | 10 | 10 | 12 | 11 | 14 | 15 | 10 | 16 | 10 | 11 | 14 | 9 | 14 | 11 | 11 | 16 | 15 | 12 | 13 | 15 | 12 | 9 | 9 | 14 | 9 | 16 | 9 | 14 | 14 | 14 | 16 | 10 | 12 | 12 | 8 | 13 | 9 | 9 | 11 | 15 | 9 | 14 | 16 | 12 | 14
92 | 68 | 45 | 93 | 136 | 186 | 233 | 277 | 327 | 374 | 423 | 479 | 521 | 572 | 622 | 10 | 16 | 11 | 8 | 12 | 11 | 16 | 9 | 13 | 9 | 11 | 10 | 16 | 12 | 9 | 13 | 9 | 16 | 11 | 11 | 8 | 16 | 12 | 8 | 15 | 12 | 15 | 8 | 13 | 9 | 11 | 14 | 9 | 10 | 16 | 14 | 15 | 11 | 15 | 15 | 11 | 9 | 11 | 11 | 14 | 16 | 10 | 11 | 15 | 14 | 8 | 13
93 | 81 | 58 | 99 | 146 | 195 | 249 | 293 | 339 | 390 | 434 | 483 | 535 | 583 | 627 | 13 | 14 | 15 | 16 | 15 | 8 | 10 | 8 | 8 | 15 | 16 | 8 | 9 | 10 | 16 | 14 | 16 | 13 | 9 | 16 | 11 | 9 | 11 | 13 | 9 | 13 | 11 | 13 | 15 | 16 | 10 | 10 | 14 | 8 | 12 | 10 | 16 | 10 | 13 | 10 | 15 | 11 | 15 | 11 | 16 | 14 | 8 | 10 | 8 | 15 | 8 | 13
94 | 66 | 44 | 92 | 139 | 185 | 232 | 282 | 323 | 372 | 425 | 477 | 537 | 578 | 624 | 15 | 12 | 9 | 8 | 12 | 10 | 11 | 15 | 16 | 11 | 11 | 9 | 15 | 9 | 11 | 11 | 12 | 16 | 11 | 8 | 11 | 12 | 15 | 12 | 8 | 16 | 9 | 8 | 8 | 16 | 14 | 11 | 15 | 13 | 14 | 11 | 8 | 16 | 12 | 16 | 16 | 16 | 13 | 15 | 10 | 11 | 9 | 11 | 11 | 10 | 13 | 12
95 | 69 | 48 | 94 | 141 | 181 | 230 | 280 | 333 | 385 | 432 | 473 | 510 | 563 | 619 | 12 | 11 | 9 | 16 | 13 | 8 | 15 | 10 | 10 | 14 | 10 | 13 | 11 | 13 | 8 | 8 | 10 | 15 | 8 | 16 | 14 | 15 | 12 | 9 | 15 | 15 | 11 | 12 | 12 | 16 | 9 | 15 | 9 | 8 | 16 | 14 | 9 | 8 | 9 | 15 | 9 | 9 | 10 | 9 | 8 | 16 | 16 | 13 | 15 | 13 | 12 | 16
96 | 58 | 40 | 78 | 127 | 177 | 227 | 272 | 318 | 363 | 410 | 466 | 511 | 556 | 600 | 15 | 8 | 8 | 9 | 8 | 10 | 12 | 8 | 16 | 16 | 8 | 9 | 12 | 16 | 9 | 13 | 14 | 14 | 13 | 9 | 10 | 15 | 12 | 8 | 11 | 9 | 12 | 14 | 8 | 14 | 9 | 14 | 14 | 10 | 10 | 13 | 14 | 15 | 13 | 14 | 12 | 8 | 9 | 16 | 11 | 13 | 10 | 11 | 13 | 10 | 10 | 11
97 | 68 | 48 | 89 | 128 | 170 | 222 | 267 | 314 | 368 | 406 | 442 | 494 | 532 | 576 | 11 | 13 | 13 | 11 | 8 | 12 | 10 | 11 | 8 | 9 | 8 | 14 | 15 | 11 | 8 | 8 | 15 | 12 | 10 | 15 | 15 | 11 | 8 | 11 | 16 | 11 | 10 | 10 | 14 | 15 | 15 | 10 | 8 | 12 | 10 | 8 | 10 | 8 | 8 | 10 | 13 | 14 | 10 | 15 | 9 | 8 | 12 | 9 | 15 | 8 | 13 | 8
98 | 65 | 46 | 92 | 153 | 215 | 268 | 315 | 365 | 411 | 455 | 499 | 547 | 598 | 642 | 16 | 9 | 10 | 11 | 10 | 9 | 13 | 14 | 15 | 16 | 15 | 15 | 16 | 16 | 15 | 15 | 14 | 15 | 13 | 11 | 8 | 8 | 15 | 16 | 14 | 9 | 12 | 15 | 9 | 9 | 13 | 15 | 10 | 10 | 10 | 14 | 10 | 11 | 15 | 8 | 10 | 16 | 12 | 10 | 12 | 13 | 13 | 13 | 13 | 8 | 8 | 15
99 | 80 | 58 | 100 | 146 | 194 | 241 | 291 | 343 | 383 | 439 | 483 | 534 | 577 | 626 | 15 | 14 | 14 | 15 | 11 | 11 | 12 | 8 | 14 | 12 | 10 | 10 | 16 | 14 | 10 | 8 | 16 | 8 | 9 | 14 | 13 | 8 | 13 | 16 | 12 | 12 | 14 | 14 | 14 | 8 | 10 | 8 | 14 | 15 | 15 | 12 | 8 | 14 | 14 | 8 | 13 | 16 | 11 | 11 | 13 | 13 | 9 | 8 | 9 | 15 | 14 | 11
100 | 64 | 45 | 83 | 137 | 180 | 224 | 279 | 328 | 382 | 433 | 475 | 524 | 571 | 627 | 12 | 12 | 13 | 8 | 10 | 9 | 9 | 10 | 15 | 9 | 14 | 16 | 16 | 10 | 8 | 9 | 12 | 12 | 12 | 8 | 13 | 16 | 16 | 10 | 11 | 12 | 15 | 11 | 14 | 14 | 10 | 16 | 13 | 13 | 15 | 10 | 13 | 10 | 9 | 10 | 15 | 16 | 9 | 9 | 10 | 14 | 15 | 8 | 14 | 14 | 12 | 16
101 | 72 | 50 | 100 | 143 | 192 | 242 | 296 | 354 | 406 | 449 | 494 | 548 | 593 | 642 | 11 | 12 | 12 | 15 | 10 | 12 | 13 | 15 | 9 | 14 | 10 | 10 | 10 | 15 | 14 | 10 | 11 | 15 | 12 | 12 | 13 | 16 | 10 | 15 | 13 | 16 | 13 | 16 | 12 | 15 | 14 | 11 | 10 | 14 | 8 | 11 | 12 | 8 | 10 | 15 | 8 | 16 | 15 | 15 | 12 | 9 | 15 | 9 | 12 | 12 | 15 | 10
102 | 64 | 44 | 85 | 125 | 168 | 219 | 260 | 306 | 362 | 400 | 440 | 487 | 533 | 577 | 12 | 8 | 14 | 10 | 10 | 10 | 13 | 8 | 8 | 9 | 10 | 13 | 10 | 10 | 14 | 9 | 13 | 11 | 14 | 13 | 10 | 10 | 10 | 11 | 8 | 8 | 15 | 15 | 15 | 14 | 13 | 14 | 8 | 10 | 10 | 10 | 12 | 12 | 8 | 8 | 11 | 14 | 13 | 9 | 14 | 9 | 10 | 13 | 8 | 13 | 11 | 12
103 | 72 | 53 | 100 | 147 | 196 | 237 | 273 | 335 | 390 | 445 | 497 | 545 | 602 | 643 | 14 | 11 | 16 | 12 | 11 | 8 | 15 | 13 | 8 | 8 | 15 | 16 | 13 | 10 | 11 | 15 | 11 | 9 | 11 | 10 | 8 | 12 | 8 | 8 | 16 | 16 | 16 | 14 | 16 | 9 | 16 | 14 | 16 | 10 | 16 | 13 | 16 | 12 | 13 | 11 | 12 | 11 | 16 | 9 | 14 | 14 | 13 | 16 | 10 | 14 | 9 | 8
104 | 84 | 55 | 112 | 154 | 202 | 249 | 295 | 342 | 381 | 427 | 479 | 524 | 581 | 619 | 15 | 14 | 13 | 13 | 14 | 15 | 12 | 16 | 8 | 9 | 11 | 14 | 14 | 9 | 9 | 16 | 13 | 8 | 12 | 14 | 15 | 13 | 8 | 10 | 12 | 9 | 13 | 13 | 8 | 11 | 10 | 10 | 11 | 10 | 13 | 12 | 9 | 12 | 15 | 16 | 10 | 9 | 16 | 10 | 15 | 13 | 13 | 16 | 8 | 11 | 8 | 11
105 | 60 | 41 | 88 | 144 | 196 | 243 | 284 | 337 | 385 | 433 | 482 | 531 | 579 | 622 | 14 | 8 | 10 | 9 | 11 | 8 | 13 | 15 | 16 | 13 | 14 | 13 | 8 | 14 | 14 | 16 | 10 | 14 | 11 | 12 | 10 | 9 | 14 | 8 | 14 | 11 | 15 | 13 | 10 | 14 | 12 | 12 | 15 | 15 | 8 | 10 | 8 | 16 | 9 | 16 | 9 | 11 | 14 | 15 | 16 | 10 | 10 | 12 | 12 | 13 | 10 | 8
106 | 73 | 48 | 101 | 160 | 203 | 253 | 297 | 340 | 389 | 431 | 481 | 531 | 572 | 622 | 9 | 14 | 15 | 10 | 12 | 13 | 15 | 13 | 16 | 16 | 13 | 14 | 12 | 10 | 8 | 13 | 11 | 13 | 14 | 12 | 8 | 12 | 11 | 13 | 10 | 15 | 9 | 9 | 13 | 8 | 13 | 15 | 11 | 10 | 13 | 8 | 13 | 10 | 15 | 12 | 10 | 12 | 14 | 14 | 11 | 11 | 9 | 10 | 10 | 10 | 16 | 14
107 | 73 | 50 | 93 | 141 | 193 | 237 | 293 | 342 | 388 | 434 | 482 | 532 | 575 | 618 | 15 | 15 | 8 | 12 | 9 | 14 | 9 | 11 | 10 | 9 | 13 | 16 | 14 | 12 | 16 | 10 | 13 | 9 | 8 | 14 | 15 | 13 | 14 | 14 | 11 | 12 | 15 | 11 | 15 | 8 | 10 | 13 | 14 | 10 | 12 | 10 | 10 | 14 | 14 | 10 | 13 | 13 | 13 | 11 | 8 | 9 | 14 | 12 | 11 | 9 | 14 | 9
108 | 61 | 42 | 86 | 134 | 190 | 234 | 278 | 318 | 363 | 411 | 460 | 512 | 556 | 603 | 10 | 9 | 8 | 15 | 8 | 11 | 10 | 15 | 8 | 15 | 14 | 11 | 13 | 16 | 15 | 12 | 10 | 13 | 8 | 13 | 15 | 10 | 11 | 8 | 9 | 9 | 10 | 12 | 14 | 11 | 9 | 11 | 15 | 13 | 9 | 11 | 10 | 13 | 16 | 10 | 16 | 14 | 14 | 8 | 8 | 10 | 14 | 12 | 8 | 9 | 15 | 15
109 | 65 | 39 | 93 | 145 | 188 | 243 | 294 | 349 | 402 | 455 | 499 | 546 | 599 | 651 | 9 | 8 | 8 | 14 | 16 | 10 | 12 | 16 | 12 | 14 | 11 | 15 | 12 | 9 | 12 | 10 | 14 | 12 | 16 | 13 | 13 | 14 | 13 | 11 | 16 | 15 | 10 | 14 | 16 | 11 | 10 | 16 | 16 | 8 | 16 | 13 | 13 | 10 | 12 | 9 | 12 | 14 | 8 | 13 | 12 | 14 | 16 | 11 | 13 | 13 | 12 | 14
110 | 78 | 53 | 105 | 147 | 190 | 244 | 291 | 337 | 383 | 441 | 490 | 528 | 564 | 610 | 14 | 15 | 14 | 10 | 16 | 9 | 15 | 12 | 11 | 10 | 13 | 8 | 11 | 12 | 9 | 11 | 12 | 15 | 14 | 13 | 15 | 12 | 10 | 10 | 8 | 14 | 12 | 12 | 8 | 14 | 13 | 11 | 15 | 13 | 16 | 14 | 11 | 13 | 12 | 13 | 13 | 9 | 8 | 8 | 8 | 9 | 10 | 9 | 9 | 12 | 16 | 9
111 | 76 | 51 | 101 | 147 | 193 | 250 | 295 | 350 | 388 | 436 | 486 | 522 | 564 | 615 | 14 | 16 | 10 | 11 | 12 | 13 | 9 | 16 | 8 | 13 | 12 | 13 | 15 | 12 | 11 | 8 | 14 | 13 | 16 | 14 | 8 | 12 | 14 | 11 | 14 | 12 | 13 | 16 | 9 | 9 | 11 | 9 | 8 | 14 | 16 | 10 | 8 | 15 | 11 | 16 | 10 | 9 | 8 | 9 | 9 | 8 | 16 | 9 | 16 | 9 | 10 | 16
112 | 66 | 46 | 95 | 146 | 193 | 237 | 285 | 334 | 370 | 421 | 471 | 519 | 566 | 617 | 13 | 12 | 8 | 13 | 9 | 11 | 13 | 16 | 13 | 15 | 8 | 15 | 14 | 9 | 8 | 16 | 12 | 9 | 8 | 15 | 14 | 10 | 8 | 16 | 10 | 9 | 16 | 14 | 9 | 8 | 8 | 11 | 16 | 11 | 10 | 14 | 12 | 16 | 11 | 11 | 13 | 16 | 11 | 8 | 13 | 9 | 9 | 16 | 15 | 13 | 8 | 15
113 | 75 | 52 | 104 | 151 | 200 | 247 | 301 | 351 | 403 | 457 | 498 | 541 | 588 | 640 | 9 | 16 | 12 | 15 | 9 | 14 | 13 | 16 | 8 | 15 | 9 | 15 | 9 | 11 | 14 | 15 | 10 | 16 | 13 | 8 | 13 | 12 | 13 | 16 | 11 | 15 | 15 | 9 | 14 | 8 | 15 | 15 | 10 | 14 | 16 | 14 | 10 | 11 | 11 | 9 | 11 | 9 | 12 | 11 | 15 | 9 | 12 | 11 | 13 | 13 | 15 | 11
114 | 83 | 58 | 112 | 164 | 208 | 255 | 304 | 362 | 417 | 464 | 525 | 568 | 616 | 665 | 15 | 12 | 15 | 16 | 14 | 11 | 15 | 14 | 13 | 11 | 16 | 12 | 8 | 10 | 14 | 12 | 11 | 13 | 11 | 12 | 11 | 12 | 13 | 13 | 12 | 15 | 15 | 16 | 14 | 16 | 13 | 12 | 14 | 11 | 11 | 11 | 15 | 15 | 15 | 16 | 14 | 12 | 8 | 9 | 10 | 9 | 14 | 15 | 15 | 10 | 12 | 12
115 | 72 | 47 | 96 | 143 | 184 | 228 | 278 | 326 | 377 | 425 | 477 | 512 | 557 | 608 | 11 | 12 | 12 | 12 | 14 | 11 | 15 | 9 | 10 | 10 | 11 | 16 | 13 | 11 | 9 | 8 | 9 | 16 | 8 | 11 | 14 | 11 | 14 | 11 | 10 | 12 | 12 | 14 | 11 | 15 | 13 | 12 | 11 | 11 | 10 | 16 | 12 | 11 | 13 | 16 | 10 | 9 | 8 | 8 | 11 | 15 | 11 | 8 | 14 | 12 | 12 | 13
116 | 62 | 43 | 82 | 135 | 183 | 222 | 275 | 327 | 381 | 430 | 479 | 519 | 562 | 609 | 8 | 8 | 12 | 15 | 8 | 11 | 11 | 9 | 11 | 15 | 15 | 12 | 16 | 9 | 13 | 10 | 8 | 8 | 14 | 9 | 14 | 16 | 10 | 13 | 14 | 14 | 14 | 10 | 15 | 14 | 15 | 10 | 8 | 12 | 15 | 14 | 15 | 14 | 9 | 11 | 14 | 10 | 8 | 8 | 10 | 14 | 9 | 10 | 9 | 13 | 9 | 16
117 | 74 | 45 | 96 | 146 | 185 | 230 | 278 | 323 | 383 | 431 | 481 | 530 | 575 | 622 | 11 | 11 | 8 | 15 | 14 | 15 | 9 | 13 | 12 | 9 | 16 | 13 | 9 | 9 | 8 | 13 | 13 | 11 | 9 | 12 | 8 | 14 | 10 | 16 | 9 | 12 | 14 | 10 | 14 | 16 | 16 | 14 | 10 | 13 | 16 | 9 | 14 | 12 | 8 | 16 | 16 | 11 | 12 | 10 | 15 | 12 | 10 | 8 | 15 | 13 | 11 | 8
118 | 77 | 49 | 100 | 153 | 208 | 270 | 316 | 358 | 405 | 453 | 490 | 535 | 574 | 618 | 12 | 9 | 16 | 12 | 13 | 15 | 15 | 8 | 14 | 13 | 16 | 10 | 15 | 16 | 8 | 16 | 15 | 15 | 16 | 16 | 12 | 11 | 11 | 12 | 10 | 8 | 11 | 13 | 11 | 12 | 8 | 16 | 13 | 13 | 8 | 14 | 9 | 8 | 8 | 12 | 13 | 10 | 14 | 8 | 10 | 12 | 8 | 9 | 10 | 9 | 10 | 15
119 | 53 | 36 | 78 | 128 | 174 | 221 | 269 | 314 | 368 | 420 | 472 | 518 | 566 | 614 | 8 | 9 | 9 | 10 | 9 | 8 | 15 | 10 | 15 | 15 | 11 | 9 | 9 | 12 | 11 | 14 | 15 | 8 | 8 | 16 | 9 | 14 | 16 | 9 | 13 | 15 | 9 | 8 | 16 | 12 | 12 | 14 | 10 | 15 | 16 | 11 | 12 | 16 | 14 | 10 | 9 | 11 | 13 | 13 | 16 | 10 | 11 | 11 | 12 | 10 | 13 | 13
120 | 63 | 40 | 90 | 139 | 185 | 232 | 280 | 333 | 374 | 423 | 475 | 524 | 576 | 622 | 10 | 8 | 11 | 11 | 13 | 10 | 14 | 13 | 13 | 11 | 9 | 16 | 14 | 8 | 8 | 16 | 15 | 13 | 10 | 9 | 12 | 12 | 9 | 15 | 14 | 10 | 15 | 14 | 11 | 12 | 10 | 8 | 9 | 9 | 16 | 15 | 8 | 14 | 16 | 14 | 13 | 14 | 12 | 10 | 10 | 16 | 12 | 14 | 16 | 11 | 10 | 9
121 | 77 | 55 | 98 | 154 | 198 | 242 | 291 | 341 | 390 | 436 | 492 | 540 | 594 | 637 | 14 | 13 | 15 | 13 | 14 | 8 | 9 | 12 | 15 | 16 | 11 | 14 | 10 | 12 | 14 | 8 | 8 | 11 | 11 | 14 | 11 | 9 | 15 | 14 | 15 | 12 | 15 | 8 | 14 | 10 | 12 | 13 | 15 | 11 | 12 | 8 | 8 | 16 | 16 | 16 | 16 | 13 | 8 | 11 | 10 | 16 | 16 | 12 | 9 | 9 | 12 | 13
122 | 80 | 54 | 100 | 150 | 195 | 249 | 290 | 335 | 388 | 447 | 501 | 552 | 604 | 661 | 9 | 16 | 14 | 15 | 14 | 12 | 10 | 10 | 10 | 16 | 8 | 16 | 10 | 10 | 15 | 10 | 14 | 14 | 12 | 14 | 10 | 9 | 11 | 11 | 12 | 16 | 9 | 8 | 12 | 16 | 15 | 10 | 14 | 15 | 14 | 16 | 14 | 16 | 9 | 15 | 12 | 14 | 9 | 16 | 12 | 13 | 12 | 15 | 16 | 15 | 11 | 15
123 | 78 | 54 | 102 | 147 | 208 | 249 | 291 | 341 | 397 | 450 | 505 | 559 | 612 | 665 | 16 | 9 | 14 | 15 | 10 | 14 | 16 | 8 | 11 | 12 | 8 | 14 | 16 | 15 | 16 | 14 | 15 | 8 | 8 | 10 | 12 | 8 | 14 | 8 | 13 | 11 | 15 | 11 | 16 | 16 | 13 | 11 | 11 | 14 | 12 | 16 | 15 | 13 | 12 | 15 | 16 | 16 | 11 | 11 | 15 | 15 | 15 | 8 | 14 | 10 | 15 | 14
124 | 73 | 54 | 96 | 142 | 190 | 237 | 279 | 325 | 375 | 422 | 471 | 522 | 565 | 616 | 14 | 15 | 11 | 14 | 11 | 8 | 15 | 8 | 8 | 15 | 10 | 13 | 9 | 14 | 13 | 12 | 10 | 15 | 11 | 11 | 9 | 9 | 8 | 16 | 13 | 13 | 10 | 10 | 16 | 13 | 11 | 10 | 16 | 8 | 13 | 10 | 12 | 10 | 11 | 16 | 10 | 10 | 16 | 15 | 8 | 15 | 12 | 8 | 12 | 10 | 15 | 14
125 | 76 | 46 | 98 | 146 | 199 | 248 | 299 | 350 | 395 | 440 | 497 | 542 | 580 | 625 | 11 | 10 | 16 | 9 | 16 | 14 | 10 | 12 | 8 | 12 | 15 | 13 | 16 | 14 | 14 | 9 | 12 | 14 | 14 | 9 | 11 | 15 | 9 | 16 | 12 | 15 | 8 | 16 | 13 | 15 | 9 | 8 | 9 | 11 | 12 | 13 | 16 | 13 | 16 | 12 | 12 | 16 | 9 | 8 | 10 | 8 | 10 | 10 | 12 | 12 | 9 | 12
126 | 76 | 46 | 95 | 143 | 200 | 255 | 308 | 364 | 416 | 463 | 514 | 565 | 618 | 663 | 8 | 15 | 11 | 12 | 14 | 16 | 8 | 11 | 14 | 10 | 13 | 11 | 15 | 15 | 12 | 15 | 9 | 15 | 16 | 15 | 16 | 11 | 16 | 10 | 15 | 16 | 9 | 16 | 13 | 16 | 11 | 12 | 8 | 11 | 15 | 13 | 13 | 14 | 10 | 14 | 14 | 11 | 14 | 12 | 16 | 10 | 15 | 12 | 8 | 14 | 14 | 9
127 | 75 | 50 | 99 | 137 | 175 | 214 | 265 | 313 | 356 | 400 | 450 | 503 | 552 | 602 | 13 | 10 | 16 | 11 | 15 | 10 | 9 | 15 | 11 | 11 | 8 | 8 | 8 | 9 | 9 | 12 | 8 | 13 | 10 | 8 | 12 | 8 | 16 | 15 | 11 | 14 | 12 | 11 | 10 | 13 | 12 | 8 | 14 | 11 | 10 | 9 | 11 | 14 | 9 | 16 | 16 | 11 | 10 | 16 | 16 | 15 | 10 | 8 | 16 | 11 | 12 | 11
128 | 79 | 53 | 101 | 150 | 197 | 248 | 287 | 327 | 374 | 416 | 468 | 515 | 567 | 617 | 11 | 16 | 13 | 13 | 10 | 16 | 12 | 10 | 10 | 16 | 10 | 13 | 12 | 11 | 11 | 13 | 11 | 14 | 12 | 14 | 13 | 9 | 9 | 8 | 11 | 11 | 9 | 9 | 13 | 11 | 8 | 15 | 11 | 8 | 12 | 11 | 14 | 16 | 12 | 10 | 10 | 13 | 14 | 10 | 16 | 14 | 9 | 13 | 11 | 13 | 14 | 12
129 | 69 | 45 | 92 | 139 | 187 | 231 | 281 | 331 | 387 | 424 | 465 | 513 | 559 | 601 | 11 | 9 | 10 | 15 | 13 | 11 | 13 | 10 | 12 | 12 | 14 | 9 | 13 | 8 | 16 | 11 | 8 | 13 | 8 | 15 | 16 | 14 | 10 | 10 | 8 | 15 | 11 | 16 | 14 | 11 | 16 | 15 | 8 | 9 | 12 | 8 | 11 | 12 | 8 | 10 | 13 | 13 | 11 | 11 | 10 | 16 | 12 | 8 | 15 | 8 | 8 | 11
130 | 68 | 42 | 97 | 143 | 197 | 237 | 277 | 332 | 385 | 439 | 482 | 518 | 557 | 601 | 9 | 8 | 16 | 9 | 13 | 13 | 13 | 16 | 8 | 13 | 15 | 10 | 13 | 13 | 15 | 13 | 8 | 12 | 8 | 12 | 12 | 8 | 10 | 10 | 15 | 16 | 13 | 11 | 15 | 12 | 16 | 10 | 11 | 14 | 14 | 15 | 15 | 9 | 8 | 11 | 9 | 8 | 11 | 8 | 9 | 10 | 11 | 9 | 13 | 8 | 15 | 8
131 | 73 | 46 | 101 | 145 | 194 | 246 | 300 | 341 | 386 | 425 | 465 | 511 | 567 | 610 | 10 | 8 | 14 | 14 | 11 | 16 | 13 | 15 | 14 | 8 | 14 | 8 | 13 | 12 | 9 | 15 | 13 | 16 | 10 | 13 | 15 | 16 | 14 | 9 | 8 | 15 | 9 | 9 | 8 | 14 | 9 | 14 | 8 | 9 | 14 | 8 | 9 | 12 | 10 | 9 | 14 | 12 | 12 | 8 | 13 | 16 | 16 | 11 | 9 | 9 | 14 | 11
132 | 89 | 59 | 117 | 167 | 209 | 249 | 301 | 354 | 396 | 439 | 483 | 526 | 578 | 623 | 15 | 16 | 13 | 15 | 15 | 15 | 14 | 14 | 16 | 12 | 10 | 12 | 15 | 9 | 10 | 8 | 14 | 8 | 9 | 9 | 11 | 11 | 14 | 16 | 15 | 14 | 16 | 8 | 8 | 8 | 12 | 14 | 9 | 8 | 10 | 16 | 11 | 11 | 13 | 9 | 9 | 16 | 8 | 10 | 9 | 14 | 15 | 14 | 14 | 10 | 9 | 12
133 | 78 | 56 | 100 | 137 | 178 | 226 | 272 | 310 | 359 | 408 | 467 | 517 | 570 | 620 | 13 | 16 | 15 | 12 | 8 | 14 | 14 | 8 | 10 | 10 | 8 | 9 | 12 | 9 | 10 | 10 | 15 | 9 | 15 | 9 | 11 | 11 | 9 | 15 | 8 | 12 | 9 | 9 | 8 | 13 | 15 | 13 | 14 | 12 | 15 | 8 | 15 | 16 | 12 | 16 | 9 | 10 | 16 | 15 | 13 | 10 | 16 | 14 | 12 | 12 | 13 | 13
134 | 75 | 45 | 104 | 157 | 209 | 252 | 299 | 352 | 396 | 443 | 501 | 550 | 598 | 640 | 8 | 12 | 13 | 12 | 15 | 15 | 13 | 16 | 15 | 14 | 12 | 12 | 14 | 15 | 11 | 12 | 10 | 11 | 10 | 12 | 12 | 13 | 14 | 8 | 15 | 15 | 8 | 15 | 12 | 16 | 8 | 8 | 8 | 14 | 12 | 13 | 13 | 16 | 14 | 15 | 9 | 10 | 16 | 14 | 11 | 16 | 11 | 10 | 11 | 9 | 11 | 11
135 | 74 | 52 | 104 | 155 | 200 | 250 | 298 | 352 | 407 | 445 | 497 | 548 | 602 | 655 | 10 | 15 | 12 | 15 | 12 | 10 | 15 | 15 | 9 | 12 | 16 | 14 | 9 | 9 | 16 | 11 | 13 | 10 | 12 | 15 | 10 | 11 | 11 | 16 | 9 | 15 | 14 | 16 | 16 | 11 | 14 | 14 | 11 | 9 | 9 | 9 | 10 | 14 | 13 | 15 | 11 | 12 | 12 | 16 | 12 | 15 | 15 | 12 | 11 | 12 | 15 | 15
136 | 62 | 38 | 79 | 131 | 182 | 224 | 259 | 308 | 351 | 398 | 444 | 496 | 539 | 585 | 8 | 8 | 8 | 14 | 10 | 14 | 8 | 9 | 14 | 11 | 14 | 13 | 13 | 13 | 15 | 10 | 10 | 9 | 10 | 13 | 10 | 8 | 8 | 9 | 12 | 10 | 16 | 11 | 9 | 9 | 12 | 13 | 8 | 12 | 14 | 13 | 8 | 10 | 15 | 13 | 16 | 11 | 11 | 14 | 13 | 8 | 8 | 14 | 16 | 13 | 9 | 8
137 | 79 | 54 | 101 | 144 | 186 | 239 | 281 | 320 | 364 | 419 | 460 | 507 | 552 | 603 | 14 | 14 | 10 | 16 | 11 | 14 | 13 | 9 | 10 | 8 | 11 | 14 | 10 | 8 | 14 | 10 | 13 | 15 | 13 | 12 | 14 | 9 | 11 | 8 | 9 | 10 | 9 | 11 | 8 | 13 | 10 | 13 | 15 | 16 | 9 | 15 | 8 | 12 | 8 | 13 | 11 | 10 | 13 | 13 | 10 | 11 | 9 | 15 | 13 | 13 | 10 | 15
138 | 78 | 53 | 105 | 155 | 212 | 259 | 310 | 358 | 405 | 451 | 503 | 558 | 603 | 648 | 16 | 9 | 12 | 16 | 10 | 15 | 15 | 12 | 15 | 13 | 8 | 14 | 14 | 16 | 11 | 16 | 15 | 9 | 9 | 14 | 11 | 16 | 12 | 12 | 14 | 9 | 14 | 11 | 12 | 15 | 9 | 11 | 15 | 10 | 13 | 8 | 16 | 8 | 14 | 14 | 15 | 11 | 14 | 15 | 13 | 11 | 8 | 13 | 12 | 15 | 10 | 8
139 | 68 | 47 | 92 | 142 | 188 | 233 | 286 | 338 | 389 | 438 | 481 | 517 | 572 | 623 | 16 | 9 | 11 | 11 | 11 | 10 | 11 | 13 | 10 | 16 | 14 | 10 | 12 | 9 | 16 | 9 | 8 | 12 | 9 | 16 | 12 | 15 | 13 | 13 | 15 | 12 | 12 | 13 | 14 | 12 | 11 | 14 | 15 | 15 | 8 | 11 | 10 | 16 | 8 | 9 | 8 | 8 | 10 | 10 | 10 | 14 | 16 | 15 | 13 | 11 | 13 | 14
140 | 77 | 53 | 100 | 146 | 198 | 248 | 297 | 338 | 379 | 423 | 475 | 533 | 579 | 625 | 16 | 8 | 14 | 15 | 14 | 10 | 12 | 11 | 15 | 13 | 8 | 10 | 10 | 15 | 16 | 11 | 12 | 14 | 16 | 8 | 13 | 16 | 11 | 9 | 10 | 11 | 9 | 11 | 14 | 8 | 8 | 11 | 9 | 13 | 9 | 13 | 14 | 14 | 12 | 12 | 16 | 15 | 14 | 13 | 10 | 12 | 10 | 14 | 11 | 11 | 15 | 9
141 | 67 | 48 | 86 | 132 | 184 | 237 | 283 | 328 | 368 | 411 | 458 | 515 | 557 | 596 | 10 | 14 | 13 | 11 | 9 | 10 | 9 | 10 | 12 | 10 | 9 | 15 | 13 | 14 | 11 | 14 | 14 | 14 | 11 | 14 | 9 | 10 | 16 | 11 | 11 | 12 | 13 | 9 | 12 | 9 | 10 | 9 | 9 | 8 | 14 | 12 | 14 | 8 | 16 | 9 | 15 | 15 | 16 | 11 | 12 | 8 | 10 | 12 | 8 | 15 | 8 | 8
142 | 77 | 52 | 106 | 150 | 195 | 252 | 295 | 338 | 394 | 438 | 482 | 531 | 576 | 625 | 12 | 14 | 14 | 12 | 10 | 15 | 16 | 13 | 12 | 8 | 8 | 16 | 8 | 13 | 13 | 11 | 16 | 14 | 16 | 11 | 9 | 9 | 16 | 9 | 10 | 10 | 10 | 13 | 14 | 13 | 14 | 15 | 10 | 14 | 9 | 11 | 9 | 8 | 12 | 15 | 11 | 11 | 15 | 12 | 10 | 13 | 13 | 9 | 8 | 11 | 14 | 16
143 | 85 | 55 | 110 | 163 | 207 | 270 | 315 | 360 | 411 | 459 | 508 | 558 | 612 | 666 | 15 | 11 | 15 | 14 | 16 | 14 | 14 | 11 | 16 | 14 | 10 | 13 | 12 | 8 | 8 | 16 | 16 | 16 | 15 | 16 | 11 | 15 | 9 | 10 | 9 | 12 | 8 | 16 | 15 | 14 | 13 | 9 | 14 | 9 | 16 | 9 | 12 | 12 | 16 | 9 | 12 | 13 | 14 | 11 | 12 | 14 | 15 | 13 | 16 | 13 | 15 | 10
144 | 85 | 56 | 114 | 163 | 213 | 263 | 306 | 354 | 401 | 443 | 498 | 540 | 584 | 625 | 14 | 11 | 15 | 16 | 13 | 16 | 14 | 15 | 16 | 12 | 12 | 9 | 11 | 15 | 15 | 9 | 13 | 13 | 12 | 12 | 13 | 8 | 11 | 11 | 10 | 16 | 8 | 14 | 10 | 11 | 12 | 14 | 15 | 8 | 8 | 11 | 16 | 13 | 16 | 10 | 9 | 16 | 9 | 8 | 8 | 11 | 15 | 10 | 14 | 9 | 8 | 10
145 | 67 | 48 | 96 | 141 | 191 | 240 | 289 | 336 | 379 | 424 | 470 | 517 | 566 | 611 | 13 | 16 | 10 | 9 | 11 | 8 | 15 | 14 | 11 | 11 | 13 | 10 | 15 | 12 | 9 | 14 | 12 | 11 | 14 | 12 | 9 | 15 | 9 | 16 | 13 | 12 | 12 | 10 | 9 | 13 | 11 | 10 | 11 | 12 | 9 | 13 | 8 | 10 | 14 | 14 | 15 | 12 | 11 | 9 | 11 | 14 | 13 | 11 | 15 | 13 | 8 | 9
146 | 64 | 47 | 92 | 137 | 185 | 234 | 278 | 333 | 380 | 431 | 481 | 541 | 598 | 650 | 9 | 13 | 11 | 14 | 9 | 8 | 14 | 14 | 13 | 8 | 10 | 14 | 12 | 13 | 15 | 8 | 14 | 11 | 15 | 9 | 9 | 13 | 9 | 13 | 14 | 12 | 15 | 14 | 15 | 10 | 8 | 14 | 12 | 16 | 15 | 8 | 11 | 8 | 15 | 16 | 14 | 15 | 16 | 15 | 14 | 13 | 15 | 15 | 15 | 10 | 13 | 14
147 | 63 | 42 | 79 | 129 | 178 | 224 | 268 | 316 | 362 | 414 | 464 | 520 | 570 | 620 | 11 | 9 | 9 | 13 | 10 | 11 | 8 | 8 | 8 | 15 | 12 | 15 | 9 | 9 | 16 | 15 | 11 | 14 | 13 | 8 | 8 | 13 | 8 | 15 | 8 | 11 | 13 | 16 | 15 | 9 | 8 | 14 | 14 | 13 | 14 | 11 | 11 | 9 | 16 | 14 | 15 | 13 | 14 | 14 | 15 | 10 | 14 | 11 | 16 | 11 | 11 | 12
148 | 70 | 44 | 91 | 138 | 181 | 220 | 259 | 306 | 353 | 412 | 450 | 497 | 547 | 593 | 11 | 13 | 9 | 11 | 12 | 14 | 8 | 13 | 16 | 9 | 14 | 8 | 8 | 10 | 11 | 14 | 9 | 13 | 8 | 9 | 13 | 10 | 8 | 8 | 9 | 14 | 16 | 8 | 14 | 9 | 16 | 8 | 15 | 15 | 14 | 15 | 8 | 9 | 10 | 11 | 10 | 8 | 13 | 16 | 15 | 9 | 13 | 13 | 11 | 10 | 12 | 13
149 | 71 | 46 | 94 | 134 | 181 | 226 | 272 | 319 | 367 | 422 | 467 | 511 | 570 | 624 | 11 | 15 | 8 | 12 | 13 | 12 | 12 | 11 | 13 | 8 | 10 | 9 | 9 | 15 | 11 | 12 | 11 | 10 | 11 | 13 | 8 | 12 | 10 | 16 | 11 | 9 | 12 | 15 | 15 | 8 | 9 | 16 | 11 | 14 | 14 | 16 | 9 | 13 | 8 | 15 | 9 | 16 | 9 | 10 | 15 | 16 | 15 | 13 | 15 | 15 | 9 | 15
150 | 84 | 57 | 108 | 160 | 209 | 261 | 305 | 359 | 407 | 458 | 506 | 557 | 607 | 656 | 14 | 14 | 13 | 16 | 14 | 13 | 16 | 8 | 15 | 16 | 12 | 9 | 15 | 8 | 13 | 13 | 14 | 14 | 11 | 13 | 8 | 12 | 16 | 8 | 16 | 14 | 15 | 9 | 10 | 11 | 14 | 13 | 9 | 13 | 16 | 13 | 9 | 14 | 13 | 12 | 13 | 10 | 15 | 13 | 11 | 15 | 9 | 15 | 13 | 8 | 14 | 14
151 | 70 | 44 | 98 | 143 | 193 | 242 | 281 | 334 | 379 | 428 | 479 | 520 | 559 | 603 | 11 | 9 | 10 | 14 | 12 | 14 | 14 | 14 | 9 | 9 | 16 | 11 | 9 | 10 | 16 | 15 | 15 | 10 | 14 | 10 | 10 | 9 | 9 | 11 | 13 | 11 | 16 | 13 | 12 | 16 | 9 | 8 | 14 | 9 | 14 | 12 | 12 | 9 | 16 | 14 | 10 | 12 | 10 | 9 | 10 | 12 | 8 | 9 | 9 | 9 | 16 | 10
152 | 75 | 49 | 106 | 158 | 205 | 241 | 295 | 351 | 393 | 434 | 483 | 531 | 574 | 620 | 13 | 13 | 15 | 8 | 16 | 10 | 16 | 15 | 12 | 16 | 15 | 9 | 9 | 15 | 9 | 14 | 9 | 8 | 10 | 9 | 13 | 11 | 14 | 16 | 15 | 14 | 11 | 16 | 8 | 13 | 9 | 12 | 9 | 14 | 8 | 10 | 14 | 16 | 8 | 11 | 14 | 10 | 11 | 13 | 12 | 11 | 12 | 8 | 12 | 13 | 9 | 12
153 | 70 | 44 | 92 | 134 | 187 | 241 | 285 | 341 | 390 | 436 | 482 | 544 | 595 | 640 | 11 | 10 | 10 | 13 | 12 | 14 | 9 | 13 | 10 | 10 | 11 | 11 | 15 | 9 | 16 | 13 | 16 | 13 | 11 | 14 | 8 | 12 | 15 | 9 | 15 | 16 | 16 | 9 | 14 | 12 | 8 | 15 | 13 | 9 | 14 | 10 | 16 | 9 | 13 | 8 | 14 | 16 | 16 | 16 | 14 | 9 | 14 | 14 | 15 | 11 | 9 | 10
154 | 74 | 47 | 93 | 142 | 188 | 239 | 291 | 341 | 380 | 435 | 482 | 541 | 583 | 636 | 11 | 12 | 16 | 8 | 11 | 16 | 11 | 8 | 13 | 12 | 9 | 15 | 9 | 15 | 11 | 11 | 13 | 14 | 12 | 12 | 14 | 11 | 13 | 14 | 15 | 13 | 8 | 14 | 11 | 9 | 10 | 9 | 11 | 16 | 15 | 13 | 12 | 13 | 10 | 12 | 16 | 14 | 13 | 16 | 14 | 9 | 9 | 10 | 16 | 12 | 12 | 13
155 | 66 | 46 | 87 | 139 | 183 | 235 | 291 | 336 | 381 | 428 | 470 | 518 | 555 | 604 | 12 | 14 | 12 | 8 | 10 | 10 | 13 | 8 | 16 | 16 | 10 | 10 | 8 | 9 | 13 | 14 | 8 | 13 | 15 | 16 | 15 | 11 | 15 | 15 | 8 | 12 | 16 | 9 | 15 | 11 | 11 | 8 | 10 | 15 | 12 | 10 | 12 | 10 | 10 | 10 | 14 | 13 | 9 | 12 | 8 | 9 | 12 | 8 | 11 | 10 | 12 | 16
156 | 84 | 52 | 108 | 150 | 197 | 249 | 290 | 340 | 397 | 446 | 494 | 543 | 586 | 640 | 15 | 15 | 13 | 9 | 16 | 16 | 9 | 15 | 12 | 9 | 10 | 11 | 13 | 10 | 8 | 16 | 16 | 12 | 15 | 9 | 8 | 13 | 8 | 12 | 8 | 14 | 12 | 16 | 12 | 15 | 16 | 14 | 9 | 11 | 13 | 16 | 15 | 10 | 10 | 13 | 16 | 9 | 11 | 13 | 9 | 12 | 14 | 8 | 14 | 12 | 13 | 15
157 | 79 | 59 | 106 | 154 | 197 | 248 | 298 | 349 | 397 | 452 | 495 | 540 | 586 | 636 | 14 | 14 | 15 | 16 | 11 | 9 | 13 | 14 | 11 | 14 | 10 | 13 | 16 | 9 | 9 | 9 | 16 | 11 | 14 | 10 | 12 | 11 | 15 | 12 | 12 | 15 | 14 | 10 | 13 | 14 | 13 | 8 | 14 | 16 | 15 | 10 | 10 | 10 | 12 | 11 | 11 | 14 | 12 | 8 | 13 | 11 | 9 | 13 | 9 | 15 | 16 | 10
158 | 70 | 45 | 96 | 132 | 186 | 228 | 271 | 322 | 379 | 427 | 482 | 532 | 578 | 620 | 12 | 11 | 14 | 8 | 14 | 11 | 16 | 10 | 8 | 9 | 9 | 10 | 11 | 16 | 12 | 15 | 10 | 10 | 13 | 9 | 12 | 8 | 13 | 10 | 15 | 10 | 11 | 15 | 15 | 16 | 15 | 11 | 8 | 12 | 13 | 15 | 12 | 15 | 16 | 12 | 11 | 14 | 12 | 13 | 13 | 12 | 12 | 9 | 14 | 8 | 12 | 8
159 | 70 | 46 | 93 | 147 | 203 | 253 | 289 | 332 | 367 | 410 | 454 | 502 | 549 | 590 | 13 | 8 | 11 | 14 | 12 | 12 | 11 | 12 | 14 | 13 | 13 | 14 | 11 | 16 | 15 | 14 | 12 | 12 | 12 | 14 | 9 | 10 | 9 | 8 | 11 | 16 | 8 | 8 | 8 | 8 | 9 | 10 | 14 | 10 | 11 | 8 | 9 | 14 | 12 | 9 | 8 | 11 | 15 | 14 | 10 | 10 | 11 | 16 | 12 | 9 | 9 | 11
160 | 70 | 44 | 96 | 140 | 195 | 250 | 303 | 359 | 415 | 468 | 524 | 576 | 617 | 668 | 10 | 13 | 12 | 9 | 13 | 13 | 16 | 10 | 9 | 14 | 9 | 12 | 14 | 11 | 14 | 16 | 11 | 14 | 16 | 14 | 14 | 10 | 13 | 16 | 16 | 16 | 13 | 11 | 14 | 12 | 15 | 15 | 11 | 13 | 15 | 14 | 14 | 16 | 12 | 14 | 16 | 9 | 15 | 12 | 14 | 11 | 8 | 8 | 13 | 15 | 11 | 12
161 | 68 | 44 | 87 | 136 | 182 | 226 | 277 | 326 | 381 | 436 | 488 | 535 | 579 | 626 | 13 | 9 | 9 | 13 | 12 | 12 | 9 | 10 | 13 | 11 | 11 | 14 | 14 | 8 | 9 | 15 | 10 | 8 | 16 | 10 | 8 | 14 | 14 | 15 | 16 | 12 | 11 | 10 | 14 | 14 | 13 | 14 | 14 | 10 | 16 | 15 | 13 | 11 | 12 | 16 | 10 | 15 | 8 | 14 | 15 | 12 | 8 | 9 | 11 | 8 | 16 | 12
162 | 68 | 43 | 85 | 138 | 193 | 244 | 294 | 347 | 395 | 437 | 480 | 528 | 571 | 615 | 9 | 8 | 15 | 11 | 14 | 11 | 9 | 8 | 16 | 15 | 11 | 11 | 14 | 14 | 13 | 14 | 12 | 13 | 13 | 13 | 11 | 10 | 14 | 15 | 15 | 11 | 11 | 16 | 14 | 10 | 9 | 15 | 11 | 8 | 12 | 11 | 15 | 10 | 9 | 9 | 13 | 11 | 9 | 15 | 9 | 11 | 9 | 14 | 9 | 14 | 8 | 13
163 | 68 | 41 | 94 | 133 | 182 | 221 | 278 | 327 | 373 | 421 | 465 | 514 | 559 | 605 | 10 | 11 | 10 | 10 | 11 | 16 | 16 | 10 | 10 | 8 | 10 | 11 | 16 | 11 | 12 | 10 | 11 | 10 | 10 | 8 | 13 | 16 | 13 | 15 | 9 | 14 | 10 | 16 | 10 | 14 | 13 | 9 | 14 | 11 | 11 | 12 | 8 | 16 | 10 | 10 | 8 | 10 | 16 | 15 | 9 | 8 | 16 | 12 | 12 | 11 | 14 | 9
164 | 83 | 53 | 108 | 160 | 208 | 260 | 310 | 350 | 406 | 460 | 505 | 549 | 591 | 646 | 16 | 10 | 13 | 14 | 16 | 14 | 15 | 10 | 16 | 14 | 11 | 11 | 8 | 11 | 13 | 16 | 12 | 14 | 12 | 14 | 8 | 14 | 15 | 13 | 15 | 9 | 8 | 8 | 14 | 11 | 15 | 16 | 16 | 8 | 16 | 14 | 13 | 13 | 10 | 9 | 11 | 9 | 11 | 13 | 10 | 8 | 15 | 9 | 15 | 16 | 14 | 10
165 | 73 | 45 | 95 | 141 | 188 | 233 | 272 | 330 | 388 | 443 | 493 | 546 | 589 | 636 | 10 | 12 | 10 | 13 | 13 | 15 | 14 | 8 | 13 | 12 | 13 | 8 | 10 | 13 | 11 | 13 | 9 | 9 | 12 | 15 | 9 | 10 | 12 | 8 | 14 | 16 | 12 | 16 | 15 | 13 | 14 | 16 | 15 | 13 | 13 | 14 | 13 | 12 | 16 | 9 | 15 | 14 | 11 | 13 | 16 | 8 | 11 | 8 | 11 | 8 | 12 | 16
166 | 71 | 49 | 97 | 157 | 211 | 253 | 301 | 352 | 403 | 451 | 504 | 545 | 587 | 636 | 9 | 15 | 12 | 13 | 12 | 10 | 16 | 10 | 16 | 16 | 12 | 16 | 15 | 13 | 10 | 16 | 8 | 10 | 10 | 14 | 9 | 14 | 13 | 12 | 10 | 12 | 14 | 15 | 12 | 10 | 13 | 16 | 14 | 12 | 13 | 9 | 12 | 16 | 11 | 14 | 8 | 9 | 16 | 8 | 10 | 8 | 9 | 15 | 11 | 11 | 12 | 15
167 | 62 | 44 | 89 | 137 | 183 | 233 | 285 | 337 | 385 | 439 | 494 | 540 | 586 | 627 | 10 | 15 | 9 | 10 | 9 | 9 | 11 | 16 | 8 | 13 | 13 | 14 | 8 | 16 | 11 | 11 | 15 | 11 | 12 | 12 | 15 | 16 | 8 | 13 | 9 | 16 | 16 | 11 | 13 | 9 | 16 | 10 | 16 | 14 | 8 | 16 | 13 | 14 | 16 | 12 | 12 | 11 | 14 | 9 | 12 | 14 | 12 | 8 | 10 | 13 | 10 | 8
168 | 73 | 47 | 96 | 141 | 179 | 219 | 272 | 316 | 369 | 421 | 467 | 519 | 558 | 604 | 8 | 16 | 14 | 9 | 13 | 13 | 11 | 12 | 10 | 9 | 10 | 16 | 8 | 11 | 9 | 10 | 8 | 14 | 8 | 10 | 11 | 15 | 14 | 13 | 13 | 9 | 11 | 11 | 15 | 13 | 13 | 12 | 13 | 15 | 14 | 10 | 9 | 11 | 13 | 13 | 16 | 9 | 14 | 13 | 8 | 9 | 12 | 10 | 8 | 15 | 9 | 14
169 | 85 | 53 | 111 | 164 | 206 | 267 | 322 | 368 | 412 | 467 | 520 | 572 | 620 | 668 | 9 | 15 | 14 | 15 | 16 | 16 | 10 | 16 | 16 | 12 | 14 | 11 | 12 | 8 | 13 | 9 | 16 | 15 | 16 | 14 | 11 | 14 | 15 | 15 | 16 | 12 | 10 | 8 | 8 | 15 | 9 | 12 | 16 | 10 | 15 | 14 | 9 | 13 | 15 | 16 | 13 | 16 | 11 | 12 | 14 | 12 | 11 | 11 | 16 | 11 | 8 | 13
170 | 84 | 57 | 107 | 156 | 205 | 254 | 306 | 350 | 399 | 445 | 499 | 547 | 587 | 635 | 15 | 12 | 14 | 16 | 13 | 14 | 9 | 14 | 9 | 16 | 15 | 9 | 9 | 9 | 16 | 15 | 13 | 16 | 10 | 10 | 14 | 16 | 11 | 11 | 10 | 15 | 8 | 11 | 12 | 12 | 16 | 9 | 9 | 14 | 8 | 15 | 11 | 15 | 15 | 13 | 15 | 8 | 10 | 15 | 10 | 8 | 8 | 14 | 8 | 9 | 15 | 16
171 | 73 | 49 | 94 | 138 | 177 | 229 | 278 | 326 | 373 | 419 | 468 | 511 | 558 | 614 | 15 | 9 | 15 | 10 | 12 | 12 | 8 | 13 | 11 | 12 | 8 | 13 | 11 | 8 | 8 | 12 | 12 | 15 | 9 | 16 | 11 | 14 | 12 | 12 | 10 | 14 | 12 | 12 | 13 | 14 | 12 | 8 | 8 | 10 | 13 | 15 | 9 | 14 | 10 | 16 | 12 | 11 | 10 | 10 | 13 | 10 | 13 | 11 | 15 | 11 | 16 | 14
172 | 71 | 44 | 91 | 135 | 184 | 228 | 279 | 321 | 374 | 417 | 468 | 523 | 571 | 612 | 8 | 15 | 9 | 12 | 13 | 14 | 10 | 10 | 11 | 11 | 9 | 13 | 8 | 15 | 15 | 11 | 12 | 14 | 8 | 10 | 11 | 14 | 15 | 11 | 10 | 9 | 14 | 9 | 13 | 13 | 14 | 13 | 10 | 16 | 9 | 8 | 8 | 16 | 14 | 13 | 16 | 10 | 15 | 14 | 10 | 12 | 12 | 14 | 13 | 9 | 8 | 11
173 | 73 | 43 | 104 | 151 | 204 | 247 | 296 | 335 | 386 | 444 | 489 | 533 | 580 | 639 | 15 | 8 | 12 | 8 | 14 | 16 | 16 | 15 | 12 | 16 | 10 | 9 | 15 | 8 | 16 | 14 | 8 | 12 | 9 | 14 | 12 | 14 | 13 | 10 | 8 | 10 | 12 | 9 | 12 | 12 | 13 | 14 | 16 | 14 | 12 | 16 | 16 | 9 | 9 | 11 | 8 | 13 | 8 | 15 | 13 | 12 | 13 | 9 | 12 | 16 | 16 | 15
174 | 66 | 42 | 92 | 130 | 171 | 220 | 261 | 312 | 355 | 403 | 446 | 499 | 543 | 592 | 12 | 8 | 12 | 10 | 16 | 8 | 12 | 14 | 9 | 8 | 12 | 9 | 9 | 9 | 11 | 12 | 12 | 10 | 12 | 15 | 8 | 10 | 11 | 12 | 15 | 11 | 12 | 13 | 8 | 13 | 11 | 11 | 9 | 16 | 11 | 12 | 8 | 14 | 10 | 11 | 15 | 16 | 10 | 12 | 9 | 9 | 13 | 13 | 12 | 16 | 13 | 8
175 | 80 | 48 | 100 | 156 | 210 | 253 | 308 | 352 | 411 | 463 | 513 | 563 | 612 | 661 | 13 | 10 | 15 | 10 | 16 | 16 | 10 | 10 | 13 | 16 | 12 | 15 | 14 | 11 | 13 | 16 | 8 | 8 | 16 | 11 | 10 | 14 | 15 | 16 | 9 | 10 | 13 | 12 | 16 | 14 | 14 | 15 | 16 | 8 | 14 | 14 | 8 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 15 | 13 | 8 | 13 | 8 | 12 | 13 | 16
176 | 82 | 52 | 101 | 160 | 204 | 248 | 297 | 347 | 399 | 446 | 489 | 543 | 597 | 641 | 15 | 12 | 16 | 9 | 15 | 15 | 8 | 11 | 16 | 13 | 15 | 15 | 10 | 13 | 10 | 11 | 13 | 8 | 9 | 14 | 13 | 15 | 12 | 9 | 10 | 10 | 16 | 14 | 14 | 11 | 14 | 13 | 15 | 14 | 10 | 8 | 8 | 11 | 13 | 11 | 15 | 9 | 14 | 16 | 10 | 14 | 15 | 15 | 9 | 9 | 16 | 10
177 | 63 | 41 | 83 | 133 | 178 | 225 | 270 | 316 | 362 | 404 | 442 | 499 | 548 | 592 | 14 | 9 | 10 | 8 | 10 | 12 | 11 | 9 | 16 | 11 | 12 | 11 | 13 | 9 | 15 | 8 | 8 | 16 | 11 | 12 | 11 | 9 | 13 | 12 | 9 | 10 | 12 | 15 | 10 | 10 | 10 | 16 | 12 | 8 | 11 | 11 | 12 | 8 | 9 | 9 | 15 | 15 | 16 | 11 | 12 | 14 | 9 | 14 | 14 | 10 | 8 | 12
178 | 77 | 53 | 103 | 151 | 190 | 240 | 283 | 332 | 378 | 423 | 475 | 528 | 586 | 633 | 14 | 15 | 10 | 14 | 13 | 11 | 14 | 12 | 9 | 9 | 16 | 14 | 10 | 11 | 10 | 8 | 15 | 8 | 12 | 15 | 8 | 13 | 10 | 12 | 13 | 11 | 12 | 13 | 8 | 13 | 9 | 16 | 10 | 9 | 11 | 15 | 9 | 16 | 16 | 11 | 9 | 16 | 13 | 15 | 13 | 15 | 16 | 14 | 15 | 13 | 9 | 10
179 | 65 | 47 | 91 | 139 | 199 | 248 | 303 | 351 | 399 | 447 | 498 | 556 | 601 | 644 | 12 | 16 | 8 | 11 | 10 | 8 | 11 | 15 | 10 | 13 | 15 | 10 | 16 | 16 | 16 | 12 | 15 | 11 | 13 | 10 | 14 | 16 | 14 | 11 | 12 | 8 | 15 | 13 | 15 | 9 | 16 | 8 | 13 | 13 | 14 | 8 | 15 | 14 | 13 | 9 | 13 | 15 | 15 | 15 | 12 | 9 | 15 | 9 | 10 | 12 | 11 | 10
180 | 63 | 41 | 85 | 137 | 189 | 239 | 281 | 323 | 372 | 427 | 480 | 533 | 592 | 641 | 12 | 9 | 10 | 10 | 11 | 11 | 9 | 13 | 12 | 13 | 15 | 12 | 16 | 11 | 12 | 13 | 11 | 14 | 16 | 9 | 11 | 14 | 8 | 9 | 16 | 8 | 10 | 8 | 12 | 16 | 13 | 8 | 8 | 16 | 15 | 16 | 12 | 15 | 13 | 13 | 15 | 13 | 11 | 14 | 16 | 15 | 14 | 14 | 16 | 12 | 12 | 9
181 | 79 | 50 | 106 | 153 | 199 | 243 | 295 | 350 | 410 | 454 | 499 | 538 | 587 | 638 | 8 | 16 | 16 | 10 | 14 | 15 | 11 | 16 | 13 | 9 | 13 | 12 | 14 | 8 | 16 | 8 | 13 | 9 | 8 | 14 | 15 | 15 | 12 | 10 | 16 | 11 | 13 | 15 | 14 | 15 | 15 | 16 | 8 | 9 | 11 | 16 | 14 | 8 | 8 | 15 | 8 | 8 | 9 | 14 | 16 | 15 | 8 | 10 | 13 | 14 | 16 | 8
182 | 65 | 40 | 90 | 131 | 180 | 229 | 277 | 331 | 382 | 431 | 482 | 523 | 580 | 623 | 8 | 9 | 9 | 14 | 11 | 14 | 15 | 10 | 14 | 9 | 9 | 9 | 12 | 13 | 11 | 13 | 15 | 12 | 10 | 12 | 11 | 14 | 9 | 14 | 13 | 16 | 12 | 13 | 10 | 15 | 13 | 13 | 9 | 12 | 15 | 13 | 13 | 8 | 15 | 15 | 8 | 9 | 11 | 13 | 16 | 14 | 16 | 11 | 10 | 12 | 11 | 10
183 | 74 | 50 | 98 | 147 | 194 | 244 | 290 | 339 | 389 | 438 | 491 | 542 | 586 | 631 | 13 | 9 | 14 | 14 | 12 | 12 | 14 | 10 | 8 | 15 | 16 | 10 | 13 | 13 | 9 | 12 | 13 | 12 | 12 | 13 | 13 | 10 | 8 | 15 | 8 | 14 | 16 | 11 | 12 | 14 | 14 | 10 | 9 | 15 | 16 | 9 | 15 | 14 | 9 | 15 | 14 | 14 | 9 | 14 | 9 | 12 | 10 | 13 | 10 | 9 | 10 | 16
184 | 70 | 47 | 90 | 133 | 174 | 232 | 290 | 335 | 384 | 441 | 486 | 533 | 583 | 630 | 15 | 8 | 10 | 14 | 9 | 14 | 11 | 9 | 10 | 13 | 10 | 10 | 9 | 10 | 10 | 12 | 15 | 16 | 11 | 16 | 13 | 16 | 16 | 13 | 15 | 12 | 10 | 8 | 15 | 10 | 12 | 12 | 16 | 16 | 13 | 12 | 13 | 15 | 8 | 9 | 13 | 12 | 8 | 14 | 10 | 13 | 15 | 12 | 10 | 9 | 12 | 16
185 | 79 | 47 | 103 | 152 | 201 | 251 | 308 | 358 | 413 | 465 | 518 | 557 | 605 | 652 | 13 | 16 | 10 | 8 | 16 | 16 | 10 | 14 | 8 | 13 | 12 | 16 | 13 | 16 | 9 | 11 | 12 | 8 | 16 | 14 | 13 | 14 | 15 | 15 | 11 | 15 | 15 | 9 | 15 | 10 | 16 | 14 | 8 | 16 | 15 | 13 | 11 | 12 | 16 | 14 | 8 | 13 | 8 | 10 | 11 | 15 | 14 | 8 | 16 | 11 | 11 | 9
186 | 68 | 44 | 94 | 141 | 187 | 237 | 281 | 326 | 373 | 421 | 474 | 534 | 591 | 639 | 11 | 8 | 15 | 10 | 11 | 13 | 15 | 11 | 10 | 13 | 15 | 9 | 13 | 8 | 16 | 9 | 16 | 14 | 11 | 9 | 11 | 12 | 10 | 11 | 12 | 10 | 14 | 9 | 15 | 8 | 12 | 12 | 15 | 10 | 12 | 11 | 8 | 14 | 15 | 16 | 16 | 16 | 14 | 14 | 14 | 16 | 16 | 11 | 13 | 9 | 13 | 13
187 | 70 | 49 | 101 | 148 | 201 | 252 | 305 | 356 | 409 | 454 | 498 | 544 | 598 | 650 | 15 | 15 | 10 | 9 | 10 | 11 | 16 | 15 | 13 | 11 | 12 | 11 | 16 | 8 | 14 | 15 | 12 | 15 | 10 | 14 | 11 | 15 | 11 | 16 | 15 | 15 | 8 | 13 | 15 | 13 | 11 | 14 | 12 | 11 | 10 | 12 | 9 | 13 | 8 | 14 | 13 | 8 | 15 | 10 | 13 | 16 | 9 | 16 | 15 | 11 | 11 | 15
188 | 72 | 45 | 102 | 145 | 194 | 237 | 296 | 340 | 386 | 439 | 491 | 542 | 584 | 639 | 10 | 9 | 16 | 10 | 12 | 15 | 14 | 16 | 11 | 13 | 11 | 8 | 14 | 11 | 10 | 14 | 13 | 8 | 9 | 13 | 16 | 16 | 13 | 14 | 15 | 8 | 11 | 10 | 11 | 16 | 10 | 9 | 16 | 11 | 16 | 10 | 14 | 8 | 14 | 16 | 14 | 13 | 14 | 10 | 14 | 11 | 9 | 8 | 12 | 16 | 11 | 16
189 | 60 | 35 | 83 | 128 | 183 | 236 | 280 | 329 | 381 | 429 | 473 | 523 | 575 | 623 | 9 | 9 | 9 | 8 | 16 | 9 | 11 | 12 | 10 | 15 | 12 | 8 | 8 | 15 | 16 | 16 | 8 | 16 | 16 | 13 | 10 | 9 | 13 | 12 | 9 | 13 | 13 | 14 | 16 | 12 | 14 | 10 | 14 | 13 | 13 | 8 | 12 | 10 | 8 | 14 | 12 | 14 | 13 | 11 | 15 | 11 | 15 | 11 | 16 | 10 | 10 | 12
190 | 68 | 50 | 87 | 137 | 173 | 216 | 264 | 320 | 362 | 409 | 457 | 509 | 569 | 618 | 13 | 13 | 9 | 15 | 10 | 8 | 11 | 8 | 15 | 15 | 10 | 10 | 8 | 9 | 9 | 10 | 9 | 11 | 9 | 14 | 14 | 11 | 12 | 11 | 16 | 14 | 11 | 15 | 10 | 13 | 8 | 11 | 9 | 15 | 8 | 15 | 10 | 15 | 12 | 11 | 15 | 10 | 16 | 11 | 16 | 15 | 13 | 16 | 12 | 16 | 8 | 13
191 | 73 | 48 | 90 | 140 | 189 | 240 | 281 | 337 | 383 | 429 | 476 | 516 | 562 | 608 | 9 | 15 | 11 | 13 | 14 | 11 | 9 | 8 | 11 | 12 | 13 | 14 | 9 | 11 | 15 | 14 | 15 | 11 | 10 | 15 | 12 | 9 | 10 | 10 | 15 | 14 | 14 | 13 | 8 | 16 | 10 | 12 | 16 | 8 | 9 | 13 | 16 | 14 | 8 | 9 | 8 | 11 | 12 | 9 | 15 | 9 | 11 | 11 | 12 | 10 | 13 | 11
192 | 70 | 47 | 89 | 139 | 194 | 232 | 276 | 328 | 377 | 430 | 485 | 531 | 571 | 621 | 9 | 12 | 13 | 13 | 8 | 15 | 10 | 9 | 10 | 9 | 15 | 16 | 16 | 13 | 11 | 15 | 11 | 9 | 8 | 10 | 11 | 8 | 15 | 10 | 15 | 16 | 12 | 9 | 14 | 12 | 8 | 15 | 14 | 15 | 14 | 10 | 16 | 10 | 16 | 13 | 9 | 13 | 8 | 16 | 13 | 8 | 8 | 11 | 13 | 9 | 16 | 12
193 | 68 | 41 | 90 | 137 | 188 | 238 | 285 | 329 | 371 | 424 | 479 | 518 | 567 | 624 | 8 | 12 | 11 | 10 | 12 | 15 | 12 | 10 | 14 | 15 | 10 | 8 | 12 | 13 | 16 | 10 | 14 | 16 | 8 | 12 | 8 | 15 | 13 | 11 | 8 | 14 | 8 | 14 | 13 | 10 | 9 | 10 | 9 | 16 | 15 | 13 | 9 | 15 | 15 | 16 | 11 | 8 | 11 | 9 | 13 | 11 | 13 | 12 | 12 | 16 | 14 | 15
194 | 66 | 49 | 91 | 144 | 192 | 235 | 281 | 333 | 381 | 434 | 486 | 535 | 583 | 640 | 13 | 12 | 13 | 11 | 9 | 8 | 14 | 11 | 16 | 8 | 13 | 16 | 12 | 12 | 15 | 9 | 8 | 11 | 12 | 12 | 9 | 12 | 10 | 15 | 16 | 11 | 15 | 10 | 13 | 15 | 8 | 12 | 11 | 13 | 13 | 16 | 11 | 13 | 12 | 16 | 11 | 16 | 13 | 9 | 9 | 10 | 14 | 15 | 13 | 12 | 16 | 16
195 | 77 | 53 | 97 | 144 | 194 | 243 | 296 | 349 | 401 | 445 | 491 | 543 | 596 | 638 | 14 | 11 | 13 | 15 | 9 | 15 | 12 | 8 | 8 | 11 | 15 | 13 | 8 | 14 | 14 | 14 | 12 | 9 | 12 | 16 | 14 | 12 | 13 | 14 | 16 | 12 | 15 | 10 | 16 | 10 | 10 | 16 | 9 | 11 | 16 | 8 | 14 | 8 | 12 | 12 | 13 | 11 | 14 | 14 | 15 | 15 | 15 | 8 | 13 | 12 | 9 | 8
196 | 74 | 57 | 94 | 145 | 194 | 240 | 284 | 330 | 385 | 432 | 482 | 528 | 571 | 616 | 13 | 16 | 14 | 14 | 9 | 8 | 8 | 12 | 13 | 14 | 10 | 14 | 12 | 11 | 11 | 15 | 9 | 9 | 13 | 15 | 11 | 13 | 10 | 10 | 8 | 13 | 9 | 16 | 14 | 13 | 12 | 16 | 13 | 10 | 12 | 12 | 16 | 15 | 11 | 8 | 9 | 14 | 15 | 8 | 11 | 8 | 9 | 15 | 8 | 11 | 16 | 10
197 | 76 | 48 | 98 | 143 | 183 | 236 | 293 | 335 | 389 | 445 | 491 | 543 | 596 | 637 | 12 | 14 | 13 | 9 | 14 | 14 | 10 | 12 | 11 | 13 | 8 | 13 | 14 | 8 | 9 | 9 | 12 | 16 | 9 | 16 | 12 | 13 | 16 | 16 | 11 | 8 | 15 | 8 | 11 | 15 | 14 | 14 | 13 | 15 | 12 | 16 | 9 | 15 | 11 | 11 | 9 | 12 | 15 | 16 | 15 | 14 | 11 | 13 | 9 | 10 | 14 | 8
198 | 73 | 50 | 97 | 143 | 193 | 247 | 294 | 335 | 383 | 432 | 490 | 538 | 581 | 636 | 13 | 11 | 16 | 10 | 11 | 12 | 16 | 8 | 11 | 12 | 9 | 14 | 9 | 16 | 14 | 11 | 14 | 11 | 15 | 14 | 12 | 11 | 13 | 11 | 10 | 10 | 10 | 11 | 12 | 10 | 11 | 15 | 11 | 14 | 14 | 10 | 16 | 16 | 10 | 16 | 12 | 11 | 15 | 10 | 14 | 12 | 9 | 8 | 12 | 13 | 14 | 16
199 | 71 | 47 | 90 | 142 | 182 | 226 | 274 | 321 | 370 | 413 | 461 | 507 | 553 | 591 | 15 | 9 | 8 | 15 | 16 | 8 | 10 | 9 | 14 | 14 | 15 | 9 | 11 | 9 | 8 | 12 | 15 | 11 | 8 | 10 | 10 | 14 | 12 | 12 | 15 | 9 | 10 | 13 | 10 | 10 | 15 | 14 | 10 | 9 | 9 | 15 | 10 | 16 | 8 | 14 | 10 | 14 | 14 | 8 | 8 | 15 | 8 | 15 | 8 | 9 | 12 | 9
200 | 73 | 44 | 101 | 153 | 205 | 258 | 309 | 351 | 395 | 439 | 493 | 543 | 602 | 654 | 8 | 15 | 9 | 12 | 16 | 13 | 15 | 13 | 13 | 15 | 16 | 8 | 16 | 16 | 8 | 12 | 16 | 10 | 14 | 13 | 8 | 15 | 12 | 16 | 11 | 10 | 8 | 13 | 14 | 8 | 10 | 12 | 8 | 10 | 10 | 16 | 15 | 12 | 11 | 16 | 10 | 14 | 10 | 16 | 15 | 12 | 16 | 16 | 12 | 11 | 14 | 15
201 | 76 | 51 | 97 | 142 | 180 | 231 | 286 | 334 | 386 | 429 | 474 | 518 | 563 | 612 | 16 | 10 | 15 | 10 | 14 | 11 | 12 | 9 | 9 | 10 | 15 | 11 | 8 | 8 | 9 | 13 | 14 | 16 | 8 | 13 | 16 | 10 | 13 | 16 | 12 | 15 | 13 | 8 | 12 | 16 | 15 | 9 | 11 | 9 | 13 | 10 | 13 | 8 | 15 | 9 | 8 | 13 | 10 | 13 | 16 | 8 | 8 | 13 | 11 | 14 | 16 | 8
202 | 61 | 41 | 86 | 149 | 193 | 240 | 283 | 341 | 391 | 445 | 497 | 557 | 603 | 641 | 9 | 10 | 13 | 9 | 10 | 10 | 12 | 13 | 15 | 16 | 16 | 16 | 12 | 11 | 10 | 11 | 8 | 16 | 14 | 9 | 12 | 10 | 13 | 8 | 14 | 12 | 16 | 16 | 16 | 13 | 13 | 8 | 14 | 16 | 14 | 10 | 15 | 11 | 14 | 12 | 16 | 16 | 16 | 12 | 10 | 10 | 15 | 11 | 10 | 8 | 12 | 8
203 | 76 | 51 | 94 | 129 | 180 | 235 | 291 | 340 | 393 | 442 | 495 | 539 | 589 | 634 | 16 | 16 | 9 | 10 | 9 | 16 | 8 | 10 | 11 | 8 | 8 | 8 | 16 | 10 | 14 | 11 | 15 | 14 | 10 | 16 | 9 | 15 | 16 | 16 | 16 | 11 | 9 | 13 | 14 | 11 | 13 | 15 | 12 | 11 | 10 | 16 | 10 | 15 | 14 | 14 | 11 | 8 | 9 | 16 | 11 | 16 | 10 | 13 | 11 | 11 | 8 | 15
204 | 76 | 55 | 94 | 148 | 198 | 248 | 299 | 352 | 401 | 446 | 486 | 527 | 580 | 629 | 11 | 14 | 14 | 16 | 10 | 11 | 8 | 10 | 12 | 16 | 10 | 16 | 10 | 15 | 13 | 12 | 13 | 14 | 11 | 12 | 14 | 15 | 10 | 12 | 11 | 16 | 12 | 14 | 13 | 9 | 14 | 13 | 14 | 10 | 13 | 8 | 13 | 8 | 8 | 11 | 8 | 11 | 12 | 10 | 11 | 13 | 13 | 16 | 15 | 11 | 10 | 13
205 | 74 | 51 | 93 | 138 | 184 | 240 | 295 | 349 | 396 | 443 | 497 | 544 | 598 | 653 | 15 | 15 | 10 | 11 | 14 | 9 | 9 | 10 | 10 | 12 | 11 | 12 | 13 | 11 | 8 | 14 | 13 | 15 | 12 | 16 | 9 | 14 | 16 | 16 | 12 | 16 | 15 | 11 | 15 | 9 | 8 | 15 | 10 | 9 | 15 | 13 | 13 | 15 | 11 | 15 | 8 | 16 | 9 | 14 | 13 | 15 | 16 | 10 | 8 | 15 | 16 | 16
206 | 74 | 54 | 95 | 142 | 182 | 230 | 286 | 332 | 382 | 434 | 479 | 529 | 579 | 631 | 16 | 13 | 13 | 12 | 10 | 10 | 10 | 11 | 11 | 12 | 11 | 13 | 12 | 9 | 8 | 11 | 14 | 14 | 10 | 10 | 13 | 15 | 13 | 15 | 12 | 8 | 11 | 15 | 8 | 16 | 16 | 10 | 15 | 10 | 15 | 12 | 15 | 14 | 8 | 8 | 12 | 15 | 15 | 8 | 12 | 10 | 15 | 13 | 15 | 14 | 12 | 11
207 | 82 | 54 | 109 | 154 | 206 | 253 | 302 | 343 | 396 | 443 | 505 | 546 | 596 | 648 | 16 | 10 | 15 | 13 | 16 | 12 | 15 | 12 | 11 | 10 | 8 | 16 | 16 | 11 | 11 | 14 | 14 | 8 | 9 | 16 | 16 | 14 | 10 | 9 | 9 | 13 | 10 | 9 | 15 | 11 | 14 | 13 | 12 | 12 | 8 | 15 | 15 | 15 | 16 | 16 | 11 | 13 | 8 | 9 | 9 | 13 | 12 | 16 | 9 | 16 | 16 | 11
208 | 78 | 55 | 102 | 152 | 202 | 253 | 296 | 347 | 395 | 431 | 487 | 541 | 581 | 629 | 10 | 16 | 16 | 13 | 12 | 11 | 8 | 16 | 11 | 11 | 13 | 15 | 13 | 12 | 14 | 11 | 15 | 8 | 14 | 14 | 10 | 11 | 8 | 14 | 16 | 10 | 16 | 9 | 15 | 10 | 14 | 9 | 8 | 8 | 8 | 12 | 14 | 11 | 15 | 16 | 11 | 15 | 15 | 13 | 11 | 10 | 10 | 9 | 9 | 12 | 13 | 14
209 | 75 | 50 | 103 | 160 | 211 | 250 | 300 | 346 | 396 | 443 | 492 | 537 | 576 | 614 | 13 | 9 | 13 | 15 | 16 | 9 | 13 | 15 | 16 | 10 | 16 | 15 | 15 | 15 | 10 | 11 | 12 | 8 | 8 | 11 | 10 | 13 | 15 | 12 | 11 | 9 | 16 | 10 | 15 | 15 | 8 | 12 | 8 | 16 | 9 | 14 | 9 | 15 | 12 | 13 | 11 | 11 | 12 | 11 | 11 | 9 | 9 | 10 | 12 | 9 | 9 | 8
210 | 75 | 49 | 98 | 138 | 184 | 237 | 287 | 324 | 379 | 424 | 479 | 530 | 574 | 625 | 12 | 9 | 15 | 13 | 13 | 13 | 10 | 13 | 11 | 9 | 12 | 8 | 14 | 9 | 14 | 9 | 16 | 16 | 12 | 9 | 15 | 8 | 11 | 16 | 8 | 12 | 9 | 8 | 13 | 15 | 11 | 16 | 9 | 10 | 16 | 10 | 16 | 15 | 13 | 11 | 13 | 13 | 16 | 9 | 16 | 12 | 8 | 8 | 15 | 9 | 13 | 14
211 | 76 | 53 | 104 | 151 | 207 | 261 | 303 | 355 | 405 | 448 | 488 | 529 | 578 | 630 | 15 | 16 | 12 | 10 | 11 | 12 | 13 | 15 | 10 | 12 | 10 | 15 | 16 | 15 | 13 | 12 | 16 | 16 | 9 | 13 | 13 | 9 | 8 | 12 | 9 | 14 | 14 | 15 | 11 | 15 | 14 | 10 | 11 | 15 | 9 | 8 | 10 | 8 | 10 | 12 | 11 | 13 | 9 | 8 | 10 | 15 | 8 | 16 | 15 | 16 | 8 | 13
212 | 66 | 44 | 90 | 136 | 184 | 223 | 267 | 313 | 364 | 409 | 444 | 499 | 551 | 592 | 8 | 11 | 15 | 10 | 11 | 11 | 15 | 9 | 16 | 12 | 10 | 8 | 11 | 9 | 13 | 15 | 9 | 8 | 8 | 14 | 8 | 15 | 13 | 8 | 11 | 10 | 14 | 11 | 13 | 12 | 14 | 12 | 11 | 12 | 8 | 14 | 9 | 8 | 8 | 10 | 13 | 16 | 10 | 16 | 8 | 14 | 14 | 16 | 11 | 8 | 14 | 8
213 | 81 | 51 | 108 | 156 | 209 | 258 | 307 | 356 | 400 | 451 | 494 | 544 | 592 | 638 | 15 | 15 | 11 | 10 | 16 | 14 | 15 | 12 | 9 | 14 | 16 | 9 | 12 | 14 | 13 | 14 | 16 | 10 | 13 | 10 | 8 | 10 | 15 | 16 | 14 | 13 | 10 | 12 | 12 | 14 | 8 | 10 | 10 | 14 | 13 | 14 | 10 | 11 | 13 | 9 | 14 | 14 | 12 | 10 | 15 | 9 | 14 | 10 | 9 | 16 | 8 | 13
214 | 73 | 48 | 100 | 143 | 199 | 247 | 287 | 342 | 396 | 445 | 489 | 532 | 571 | 615 | 15 | 11 | 8 | 14 | 15 | 10 | 14 | 13 | 10 | 14 | 11 | 8 | 9 | 16 | 15 | 16 | 13 | 11 | 9 | 15 | 11 | 11 | 10 | 8 | 15 | 10 | 14 | 16 | 15 | 13 | 10 | 16 | 10 | 16 | 15 | 8 | 8 | 8 | 12 | 16 | 13 | 9 | 11 | 10 | 9 | 12 | 9 | 9 | 10 | 11 | 14 | 9
215 | 70 | 47 | 89 | 137 | 189 | 233 | 292 | 336 | 377 | 420 | 465 | 509 | 561 | 615 | 14 | 11 | 9 | 13 | 13 | 10 | 8 | 11 | 12 | 11 | 9 | 16 | 13 | 14 | 11 | 14 | 14 | 8 | 10 | 12 | 15 | 15 | 15 | 14 | 10 | 9 | 16 | 9 | 9 | 12 | 8 | 12 | 11 | 8 | 8 | 16 | 9 | 12 | 9 | 15 | 13 | 12 | 10 | 9 | 15 | 15 | 14 | 8 | 9 | 15 | 16 | 14
216 | 74 | 50 | 91 | 148 | 190 | 238 | 290 | 345 | 404 | 457 | 506 | 555 | 606 | 655 | 12 | 8 | 15 | 15 | 16 | 8 | 8 | 9 | 15 | 15 | 16 | 11 | 13 | 8 | 9 | 12 | 11 | 14 | 14 | 9 | 11 | 13 | 16 | 12 | 10 | 15 | 14 | 16 | 15 | 14 | 14 | 16 | 12 | 16 | 16 | 9 | 9 | 12 | 12 | 16 | 16 | 13 | 9 | 11 | 8 | 14 | 13 | 16 | 16 | 12 | 12 | 9
217 | 67 | 45 | 92 | 143 | 187 | 239 | 284 | 324 | 373 | 415 | 466 | 516 | 567 | 613 | 9 | 13 | 8 | 15 | 13 | 9 | 13 | 12 | 13 | 11 | 16 | 11 | 9 | 9 | 12 | 14 | 10 | 14 | 12 | 16 | 15 | 9 | 8 | 13 | 8 | 8 | 8 | 16 | 8 | 11 | 15 | 15 | 8 | 11 | 10 | 13 | 8 | 14 | 13 | 16 | 13 | 10 | 13 | 14 | 11 | 15 | 9 | 16 | 15 | 13 | 10 | 8
218 | 65 | 48 | 86 | 131 | 178 | 230 | 274 | 316 | 367 | 412 | 469 | 508 | 557 | 603 | 10 | 9 | 13 | 16 | 9 | 8 | 9 | 12 | 10 | 14 | 12 | 9 | 8 | 12 | 12 | 15 | 15 | 11 | 10 | 16 | 10 | 10 | 9 | 15 | 14 | 8 | 10 | 10 | 10 | 14 | 14 | 13 | 12 | 10 | 11 | 12 | 16 | 14 | 12 | 15 | 8 | 12 | 11 | 8 | 12 | 14 | 12 | 11 | 9 | 12 | 14 | 11
219 | 68 | 42 | 86 | 133 | 178 | 226 | 270 | 313 | 362 | 420 | 471 | 515 | 548 | 598 | 16 | 9 | 9 | 8 | 11 | 15 | 9 | 9 | 8 | 12 | 14 | 13 | 10 | 8 | 16 | 11 | 12 | 10 | 16 | 10 | 16 | 12 | 8 | 8 | 11 | 10 | 14 | 8 | 16 | 8 | 13 | 12 | 16 | 12 | 15 | 15 | 13 | 16 | 8 | 14 | 9 | 9 | 15 | 11 | 8 | 8 | 8 | 9 | 14 | 16 | 12 | 8
220 | 65 | 46 | 95 | 151 | 200 | 246 | 290 | 341 | 392 | 439 | 494 | 542 | 593 | 651 | 14 | 8 | 14 | 10 | 9 | 10 | 16 | 14 | 14 | 14 | 16 | 12 | 16 | 9 | 14 | 10 | 13 | 8 | 10 | 15 | 9 | 13 | 11 | 11 | 9 | 14 | 15 | 13 | 11 | 13 | 14 | 13 | 16 | 8 | 15 | 8 | 14 | 12 | 14 | 15 | 14 | 10 | 10 | 14 | 12 | 13 | 14 | 12 | 12 | 16 | 14 | 16
221 | 73 | 53 | 100 | 139 | 190 | 246 | 286 | 320 | 370 | 416 | 465 | 508 | 554 | 601 | 8 | 15 | 15 | 15 | 10 | 10 | 12 | 15 | 10 | 8 | 10 | 11 | 11 | 10 | 14 | 16 | 16 | 16 | 9 | 15 | 14 | 8 | 8 | 10 | 8 | 8 | 8 | 10 | 15 | 14 | 9 | 12 | 16 | 9 | 13 | 8 | 9 | 14 | 12 | 14 | 13 | 8 | 13 | 9 | 13 | 11 | 14 | 8 | 8 | 12 | 16 | 11
222 | 55 | 37 | 84 | 129 | 175 | 224 | 279 | 321 | 366 | 414 | 455 | 504 | 551 | 591 | 10 | 9 | 9 | 9 | 8 | 10 | 14 | 15 | 13 | 9 | 10 | 13 | 9 | 13 | 16 | 8 | 11 | 9 | 13 | 16 | 12 | 12 | 15 | 16 | 8 | 8 | 16 | 10 | 10 | 10 | 10 | 15 | 12 | 13 | 12 | 11 | 13 | 9 | 11 | 8 | 11 | 10 | 14 | 14 | 14 | 9 | 16 | 8 | 8 | 9 | 11 | 12
223 | 80 | 55 | 112 | 159 | 217 | 263 | 311 | 354 | 406 | 458 | 514 | 556 | 600 | 645 | 12 | 16 | 14 | 13 | 13 | 12 | 16 | 16 | 13 | 13 | 13 | 8 | 15 | 16 | 15 | 12 | 15 | 11 | 12 | 8 | 13 | 16 | 8 | 11 | 9 | 12 | 11 | 11 | 10 | 16 | 13 | 13 | 11 | 16 | 12 | 13 | 15 | 14 | 16 | 11 | 12 | 10 | 9 | 11 | 10 | 9 | 15 | 10 | 16 | 9 | 10 | 10
224 | 73 | 47 | 98 | 142 | 191 | 239 | 293 | 349 | 402 | 451 | 498 | 548 | 603 | 643 | 10 | 11 | 13 | 13 | 16 | 10 | 16 | 9 | 13 | 10 | 11 | 10 | 13 | 14 | 14 | 8 | 11 | 12 | 14 | 11 | 11 | 14 | 14 | 15 | 16 | 15 | 9 | 16 | 11 | 13 | 15 | 14 | 8 | 13 | 16 | 12 | 12 | 11 | 10 | 14 | 14 | 12 | 11 | 13 | 16 | 8 | 16 | 15 | 9 | 12 | 8 | 11
225 | 83 | 55 | 106 | 149 | 190 | 236 | 286 | 334 | 384 | 424 | 462 | 513 | 555 | 598 | 16 | 15 | 10 | 14 | 14 | 14 | 12 | 11 | 13 | 11 | 10 | 9 | 8 | 9 | 14 | 10 | 12 | 14 | 10 | 10 | 13 | 8 | 14 | 15 | 9 | 16 | 9 | 14 | 14 | 16 | 8 | 12 | 10 | 13 | 9 | 8 | 8 | 10 | 11 | 9 | 9 | 11 | 16 | 15 | 14 | 10 | 8 | 10 | 8 | 10 | 16 | 9
226 | 69 | 42 | 85 | 136 | 191 | 244 | 290 | 332 | 372 | 418 | 461 | 511 | 553 | 606 | 8 | 11 | 8 | 15 | 12 | 15 | 8 | 8 | 14 | 12 | 9 | 16 | 15 | 16 | 11 | 13 | 8 | 16 | 13 | 16 | 16 | 13 | 8 | 9 | 12 | 9 | 8 | 13 | 9 | 8 | 14 | 9 | 8 | 13 | 16 | 9 | 10 | 16 | 8 | 9 | 10 | 13 | 15 | 12 | 13 | 8 | 9 | 12 | 12 | 15 | 13 | 13
227 | 66 | 38 | 93 | 132 | 188 | 237 | 285 | 322 | 371 | 418 | 459 | 506 | 548 | 602 | 9 | 12 | 9 | 8 | 16 | 12 | 14 | 13 | 8 | 13 | 8 | 10 | 15 | 12 | 13 | 16 | 13 | 13 | 9 | 14 | 14 | 9 | 13 | 12 | 8 | 13 | 8 | 8 | 16 | 10 | 9 | 14 | 9 | 10 | 13 | 15 | 15 | 8 | 10 | 8 | 11 | 8 | 14 | 14 | 8 | 11 | 15 | 8 | 14 | 14 | 13 | 13
228 | 61 | 43 | 80 | 136 | 183 | 231 | 283 | 336 | 386 | 438 | 483 | 529 | 575 | 628 | 16 | 8 | 9 | 10 | 10 | 8 | 10 | 9 | 14 | 16 | 15 | 11 | 10 | 10 | 12 | 15 | 14 | 15 | 11 | 8 | 15 | 12 | 15 | 10 | 15 | 15 | 12 | 11 | 15 | 12 | 13 | 10 | 14 | 15 | 10 | 13 | 8 | 10 | 15 | 12 | 11 | 10 | 15 | 10 | 15 | 11 | 9 | 11 | 13 | 14 | 11 | 15
229 | 73 | 45 | 99 | 142 | 196 | 244 | 290 | 344 | 385 | 433 | 485 | 536 | 581 | 629 | 10 | 9 | 16 | 10 | 13 | 15 | 11 | 15 | 15 | 11 | 8 | 9 | 13 | 15 | 13 | 13 | 15 | 10 | 10 | 13 | 16 | 8 | 8 | 14 | 16 | 9 | 16 | 13 | 13 | 11 | 8 | 9 | 10 | 12 | 12 | 14 | 9 | 16 | 16 | 11 | 14 | 16 | 12 | 9 | 11 | 16 | 8 | 10 | 13 | 16 | 8 | 11
230 | 70 | 45 | 96 | 136 | 198 | 249 | 308 | 356 | 404 | 460 | 505 | 549 | 594 | 649 | 16 | 8 | 13 | 8 | 10 | 15 | 11 | 15 | 8 | 8 | 13 | 11 | 16 | 16 | 15 | 15 | 12 | 10 | 15 | 14 | 16 | 14 | 13 | 16 | 15 | 8 | 13 | 12 | 13 | 12 | 14 | 9 | 14 | 10 | 16 | 16 | 9 | 11 | 9 | 16 | 13 | 9 | 11 | 11 | 8 | 15 | 9 | 13 | 16 | 12 | 11 | 16
231 | 67 | 44 | 90 | 140 | 181 | 231 | 271 | 320 | 358 | 406 | 459 | 517 | 570 | 613 | 8 | 11 | 9 | 16 | 11 | 12 | 10 | 13 | 11 | 11 | 12 | 16 | 11 | 8 | 14 | 8 | 11 | 9 | 14 | 16 | 11 | 13 | 8 | 8 | 8 | 16 | 13 | 12 | 8 | 9 | 12 | 9 | 9 | 10 | 15 | 14 | 8 | 15 | 15 | 15 | 16 | 16 | 11 | 15 | 14 | 11 | 12 | 16 | 13 | 12 | 8 | 10
232 | 67 | 49 | 85 | 133 | 180 | 233 | 287 | 335 | 390 | 441 | 485 | 544 | 591 | 634 | 11 | 9 | 16 | 13 | 8 | 10 | 10 | 8 | 15 | 14 | 10 | 9 | 13 | 12 | 11 | 11 | 13 | 15 | 16 | 9 | 11 | 15 | 16 | 12 | 8 | 11 | 16 | 13 | 13 | 11 | 16 | 15 | 12 | 15 | 12 | 12 | 14 | 12 | 10 | 8 | 15 | 13 | 16 | 15 | 10 | 12 | 16 | 9 | 9 | 11 | 9 | 14
233 | 75 | 47 | 100 | 151 | 203 | 249 | 290 | 347 | 388 | 434 | 475 | 524 | 561 | 611 | 11 | 16 | 9 | 11 | 12 | 16 | 14 | 11 | 15 | 12 | 15 | 9 | 15 | 13 | 14 | 10 | 10 | 14 | 8 | 14 | 11 | 13 | 8 | 9 | 16 | 14 | 15 | 12 | 10 | 14 | 9 | 8 | 11 | 11 | 14 | 10 | 12 | 8 | 12 | 9 | 12 | 13 | 10 | 14 | 10 | 9 | 10 | 8 | 15 | 14 | 12 | 9
234 | 80 | 51 | 108 | 160 | 207 | 263 | 310 | 352 | 406 | 457 | 500 | 552 | 608 | 651 | 11 | 10 | 16 | 14 | 15 | 14 | 16 | 12 | 10 | 12 | 15 | 15 | 10 | 9 | 12 | 16 | 15 | 13 | 14 | 14 | 14 | 11 | 10 | 12 | 14 | 12 | 8 | 8 | 15 | 16 | 13 | 10 | 15 | 14 | 10 | 12 | 9 | 12 | 13 | 9 | 12 | 15 | 11 | 14 | 16 | 15 | 12 | 13 | 8 | 8 | 15 | 12
235 | 71 | 52 | 101 | 146 | 189 | 244 | 300 | 346 | 394 | 439 | 477 | 524 | 582 | 621 | 9 | 14 | 13 | 16 | 10 | 9 | 15 | 15 | 9 | 14 | 10 | 12 | 9 | 13 | 9 | 12 | 16 | 15 | 13 | 11 | 16 | 14 | 14 | 12 | 16 | 11 | 11 | 8 | 10 | 11 | 12 | 15 | 9 | 11 | 14 | 11 | 8 | 8 | 8 | 14 | 13 | 13 | 13 | 8 | 14 | 15 | 13 | 16 | 9 | 10 | 12 | 8
236 | 59 | 40 | 89 | 142 | 199 | 255 | 297 | 343 | 392 | 444 | 488 | 537 | 586 | 638 | 13 | 10 | 9 | 8 | 11 | 8 | 15 | 15 | 14 | 15 | 13 | 11 | 15 | 15 | 14 | 13 | 12 | 16 | 12 | 16 | 10 | 13 | 11 | 8 | 12 | 8 | 11 | 15 | 14 | 11 | 10 | 14 | 14 | 11 | 15 | 12 | 13 | 10 | 10 | 11 | 9 | 13 | 13 | 14 | 13 | 11 | 12 | 13 | 15 | 13 | 16 | 8
237 | 73 | 52 | 90 | 130 | 171 | 219 | 272 | 329 | 380 | 426 | 481 | 525 | 577 | 627 | 16 | 12 | 8 | 16 | 8 | 13 | 9 | 8 | 9 | 8 | 8 | 15 | 8 | 10 | 8 | 15 | 9 | 9 | 14 | 16 | 15 | 14 | 9 | 15 | 16 | 13 | 12 | 16 | 8 | 16 | 12 | 15 | 16 | 12 | 10 | 8 | 14 | 16 | 12 | 13 | 9 | 13 | 11 | 11 | 16 | 12 | 15 | 9 | 12 | 15 | 12 | 11
238 | 76 | 49 | 98 | 150 | 198 | 235 | 273 | 311 | 351 | 398 | 449 | 493 | 538 | 592 | 9 | 16 | 10 | 14 | 15 | 12 | 14 | 8 | 12 | 13 | 13 | 14 | 13 | 13 | 14 | 8 | 8 | 9 | 9 | 11 | 8 | 9 | 13 | 8 | 10 | 8 | 9 | 11 | 11 | 12 | 8 | 9 | 11 | 9 | 15 | 12 | 13 | 9 | 15 | 14 | 13 | 11 | 10 | 10 | 9 | 11 | 9 | 16 | 12 | 14 | 12 | 16
239 | 72 | 49 | 91 | 144 | 187 | 233 | 275 | 331 | 373 | 421 | 477 | 518 | 572 | 626 | 9 | 14 | 14 | 12 | 9 | 14 | 8 | 11 | 15 | 13 | 12 | 13 | 12 | 9 | 8 | 14 | 13 | 11 | 14 | 8 | 12 | 12 | 10 | 8 | 15 | 15 | 16 | 10 | 13 | 12 | 8 | 9 | 11 | 14 | 11 | 12 | 11 | 16 | 15 | 14 | 8 | 12 | 8 | 13 | 15 | 16 | 14 | 9 | 16 | 8 | 15 | 15
240 | 63 | 45 | 91 | 140 | 189 | 242 | 296 | 340 | 383 | 433 | 480 | 524 | 569 | 623 | 13 | 8 | 10 | 14 | 9 | 9 | 15 | 13 | 15 | 12 | 14 | 8 | 16 | 8 | 13 | 12 | 13 | 13 | 12 | 15 | 16 | 13 | 16 | 9 | 8 | 8 | 13 | 15 | 11 | 12 | 9 | 11 | 12 | 16 | 13 | 9 | 12 | 12 | 8 | 15 | 12 | 8 | 13 | 11 | 9 | 10 | 11 | 15 | 10 | 16 | 14 | 14
241 | 70 | 45 | 100 | 146 | 192 | 245 | 296 | 344 | 393 | 441 | 493 | 546 | 591 | 634 | 10 | 9 | 12 | 14 | 10 | 15 | 14 | 16 | 11 | 9 | 14 | 12 | 8 | 15 | 11 | 12 | 16 | 11 | 12 | 14 | 16 | 9 | 15 | 11 | 9 | 14 | 13 | 12 | 12 | 10 | 12 | 15 | 15 | 14 | 9 | 10 | 12 | 14 | 12 | 14 | 13 | 10 | 16 | 14 | 8 | 11 | 16 | 10 | 9 | 8 | 16 | 10
242 | 81 | 55 | 102 | 144 | 186 | 232 | 278 | 334 | 385 | 435 | 478 | 532 | 582 | 631 | 15 | 16 | 9 | 15 | 16 | 10 | 9 | 12 | 11 | 11 | 12 | 8 | 13 | 10 | 11 | 8 | 14 | 8 | 9 | 15 | 11 | 11 | 9 | 15 | 11 | 16 | 13 | 16 | 10 | 16 | 9 | 16 | 14 | 15 | 10 | 11 | 13 | 11 | 11 | 8 | 13 | 11 | 14 | 16 | 14 | 13 | 14 | 9 | 8 | 14 | 15 | 12
243 | 67 | 39 | 84 | 132 | 193 | 237 | 288 | 335 | 383 | 424 | 469 | 515 | 559 | 604 | 11 | 10 | 10 | 8 | 13 | 15 | 8 | 9 | 12 | 13 | 8 | 15 | 16 | 16 | 14 | 15 | 13 | 12 | 9 | 10 | 15 | 15 | 12 | 9 | 13 | 12 | 13 | 9 | 15 | 11 | 8 | 14 | 12 | 8 | 12 | 9 | 12 | 15 | 10 | 8 | 10 | 10 | 11 | 15 | 8 | 9 | 13 | 14 | 12 | 9 | 8 | 16
244 | 83 | 54 | 106 | 157 | 208 | 254 | 297 | 341 | 389 | 429 | 486 | 538 | 580 | 621 | 14 | 16 | 15 | 9 | 15 | 14 | 13 | 10 | 10 | 16 | 11 | 14 | 11 | 14 | 13 | 13 | 9 | 14 | 14 | 9 | 13 | 9 | 9 | 12 | 10 | 8 | 13 | 13 | 15 | 8 | 10 | 15 | 13 | 9 | 9 | 9 | 12 | 15 | 15 | 15 | 8 | 16 | 16 | 12 | 11 | 10 | 10 | 11 | 10 | 13 | 10 | 8
245 | 69 | 46 | 93 | 137 | 189 | 240 | 291 | 339 | 384 | 432 | 483 | 528 | 576 | 624 | 11 | 8 | 15 | 12 | 13 | 10 | 10 | 14 | 16 | 10 | 8 | 10 | 10 | 15 | 12 | 15 | 8 | 15 | 15 | 13 | 12 | 14 | 9 | 16 | 14 | 11 | 15 | 8 | 13 | 16 | 8 | 8 | 16 | 8 | 16 | 8 | 14 | 9 | 16 | 12 | 12 | 13 | 10 | 10 | 9 | 15 | 13 | 11 | 14 | 15 | 10 | 9
246 | 73 | 53 | 103 | 158 | 203 | 260 | 308 | 362 | 402 | 444 | 499 | 560 | 609 | 652 | 12 | 14 | 14 | 13 | 8 | 12 | 14 | 16 | 16 | 16 | 11 | 12 | 13 | 9 | 10 | 13 | 16 | 16 | 11 | 14 | 15 | 12 | 11 | 10 | 15 | 12 | 15 | 12 | 8 | 10 | 8 | 14 | 12 | 8 | 14 | 8 | 16 | 16 | 14 | 9 | 14 | 15 | 16 | 16 | 8 | 15 | 16 | 10 | 9 | 10 | 10 | 14
247 | 81 | 58 | 102 | 161 | 200 | 239 | 295 | 344 | 388 | 440 | 488 | 539 | 589 | 642 | 14 | 14 | 15 | 15 | 13 | 10 | 8 | 13 | 14 | 16 | 16 | 13 | 10 | 10 | 9 | 10 | 10 | 9 | 12 | 8 | 13 | 14 | 13 | 16 | 10 | 9 | 14 | 16 | 9 | 12 | 9 | 14 | 9 | 16 | 14 | 13 | 13 | 13 | 10 | 12 | 15 | 12 | 10 | 14 | 11 | 15 | 14 | 10 | 11 | 16 | 13 | 13
248 | 80 | 50 | 102 | 148 | 201 | 251 | 306 | 355 | 401 | 443 | 488 | 545 | 593 | 631 | 12 | 9 | 14 | 15 | 16 | 14 | 14 | 8 | 9 | 16 | 12 | 9 | 11 | 14 | 12 | 16 | 13 | 14 | 15 | 8 | 16 | 12 | 11 | 16 | 8 | 16 | 14 | 11 | 9 | 14 | 13 | 10 | 11 | 9 | 11 | 11 | 8 | 15 | 13 | 9 | 16 | 12 | 16 | 13 | 15 | 13 | 11 | 9 | 8 | 8 | 11 | 11
249 | 77 | 46 | 100 | 144 | 191 | 236 | 278 | 322 | 359 | 411 | 461 | 506 | 550 | 609 | 8 | 16 | 10 | 12 | 15 | 16 | 15 | 8 | 8 | 9 | 16 | 11 | 9 | 9 | 16 | 13 | 8 | 9 | 15 | 13 | 8 | 11 | 14 | 9 | 13 | 10 | 12 | 9 | 9 | 11 | 9 | 8 | 10 | 16 | 13 | 13 | 8 | 11 | 16 | 15 | 9 | 15 | 8 | 13 | 14 | 9 | 8 | 13 | 13 | 15 | 15 | 16
250 | 70 | 51 | 99 | 152 | 200 | 254 | 309 | 348 | 400 | 448 | 498 | 550 | 598 | 644 | 10 | 10 | 16 | 15 | 11 | 8 | 13 | 16 | 15 | 15 | 11 | 12 | 14 | 13 | 11 | 10 | 16 | 13 | 15 | 10 | 15 | 16 | 9 | 15 | 10 | 9 | 9 | 11 | 12 | 10 | 16 | 14 | 15 | 9 | 9 | 15 | 14 | 14 | 10 | 12 | 12 | 14 | 11 | 15 | 11 | 12 | 12 | 13 | 9 | 10 | 12 | 15
251 | 71 | 45 | 97 | 141 | 183 | 235 | 282 | 340 | 388 | 439 | 493 | 544 | 598 | 650 | 9 | 11 | 11 | 14 | 12 | 14 | 14 | 12 | 10 | 10 | 10 | 14 | 10 | 9 | 13 | 10 | 13 | 12 | 11 | 16 | 16 | 10 | 11 | 10 | 15 | 12 | 15 | 16 | 13 | 12 | 14 | 9 | 11 | 10 | 15 | 15 | 16 | 15 | 12 | 11 | 14 | 10 | 15 | 12 | 14 | 15 | 11 | 14 | 15 | 11 | 15 | 11
252 | 73 | 45 | 90 | 137 | 178 | 224 | 274 | 316 | 363 | 408 | 452 | 503 | 550 | 608 | 12 | 12 | 10 | 11 | 14 | 14 | 8 | 9 | 9 | 15 | 8 | 15 | 9 | 10 | 14 | 8 | 11 | 10 | 14 | 11 | 15 | 9 | 16 | 10 | 16 | 8 | 9 | 9 | 10 | 14 | 15 | 8 | 11 | 14 | 12 | 8 | 12 | 9 | 12 | 11 | 14 | 12 | 15 | 10 | 15 | 9 | 12 | 11 | 16 | 16 | 13 | 13
253 | 73 | 47 | 96 | 154 | 212 | 256 | 302 | 347 | 391 | 443 | 495 | 545 | 593 | 638 | 8 | 16 | 13 | 10 | 16 | 10 | 9 | 14 | 15 | 13 | 14 | 16 | 15 | 15 | 15 | 13 | 8 | 12 | 10 | 14 | 10 | 14 | 11 | 11 | 11 | 10 | 10 | 14 | 10 | 11 | 14 | 9 | 11 | 16 | 16 | 9 | 13 | 16 | 8 | 15 | 13 | 11 | 10 | 16 | 9 | 15 | 11 | 13 | 8 | 15 | 11 | 11
254 | 74 | 49 | 100 | 149 | 205 | 254 | 298 | 348 | 399 | 458 | 507 | 550 | 602 | 644 | 16 | 8 | 12 | 13 | 13 | 12 | 16 | 10 | 9 | 12 | 14 | 14 | 15 | 14 | 11 | 16 | 8 | 15 | 10 | 16 | 8 | 16 | 9 | 11 | 13 | 10 | 13 | 14 | 15 | 14 | 13 | 9 | 15 | 16 | 16 | 12 | 9 | 12 | 15 | 13 | 8 | 10 | 13 | 12 | 16 | 14 | 8 | 14 | 9 | 15 | 10 | 8
255 | 67 | 42 | 88 | 139 | 188 | 231 | 275 | 326 | 367 | 423 | 474 | 515 | 561 | 606 | 8 | 8 | 10 | 16 | 9 | 16 | 10 | 11 | 15 | 10 | 15 | 11 | 12 | 13 | 12 | 12 | 12 | 9 | 11 | 11 | 9 | 9 | 13 | 13 | 14 | 16 | 9 | 12 | 8 | 12 | 12 | 9 | 11 | 16 | 14 | 15 | 11 | 13 | 13 | 14 | 8 | 9 | 12 | 12 | 9 | 12 | 16 | 9 | 13 | 8 | 12 | 12
256 | 66 | 35 | 84 | 130 | 182 | 232 | 278 | 331 | 384 | 433 | 492 | 538 | 594 | 647 | 8 | 8 | 10 | 9 | 15 | 16 | 10 | 8 | 8 | 14 | 8 | 16 | 15 | 11 | 10 | 16 | 9 | 10 | 16 | 15 | 12 | 9 | 9 | 16 | 14 | 16 | 10 | 13 | 9 | 16 | 13 | 15 | 16 | 8 | 15 | 10 | 15 | 14 | 16 | 14 | 13 | 12 | 12 | 9 | 11 | 14 | 16 | 15 | 12 | 14 | 14 | 13
257 | 83 | 54 | 106 | 158 | 205 | 252 | 305 | 360 | 413 | 454 | 510 | 557 | 598 | 641 | 9 | 16 | 14 | 15 | 14 | 15 | 14 | 9 | 16 | 8 | 16 | 12 | 14 | 9 | 13 | 11 | 13 | 12 | 13 | 9 | 14 | 11 | 14 | 14 | 13 | 14 | 12 | 16 | 11 | 15 | 14 | 13 | 9 | 10 | 12 | 10 | 15 | 16 | 14 | 11 | 15 | 11 | 11 | 10 | 10 | 10 | 13 | 8 | 9 | 15 | 10 | 9
258 | 77 | 52 | 97 | 143 | 186 | 241 | 293 | 338 | 393 | 437 | 486 | 528 | 580 | 626 | 16 | 10 | 13 | 13 | 11 | 14 | 9 | 11 | 9 | 11 | 15 | 11 | 9 | 12 | 13 | 9 | 15 | 12 | 14 | 14 | 15 | 10 | 13 | 14 | 10 | 13 | 10 | 12 | 16 | 12 | 11 | 16 | 16 | 11 | 9 | 8 | 8 | 13 | 14 | 14 | 11 | 12 | 8 | 11 | 13 | 12 | 12 | 15 | 9 | 14 | 14 | 9
259 | 67 | 46 | 90 | 143 | 189 | 235 | 275 | 325 | 370 | 415 | 459 | 509 | 556 | 600 | 11 | 16 | 11 | 8 | 12 | 9 | 15 | 8 | 10 | 15 | 12 | 16 | 14 | 9 | 14 | 9 | 8 | 12 | 12 | 14 | 9 | 9 | 8 | 14 | 11 | 13 | 14 | 12 | 13 | 8 | 8 | 16 | 8 | 16 | 9 | 12 | 14 | 12 | 10 | 8 | 14 | 11 | 16 | 9 | 12 | 11 | 9 | 15 | 13 | 12 | 8 | 11
260 | 67 | 41 | 93 | 143 | 187 | 235 | 285 | 334 | 382 | 435 | 479 | 532 | 578 | 622 | 8 | 8 | 13 | 12 | 12 | 14 | 14 | 12 | 15 | 9 | 10 | 16 | 11 | 10 | 8 | 15 | 11 | 12 | 12 | 13 | 14 | 8 | 14 | 14 | 14 | 11 | 8 | 16 | 12 | 12 | 12 | 12 | 13 | 13 | 11 | 16 | 12 | 9 | 14 | 9 | 11 | 12 | 15 | 15 | 9 | 14 | 8 | 15 | 12 | 9 | 11 | 12
261 | 81 | 58 | 97 | 150 | 194 | 240 | 284 | 324 | 374 | 414 | 455 | 507 | 557 | 603 | 16 | 16 | 12 | 14 | 13 | 10 | 8 | 8 | 13 | 15 | 16 | 9 | 9 | 8 | 11 | 16 | 9 | 9 | 13 | 15 | 12 | 8 | 10 | 14 | 10 | 9 | 8 | 13 | 12 | 13 | 15 | 10 | 9 | 13 | 8 | 10 | 8 | 8 | 16 | 9 | 9 | 11 | 16 | 16 | 14 | 16 | 10 | 10 | 10 | 12 | 11 | 13
262 | 81 | 49 | 108 | 159 | 201 | 258 | 311 | 355 | 401 | 456 | 502 | 557 | 610 | 647 | 9 | 13 | 14 | 13 | 16 | 16 | 14 | 13 | 12 | 15 | 8 | 16 | 11 | 11 | 9 | 11 | 16 | 16 | 12 | 13 | 11 | 14 | 14 | 14 | 13 | 9 | 13 | 9 | 8 | 12 | 16 | 10 | 16 | 11 | 13 | 15 | 15 | 13 | 8 | 10 | 11 | 14 | 16 | 14 | 11 | 10 | 16 | 16 | 8 | 8 | 10 | 11
263 | 80 | 57 | 105 | 162 | 208 | 263 | 309 | 359 | 404 | 448 | 493 | 542 | 588 | 645 | 16 | 15 | 13 | 13 | 15 | 8 | 12 | 13 | 14 | 15 | 14 | 14 | 9 | 15 | 9 | 13 | 15 | 9 | 15 | 16 | 11 | 16 | 9 | 10 | 16 | 11 | 10 | 13 | 9 | 12 | 10 | 14 | 14 | 11 | 8 | 11 | 13 | 8 | 10 | 14 | 8 | 13 | 16 | 12 | 10 | 10 | 15 | 11 | 14 | 14 | 16 | 13
264 | 68 | 46 | 94 | 153 | 199 | 252 | 303 | 356 | 405 | 457 | 500 | 546 | 590 | 641 | 13 | 13 | 10 | 10 | 11 | 11 | 11 | 15 | 15 | 14 | 16 | 14 | 9 | 10 | 15 | 12 | 15 | 16 | 9 | 13 | 16 | 16 | 10 | 9 | 15 | 11 | 13 | 14 | 15 | 13 | 13 | 8 | 14 | 10 | 12 | 16 | 11 | 13 | 9 | 10 | 9 | 14 | 13 | 10 | 14 | 14 | 8 | 8 | 14 | 13 | 9 | 15
265 | 76 | 51 | 99 | 152 | 208 | 255 | 296 | 336 | 389 | 437 | 486 | 534 | 581 | 628 | 14 | 12 | 15 | 10 | 9 | 16 | 12 | 11 | 16 | 12 | 15 | 10 | 15 | 16 | 15 | 10 | 13 | 16 | 9 | 9 | 10 | 10 | 8 | 13 | 8 | 11 | 9 | 12 | 13 | 10 | 15 | 15 | 10 | 13 | 14 | 11 | 13 | 10 | 12 | 14 | 9 | 9 | 15 | 15 | 10 | 13 | 12 | 12 | 13 | 9 | 12 | 13
266 | 75 | 44 | 95 | 139 | 180 | 232 | 277 | 318 | 369 | 414 | 464 | 506 | 549 | 590 | 10 | 12 | 10 | 12 | 15 | 16 | 12 | 8 | 10 | 13 | 8 | 13 | 8 | 8 | 15 | 10 | 8 | 13 | 15 | 16 | 16 | 8 | 10 | 11 | 10 | 8 | 13 | 10 | 13 | 15 | 10 | 13 | 8 | 12 | 11 | 14 | 12 | 8 | 16 | 14 | 11 | 15 | 8 | 8 | 10 | 13 | 12 | 8 | 8 | 8 | 14 | 11
267 | 72 | 49 | 95 | 145 | 190 | 235 | 284 | 324 | 372 | 421 | 464 | 518 | 559 | 611 | 13 | 12 | 16 | 8 | 14 | 9 | 10 | 13 | 14 | 12 | 12 | 12 | 13 | 11 | 9 | 12 | 16 | 8 | 10 | 11 | 10 | 13 | 15 | 11 | 9 | 15 | 8 | 8 | 13 | 11 | 16 | 8 | 15 | 16 | 10 | 8 | 8 | 9 | 12 | 14 | 13 | 13 | 12 | 16 | 9 | 8 | 13 | 11 | 11 | 15 | 12 | 14
268 | 79 | 55 | 99 | 147 | 196 | 244 | 287 | 341 | 383 | 433 | 478 | 520 | 573 | 614 | 13 | 13 | 13 | 16 | 14 | 10 | 12 | 8 | 16 | 13 | 10 | 9 | 8 | 16 | 12 | 13 | 10 | 12 | 11 | 15 | 11 | 13 | 10 | 9 | 14 | 11 | 13 | 16 | 11 | 9 | 9 | 13 | 12 | 9 | 14 | 15 | 8 | 9 | 15 | 13 | 13 | 10 | 10 | 9 | 11 | 14 | 16 | 12 | 12 | 9 | 9 | 11
269 | 87 | 59 | 106 | 165 | 216 | 264 | 307 | 351 | 391 | 437 | 482 | 537 | 575 | 627 | 15 | 14 | 15 | 15 | 16 | 12 | 9 | 10 | 14 | 15 | 14 | 16 | 13 | 13 | 9 | 16 | 14 | 13 | 12 | 9 | 10 | 10 | 8 | 15 | 10 | 8 | 14 | 12 | 10 | 10 | 12 | 8 | 11 | 12 | 10 | 13 | 8 | 14 | 13 | 10 | 12 | 16 | 13 | 14 | 11 | 9 | 9 | 9 | 9 | 13 | 14 | 16
270 | 66 | 39 | 93 | 137 | 177 | 224 | 277 | 325 | 364 | 412 | 458 | 504 | 559 | 605 | 8 | 9 | 14 | 8 | 13 | 14 | 11 | 16 | 11 | 14 | 8 | 11 | 11 | 13 | 8 | 8 | 8 | 9 | 15 | 15 | 10 | 16 | 16 | 11 | 8 | 16 | 14 | 10 | 9 | 9 | 13 | 8 | 11 | 13 | 14 | 10 | 12 | 9 | 12 | 13 | 11 | 10 | 13 | 12 | 15 | 9 | 16 | 15 | 10 | 11 | 12 | 13
271 | 70 | 45 | 98 | 146 | 193 | 239 | 293 | 345 | 390 | 433 | 480 | 521 | 569 | 614 | 11 | 11 | 12 | 11 | 10 | 15 | 15 | 13 | 14 | 8 | 16 | 10 | 15 | 9 | 9 | 14 | 12 | 16 | 8 | 10 | 13 | 12 | 13 | 16 | 13 | 14 | 10 | 15 | 13 | 14 | 10 | 8 | 8 | 11 | 9 | 15 | 8 | 16 | 8 | 15 | 9 | 10 | 8 | 14 | 13 | 10 | 15 | 10 | 16 | 8 | 8 | 13
272 | 66 | 38 | 86 | 135 | 186 | 229 | 282 | 330 | 372 | 414 | 466 | 518 | 558 | 614 | 9 | 10 | 8 | 11 | 12 | 16 | 11 | 9 | 11 | 12 | 10 | 16 | 16 | 11 | 13 | 11 | 12 | 10 | 9 | 12 | 14 | 13 | 16 | 10 | 9 | 14 | 14 | 11 | 13 | 11 | 8 | 10 | 15 | 10 | 9 | 8 | 16 | 13 | 8 | 15 | 16 | 8 | 16 | 12 | 8 | 14 | 8 | 10 | 16 | 15 | 12 | 13
273 | 79 | 51 | 98 | 153 | 198 | 245 | 294 | 337 | 374 | 431 | 479 | 528 | 570 | 621 | 10 | 10 | 16 | 15 | 15 | 13 | 11 | 8 | 10 | 15 | 14 | 16 | 16 | 9 | 8 | 12 | 13 | 8 | 16 | 10 | 10 | 11 | 13 | 15 | 9 | 9 | 15 | 10 | 9 | 8 | 11 | 9 | 15 | 11 | 16 | 15 | 12 | 14 | 9 | 13 | 8 | 12 | 13 | 16 | 8 | 16 | 10 | 8 | 16 | 10 | 10 | 15
274 | 71 | 42 | 103 | 148 | 199 | 258 | 305 | 361 | 411 | 453 | 496 | 540 | 592 | 644 | 9 | 13 | 12 | 8 | 14 | 15 | 16 | 16 | 9 | 12 | 10 | 14 | 11 | 12 | 15 | 13 | 11 | 16 | 16 | 16 | 14 | 11 | 8 | 14 | 15 | 15 | 13 | 13 | 12 | 13 | 12 | 13 | 16 | 9 | 9 | 8 | 12 | 13 | 8 | 10 | 11 | 9 | 14 | 10 | 16 | 15 | 8 | 13 | 12 | 15 | 10 | 15
275 | 76 | 54 | 102 | 148 | 195 | 250 | 290 | 334 | 375 | 421 | 470 | 525 | 574 | 618 | 13 | 13 | 15 | 13 | 10 | 12 | 13 | 13 | 16 | 10 | 10 | 10 | 16 | 12 | 8 | 11 | 15 | 15 | 12 | 13 | 10 | 12 | 8 | 10 | 9 | 12 | 14 | 9 | 8 | 8 | 11 | 14 | 9 | 12 | 16 | 9 | 16 | 8 | 12 | 13 | 14 | 14 | 13 | 14 | 9 | 14 | 14 | 12 | 11 | 16 | 9 | 8
276 | 65 | 41 | 91 | 143 | 199 | 250 | 299 | 351 | 401 | 453 | 498 | 553 | 593 | 635 | 15 | 8 | 9 | 9 | 8 | 16 | 14 | 12 | 9 | 14 | 14 | 15 | 14 | 12 | 15 | 15 | 16 | 11 | 16 | 8 | 14 | 12 | 11 | 12 | 15 | 12 | 9 | 16 | 14 | 15 | 11 | 10 | 11 | 13 | 16 | 12 | 12 | 9 | 10 | 14 | 15 | 14 | 11 | 15 | 10 | 10 | 11 | 9 | 9 | 11 | 14 | 8
277 | 73 | 45 | 98 | 133 | 188 | 243 | 290 | 340 | 388 | 437 | 490 | 532 | 585 | 628 | 10 | 13 | 9 | 13 | 13 | 15 | 16 | 9 | 9 | 9 | 9 | 8 | 15 | 12 | 12 | 16 | 12 | 13 | 15 | 15 | 9 | 12 | 12 | 14 | 15 | 10 | 11 | 14 | 16 | 9 | 14 | 9 | 9 | 16 | 8 | 16 | 11 | 13 | 13 | 16 | 15 | 8 | 10 | 9 | 11 | 16 | 14 | 12 | 8 | 8 | 16 | 11
278 | 56 | 36 | 79 | 126 | 169 | 229 | 277 | 328 | 373 | 419 | 473 | 514 | 560 | 608 | 11 | 8 | 8 | 9 | 8 | 12 | 8 | 15 | 10 | 13 | 10 | 14 | 9 | 8 | 16 | 10 | 14 | 16 | 14 | 16 | 15 | 8 | 13 | 12 | 15 | 12 | 8 | 16 | 15 | 8 | 14 | 8 | 14 | 9 | 10 | 13 | 14 | 9 | 15 | 16 | 9 | 16 | 8 | 8 | 11 | 11 | 11 | 13 | 11 | 16 | 11 | 10
279 | 76 | 51 | 101 | 146 | 194 | 242 | 288 | 334 | 385 | 440 | 481 | 532 | 581 | 622 | 12 | 14 | 12 | 13 | 11 | 14 | 9 | 16 | 16 | 12 | 8 | 9 | 8 | 14 | 16 | 10 | 10 | 13 | 10 | 15 | 11 | 8 | 12 | 15 | 13 | 10 | 14 | 9 | 12 | 9 | 15 | 15 | 13 | 12 | 15 | 15 | 8 | 15 | 10 | 8 | 15 | 10 | 14 | 12 | 16 | 9 | 15 | 9 | 8 | 9 | 12 | 12
280 | 71 | 53 | 99 | 147 | 191 | 247 | 288 | 326 | 372 | 420 | 470 | 519 | 560 | 612 | 8 | 15 | 14 | 16 | 9 | 9 | 13 | 15 | 13 | 10 | 14 | 11 | 9 | 9 | 12 | 14 | 15 | 14 | 13 | 14 | 11 | 9 | 10 | 11 | 9 | 9 | 12 | 8 | 16 | 8 | 11 | 11 | 14 | 11 | 11 | 12 | 11 | 10 | 13 | 16 | 11 | 9 | 16 | 13 | 11 | 8 | 10 | 12 | 14 | 15 | 9 | 14
281 | 78 | 48 | 104 | 151 | 199 | 243 | 277 | 312 | 360 | 407 | 454 | 506 | 555 | 599 | 11 | 9 | 14 | 14 | 16 | 14 | 12 | 14 | 12 | 12 | 11 | 12 | 14 | 10 | 11 | 13 | 16 | 8 | 9 | 11 | 9 | 8 | 9 | 8 | 8 | 8 | 11 | 8 | 12 | 12 | 8 | 16 | 8 | 9 | 14 | 16 | 8 | 10 | 13 | 16 | 12 | 12 | 14 | 14 | 10 | 12 | 16 | 11 | 11 | 13 | 10 | 10
282 | 70 | 40 | 92 | 142 | 183 | 245 | 300 | 357 | 411 | 458 | 503 | 549 | 602 | 652 | 10 | 8 | 14 | 8 | 16 | 14 | 10 | 12 | 14 | 9 | 13 | 14 | 8 | 11 | 11 | 11 | 15 | 15 | 16 | 16 | 10 | 16 | 15 | 14 | 14 | 15 | 13 | 15 | 14 | 11 | 13 | 16 | 13 | 15 | 8 | 11 | 11 | 9 | 14 | 11 | 12 | 10 | 8 | 16 | 13 | 9 | 15 | 16 | 13 | 15 | 12 | 10
283 | 77 | 58 | 108 | 156 | 203 | 258 | 306 | 348 | 398 | 446 | 497 | 534 | 582 | 629 | 16 | 15 | 11 | 16 | 11 | 8 | 15 | 16 | 9 | 15 | 10 | 14 | 9 | 13 | 11 | 14 | 12 | 12 | 16 | 15 | 12 | 8 | 12 | 16 | 9 | 8 | 16 | 9 | 11 | 12 | 11 | 16 | 9 | 11 | 14 | 14 | 16 | 8 | 14 | 13 | 8 | 8 | 8 | 13 | 14 | 12 | 8 | 14 | 14 | 11 | 13 | 9
284 | 74 | 48 | 96 | 140 | 189 | 242 | 287 | 332 | 382 | 436 | 491 | 538 | 577 | 624 | 15 | 13 | 12 | 8 | 15 | 11 | 10 | 12 | 8 | 12 | 8 | 16 | 15 | 8 | 15 | 11 | 16 | 10 | 12 | 15 | 11 | 12 | 9 | 13 | 10 | 8 | 12 | 15 | 13 | 8 | 16 | 13 | 9 | 16 | 14 | 15 | 16 | 16 | 8 | 15 | 10 | 13 | 8 | 16 | 9 | 8 | 12 | 10 | 8 | 11 | 16 | 12
285 | 67 | 45 | 95 | 144 | 191 | 250 | 294 | 340 | 393 | 446 | 492 | 536 | 582 | 635 | 12 | 14 | 10 | 9 | 11 | 11 | 15 | 13 | 10 | 13 | 14 | 12 | 9 | 16 | 12 | 10 | 16 | 13 | 16 | 14 | 13 | 13 | 10 | 8 | 10 | 10 | 12 | 14 | 13 | 13 | 11 | 16 | 13 | 12 | 14 | 14 | 15 | 14 | 9 | 8 | 11 | 11 | 14 | 8 | 9 | 13 | 15 | 9 | 13 | 10 | 16 | 14
286 | 78 | 50 | 102 | 145 | 190 | 234 | 282 | 331 | 376 | 430 | 474 | 528 | 577 | 619 | 14 | 11 | 9 | 16 | 15 | 13 | 11 | 13 | 13 | 9 | 8 | 13 | 14 | 10 | 13 | 8 | 12 | 12 | 10 | 10 | 10 | 12 | 11 | 15 | 12 | 12 | 14 | 11 | 11 | 13 | 11 | 10 | 10 | 13 | 16 | 15 | 10 | 12 | 13 | 9 | 14 | 14 | 15 | 11 | 13 | 9 | 11 | 16 | 8 | 9 | 12 | 13
287 | 71 | 47 | 98 | 148 | 190 | 239 | 289 | 337 | 376 | 414 | 455 | 501 | 551 | 597 | 10 | 9 | 13 | 15 | 16 | 8 | 16 | 11 | 12 | 14 | 8 | 16 | 13 | 11 | 10 | 8 | 14 | 9 | 14 | 12 | 14 | 16 | 9 | 11 | 11 | 14 | 8 | 15 | 11 | 9 | 9 | 10 | 11 | 10 | 8 | 9 | 11 | 8 | 14 | 8 | 13 | 8 | 13 | 12 | 12 | 14 | 9 | 15 | 14 | 9 | 10 | 13
288 | 62 | 43 | 85 | 140 | 187 | 234 | 266 | 324 | 369 | 420 | 459 | 504 | 556 | 604 | 10 | 8 | 9 | 16 | 9 | 10 | 8 | 15 | 14 | 16 | 12 | 13 | 9 | 9 | 14 | 15 | 11 | 8 | 13 | 15 | 8 | 8 | 8 | 8 | 14 | 15 | 13 | 16 | 11 | 12 | 14 | 8 | 16 | 11 | 8 | 16 | 9 | 9 | 12 | 9 | 10 | 12 | 8 | 15 | 11 | 13 | 12 | 16 | 8 | 16 | 15 | 9
289 | 62 | 40 | 87 | 136 | 185 | 225 | 272 | 325 | 376 | 424 | 469 | 513 | 568 | 611 | 8 | 10 | 14 | 8 | 9 | 13 | 11 | 14 | 9 | 14 | 15 | 11 | 11 | 14 | 11 | 13 | 8 | 12 | 10 | 10 | 13 | 11 | 15 | 8 | 12 | 16 | 9 | 16 | 13 | 16 | 13 | 9 | 15 | 12 | 13 | 8 | 12 | 11 | 9 | 13 | 8 | 16 | 9 | 11 | 15 | 13 | 11 | 16 | 8 | 14 | 10 | 11
290 | 77 | 51 | 103 | 148 | 203 | 249 | 290 | 325 | 379 | 435 | 482 | 532 | 578 | 623 | 15 | 11 | 12 | 13 | 12 | 14 | 16 | 10 | 9 | 13 | 10 | 13 | 14 | 13 | 14 | 14 | 10 | 14 | 14 | 8 | 8 | 13 | 9 | 11 | 9 | 10 | 8 | 8 | 14 | 9 | 15 | 16 | 12 | 15 | 16 | 13 | 9 | 13 | 16 | 9 | 12 | 14 | 14 | 10 | 8 | 9 | 13 | 16 | 8 | 15 | 9 | 13
291 | 70 | 48 | 93 | 134 | 176 | 232 | 282 | 328 | 379 | 426 | 465 | 514 | 552 | 603 | 13 | 15 | 8 | 12 | 14 | 8 | 15 | 8 | 8 | 11 | 12 | 10 | 11 | 9 | 13 | 9 | 14 | 11 | 16 | 15 | 15 | 11 | 12 | 12 | 8 | 15 | 9 | 14 | 16 | 9 | 13 | 13 | 16 | 15 | 8 | 8 | 9 | 11 | 11 | 8 | 15 | 11 | 13 | 10 | 12 | 8 | 8 | 10 | 16 | 15 | 11 | 9
292 | 66 | 41 | 89 | 135 | 179 | 223 | 271 | 319 | 372 | 415 | 468 | 511 | 564 | 605 | 14 | 9 | 10 | 8 | 10 | 15 | 13 | 10 | 9 | 15 | 9 | 13 | 10 | 11 | 10 | 13 | 15 | 9 | 9 | 11 | 14 | 13 | 11 | 10 | 14 | 8 | 13 | 13 | 12 | 13 | 13 | 15 | 9 | 10 | 12 | 12 | 16 | 13 | 10 | 14 | 11 | 9 | 10 | 13 | 14 | 12 | 13 | 14 | 8 | 10 | 14 | 9
293 | 72 | 42 | 90 | 127 | 170 | 223 | 268 | 318 | 364 | 406 | 454 | 500 | 540 | 588 | 11 | 11 | 8 | 12 | 15 | 15 | 8 | 10 | 12 | 8 | 9 | 8 | 14 | 8 | 10 | 11 | 12 | 13 | 15 | 13 | 12 | 9 | 13 | 11 | 15 | 16 | 11 | 8 | 11 | 14 | 12 | 9 | 15 | 9 | 8 | 10 | 13 | 13 | 8 | 14 | 14 | 15 | 9 | 8 | 12 | 8 | 8 | 12 | 14 | 8 | 12 | 14
294 | 77 | 51 | 102 | 147 | 190 | 232 | 280 | 325 | 376 | 432 | 476 | 533 | 578 | 629 | 14 | 14 | 11 | 12 | 14 | 12 | 12 | 13 | 9 | 13 | 10 | 13 | 10 | 16 | 9 | 8 | 8 | 9 | 9 | 16 | 15 | 9 | 10 | 14 | 13 | 12 | 11 | 9 | 10 | 16 | 9 | 16 | 11 | 16 | 15 | 14 | 14 | 9 | 9 | 12 | 16 | 15 | 14 | 12 | 13 | 15 | 9 | 8 | 14 | 16 | 8 | 13
295 | 68 | 46 | 93 | 140 | 194 | 246 | 302 | 348 | 399 | 445 | 488 | 536 | 578 | 624 | 11 | 15 | 10 | 10 | 12 | 10 | 10 | 15 | 9 | 16 | 11 | 11 | 12 | 15 | 11 | 16 | 15 | 10 | 14 | 13 | 15 | 11 | 14 | 16 | 16 | 8 | 9 | 13 | 11 | 11 | 16 | 13 | 14 | 8 | 9 | 15 | 13 | 9 | 13 | 8 | 10 | 11 | 11 | 16 | 8 | 10 | 8 | 16 | 12 | 11 | 8 | 15
296 | 69 | 46 | 94 | 138 | 182 | 232 | 281 | 330 | 376 | 419 | 469 | 515 | 562 | 611 | 9 | 15 | 12 | 10 | 11 | 12 | 11 | 14 | 10 | 16 | 8 | 10 | 10 | 8 | 15 | 11 | 8 | 15 | 14 | 13 | 11 | 8 | 15 | 15 | 15 | 11 | 14 | 9 | 8 | 16 | 12 | 10 | 10 | 8 | 9 | 16 | 14 | 15 | 8 | 13 | 10 | 11 | 16 | 9 | 10 | 13 | 8 | 16 | 9 | 16 | 10 | 14
297 | 73 | 48 | 89 | 125 | 182 | 222 | 280 | 322 | 375 | 427 | 477 | 527 | 574 | 623 | 12 | 13 | 13 | 10 | 10 | 15 | 8 | 8 | 10 | 9 | 8 | 9 | 16 | 13 | 15 | 13 | 10 | 9 | 12 | 9 | 16 | 13 | 16 | 13 | 11 | 8 | 9 | 14 | 14 | 13 | 11 | 15 | 12 | 16 | 13 | 11 | 10 | 14 | 12 | 14 | 10 | 15 | 16 | 9 | 9 | 14 | 13 | 11 | 15 | 9 | 16 | 9
298 | 70 | 51 | 95 | 142 | 194 | 252 | 296 | 350 | 393 | 435 | 480 | 528 | 585 | 628 | 14 | 10 | 11 | 16 | 9 | 10 | 9 | 16 | 9 | 14 | 10 | 14 | 16 | 13 | 9 | 14 | 11 | 16 | 16 | 15 | 14 | 9 | 10 | 11 | 16 | 13 | 13 | 12 | 12 | 11 | 12 | 8 | 8 | 8 | 10 | 16 | 14 | 8 | 10 | 13 | 11 | 10 | 11 | 16 | 16 | 16 | 16 | 9 | 9 | 15 | 10 | 9
299 | 60 | 37 | 91 | 133 | 183 | 232 | 291 | 333 | 380 | 428 | 478 | 531 | 578 | 625 | 8 | 9 | 12 | 8 | 15 | 8 | 16 | 15 | 12 | 12 | 10 | 8 | 10 | 14 | 12 | 14 | 12 | 14 | 12 | 11 | 16 | 16 | 11 | 16 | 8 | 12 | 12 | 10 | 11 | 12 | 9 | 15 | 13 | 9 | 11 | 15 | 10 | 16 | 8 | 16 | 16 | 16 | 10 | 11 | 10 | 10 | 11 | 16 | 10 | 11 | 12 | 14
300 | 73 | 48 | 103 | 147 | 198 | 255 | 306 | 349 | 396 | 445 | 499 | 550 | 589 | 639 | 9 | 14 | 11 | 14 | 14 | 11 | 16 | 14 | 9 | 9 | 10 | 16 | 13 | 16 | 11 | 11 | 14 | 16 | 16 | 11 | 16 | 8 | 11 | 16 | 11 | 9 | 11 | 12 | 9 | 10 | 16 | 12 | 12 | 8 | 16 | 13 | 13 | 11 | 14 | 16 | 16 | 15 | 10 | 10 | 9 | 8 | 13 | 9 | 12 | 12 | 15 | 11
301 | 65 | 40 | 88 | 132 | 175 | 223 | 269 | 317 | 369 | 419 | 480 | 525 | 574 | 616 | 10 | 8 | 12 | 10 | 16 | 9 | 14 | 9 | 15 | 8 | 9 | 12 | 8 | 13 | 14 | 8 | 9 | 12 | 11 | 16 | 13 | 8 | 9 | 16 | 14 | 13 | 10 | 11 | 15 | 12 | 11 | 14 | 12 | 8 | 16 | 14 | 16 | 16 | 13 | 16 | 9 | 11 | 14 | 11 | 9 | 16 | 13 | 11 | 8 | 9 | 12 | 13
302 | 68 | 47 | 89 | 139 | 183 | 236 | 289 | 332 | 379 | 429 | 479 | 533 | 586 | 637 | 8 | 11 | 12 | 16 | 10 | 11 | 12 | 9 | 12 | 15 | 14 | 9 | 11 | 10 | 9 | 14 | 12 | 15 | 11 | 15 | 10 | 15 | 16 | 12 | 9 | 12 | 9 | 13 | 13 | 14 | 11 | 9 | 16 | 9 | 12 | 13 | 15 | 10 | 10 | 15 | 11 | 13 | 14 | 16 | 12 | 12 | 13 | 16 | 13 | 11 | 15 | 12
303 | 63 | 40 | 91 | 136 | 179 | 218 | 268 | 317 | 369 | 410 | 455 | 503 | 551 | 605 | 9 | 10 | 8 | 13 | 12 | 11 | 12 | 16 | 11 | 10 | 11 | 13 | 12 | 11 | 12 | 8 | 8 | 8 | 9 | 14 | 12 | 16 | 12 | 10 | 11 | 13 | 16 | 9 | 16 | 10 | 12 | 14 | 12 | 10 | 8 | 11 | 13 | 14 | 9 | 9 | 13 | 9 | 16 | 10 | 8 | 15 | 10 | 15 | 11 | 16 | 14 | 13
304 | 71 | 47 | 91 | 147 | 185 | 223 | 265 | 309 | 358 | 408 | 463 | 513 | 553 | 608 | 14 | 8 | 13 | 12 | 12 | 12 | 8 | 12 | 12 | 13 | 15 | 16 | 9 | 13 | 8 | 8 | 9 | 12 | 8 | 9 | 12 | 8 | 10 | 12 | 8 | 12 | 9 | 15 | 16 | 13 | 8 | 12 | 11 | 16 | 8 | 15 | 16 | 15 | 14 | 10 | 13 | 13 | 9 | 15 | 8 | 10 | 14 | 8 | 15 | 14 | 12 | 14
305 | 77 | 51 | 97 | 143 | 188 | 239 | 282 | 332 | 383 | 435 | 481 | 527 | 571 | 623 | 13 | 12 | 10 | 16 | 11 | 15 | 10 | 10 | 13 | 12 | 8 | 13 | 9 | 15 | 12 | 9 | 15 | 10 | 15 | 11 | 11 | 15 | 8 | 9 | 14 | 14 | 9 | 13 | 14 | 16 | 13 | 8 | 11 | 15 | 11 | 15 | 13 | 14 | 10 | 9 | 11 | 12 | 13 | 10 | 13 | 12 | 10 | 9 | 12 | 11 | 16 | 13
306 | 60 | 42 | 85 | 131 | 186 | 232 | 285 | 342 | 399 | 444 | 492 | 544 | 599 | 650 | 9 | 9 | 10 | 14 | 9 | 9 | 14 | 11 | 14 | 11 | 9 | 12 | 14 | 13 | 12 | 16 | 15 | 11 | 11 | 9 | 13 | 15 | 14 | 11 | 16 | 15 | 13 | 13 | 16 | 14 | 16 | 11 | 9 | 15 | 13 | 8 | 10 | 16 | 9 | 13 | 12 | 15 | 15 | 10 | 14 | 11 | 15 | 15 | 10 | 15 | 11 | 15
307 | 76 | 52 | 107 | 158 | 207 | 259 | 300 | 344 | 403 | 454 | 499 | 539 | 594 | 651 | 16 | 15 | 8 | 13 | 14 | 10 | 15 | 16 | 9 | 12 | 16 | 14 | 15 | 10 | 9 | 15 | 12 | 14 | 10 | 16 | 8 | 9 | 15 | 9 | 14 | 8 | 12 | 10 | 13 | 15 | 15 | 16 | 16 | 15 | 9 | 11 | 11 | 9 | 13 | 12 | 8 | 12 | 8 | 12 | 12 | 16 | 11 | 16 | 16 | 16 | 16 | 9
308 | 70 | 40 | 94 | 150 | 198 | 245 | 285 | 331 | 372 | 424 | 473 | 522 | 570 | 610 | 8 | 11 | 13 | 8 | 15 | 15 | 8 | 16 | 15 | 14 | 15 | 12 | 15 | 11 | 8 | 14 | 12 | 8 | 12 | 15 | 9 | 12 | 8 | 11 | 13 | 13 | 9 | 11 | 9 | 13 | 10 | 9 | 13 | 10 | 14 | 15 | 11 | 14 | 10 | 14 | 11 | 8 | 16 | 14 | 15 | 8 | 9 | 16 | 8 | 12 | 12 | 8
309 | 73 | 50 | 99 | 150 | 195 | 243 | 294 | 343 | 393 | 437 | 488 | 542 | 596 | 639 | 10 | 14 | 15 | 11 | 13 | 10 | 14 | 12 | 8 | 15 | 15 | 13 | 14 | 10 | 9 | 12 | 11 | 14 | 9 | 14 | 9 | 12 | 15 | 15 | 11 | 15 | 15 | 8 | 10 | 13 | 11 | 16 | 9 | 16 | 8 | 11 | 10 | 13 | 16 | 12 | 16 | 11 | 12 | 15 | 13 | 14 | 16 | 11 | 15 | 11 | 8 | 9
310 | 66 | 46 | 84 | 130 | 185 | 228 | 275 | 331 | 375 | 421 | 463 | 515 | 554 | 605 | 16 | 9 | 9 | 12 | 12 | 8 | 9 | 9 | 12 | 13 | 13 | 8 | 12 | 13 | 16 | 14 | 10 | 10 | 15 | 8 | 11 | 12 | 10 | 14 | 15 | 11 | 14 | 16 | 11 | 9 | 15 | 9 | 10 | 8 | 15 | 13 | 15 | 10 | 8 | 9 | 15 | 12 | 12 | 13 | 10 | 10 | 11 | 8 | 9 | 16 | 15 | 11
311 | 68 | 44 | 87 | 134 | 188 | 239 | 284 | 332 | 384 | 437 | 485 | 530 | 580 | 631 | 12 | 12 | 9 | 11 | 8 | 16 | 8 | 11 | 13 | 13 | 11 | 10 | 13 | 14 | 16 | 11 | 15 | 9 | 16 | 11 | 16 | 9 | 10 | 10 | 11 | 14 | 15 | 8 | 15 | 16 | 12 | 9 | 10 | 15 | 16 | 12 | 8 | 14 | 15 | 11 | 12 | 11 | 10 | 12 | 14 | 10 | 15 | 11 | 10 | 12 | 14 | 15
312 | 75 | 51 | 107 | 148 | 190 | 239 | 291 | 344 | 392 | 448 | 490 | 533 | 579 | 631 | 14 | 9 | 14 | 14 | 11 | 13 | 16 | 16 | 9 | 10 | 10 | 12 | 11 | 14 | 9 | 8 | 10 | 13 | 14 | 12 | 16 | 8 | 13 | 15 | 16 | 9 | 16 | 12 | 14 | 13 | 10 | 11 | 11 | 15 | 16 | 14 | 8 | 8 | 12 | 14 | 10 | 10 | 10 | 13 | 15 | 8 | 12 | 11 | 12 | 15 | 9 | 16
313 | 81 | 49 | 101 | 162 | 205 | 251 | 302 | 347 | 397 | 448 | 502 | 550 | 595 | 656 | 11 | 8 | 14 | 16 | 16 | 16 | 11 | 9 | 16 | 16 | 13 | 16 | 10 | 14 | 11 | 8 | 8 | 15 | 13 | 10 | 11 | 16 | 12 | 12 | 12 | 16 | 9 | 8 | 12 | 13 | 14 | 11 | 16 | 16 | 10 | 9 | 13 | 12 | 16 | 13 | 12 | 10 | 11 | 15 | 13 | 9 | 12 | 11 | 16 | 13 | 16 | 16
314 | 75 | 51 | 104 | 150 | 198 | 245 | 292 | 347 | 394 | 443 | 488 | 538 | 585 | 628 | 10 | 15 | 16 | 10 | 14 | 10 | 16 | 13 | 13 | 16 | 9 | 8 | 8 | 14 | 10 | 16 | 12 | 9 | 13 | 13 | 8 | 11 | 15 | 13 | 15 | 11 | 15 | 14 | 16 | 15 | 8 | 8 | 13 | 14 | 14 | 8 | 15 | 8 | 13 | 9 | 8 | 14 | 15 | 13 | 8 | 16 | 15 | 8 | 11 | 10 | 8 | 14
315 | 67 | 45 | 90 | 138 | 190 | 240 | 285 | 342 | 392 | 437 | 488 | 537 | 575 | 626 | 11 | 13 | 12 | 9 | 14 | 8 | 14 | 9 | 12 | 12 | 12 | 12 | 14 | 11 | 11 | 16 | 14 | 9 | 15 | 12 | 15 | 12 | 8 | 10 | 13 | 15 | 16 | 13 | 14 | 14 | 10 | 12 | 12 | 13 | 10 | 10 | 12 | 15 | 9 | 15 | 10 | 10 | 13 | 16 | 10 | 10 | 8 | 10 | 14 | 12 | 15 | 10
316 | 66 | 50 | 91 | 131 | 184 | 238 | 280 | 330 | 373 | 424 | 474 | 525 | 567 | 612 | 9 | 10 | 16 | 15 | 8 | 8 | 14 | 11 | 8 | 8 | 13 | 11 | 10 | 16 | 14 | 13 | 13 | 11 | 16 | 14 | 12 | 8 | 11 | 11 | 16 | 12 | 9 | 13 | 8 | 14 | 13 | 8 | 16 | 13 | 8 | 14 | 13 | 9 | 14 | 14 | 15 | 12 | 13 | 11 | 14 | 8 | 9 | 11 | 11 | 10 | 10 | 14
317 | 85 | 56 | 106 | 155 | 201 | 252 | 307 | 353 | 402 | 451 | 504 | 549 | 602 | 651 | 12 | 15 | 16 | 13 | 14 | 15 | 13 | 8 | 11 | 13 | 13 | 12 | 11 | 16 | 8 | 11 | 11 | 14 | 15 | 11 | 15 | 14 | 12 | 14 | 10 | 13 | 9 | 14 | 16 | 11 | 12 | 10 | 8 | 16 | 15 | 10 | 13 | 11 | 16 | 13 | 8 | 14 | 8 | 15 | 14 | 14 | 16 | 9 | 9 | 9 | 15 | 16
318 | 63 | 37 | 92 | 148 | 204 | 260 | 305 | 350 | 394 | 450 | 496 | 548 | 597 | 639 | 9 | 10 | 10 | 8 | 14 | 12 | 13 | 16 | 15 | 12 | 13 | 16 | 9 | 16 | 16 | 15 | 12 | 15 | 14 | 15 | 9 | 15 | 12 | 9 | 12 | 9 | 13 | 11 | 8 | 13 | 10 | 13 | 12 | 13 | 15 | 16 | 11 | 9 | 10 | 16 | 12 | 16 | 11 | 13 | 8 | 14 | 12 | 15 | 9 | 10 | 8 | 15
319 | 69 | 47 | 89 | 131 | 178 | 229 | 286 | 338 | 385 | 428 | 481 | 530 | 579 | 630 | 13 | 10 | 14 | 10 | 9 | 13 | 8 | 12 | 9 | 12 | 9 | 12 | 11 | 12 | 16 | 8 | 15 | 13 | 11 | 12 | 15 | 10 | 16 | 16 | 14 | 15 | 13 | 10 | 15 | 12 | 8 | 12 | 10 | 15 | 8 | 10 | 15 | 10 | 13 | 15 | 13 | 15 | 9 | 12 | 8 | 15 | 11 | 15 | 12 | 12 | 13 | 14
320 | 78 | 51 | 105 | 155 | 203 | 248 | 289 | 328 | 380 | 424 | 473 | 522 | 577 | 635 | 9 | 16 | 12 | 14 | 15 | 12 | 14 | 13 | 11 | 11 | 13 | 15 | 9 | 16 | 9 | 14 | 9 | 16 | 9 | 11 | 12 | 9 | 9 | 11 | 9 | 9 | 11 | 10 | 15 | 11 | 16 | 10 | 8 | 10 | 15 | 11 | 11 | 10 | 14 | 14 | 10 | 16 | 15 | 8 | 11 | 16 | 13 | 15 | 14 | 16 | 15 | 13
321 | 82 | 50 | 109 | 162 | 220 | 265 | 304 | 352 | 403 | 443 | 501 | 549 | 598 | 644 | 14 | 13 | 15 | 8 | 16 | 16 | 15 | 12 | 12 | 16 | 13 | 12 | 16 | 14 | 15 | 13 | 8 | 14 | 12 | 11 | 10 | 12 | 9 | 8 | 16 | 15 | 9 | 8 | 11 | 14 | 14 | 12 | 8 | 8 | 8 | 16 | 14 | 15 | 13 | 16 | 10 | 15 | 15 | 8 | 10 | 14 | 14 | 11 | 13 | 9 | 16 | 8
322 | 73 | 50 | 94 | 147 | 189 | 237 | 279 | 330 | 372 | 423 | 477 | 522 | 565 | 623 | 11 | 12 | 15 | 12 | 13 | 10 | 13 | 8 | 13 | 9 | 15 | 16 | 8 | 13 | 10 | 11 | 12 | 9 | 13 | 14 | 11 | 10 | 9 | 12 | 12 | 15 | 9 | 15 | 10 | 11 | 13 | 8 | 10 | 16 | 11 | 14 | 16 | 9 | 16 | 13 | 8 | 9 | 15 | 13 | 10 | 12 | 8 | 13 | 10 | 16 | 16 | 16
323 | 81 | 58 | 104 | 146 | 200 | 249 | 303 | 349 | 395 | 449 | 499 | 540 | 589 | 634 | 16 | 13 | 13 | 16 | 12 | 11 | 14 | 9 | 13 | 9 | 9 | 11 | 10 | 12 | 16 | 16 | 16 | 12 | 10 | 11 | 15 | 16 | 10 | 13 | 10 | 13 | 13 | 10 | 16 | 9 | 11 | 10 | 11 | 15 | 14 | 14 | 11 | 14 | 10 | 15 | 9 | 9 | 9 | 14 | 11 | 11 | 13 | 14 | 14 | 12 | 10 | 9
324 | 79 | 48 | 108 | 158 | 204 | 260 | 308 | 360 | 414 | 468 | 513 | 556 | 611 | 660 | 16 | 14 | 9 | 9 | 15 | 16 | 13 | 16 | 15 | 10 | 10 | 15 | 12 | 14 | 12 | 8 | 15 | 13 | 16 | 12 | 14 | 9 | 10 | 15 | 9 | 12 | 16 | 15 | 12 | 15 | 12 | 15 | 14 | 8 | 16 | 16 | 11 | 14 | 11 | 9 | 9 | 12 | 8 | 14 | 13 | 13 | 13 | 16 | 14 | 9 | 16 | 10
325 | 72 | 47 | 103 | 156 | 201 | 247 | 298 | 353 | 400 | 454 | 502 | 552 | 602 | 638 | 12 | 9 | 14 | 12 | 15 | 10 | 16 | 15 | 11 | 12 | 16 | 14 | 9 | 10 | 13 | 13 | 9 | 15 | 9 | 13 | 9 | 16 | 12 | 14 | 13 | 15 | 13 | 14 | 11 | 15 | 9 | 12 | 15 | 12 | 14 | 13 | 11 | 12 | 14 | 11 | 9 | 14 | 16 | 11 | 15 | 12 | 13 | 10 | 10 | 9 | 9 | 8
326 | 71 | 41 | 99 | 149 | 199 | 243 | 297 | 340 | 389 | 442 | 492 | 537 | 588 | 640 | 9 | 14 | 9 | 9 | 16 | 14 | 13 | 15 | 15 | 12 | 12 | 11 | 10 | 14 | 13 | 13 | 12 | 9 | 15 | 8 | 9 | 16 | 15 | 14 | 9 | 13 | 8 | 13 | 13 | 13 | 12 | 11 | 12 | 16 | 11 | 14 | 8 | 13 | 13 | 16 | 11 | 9 | 16 | 9 | 15 | 13 | 13 | 10 | 16 | 12 | 9 | 15
327 | 74 | 50 | 101 | 144 | 189 | 237 | 285 | 342 | 395 | 449 | 505 | 547 | 598 | 655 | 11 | 10 | 13 | 16 | 16 | 8 | 11 | 16 | 14 | 13 | 8 | 8 | 10 | 12 | 11 | 12 | 16 | 8 | 12 | 12 | 13 | 8 | 14 | 13 | 16 | 11 | 15 | 15 | 13 | 16 | 15 | 9 | 11 | 15 | 13 | 15 | 16 | 12 | 16 | 12 | 11 | 9 | 13 | 9 | 13 | 11 | 11 | 16 | 15 | 14 | 16 | 12
328 | 64 | 42 | 88 | 144 | 195 | 255 | 299 | 347 | 402 | 448 | 501 | 550 | 598 | 638 | 13 | 10 | 10 | 9 | 13 | 9 | 13 | 11 | 15 | 14 | 15 | 12 | 13 | 12 | 16 | 10 | 16 | 14 | 15 | 15 | 9 | 13 | 11 | 11 | 14 | 14 | 12 | 8 | 12 | 13 | 15 | 15 | 8 | 14 | 12 | 12 | 12 | 12 | 13 | 16 | 13 | 10 | 12 | 14 | 8 | 16 | 12 | 12 | 9 | 13 | 10 | 8
329 | 58 | 39 | 80 | 120 | 160 | 219 | 258 | 295 | 342 | 399 | 451 | 506 | 564 | 611 | 8 | 10 | 10 | 11 | 11 | 8 | 14 | 8 | 11 | 10 | 11 | 8 | 10 | 9 | 11 | 10 | 15 | 14 | 14 | 16 | 14 | 8 | 8 | 9 | 12 | 8 | 9 | 8 | 14 | 13 | 9 | 11 | 12 | 16 | 15 | 14 | 9 | 16 | 11 | 16 | 12 | 13 | 16 | 14 | 13 | 16 | 14 | 15 | 10 | 10 | 16 | 11
330 | 71 | 46 | 99 | 153 | 196 | 243 | 282 | 334 | 386 | 444 | 498 | 542 | 590 | 638 | 15 | 13 | 10 | 8 | 16 | 9 | 14 | 14 | 12 | 15 | 11 | 16 | 13 | 8 | 13 | 9 | 13 | 11 | 11 | 12 | 8 | 10 | 11 | 10 | 16 | 11 | 12 | 13 | 15 | 13 | 14 | 10 | 16 | 14 | 12 | 16 | 12 | 16 | 13 | 13 | 13 | 14 | 9 | 8 | 13 | 13 | 10 | 12 | 15 | 10 | 13 | 10
331 | 61 | 45 | 93 | 140 | 189 | 244 | 291 | 341 | 392 | 433 | 483 | 526 | 568 | 600 | 10 | 10 | 15 | 10 | 8 | 8 | 16 | 16 | 13 | 16 | 10 | 8 | 11 | 10 | 14 | 14 | 10 | 15 | 16 | 14 | 14 | 10 | 12 | 11 | 12 | 16 | 11 | 11 | 16 | 12 | 8 | 15 | 15 | 8 | 9 | 9 | 12 | 14 | 11 | 13 | 15 | 8 | 8 | 12 | 13 | 8 | 12 | 9 | 8 | 8 | 8 | 8
332 | 76 | 54 | 93 | 151 | 207 | 260 | 311 | 364 | 416 | 467 | 509 | 565 | 604 | 662 | 13 | 16 | 14 | 11 | 14 | 8 | 9 | 8 | 15 | 16 | 13 | 14 | 12 | 14 | 15 | 15 | 9 | 13 | 16 | 15 | 15 | 11 | 12 | 13 | 11 | 14 | 13 | 15 | 16 | 10 | 14 | 12 | 14 | 14 | 14 | 9 | 8 | 11 | 12 | 11 | 14 | 14 | 16 | 12 | 9 | 10 | 8 | 12 | 11 | 15 | 16 | 16
333 | 74 | 53 | 94 | 143 | 200 | 245 | 291 | 338 | 389 | 445 | 490 | 542 | 596 | 651 | 10 | 15 | 13 | 15 | 10 | 11 | 10 | 10 | 15 | 8 | 13 | 13 | 15 | 12 | 14 | 16 | 8 | 13 | 8 | 16 | 11 | 9 | 10 | 16 | 15 | 8 | 15 | 9 | 15 | 15 | 9 | 12 | 16 | 16 | 10 | 14 | 9 | 16 | 8 | 12 | 11 | 16 | 14 | 11 | 13 | 16 | 10 | 15 | 15 | 12 | 13 | 15
334 | 80 | 54 | 107 | 155 | 195 | 236 | 285 | 329 | 381 | 431 | 473 | 522 | 572 | 626 | 12 | 14 | 16 | 12 | 13 | 13 | 14 | 13 | 14 | 15 | 9 | 10 | 9 | 8 | 15 | 8 | 8 | 15 | 8 | 10 | 11 | 16 | 13 | 9 | 8 | 12 | 12 | 12 | 13 | 13 | 12 | 14 | 14 | 11 | 13 | 12 | 9 | 12 | 11 | 10 | 8 | 15 | 14 | 12 | 11 | 16 | 9 | 14 | 16 | 12 | 10 | 16
335 | 78 | 54 | 105 | 162 | 213 | 257 | 308 | 362 | 415 | 461 | 512 | 555 | 600 | 640 | 16 | 11 | 11 | 16 | 8 | 16 | 15 | 12 | 15 | 12 | 14 | 16 | 15 | 11 | 9 | 16 | 15 | 9 | 9 | 11 | 13 | 9 | 16 | 13 | 14 | 14 | 10 | 16 | 14 | 12 | 16 | 11 | 11 | 12 | 10 | 13 | 9 | 16 | 15 | 11 | 10 | 8 | 14 | 11 | 11 | 13 | 8 | 13 | 14 | 10 | 8 | 8
336 | 63 | 39 | 85 | 130 | 182 | 228 | 278 | 330 | 378 | 424 | 476 | 516 | 568 | 612 | 8 | 10 | 10 | 11 | 12 | 12 | 13 | 9 | 8 | 9 | 15 | 13 | 9 | 12 | 15 | 16 | 11 | 14 | 8 | 13 | 16 | 9 | 15 | 10 | 15 | 11 | 12 | 14 | 16 | 8 | 12 | 12 | 16 | 9 | 8 | 13 | 13 | 9 | 14 | 16 | 10 | 10 | 12 | 8 | 15 | 12 | 12 | 13 | 10 | 9 | 13 | 12
337 | 63 | 46 | 88 | 136 | 181 | 233 | 286 | 330 | 378 | 423 | 471 | 525 | 568 | 611 | 9 | 11 | 13 | 13 | 8 | 9 | 10 | 15 | 11 | 11 | 13 | 13 | 8 | 8 | 13 | 16 | 15 | 10 | 11 | 16 | 12 | 15 | 10 | 16 | 8 | 16 | 12 | 8 | 14 | 8 | 16 | 10 | 9 | 10 | 14 | 12 | 12 | 14 | 10 | 12 | 11 | 15 | 12 | 16 | 10 | 9 | 12 | 12 | 15 | 12 | 8 | 8
338 | 64 | 47 | 92 | 126 | 178 | 219 | 259 | 316 | 355 | 402 | 454 | 501 | 551 | 592 | 10 | 14 | 15 | 8 | 8 | 9 | 14 | 14 | 8 | 9 | 8 | 9 | 15 | 9 | 15 | 13 | 16 | 9 | 8 | 8 | 14 | 9 | 9 | 8 | 15 | 10 | 16 | 16 | 11 | 8 | 11 | 9 | 11 | 15 | 11 | 10 | 14 | 12 | 10 | 16 | 14 | 8 | 10 | 15 | 16 | 8 | 13 | 13 | 8 | 9 | 14 | 10
339 | 76 | 44 | 92 | 139 | 179 | 229 | 279 | 327 | 378 | 425 | 467 | 521 | 572 | 627 | 9 | 15 | 12 | 8 | 16 | 16 | 8 | 8 | 11 | 10 | 16 | 10 | 8 | 14 | 9 | 9 | 12 | 15 | 13 | 10 | 8 | 16 | 13 | 13 | 9 | 11 | 15 | 13 | 15 | 16 | 9 | 11 | 13 | 15 | 8 | 11 | 9 | 9 | 16 | 8 | 11 | 15 | 14 | 14 | 8 | 14 | 14 | 15 | 9 | 16 | 15 | 15
340 | 71 | 39 | 96 | 148 | 204 | 246 | 301 | 342 | 384 | 437 | 482 | 531 | 579 | 627 | 9 | 8 | 14 | 8 | 16 | 16 | 14 | 11 | 13 | 14 | 12 | 13 | 16 | 15 | 9 | 16 | 14 | 11 | 9 | 8 | 10 | 16 | 15 | 14 | 15 | 9 | 8 | 9 | 11 | 10 | 10 | 11 | 14 | 14 | 13 | 12 | 15 | 10 | 11 | 9 | 8 | 13 | 16 | 12 | 11 | 16 | 11 | 10 | 10 | 8 | 16 | 14
341 | 67 | 44 | 91 | 150 | 196 | 249 | 302 | 352 | 393 | 444 | 489 | 533 | 577 | 618 | 8 | 16 | 9 | 11 | 9 | 14 | 8 | 16 | 13 | 16 | 16 | 14 | 8 | 16 | 11 | 11 | 16 | 14 | 9 | 14 | 15 | 14 | 16 | 8 | 12 | 11 | 11 | 16 | 14 | 11 | 8 | 8 | 15 | 15 | 9 | 12 | 14 | 9 | 14 | 8 | 12 | 9 | 9 | 14 | 12 | 15 | 9 | 8 | 9 | 15 | 9 | 8
342 | 76 | 48 | 100 | 150 | 203 | 243 | 289 | 336 | 388 | 440 | 485 | 526 | 573 | 620 | 10 | 9 | 14 | 15 | 16 | 12 | 16 | 8 | 16 | 9 | 12 | 13 | 15 | 12 | 10 | 16 | 10 | 9 | 12 | 9 | 9 | 10 | 15 | 12 | 12 | 10 | 13 | 12 | 15 | 12 | 12 | 13 | 14 | 9 | 13 | 16 | 12 | 10 | 15 | 8 | 9 | 11 | 8 | 13 | 13 | 11 | 12 | 11 | 10 | 12 | 15 | 10
343 | 76 | 48 | 98 | 141 | 180 | 227 | 272 | 309 | 356 | 403 | 460 | 498 | 551 | 589 | 14 | 10 | 9 | 15 | 14 | 14 | 9 | 13 | 8 | 15 | 11 | 9 | 8 | 10 | 9 | 12 | 10 | 15 | 9 | 13 | 8 | 14 | 10 | 13 | 9 | 9 | 8 | 11 | 16 | 10 | 11 | 10 | 9 | 15 | 15 | 8 | 15 | 16 | 10 | 16 | 8 | 8 | 12 | 10 | 13 | 9 | 15 | 16 | 11 | 9 | 8 | 10
344 | 55 | 38 | 80 | 137 | 190 | 245 | 290 | 336 | 380 | 426 | 473 | 529 | 574 | 621 | 11 | 8 | 11 | 8 | 8 | 9 | 16 | 9 | 15 | 15 | 14 | 13 | 10 | 16 | 12 | 15 | 16 | 11 | 12 | 16 | 12 | 11 | 10 | 12 | 14 | 12 | 11 | 9 | 12 | 8 | 16 | 8 | 15 | 14 | 8 | 9 | 12 | 12 | 9 | 14 | 15 | 10 | 15 | 16 | 11 | 11 | 15 | 8 | 16 | 8 | 9 | 14
345 | 72 | 51 | 94 | 145 | 194 | 233 | 279 | 322 | 367 | 412 | 455 | 495 | 556 | 598 | 14 | 14 | 12 | 11 | 11 | 10 | 12 | 10 | 13 | 13 | 9 | 16 | 16 | 12 | 12 | 9 | 11 | 8 | 12 | 8 | 8 | 14 | 14 | 10 | 10 | 12 | 10 | 11 | 12 | 14 | 10 | 9 | 10 | 12 | 11 | 12 | 8 | 10 | 12 | 13 | 12 | 9 | 8 | 11 | 14 | 16 | 15 | 16 | 10 | 12 | 9 | 11
346 | 61 | 45 | 83 | 126 | 168 | 212 | 260 | 304 | 347 | 401 | 446 | 499 | 552 | 609 | 8 | 10 | 15 | 12 | 8 | 8 | 12 | 10 | 9 | 16 | 10 | 8 | 9 | 9 | 13 | 11 | 8 | 10 | 14 | 12 | 13 | 12 | 14 | 9 | 10 | 10 | 13 | 11 | 10 | 11 | 14 | 8 | 13 | 13 | 15 | 13 | 10 | 10 | 14 | 11 | 16 | 12 | 13 | 12 | 10 | 16 | 12 | 15 | 10 | 15 | 16 | 16
347 | 83 | 56 | 106 | 142 | 187 | 243 | 301 | 345 | 393 | 440 | 489 | 537 | 590 | 635 | 12 | 15 | 15 | 14 | 15 | 12 | 8 | 15 | 12 | 8 | 8 | 8 | 10 | 10 | 10 | 15 | 15 | 13 | 15 | 13 | 16 | 12 | 16 | 14 | 10 | 15 | 11 | 8 | 9 | 12 | 16 | 11 | 11 | 12 | 9 | 15 | 14 | 12 | 14 | 9 | 16 | 10 | 14 | 8 | 12 | 14 | 11 | 16 | 15 | 8 | 9 | 13
348 | 75 | 46 | 102 | 148 | 201 | 248 | 291 | 338 | 389 | 432 | 473 | 516 | 557 | 604 | 13 | 13 | 8 | 12 | 14 | 15 | 16 | 11 | 8 | 13 | 11 | 14 | 12 | 16 | 16 | 9 | 8 | 16 | 14 | 9 | 10 | 11 | 13 | 9 | 13 | 14 | 8 | 12 | 16 | 9 | 16 | 10 | 9 | 10 | 12 | 12 | 15 | 9 | 8 | 9 | 9 | 12 | 14 | 8 | 11 | 9 | 9 | 12 | 12 | 13 | 13 | 9
349 | 77 | 46 | 98 | 145 | 190 | 240 | 294 | 342 | 396 | 438 | 486 | 536 | 581 | 624 | 10 | 10 | 10 | 16 | 16 | 15 | 9 | 12 | 14 | 9 | 13 | 11 | 11 | 14 | 12 | 8 | 14 | 8 | 15 | 13 | 9 | 14 | 15 | 16 | 9 | 14 | 14 | 11 | 14 | 13 | 12 | 15 | 11 | 10 | 12 | 9 | 10 | 13 | 16 | 9 | 15 | 11 | 11 | 13 | 9 | 16 | 12 | 8 | 14 | 8 | 12 | 9
350 | 63 | 42 | 86 | 127 | 172 | 216 | 260 | 313 | 361 | 410 | 463 | 501 | 549 | 600 | 11 | 9 | 9 | 13 | 8 | 13 | 12 | 11 | 13 | 10 | 10 | 8 | 16 | 9 | 11 | 9 | 14 | 9 | 13 | 8 | 11 | 9 | 11 | 13 | 12 | 15 | 13 | 13 | 11 | 13 | 11 | 13 | 14 | 11 | 12 | 12 | 16 | 8 | 16 | 13 | 13 | 9 | 8 | 8 | 11 | 9 | 15 | 13 | 11 | 14 | 16 | 10
351 | 73 | 47 | 98 | 140 | 184 | 238 | 284 | 332 | 379 | 430 | 479 | 527 | 570 | 616 | 12 | 12 | 9 | 14 | 10 | 16 | 10 | 15 | 11 | 10 | 10 | 11 | 9 | 12 | 13 | 10 | 14 | 15 | 14 | 11 | 15 | 13 | 8 | 10 | 13 | 15 | 11 | 9 | 13 | 11 | 10 | 13 | 14 | 13 | 16 | 8 | 12 | 13 | 8 | 16 | 12 | 12 | 16 | 8 | 11 | 12 | 12 | 8 | 9 | 16 | 10 | 11
352 | 87 | 62 | 107 | 160 | 207 | 254 | 306 | 350 | 393 | 444 | 485 | 537 | 580 | 623 | 16 | 14 | 16 | 16 | 13 | 12 | 12 | 8 | 15 | 12 | 12 | 14 | 10 | 16 | 8 | 13 | 13 | 12 | 12 | 10 | 15 | 13 | 8 | 16 | 13 | 12 | 11 | 8 | 10 | 8 | 16 | 9 | 8 | 14 | 15 | 14 | 11 | 9 | 10 | 11 | 14 | 11 | 12 | 15 | 8 | 8 | 11 | 16 | 8 | 12 | 12 | 11
353 | 78 | 51 | 103 | 150 | 198 | 247 | 301 | 347 | 392 | 430 | 474 | 521 | 557 | 609 | 13 | 9 | 13 | 16 | 13 | 14 | 11 | 14 | 11 | 10 | 12 | 14 | 11 | 16 | 12 | 9 | 10 | 15 | 13 | 11 | 12 | 11 | 15 | 16 | 10 | 12 | 14 | 10 | 14 | 8 | 12 | 11 | 8 | 11 | 9 | 10 | 14 | 9 | 13 | 8 | 14 | 10 | 10 | 13 | 9 | 11 | 8 | 8 | 16 | 15 | 11 | 10
354 | 81 | 53 | 103 | 151 | 198 | 240 | 285 | 332 | 381 | 431 | 467 | 519 | 572 | 621 | 14 | 10 | 16 | 13 | 12 | 16 | 14 | 8 | 13 | 15 | 10 | 10 | 15 | 13 | 10 | 9 | 11 | 10 | 9 | 12 | 9 | 16 | 11 | 9 | 15 | 10 | 9 | 13 | 9 | 14 | 16 | 10 | 14 | 15 | 11 | 10 | 10 | 9 | 8 | 9 | 10 | 13 | 14 | 15 | 15 | 11 | 15 | 12 | 14 | 14 | 8 | 13
355 | 81 | 55 | 101 | 154 | 204 | 251 | 293 | 339 | 381 | 429 | 480 | 531 | 576 | 631 | 16 | 14 | 11 | 14 | 12 | 14 | 11 | 9 | 12 | 16 | 13 | 12 | 12 | 13 | 13 | 12 | 16 | 9 | 12 | 10 | 8 | 9 | 12 | 13 | 13 | 9 | 11 | 13 | 12 | 14 | 8 | 8 | 12 | 10 | 16 | 10 | 12 | 14 | 11 | 14 | 15 | 11 | 15 | 10 | 8 | 11 | 16 | 10 | 16 | 12 | 12 | 15
356 | 67 | 40 | 91 | 132 | 180 | 229 | 267 | 309 | 367 | 417 | 461 | 515 | 571 | 618 | 12 | 9 | 9 | 10 | 15 | 12 | 8 | 16 | 12 | 8 | 10 | 11 | 16 | 11 | 12 | 9 | 10 | 15 | 12 | 12 | 9 | 8 | 13 | 8 | 12 | 10 | 12 | 8 | 12 | 15 | 16 | 15 | 10 | 13 | 11 | 16 | 9 | 14 | 12 | 9 | 13 | 12 | 14 | 15 | 16 | 16 | 15 | 9 | 8 | 15 | 10 | 14
357 | 76 | 47 | 95 | 135 | 186 | 237 | 277 | 333 | 372 | 419 | 468 | 524 | 575 | 625 | 15 | 9 | 10 | 13 | 14 | 15 | 8 | 11 | 15 | 8 | 8 | 9 | 8 | 15 | 12 | 16 | 13 | 14 | 11 | 13 | 11 | 9 | 9 | 11 | 16 | 14 | 10 | 16 | 9 | 12 | 9 | 9 | 8 | 16 | 14 | 9 | 13 | 12 | 16 | 8 | 14 | 15 | 11 | 16 | 12 | 13 | 11 | 15 | 16 | 10 | 13 | 11
358 | 76 | 53 | 105 | 147 | 191 | 236 | 276 | 326 | 384 | 424 | 472 | 526 | 575 | 618 | 14 | 9 | 15 | 15 | 15 | 8 | 14 | 15 | 11 | 10 | 13 | 8 | 10 | 9 | 13 | 12 | 15 | 8 | 9 | 13 | 8 | 11 | 8 | 13 | 10 | 13 | 11 | 16 | 16 | 16 | 16 | 10 | 10 | 11 | 10 | 9 | 13 | 11 | 11 | 13 | 13 | 11 | 15 | 15 | 8 | 13 | 12 | 16 | 12 | 10 | 13 | 8
359 | 79 | 59 | 110 | 146 | 194 | 240 | 288 | 335 | 377 | 416 | 458 | 496 | 544 | 591 | 16 | 13 | 16 | 14 | 8 | 12 | 15 | 16 | 12 | 8 | 8 | 8 | 13 | 8 | 12 | 15 | 10 | 15 | 8 | 13 | 10 | 11 | 15 | 12 | 11 | 11 | 9 | 16 | 11 | 14 | 9 | 8 | 10 | 10 | 8 | 11 | 13 | 8 | 11 | 10 | 10 | 9 | 11 | 8 | 13 | 8 | 14 | 13 | 16 | 11 | 12 | 8
360 | 65 | 43 | 92 | 144 | 192 | 234 | 287 | 329 | 371 | 427 | 468 | 515 | 552 | 602 | 14 | 9 | 8 | 12 | 11 | 11 | 11 | 16 | 14 | 8 | 14 | 16 | 9 | 15 | 15 | 9 | 10 | 9 | 11 | 12 | 16 | 11 | 11 | 15 | 9 | 8 | 13 | 12 | 10 | 11 | 8 | 13 | 16 | 16 | 12 | 12 | 9 | 12 | 12 | 8 | 10 | 11 | 13 | 13 | 8 | 9 | 9 | 11 | 11 | 12 | 13 | 14
361 | 72 | 53 | 94 | 135 | 182 | 234 | 291 | 350 | 398 | 439 | 489 | 537 | 585 | 635 | 14 | 13 | 16 | 10 | 11 | 8 | 8 | 14 | 15 | 8 | 8 | 10 | 11 | 9 | 13 | 14 | 15 | 14 | 8 | 15 | 16 | 16 | 15 | 10 | 15 | 16 | 14 | 14 | 12 | 12 | 10 | 14 | 11 | 8 | 11 | 11 | 13 | 11 | 12 | 14 | 10 | 14 | 10 | 14 | 12 | 12 | 14 | 10 | 16 | 10 | 16 | 8
362 | 64 | 41 | 89 | 132 | 179 | 229 | 270 | 313 | 367 | 420 | 474 | 528 | 586 | 632 | 8 | 13 | 8 | 12 | 12 | 11 | 15 | 10 | 10 | 13 | 8 | 12 | 8 | 13 | 13 | 13 | 13 | 14 | 8 | 15 | 13 | 9 | 9 | 10 | 9 | 10 | 15 | 9 | 15 | 16 | 8 | 15 | 12 | 13 | 15 | 13 | 13 | 15 | 16 | 10 | 16 | 10 | 15 | 13 | 10 | 16 | 16 | 16 | 11 | 9 | 14 | 12
363 | 72 | 52 | 98 | 148 | 197 | 241 | 288 | 327 | 372 | 420 | 461 | 506 | 555 | 607 | 13 | 14 | 14 | 11 | 10 | 10 | 12 | 14 | 12 | 15 | 12 | 11 | 14 | 12 | 8 | 15 | 11 | 16 | 8 | 9 | 14 | 11 | 9 | 13 | 9 | 12 | 8 | 10 | 9 | 15 | 10 | 11 | 8 | 11 | 13 | 16 | 10 | 8 | 15 | 8 | 12 | 10 | 15 | 8 | 9 | 16 | 11 | 13 | 10 | 16 | 12 | 14
364 | 66 | 43 | 85 | 135 | 173 | 216 | 263 | 316 | 367 | 412 | 468 | 509 | 564 | 615 | 15 | 9 | 10 | 9 | 8 | 15 | 8 | 11 | 15 | 15 | 9 | 11 | 8 | 8 | 13 | 9 | 15 | 8 | 10 | 10 | 11 | 10 | 15 | 11 | 12 | 12 | 13 | 16 | 15 | 12 | 13 | 11 | 10 | 11 | 16 | 8 | 15 | 14 | 15 | 12 | 10 | 9 | 9 | 13 | 15 | 11 | 14 | 15 | 16 | 12 | 9 | 14
365 | 71 | 52 | 94 | 142 | 197 | 245 | 290 | 329 | 384 | 437 | 488 | 533 | 576 | 623 | 13 | 9 | 14 | 16 | 8 | 11 | 10 | 13 | 14 | 8 | 15 | 11 | 14 | 9 | 16 | 16 | 11 | 9 | 15 | 13 | 8 | 9 | 15 | 13 | 9 | 10 | 10 | 10 | 15 | 14 | 15 | 11 | 13 | 14 | 12 | 14 | 10 | 9 | 16 | 16 | 16 | 10 | 11 | 8 | 13 | 9 | 8 | 13 | 8 | 11 | 12 | 16
366 | 80 | 54 | 102 | 149 | 198 | 250 | 300 | 346 | 390 | 430 | 474 | 517 | 568 | 611 | 16 | 11 | 11 | 16 | 16 | 10 | 12 | 10 | 16 | 10 | 12 | 9 | 11 | 12 | 11 | 15 | 16 | 10 | 16 | 10 | 13 | 13 | 9 | 15 | 11 | 11 | 12 | 12 | 9 | 13 | 8 | 14 | 12 | 10 | 10 | 8 | 12 | 16 | 8 | 8 | 11 | 10 | 9 | 13 | 16 | 15 | 11 | 9 | 12 | 10 | 8 | 13
367 | 79 | 56 | 102 | 150 | 206 | 247 | 291 | 338 | 382 | 420 | 464 | 503 | 560 | 608 | 15 | 16 | 15 | 10 | 11 | 12 | 11 | 12 | 8 | 12 | 14 | 14 | 13 | 14 | 15 | 14 | 11 | 9 | 9 | 12 | 11 | 11 | 11 | 11 | 14 | 10 | 12 | 11 | 9 | 16 | 8 | 11 | 9 | 8 | 13 | 8 | 11 | 11 | 14 | 8 | 12 | 8 | 9 | 10 | 13 | 14 | 15 | 15 | 10 | 13 | 10 | 15
368 | 86 | 59 | 112 | 159 | 214 | 258 | 300 | 341 | 383 | 422 | 479 | 535 | 583 | 627 | 13 | 16 | 15 | 15 | 11 | 16 | 16 | 10 | 8 | 14 | 9 | 16 | 13 | 14 | 12 | 16 | 8 | 14 | 12 | 10 | 9 | 10 | 8 | 15 | 11 | 14 | 8 | 8 | 10 | 10 | 9 | 13 | 10 | 11 | 8 | 10 | 15 | 13 | 15 | 14 | 16 | 16 | 15 | 9 | 12 | 13 | 11 | 12 | 13 | 10 | 11 | 10
369 | 70 | 51 | 101 | 147 | 188 | 226 | 280 | 317 | 352 | 406 | 462 | 517 | 560 | 605 | 9 | 15 | 12 | 15 | 10 | 9 | 16 | 15 | 16 | 9 | 10 | 11 | 8 | 8 | 12 | 13 | 10 | 8 | 11 | 9 | 8 | 16 | 16 | 14 | 8 | 8 | 11 | 10 | 8 | 10 | 8 | 9 | 10 | 13 | 16 | 15 | 13 | 13 | 14 | 16 | 16 | 13 | 16 | 10 | 10 | 13 | 8 | 12 | 15 | 8 | 14 | 8
370 | 70 | 48 | 101 | 144 | 196 | 246 | 306 | 354 | 406 | 459 | 513 | 563 | 611 | 662 | 13 | 15 | 9 | 11 | 12 | 10 | 15 | 16 | 13 | 9 | 8 | 13 | 16 | 10 | 14 | 12 | 11 | 9 | 14 | 16 | 15 | 16 | 15 | 14 | 12 | 11 | 14 | 11 | 13 | 14 | 13 | 12 | 13 | 16 | 13 | 11 | 14 | 14 | 15 | 11 | 14 | 15 | 10 | 11 | 14 | 12 | 10 | 12 | 10 | 15 | 10 | 16
371 | 75 | 52 | 96 | 145 | 187 | 233 | 285 | 334 | 379 | 426 | 474 | 529 | 578 | 624 | 16 | 12 | 16 | 8 | 9 | 14 | 10 | 11 | 10 | 14 | 10 | 15 | 12 | 9 | 11 | 10 | 13 | 11 | 9 | 13 | 10 | 13 | 13 | 16 | 11 | 13 | 12 | 13 | 8 | 10 | 15 | 12 | 12 | 10 | 15 | 10 | 9 | 16 | 10 | 13 | 15 | 12 | 12 | 16 | 11 | 10 | 12 | 16 | 15 | 15 | 8 | 8
372 | 78 | 47 | 104 | 157 | 207 | 255 | 306 | 355 | 406 | 454 | 505 | 557 | 608 | 647 | 8 | 12 | 12 | 15 | 16 | 15 | 11 | 15 | 11 | 14 | 15 | 13 | 12 | 16 | 13 | 9 | 10 | 14 | 10 | 14 | 10 | 12 | 13 | 16 | 11 | 12 | 14 | 12 | 14 | 10 | 11 | 16 | 8 | 13 | 11 | 16 | 10 | 15 | 15 | 11 | 13 | 15 | 8 | 16 | 16 | 16 | 8 | 11 | 8 | 9 | 14 | 8
373 | 68 | 41 | 91 | 133 | 184 | 240 | 292 | 343 | 387 | 435 | 481 | 531 | 578 | 622 | 8 | 13 | 8 | 12 | 16 | 11 | 11 | 12 | 8 | 15 | 8 | 11 | 14 | 14 | 14 | 9 | 13 | 15 | 14 | 14 | 10 | 14 | 15 | 13 | 12 | 12 | 11 | 16 | 10 | 8 | 11 | 15 | 8 | 16 | 11 | 13 | 9 | 13 | 11 | 13 | 14 | 11 | 12 | 13 | 15 | 11 | 9 | 12 | 10 | 15 | 9 | 10
374 | 65 | 44 | 91 | 146 | 195 | 237 | 282 | 320 | 367 | 414 | 457 | 508 | 550 | 606 | 12 | 13 | 11 | 8 | 8 | 13 | 11 | 15 | 16 | 11 | 16 | 12 | 10 | 14 | 15 | 10 | 13 | 10 | 9 | 10 | 11 | 13 | 8 | 13 | 8 | 11 | 11 | 8 | 14 | 10 | 9 | 14 | 12 | 8 | 15 | 12 | 16 | 9 | 8 | 10 | 15 | 10 | 11 | 15 | 10 | 10 | 11 | 11 | 16 | 13 | 15 | 12
375 | 87 | 58 | 104 | 157 | 201 | 242 | 297 | 346 | 403 | 444 | 497 | 543 | 596 | 651 | 16 | 15 | 11 | 16 | 16 | 13 | 9 | 8 | 14 | 14 | 13 | 12 | 14 | 12 | 9 | 9 | 9 | 11 | 9 | 12 | 16 | 11 | 15 | 13 | 12 | 14 | 9 | 14 | 16 | 14 | 13 | 14 | 8 | 14 | 11 | 8 | 16 | 11 | 13 | 13 | 8 | 14 | 12 | 12 | 16 | 11 | 13 | 13 | 15 | 12 | 16 | 12
376 | 72 | 47 | 102 | 148 | 189 | 230 | 275 | 326 | 378 | 438 | 489 | 539 | 583 | 629 | 8 | 12 | 12 | 15 | 14 | 11 | 14 | 16 | 15 | 14 | 9 | 8 | 15 | 10 | 8 | 8 | 8 | 11 | 9 | 13 | 11 | 11 | 12 | 11 | 16 | 9 | 15 | 11 | 14 | 13 | 9 | 16 | 16 | 14 | 15 | 15 | 11 | 11 | 15 | 14 | 13 | 11 | 12 | 14 | 8 | 16 | 9 | 11 | 10 | 11 | 9 | 16
377 | 82 | 53 | 107 | 162 | 207 | 252 | 300 | 344 | 404 | 452 | 499 | 545 | 589 | 636 | 13 | 15 | 16 | 9 | 16 | 13 | 14 | 11 | 15 | 15 | 9 | 16 | 12 | 11 | 8 | 14 | 12 | 12 | 8 | 13 | 15 | 8 | 11 | 14 | 8 | 15 | 9 | 12 | 16 | 16 | 14 | 14 | 10 | 14 | 15 | 9 | 9 | 14 | 10 | 14 | 11 | 12 | 13 | 10 | 9 | 12 | 13 | 10 | 13 | 16 | 8 | 10
378 | 71 | 43 | 97 | 146 | 196 | 244 | 287 | 336 | 384 | 428 | 469 | 516 | 566 | 620 | 13 | 8 | 13 | 9 | 13 | 15 | 16 | 10 | 13 | 11 | 9 | 16 | 14 | 16 | 8 | 12 | 14 | 8 | 12 | 14 | 10 | 8 | 11 | 14 | 9 | 16 | 14 | 10 | 14 | 11 | 9 | 14 | 10 | 9 | 9 | 16 | 10 | 8 | 11 | 12 | 15 | 10 | 14 | 8 | 10 | 10 | 16 | 14 | 15 | 15 | 16 | 8
379 | 68 | 42 | 99 | 140 | 198 | 242 | 285 | 337 | 376 | 425 | 476 | 524 | 574 | 613 | 8 | 11 | 8 | 15 | 11 | 15 | 15 | 16 | 8 | 13 | 12 | 8 | 16 | 10 | 16 | 16 | 13 | 10 | 12 | 9 | 14 | 9 | 11 | 9 | 16 | 8 | 14 | 14 | 9 | 10 | 8 | 12 | 16 | 16 | 8 | 9 | 15 | 11 | 15 | 10 | 11 | 15 | 8 | 14 | 10 | 11 | 16 | 13 | 8 | 13 | 8 | 10
380 | 64 | 41 | 89 | 139 | 196 | 245 | 301 | 339 | 383 | 434 | 483 | 526 | 578 | 626 | 9 | 8 | 8 | 16 | 12 | 11 | 14 | 11 | 16 | 8 | 10 | 16 | 16 | 14 | 15 | 12 | 11 | 15 | 8 | 15 | 11 | 16 | 13 | 16 | 9 | 12 | 8 | 9 | 10 | 9 | 12 | 13 | 13 | 16 | 8 | 14 | 13 | 16 | 8 | 12 | 14 | 9 | 12 | 8 | 13 | 16 | 14 | 9 | 10 | 13 | 12 | 13
381 | 85 | 57 | 108 | 152 | 192 | 235 | 278 | 325 | 377 | 424 | 471 | 519 | 576 | 616 | 16 | 14 | 14 | 13 | 14 | 14 | 10 | 13 | 13 | 10 | 11 | 10 | 9 | 9 | 12 | 10 | 9 | 11 | 13 | 10 | 14 | 11 | 10 | 8 | 8 | 15 | 13 | 11 | 13 | 15 | 15 | 9 | 16 | 9 | 14 | 8 | 15 | 10 | 10 | 12 | 9 | 14 | 15 | 10 | 14 | 15 | 15 | 13 | 8 | 9 | 13 | 10
382 | 71 | 52 | 92 | 132 | 180 | 231 | 280 | 325 | 376 | 419 | 468 | 517 | 561 | 605 | 8 | 14 | 15 | 15 | 8 | 11 | 12 | 9 | 11 | 9 | 10 | 10 | 8 | 14 | 15 | 11 | 13 | 11 | 14 | 13 | 10 | 15 | 13 | 11 | 8 | 13 | 8 | 16 | 12 | 15 | 10 | 14 | 10 | 10 | 8 | 15 | 10 | 13 | 14 | 12 | 11 | 10 | 12 | 16 | 12 | 10 | 8 | 14 | 14 | 12 | 8 | 10
383 | 75 | 47 | 101 | 147 | 204 | 256 | 306 | 358 | 406 | 455 | 499 | 555 | 605 | 658 | 10 | 10 | 14 | 13 | 15 | 13 | 16 | 10 | 15 | 9 | 11 | 11 | 16 | 13 | 14 | 14 | 13 | 10 | 15 | 14 | 13 | 10 | 15 | 12 | 12 | 14 | 12 | 14 | 15 | 13 | 12 | 8 | 15 | 12 | 14 | 8 | 12 | 13 | 11 | 8 | 16 | 16 | 14 | 10 | 16 | 12 | 9 | 13 | 12 | 14 | 15 | 12
384 | 64 | 45 | 85 | 137 | 188 | 246 | 294 | 336 | 385 | 433 | 485 | 533 | 579 | 621 | 12 | 8 | 14 | 11 | 8 | 11 | 8 | 13 | 12 | 9 | 16 | 15 | 14 | 12 | 9 | 16 | 14 | 15 | 15 | 14 | 10 | 16 | 12 | 10 | 9 | 10 | 8 | 15 | 12 | 9 | 14 | 14 | 14 | 8 | 15 | 11 | 11 | 15 | 14 | 12 | 13 | 8 | 16 | 11 | 10 | 8 | 14 | 14 | 8 | 11 | 9 | 14
385 | 70 | 40 | 91 | 146 | 197 | 238 | 284 | 335 | 388 | 447 | 489 | 538 | 577 | 632 | 8 | 14 | 8 | 10 | 16 | 14 | 9 | 12 | 13 | 12 | 15 | 15 | 14 | 9 | 13 | 15 | 8 | 12 | 11 | 10 | 11 | 11 | 13 | 11 | 13 | 13 | 12 | 13 | 13 | 14 | 11 | 15 | 14 | 14 | 15 | 16 | 9 | 13 | 8 | 12 | 11 | 9 | 13 | 16 | 11 | 10 | 9 | 9 | 8 | 15 | 16 | 16
386 | 82 | 53 | 110 | 168 | 225 | 276 | 325 | 379 | 434 | 486 | 535 | 582 | 624 | 678 | 10 | 14 | 16 | 13 | 13 | 16 | 13 | 15 | 14 | 16 | 13 | 15 | 14 | 16 | 13 | 14 | 8 | 16 | 11 | 16 | 12 | 15 | 12 | 10 | 13 | 15 | 10 | 16 | 13 | 16 | 12 | 14 | 13 | 10 | 16 | 13 | 10 | 9 | 16 | 14 | 11 | 15 | 10 | 11 | 14 | 9 | 11 | 8 | 16 | 12 | 10 | 16
387 | 85 | 56 | 109 | 158 | 208 | 257 | 310 | 357 | 407 | 460 | 509 | 554 | 606 | 660 | 12 | 12 | 16 | 16 | 15 | 14 | 10 | 14 | 11 | 10 | 15 | 13 | 13 | 10 | 11 | 16 | 12 | 14 | 13 | 10 | 15 | 13 | 15 | 10 | 11 | 9 | 12 | 15 | 14 | 15 | 13 | 8 | 10 | 14 | 16 | 13 | 13 | 14 | 12 | 10 | 10 | 12 | 15 | 8 | 16 | 12 | 16 | 8 | 15 | 14 | 12 | 13
388 | 72 | 46 | 99 | 145 | 189 | 237 | 281 | 328 | 385 | 428 | 471 | 516 | 563 | 613 | 13 | 11 | 10 | 12 | 10 | 16 | 13 | 14 | 16 | 12 | 10 | 8 | 11 | 10 | 14 | 9 | 15 | 10 | 9 | 14 | 11 | 12 | 13 | 8 | 9 | 13 | 10 | 15 | 15 | 14 | 15 | 13 | 12 | 15 | 8 | 8 | 12 | 9 | 14 | 8 | 9 | 11 | 14 | 11 | 10 | 12 | 15 | 10 | 14 | 9 | 12 | 15
389 | 75 | 51 | 96 | 155 | 198 | 248 | 295 | 336 | 391 | 447 | 493 | 541 | 588 | 640 | 15 | 12 | 14 | 10 | 10 | 14 | 12 | 9 | 13 | 15 | 15 | 16 | 11 | 14 | 10 | 8 | 16 | 11 | 10 | 13 | 13 | 14 | 10 | 10 | 14 | 9 | 8 | 10 | 15 | 16 | 13 | 11 | 13 | 16 | 16 | 11 | 14 | 8 | 15 | 9 | 9 | 14 | 16 | 9 | 13 | 9 | 12 | 13 | 10 | 15 | 16 | 11
390 | 84 | 59 | 105 | 156 | 207 | 262 | 310 | 361 | 410 | 452 | 497 | 549 | 587 | 634 | 15 | 14 | 16 | 14 | 14 | 11 | 12 | 9 | 16 | 15 | 8 | 12 | 11 | 15 | 12 | 13 | 14 | 16 | 16 | 9 | 11 | 9 | 14 | 14 | 11 | 13 | 14 | 13 | 10 | 16 | 11 | 12 | 16 | 9 | 8 | 9 | 11 | 16 | 8 | 10 | 14 | 15 | 13 | 10 | 8 | 8 | 11 | 11 | 12 | 8 | 12 | 15
391 | 69 | 45 | 91 | 131 | 176 | 225 | 269 | 314 | 366 | 419 | 459 | 505 | 550 | 599 | 8 | 14 | 13 | 10 | 8 | 16 | 13 | 9 | 8 | 11 | 13 | 8 | 13 | 9 | 8 | 15 | 9 | 10 | 16 | 14 | 8 | 16 | 11 | 9 | 16 | 8 | 13 | 8 | 14 | 13 | 15 | 10 | 15 | 10 | 14 | 14 | 8 | 11 | 12 | 9 | 12 | 14 | 12 | 8 | 11 | 8 | 14 | 12 | 13 | 9 | 14 | 13
392 | 73 | 45 | 104 | 145 | 193 | 242 | 296 | 348 | 400 | 446 | 499 | 553 | 603 | 657 | 8 | 14 | 11 | 12 | 15 | 13 | 16 | 15 | 9 | 16 | 8 | 8 | 11 | 10 | 12 | 15 | 10 | 16 | 10 | 13 | 16 | 12 | 14 | 12 | 14 | 13 | 13 | 12 | 10 | 16 | 10 | 16 | 12 | 13 | 8 | 13 | 16 | 13 | 13 | 11 | 14 | 10 | 16 | 14 | 12 | 16 | 14 | 8 | 13 | 16 | 15 | 10
393 | 71 | 46 | 96 | 143 | 187 | 223 | 269 | 316 | 359 | 405 | 443 | 488 | 529 | 576 | 10 | 15 | 13 | 8 | 11 | 14 | 11 | 14 | 13 | 9 | 14 | 11 | 12 | 11 | 9 | 12 | 10 | 8 | 9 | 9 | 14 | 10 | 8 | 14 | 11 | 13 | 9 | 14 | 14 | 8 | 11 | 10 | 8 | 9 | 16 | 13 | 9 | 12 | 9 | 8 | 9 | 12 | 10 | 14 | 9 | 13 | 8 | 11 | 9 | 16 | 14 | 8
394 | 85 | 57 | 102 | 151 | 199 | 244 | 288 | 331 | 380 | 429 | 474 | 522 | 564 | 607 | 16 | 16 | 9 | 16 | 15 | 13 | 9 | 8 | 13 | 10 | 10 | 16 | 12 | 15 | 8 | 13 | 10 | 11 | 8 | 16 | 12 | 11 | 9 | 12 | 9 | 9 | 13 | 12 | 15 | 16 | 8 | 10 | 15 | 8 | 13 | 13 | 15 | 8 | 8 | 14 | 8 | 15 | 14 | 11 | 10 | 14 | 9 | 9 | 9 | 13 | 8 | 13
395 | 70 | 46 | 99 | 141 | 189 | 242 | 285 | 333 | 381 | 431 | 484 | 527 | 580 | 621 | 10 | 12 | 14 | 10 | 15 | 9 | 14 | 15 | 11 | 12 | 9 | 10 | 14 | 10 | 11 | 13 | 15 | 16 | 14 | 8 | 12 | 9 | 9 | 13 | 15 | 12 | 12 | 9 | 10 | 12 | 14 | 12 | 8 | 13 | 14 | 15 | 14 | 10 | 15 | 14 | 8 | 8 | 14 | 13 | 10 | 15 | 14 | 14 | 8 | 8 | 9 | 16
396 | 74 | 48 | 100 | 151 | 196 | 243 | 296 | 354 | 392 | 438 | 489 | 542 | 588 | 632 | 12 | 15 | 9 | 12 | 11 | 15 | 12 | 14 | 15 | 9 | 13 | 14 | 13 | 8 | 16 | 8 | 10 | 13 | 15 | 9 | 16 | 10 | 11 | 16 | 15 | 14 | 13 | 16 | 8 | 8 | 8 | 14 | 13 | 8 | 16 | 9 | 12 | 11 | 16 | 12 | 12 | 12 | 14 | 15 | 11 | 13 | 9 | 13 | 12 | 8 | 12 | 12
397 | 71 | 42 | 94 | 141 | 189 | 243 | 295 | 345 | 391 | 437 | 484 | 533 | 591 | 640 | 13 | 9 | 10 | 10 | 13 | 16 | 12 | 11 | 10 | 15 | 13 | 9 | 8 | 15 | 14 | 11 | 15 | 16 | 8 | 15 | 12 | 15 | 9 | 16 | 11 | 10 | 13 | 16 | 12 | 12 | 13 | 9 | 11 | 13 | 8 | 14 | 9 | 14 | 10 | 14 | 9 | 11 | 15 | 14 | 14 | 16 | 14 | 14 | 12 | 14 | 13 | 10
398 | 72 | 47 | 97 | 138 | 186 | 237 | 289 | 347 | 390 | 440 | 489 | 534 | 581 | 625 | 11 | 14 | 8 | 14 | 16 | 9 | 13 | 12 | 8 | 8 | 16 | 9 | 8 | 14 | 12 | 14 | 11 | 16 | 14 | 10 | 14 | 9 | 16 | 13 | 12 | 15 | 15 | 16 | 8 | 13 | 11 | 11 | 8 | 13 | 15 | 14 | 11 | 10 | 16 | 12 | 11 | 11 | 10 | 13 | 14 | 13 | 12 | 8 | 8 | 15 | 10 | 11
399 | 79 | 50 | 107 | 162 | 208 | 263 | 320 | 364 | 416 | 465 | 521 | 575 | 628 | 664 | 12 | 12 | 12 | 14 | 16 | 13 | 12 | 16 | 15 | 12 | 13 | 15 | 15 | 11 | 12 | 8 | 15 | 14 | 13 | 13 | 14 | 16 | 16 | 11 | 12 | 12 | 12 | 8 | 11 | 16 | 12 | 13 | 9 | 14 | 10 | 16 | 15 | 14 | 13 | 14 | 14 | 15 | 10 | 15 | 10 | 15 | 12 | 16 | 12 | 8 | 8 | 8
400 | 78 | 53 | 95 | 134 | 186 | 236 | 286 | 333 | 373 | 424 | 468 | 523 | 577 | 619 | 14 | 11 | 15 | 13 | 16 | 9 | 8 | 9 | 8 | 10 | 10 | 11 | 10 | 14 | 16 | 12 | 14 | 8 | 14 | 14 | 12 | 11 | 13 | 14 | 16 | 10 | 12 | 9 | 9 | 15 | 8 | 8 | 14 | 16 | 10 | 11 | 8 | 13 | 11 | 12 | 16 | 9 | 16 | 14 | 13 | 12 | 14 | 15 | 8 | 10 | 14 | 10
401 | 71 | 48 | 94 | 143 | 188 | 243 | 294 | 339 | 386 | 429 | 477 | 531 | 573 | 624 | 13 | 10 | 13 | 12 | 14 | 9 | 9 | 14 | 14 | 11 | 13 | 11 | 9 | 15 | 11 | 10 | 14 | 10 | 15 | 16 | 15 | 13 | 11 | 12 | 9 | 9 | 13 | 14 | 16 | 11 | 9 | 11 | 9 | 12 | 14 | 8 | 11 | 10 | 11 | 16 | 15 | 12 | 14 | 13 | 13 | 9 | 10 | 10 | 10 | 16 | 12 | 13
402 | 56 | 38 | 85 | 129 | 187 | 240 | 298 | 339 | 380 | 428 | 473 | 524 | 575 | 623 | 12 | 8 | 10 | 8 | 8 | 10 | 15 | 14 | 13 | 11 | 9 | 11 | 12 | 14 | 16 | 16 | 12 | 12 | 13 | 16 | 15 | 16 | 15 | 12 | 13 | 11 | 8 | 9 | 11 | 8 | 10 | 12 | 12 | 12 | 11 | 13 | 8 | 15 | 8 | 14 | 14 | 16 | 13 | 8 | 13 | 15 | 9 | 14 | 8 | 16 | 16 | 8
403 | 61 | 41 | 80 | 124 | 180 | 227 | 275 | 321 | 365 | 413 | 455 | 504 | 547 | 600 | 9 | 13 | 8 | 11 | 10 | 10 | 10 | 9 | 12 | 10 | 12 | 10 | 16 | 16 | 10 | 14 | 12 | 8 | 14 | 13 | 13 | 16 | 10 | 9 | 15 | 13 | 8 | 10 | 15 | 8 | 11 | 10 | 11 | 13 | 8 | 16 | 8 | 14 | 8 | 12 | 10 | 9 | 16 | 14 | 9 | 11 | 10 | 13 | 10 | 16 | 15 | 12
404 | 84 | 57 | 107 | 154 | 212 | 263 | 320 | 373 | 418 | 459 | 500 | 542 | 591 | 636 | 15 | 12 | 14 | 16 | 13 | 14 | 12 | 11 | 8 | 16 | 15 | 8 | 15 | 14 | 15 | 14 | 10 | 14 | 12 | 15 | 13 | 16 | 12 | 16 | 11 | 14 | 12 | 16 | 10 | 10 | 11 | 14 | 8 | 10 | 14 | 9 | 14 | 11 | 8 | 8 | 15 | 8 | 8 | 11 | 14 | 11 | 12 | 12 | 9 | 8 | 16 | 12
405 | 83 | 59 | 106 | 157 | 205 | 259 | 309 | 353 | 403 | 442 | 486 | 534 | 583 | 629 | 15 | 15 | 15 | 14 | 11 | 13 | 9 | 14 | 15 | 10 | 15 | 11 | 13 | 12 | 11 | 12 | 14 | 16 | 16 | 8 | 15 | 10 | 9 | 16 | 12 | 12 | 9 | 11 | 8 | 15 | 15 | 12 | 9 | 9 | 10 | 11 | 11 | 12 | 12 | 9 | 13 | 12 | 8 | 15 | 9 | 16 | 8 | 16 | 10 | 12 | 12 | 12
406 | 76 | 48 | 100 | 145 | 196 | 246 | 296 | 340 | 385 | 433 | 486 | 540 | 581 | 630 | 12 | 9 | 11 | 16 | 15 | 13 | 8 | 16 | 11 | 8 | 12 | 14 | 15 | 9 | 12 | 15 | 15 | 12 | 12 | 11 | 10 | 10 | 14 | 16 | 9 | 13 | 14 | 8 | 11 | 11 | 15 | 8 | 16 | 13 | 9 | 10 | 15 | 11 | 15 | 12 | 16 | 13 | 16 | 9 | 10 | 13 | 10 | 8 | 8 | 15 | 16 | 10
407 | 71 | 46 | 93 | 143 | 190 | 230 | 278 | 334 | 383 | 430 | 472 | 520 | 574 | 620 | 14 | 11 | 9 | 12 | 14 | 11 | 10 | 12 | 13 | 14 | 15 | 8 | 15 | 9 | 9 | 14 | 9 | 10 | 12 | 9 | 9 | 13 | 10 | 16 | 11 | 14 | 16 | 15 | 8 | 12 | 13 | 16 | 11 | 12 | 13 | 11 | 8 | 11 | 15 | 8 | 12 | 10 | 16 | 10 | 16 | 11 | 16 | 11 | 16 | 12 | 10 | 8
408 | 73 | 55 | 96 | 145 | 185 | 238 | 287 | 339 | 385 | 422 | 473 | 519 | 574 | 624 | 13 | 16 | 11 | 15 | 8 | 10 | 15 | 8 | 16 | 9 | 11 | 13 | 8 | 12 | 8 | 12 | 14 | 15 | 11 | 13 | 15 | 11 | 9 | 14 | 15 | 15 | 10 | 12 | 9 | 14 | 9 | 14 | 8 | 12 | 8 | 9 | 10 | 16 | 11 | 14 | 9 | 12 | 10 | 15 | 10 | 16 | 13 | 16 | 13 | 14 | 9 | 14
409 | 70 | 46 | 86 | 130 | 186 | 226 | 274 | 316 | 366 | 411 | 463 | 516 | 563 | 622 | 16 | 8 | 14 | 8 | 16 | 8 | 8 | 8 | 8 | 11 | 9 | 16 | 15 | 12 | 15 | 14 | 9 | 11 | 12 | 8 | 14 | 15 | 10 | 9 | 11 | 10 | 12 | 9 | 12 | 14 | 9 | 15 | 12 | 8 | 15 | 10 | 11 | 12 | 13 | 16 | 15 | 13 | 9 | 16 | 13 | 11 | 8 | 15 | 15 | 16 | 15 | 13
410 | 65 | 42 | 93 | 147 | 194 | 241 | 280 | 335 | 390 | 428 | 475 | 529 | 564 | 618 | 9 | 11 | 14 | 8 | 8 | 15 | 16 | 12 | 16 | 13 | 12 | 13 | 14 | 12 | 8 | 13 | 14 | 9 | 8 | 16 | 12 | 11 | 8 | 8 | 13 | 15 | 12 | 15 | 16 | 16 | 11 | 12 | 8 | 8 | 11 | 11 | 11 | 13 | 15 | 8 | 16 | 16 | 11 | 11 | 8 | 9 | 10 | 8 | 10 | 13 | 16 | 15
411 | 70 | 45 | 94 | 140 | 187 | 230 | 277 | 318 | 371 | 411 | 458 | 497 | 548 | 588 | 8 | 13 | 8 | 16 | 11 | 14 | 11 | 13 | 12 | 16 | 8 | 10 | 8 | 10 | 15 | 14 | 13 | 9 | 13 | 8 | 8 | 16 | 10 | 13 | 14 | 10 | 9 | 8 | 13 | 11 | 13 | 16 | 10 | 11 | 8 | 11 | 16 | 10 | 12 | 9 | 13 | 9 | 9 | 8 | 9 | 10 | 16 | 16 | 8 | 12 | 9 | 11
412 | 66 | 43 | 91 | 132 | 188 | 228 | 274 | 337 | 390 | 438 | 487 | 546 | 593 | 638 | 9 | 13 | 10 | 11 | 9 | 14 | 16 | 9 | 10 | 8 | 8 | 15 | 16 | 13 | 11 | 16 | 9 | 13 | 8 | 10 | 13 | 10 | 11 | 12 | 15 | 16 | 16 | 16 | 15 | 11 | 12 | 15 | 16 | 10 | 11 | 11 | 13 | 8 | 14 | 14 | 16 | 12 | 15 | 16 | 10 | 15 | 8 | 14 | 12 | 10 | 12 | 11
413 | 67 | 47 | 90 | 136 | 179 | 227 | 271 | 319 | 368 | 412 | 462 | 502 | 554 | 601 | 9 | 14 | 11 | 13 | 11 | 9 | 10 | 13 | 13 | 13 | 11 | 9 | 11 | 10 | 9 | 13 | 8 | 16 | 12 | 12 | 10 | 9 | 13 | 12 | 13 | 12 | 9 | 14 | 12 | 14 | 10 | 13 | 9 | 14 | 12 | 9 | 15 | 16 | 11 | 8 | 8 | 10 | 13 | 9 | 13 | 10 | 16 | 13 | 11 | 14 | 10 | 12
414 | 73 | 47 | 97 | 143 | 198 | 243 | 288 | 331 | 381 | 440 | 497 | 547 | 590 | 638 | 11 | 15 | 10 | 11 | 11 | 15 | 13 | 11 | 11 | 12 | 15 | 8 | 16 | 16 | 11 | 12 | 11 | 12 | 10 | 12 | 10 | 9 | 15 | 11 | 12 | 8 | 12 | 11 | 16 | 13 | 11 | 10 | 15 | 14 | 16 | 14 | 15 | 16 | 10 | 16 | 13 | 14 | 13 | 10 | 14 | 8 | 9 | 12 | 12 | 8 | 16 | 12
415 | 72 | 51 | 93 | 148 | 196 | 243 | 283 | 324 | 378 | 433 | 477 | 534 | 580 | 629 | 9 | 11 | 16 | 15 | 12 | 9 | 9 | 12 | 12 | 13 | 15 | 15 | 12 | 14 | 14 | 8 | 13 | 14 | 8 | 12 | 9 | 11 | 8 | 12 | 13 | 8 | 11 | 9 | 16 | 13 | 12 | 13 | 16 | 11 | 16 | 12 | 10 | 9 | 14 | 11 | 13 | 14 | 15 | 15 | 10 | 8 | 14 | 14 | 14 | 10 | 10 | 15
416 | 68 | 44 | 92 | 134 | 186 | 234 | 286 | 332 | 377 | 421 | 470 | 511 | 558 | 608 | 9 | 16 | 11 | 8 | 16 | 8 | 13 | 11 | 10 | 15 | 9 | 8 | 13 | 16 | 12 | 11 | 11 | 8 | 14 | 15 | 16 | 14 | 12 | 10 | 12 | 10 | 13 | 11 | 8 | 13 | 9 | 15 | 9 | 11 | 11 | 13 | 13 | 8 | 14 | 14 | 11 | 10 | 8 | 12 | 12 | 14 | 11 | 10 | 15 | 11 | 10 | 14
417 | 68 | 44 | 91 | 142 | 187 | 235 | 294 | 343 | 390 | 429 | 471 | 518 | 567 | 610 | 12 | 13 | 8 | 11 | 9 | 15 | 10 | 13 | 12 | 10 | 13 | 16 | 15 | 11 | 11 | 8 | 11 | 11 | 11 | 15 | 15 | 14 | 16 | 14 | 13 | 15 | 8 | 13 | 11 | 15 | 10 | 11 | 9 | 11 | 11 | 8 | 9 | 14 | 9 | 10 | 12 | 13 | 9 | 13 | 9 | 16 | 12 | 12 | 11 | 10 | 10 | 12
418 | 75 | 49 | 106 | 163 | 216 | 258 | 309 | 354 | 401 | 453 | 499 | 543 | 597 | 641 | 16 | 11 | 10 | 12 | 11 | 15 | 16 | 15 | 16 | 15 | 10 | 16 | 13 | 11 | 16 | 13 | 11 | 9 | 12 | 10 | 13 | 11 | 13 | 14 | 11 | 10 | 16 | 8 | 10 | 16 | 8 | 13 | 15 | 13 | 11 | 13 | 12 | 14 | 10 | 10 | 11 | 10 | 12 | 11 | 15 | 12 | 13 | 14 | 13 | 14 | 8 | 9
419 | 74 | 50 | 92 | 147 | 195 | 240 | 292 | 338 | 377 | 415 | 467 | 505 | 549 | 607 | 10 | 11 | 14 | 15 | 9 | 15 | 8 | 10 | 14 | 15 | 16 | 10 | 13 | 8 | 15 | 12 | 10 | 9 | 13 | 13 | 16 | 16 | 11 | 9 | 13 | 8 | 16 | 9 | 8 | 12 | 11 | 8 | 8 | 12 | 10 | 8 | 14 | 16 | 10 | 12 | 13 | 8 | 9 | 8 | 14 | 14 | 8 | 8 | 16 | 15 | 16 | 11
420 | 83 | 54 | 106 | 153 | 204 | 250 | 295 | 347 | 388 | 436 | 477 | 516 | 565 | 606 | 12 | 11 | 16 | 15 | 14 | 15 | 10 | 13 | 14 | 9 | 10 | 14 | 13 | 16 | 10 | 12 | 14 | 13 | 9 | 10 | 10 | 14 | 11 | 10 | 14 | 15 | 13 | 10 | 8 | 14 | 11 | 8 | 12 | 12 | 14 | 10 | 8 | 10 | 11 | 12 | 12 | 8 | 8 | 11 | 16 | 13 | 10 | 10 | 9 | 8 | 8 | 16
421 | 74 | 46 | 92 | 147 | 195 | 257 | 307 | 358 | 397 | 446 | 487 | 539 | 593 | 651 | 9 | 16 | 9 | 12 | 16 | 12 | 9 | 9 | 16 | 15 | 9 | 15 | 12 | 8 | 14 | 14 | 16 | 15 | 16 | 15 | 15 | 12 | 9 | 14 | 12 | 12 | 12 | 15 | 9 | 10 | 12 | 8 | 15 | 15 | 9 | 10 | 8 | 11 | 11 | 11 | 11 | 12 | 14 | 15 | 14 | 15 | 11 | 14 | 14 | 13 | 16 | 15
422 | 66 | 43 | 89 | 137 | 183 | 231 | 279 | 333 | 379 | 418 | 464 | 511 | 565 | 609 | 8 | 11 | 10 | 14 | 12 | 11 | 10 | 13 | 12 | 15 | 8 | 13 | 9 | 12 | 12 | 13 | 8 | 15 | 12 | 13 | 13 | 9 | 11 | 15 | 10 | 16 | 13 | 15 | 12 | 10 | 10 | 14 | 9 | 8 | 11 | 11 | 16 | 12 | 8 | 10 | 9 | 9 | 13 | 16 | 9 | 15 | 16 | 14 | 16 | 10 | 8 | 10
423 | 87 | 55 | 109 | 156 | 199 | 243 | 298 | 347 | 392 | 444 | 479 | 522 | 577 | 620 | 13 | 15 | 14 | 13 | 16 | 16 | 11 | 11 | 9 | 16 | 14 | 8 | 8 | 11 | 13 | 11 | 11 | 9 | 9 | 15 | 15 | 16 | 12 | 12 | 15 | 8 | 10 | 16 | 9 | 15 | 12 | 9 | 14 | 10 | 13 | 15 | 9 | 9 | 9 | 8 | 9 | 12 | 8 | 14 | 14 | 16 | 12 | 13 | 11 | 8 | 11 | 13
424 | 61 | 38 | 83 | 128 | 176 | 221 | 276 | 326 | 369 | 424 | 469 | 504 | 552 | 604 | 9 | 8 | 10 | 11 | 15 | 8 | 9 | 13 | 11 | 12 | 9 | 13 | 8 | 15 | 10 | 15 | 15 | 14 | 8 | 8 | 14 | 13 | 15 | 13 | 8 | 14 | 13 | 15 | 9 | 15 | 9 | 10 | 15 | 10 | 14 | 16 | 14 | 12 | 9 | 10 | 9 | 10 | 8 | 8 | 8 | 15 | 11 | 14 | 16 | 11 | 11 | 14
425 | 85 | 56 | 109 | 162 | 210 | 264 | 325 | 373 | 415 | 456 | 504 | 557 | 612 | 654 | 15 | 15 | 15 | 11 | 16 | 13 | 15 | 9 | 12 | 11 | 15 | 15 | 16 | 14 | 8 | 10 | 14 | 11 | 16 | 13 | 13 | 16 | 16 | 16 | 13 | 14 | 9 | 12 | 11 | 10 | 11 | 10 | 11 | 9 | 8 | 13 | 12 | 9 | 11 | 16 | 10 | 11 | 16 | 16 | 16 | 9 | 14 | 16 | 8 | 9 | 14 | 11
426 | 65 | 43 | 92 | 140 | 191 | 241 | 277 | 332 | 385 | 439 | 492 | 540 | 591 | 634 | 9 | 11 | 8 | 15 | 8 | 14 | 13 | 14 | 13 | 13 | 14 | 8 | 8 | 16 | 12 | 15 | 12 | 16 | 14 | 8 | 8 | 8 | 11 | 9 | 15 | 10 | 16 | 14 | 16 | 8 | 14 | 15 | 13 | 16 | 9 | 16 | 15 | 16 | 11 | 11 | 14 | 11 | 12 | 11 | 16 | 10 | 12 | 13 | 8 | 11 | 9 | 15
427 | 73 | 50 | 100 | 146 | 190 | 235 | 287 | 337 | 389 | 440 | 485 | 535 | 578 | 628 | 16 | 8 | 14 | 12 | 9 | 14 | 15 | 12 | 14 | 10 | 14 | 8 | 10 | 9 | 13 | 12 | 13 | 9 | 8 | 15 | 12 | 15 | 14 | 11 | 12 | 15 | 12 | 11 | 14 | 11 | 15 | 12 | 11 | 15 | 15 | 10 | 10 | 11 | 16 | 8 | 16 | 16 | 9 | 9 | 11 | 8 | 14 | 10 | 11 | 10 | 14 | 15
428 | 65 | 44 | 92 | 141 | 192 | 238 | 292 | 344 | 392 | 436 | 484 | 534 | 589 | 638 | 14 | 8 | 12 | 10 | 8 | 13 | 15 | 12 | 11 | 11 | 12 | 15 | 14 | 16 | 9 | 12 | 13 | 8 | 11 | 14 | 12 | 15 | 14 | 13 | 12 | 14 | 10 | 16 | 8 | 10 | 14 | 16 | 13 | 10 | 8 | 13 | 16 | 10 | 11 | 11 | 9 | 13 | 13 | 15 | 12 | 12 | 15 | 16 | 15 | 14 | 8 | 12
429 | 70 | 51 | 86 | 136 | 179 | 224 | 272 | 325 | 368 | 412 | 467 | 522 | 564 | 613 | 9 | 11 | 15 | 16 | 11 | 8 | 8 | 8 | 13 | 16 | 9 | 12 | 8 | 11 | 14 | 10 | 10 | 15 | 10 | 10 | 16 | 9 | 13 | 10 | 11 | 15 | 12 | 15 | 8 | 16 | 9 | 10 | 16 | 12 | 8 | 8 | 12 | 16 | 15 | 12 | 15 | 16 | 9 | 15 | 9 | 8 | 13 | 12 | 8 | 11 | 15 | 15
430 | 65 | 42 | 91 | 135 | 179 | 218 | 272 | 320 | 370 | 429 | 469 | 514 | 552 | 601 | 13 | 12 | 9 | 8 | 13 | 10 | 12 | 14 | 8 | 12 | 10 | 14 | 9 | 12 | 12 | 11 | 8 | 14 | 8 | 9 | 15 | 14 | 13 | 12 | 12 | 10 | 16 | 10 | 11 | 15 | 12 | 12 | 13 | 16 | 15 | 15 | 8 | 10 | 12 | 10 | 11 | 14 | 11 | 9 | 9 | 8 | 10 | 11 | 8 | 15 | 12 | 14
431 | 62 | 41 | 89 | 134 | 179 | 219 | 264 | 312 | 353 | 409 | 462 | 516 | 560 | 605 | 9 | 10 | 12 | 10 | 8 | 13 | 11 | 16 | 16 | 9 | 9 | 11 | 14 | 12 | 11 | 8 | 8 | 8 | 15 | 9 | 11 | 14 | 8 | 12 | 16 | 8 | 11 | 13 | 9 | 12 | 8 | 12 | 13 | 13 | 16 | 14 | 10 | 14 | 15 | 14 | 15 | 8 | 15 | 16 | 13 | 8 | 11 | 12 | 12 | 8 | 10 | 15
432 | 75 | 51 | 96 | 141 | 190 | 237 | 281 | 324 | 366 | 410 | 451 | 505 | 549 | 604 | 12 | 12 | 11 | 16 | 15 | 9 | 10 | 11 | 14 | 11 | 10 | 10 | 11 | 10 | 13 | 15 | 16 | 10 | 9 | 12 | 8 | 13 | 11 | 12 | 14 | 12 | 9 | 8 | 14 | 9 | 8 | 11 | 8 | 11 | 16 | 9 | 11 | 9 | 12 | 9 | 16 | 15 | 14 | 9 | 9 | 14 | 10 | 11 | 11 | 16 | 15 | 13
433 | 76 | 48 | 99 | 141 | 194 | 240 | 289 | 337 | 387 | 443 | 493 | 531 | 578 | 628 | 16 | 14 | 8 | 10 | 12 | 16 | 11 | 12 | 9 | 8 | 16 | 9 | 14 | 14 | 10 | 15 | 14 | 15 | 8 | 9 | 14 | 10 | 13 | 12 | 14 | 9 | 13 | 12 | 14 | 13 | 14 | 9 | 16 | 10 | 14 | 16 | 16 | 8 | 11 | 15 | 9 | 8 | 13 | 8 | 16 | 8 | 11 | 12 | 13 | 13 | 12 | 12
434 | 59 | 39 | 83 | 131 | 183 | 235 | 277 | 334 | 385 | 439 | 491 | 532 | 582 | 629 | 9 | 11 | 8 | 11 | 10 | 10 | 14 | 10 | 10 | 12 | 11 | 15 | 14 | 9 | 15 | 14 | 13 | 8 | 16 | 15 | 8 | 14 | 12 | 8 | 16 | 15 | 11 | 15 | 12 | 11 | 12 | 16 | 10 | 15 | 13 | 16 | 12 | 15 | 11 | 14 | 9 | 13 | 10 | 9 | 15 | 12 | 12 | 11 | 12 | 9 | 13 | 13
435 | 75 | 51 | 102 | 160 | 206 | 257 | 300 | 345 | 394 | 446 | 495 | 550 | 595 | 643 | 13 | 15 | 13 | 10 | 13 | 11 | 15 | 12 | 16 | 12 | 14 | 16 | 10 | 8 | 14 | 14 | 16 | 12 | 9 | 14 | 9 | 16 | 8 | 10 | 12 | 8 | 16 | 9 | 14 | 12 | 14 | 9 | 13 | 13 | 10 | 16 | 14 | 12 | 9 | 14 | 13 | 12 | 15 | 15 | 13 | 12 | 9 | 11 | 12 | 14 | 8 | 14
436 | 82 | 53 | 104 | 149 | 191 | 245 | 287 | 332 | 380 | 425 | 479 | 529 | 584 | 632 | 13 | 12 | 14 | 14 | 13 | 16 | 10 | 12 | 13 | 9 | 13 | 10 | 8 | 15 | 8 | 11 | 14 | 15 | 11 | 14 | 10 | 11 | 13 | 8 | 10 | 15 | 10 | 10 | 13 | 14 | 13 | 8 | 16 | 9 | 10 | 10 | 13 | 15 | 14 | 12 | 11 | 16 | 11 | 12 | 14 | 13 | 16 | 12 | 14 | 10 | 15 | 9
437 | 69 | 46 | 90 | 131 | 182 | 232 | 278 | 325 | 368 | 424 | 471 | 511 | 561 | 607 | 13 | 13 | 10 | 10 | 15 | 8 | 13 | 8 | 10 | 8 | 11 | 12 | 13 | 11 | 13 | 14 | 9 | 13 | 16 | 12 | 8 | 14 | 9 | 15 | 14 | 10 | 13 | 10 | 8 | 13 | 9 | 13 | 15 | 14 | 14 | 13 | 16 | 8 | 8 | 15 | 8 | 10 | 14 | 8 | 10 | 10 | 15 | 15 | 8 | 8 | 15 | 15
438 | 84 | 57 | 116 | 159 | 211 | 260 | 305 | 349 | 393 | 436 | 484 | 529 | 581 | 627 | 15 | 15 | 12 | 15 | 11 | 16 | 16 | 16 | 13 | 9 | 8 | 13 | 8 | 16 | 14 | 14 | 13 | 14 | 9 | 13 | 16 | 9 | 12 | 8 | 9 | 15 | 9 | 11 | 12 | 8 | 13 | 11 | 11 | 11 | 12 | 9 | 11 | 10 | 13 | 14 | 11 | 8 | 16 | 10 | 12 | 11 | 13 | 16 | 13 | 9 | 9 | 15
439 | 81 | 60 | 98 | 146 | 200 | 255 | 306 | 358 | 397 | 435 | 479 | 526 | 580 | 623 | 16 | 14 | 16 | 14 | 8 | 13 | 8 | 9 | 12 | 13 | 8 | 15 | 12 | 10 | 16 | 16 | 14 | 13 | 12 | 16 | 9 | 15 | 13 | 14 | 14 | 8 | 14 | 16 | 8 | 14 | 9 | 8 | 9 | 8 | 8 | 13 | 9 | 9 | 13 | 13 | 12 | 11 | 15 | 9 | 15 | 11 | 14 | 14 | 10 | 11 | 10 | 12
440 | 69 | 51 | 94 | 142 | 188 | 231 | 276 | 328 | 383 | 422 | 469 | 515 | 562 | 620 | 14 | 15 | 9 | 13 | 9 | 9 | 9 | 16 | 11 | 10 | 11 | 16 | 8 | 11 | 11 | 16 | 10 | 12 | 12 | 9 | 8 | 14 | 12 | 11 | 14 | 12 | 13 | 13 | 13 | 16 | 16 | 10 | 8 | 11 | 12 | 8 | 10 | 9 | 15 | 13 | 8 | 12 | 11 | 15 | 8 | 12 | 16 | 11 | 15 | 12 | 15 | 16
441 | 74 | 49 | 99 | 149 | 197 | 244 | 305 | 352 | 392 | 436 | 483 | 523 | 575 | 632 | 11 | 13 | 13 | 12 | 12 | 13 | 12 | 13 | 11 | 11 | 16 | 12 | 16 | 8 | 11 | 13 | 16 | 11 | 12 | 8 | 16 | 14 | 15 | 16 | 11 | 10 | 10 | 16 | 9 | 11 | 11 | 9 | 11 | 12 | 13 | 8 | 16 | 15 | 8 | 8 | 8 | 9 | 14 | 9 | 14 | 13 | 16 | 9 | 14 | 16 | 12 | 15
442 | 66 | 40 | 93 | 145 | 190 | 233 | 276 | 319 | 367 | 408 | 457 | 504 | 550 | 597 | 8 | 9 | 14 | 9 | 13 | 13 | 12 | 15 | 9 | 11 | 16 | 16 | 16 | 10 | 9 | 10 | 9 | 14 | 9 | 11 | 12 | 11 | 10 | 10 | 15 | 9 | 11 | 8 | 10 | 16 | 14 | 8 | 8 | 8 | 16 | 9 | 8 | 15 | 14 | 12 | 8 | 14 | 11 | 14 | 15 | 8 | 13 | 10 | 9 | 11 | 11 | 16
443 | 83 | 57 | 104 | 145 | 202 | 258 | 307 | 351 | 398 | 451 | 495 | 544 | 592 | 636 | 12 | 15 | 14 | 16 | 15 | 11 | 8 | 13 | 11 | 9 | 8 | 13 | 14 | 16 | 16 | 11 | 14 | 16 | 14 | 12 | 11 | 8 | 15 | 15 | 9 | 13 | 12 | 10 | 12 | 13 | 9 | 13 | 16 | 12 | 12 | 13 | 9 | 11 | 16 | 8 | 11 | 11 | 15 | 12 | 14 | 8 | 12 | 14 | 10 | 11 | 8 | 15
444 | 62 | 44 | 81 | 125 | 173 | 223 | 271 | 311 | 353 | 402 | 451 | 493 | 532 | 567 | 10 | 11 | 12 | 11 | 8 | 10 | 9 | 10 | 9 | 8 | 15 | 12 | 8 | 14 | 15 | 11 | 15 | 15 | 10 | 10 | 8 | 16 | 13 | 11 | 8 | 13 | 8 | 11 | 9 | 10 | 11 | 12 | 13 | 11 | 16 | 9 | 10 | 15 | 14 | 10 | 9 | 8 | 9 | 16 | 11 | 12 | 8 | 8 | 8 | 10 | 9 | 8
445 | 66 | 42 | 89 | 132 | 184 | 230 | 279 | 336 | 380 | 421 | 480 | 521 | 577 | 626 | 11 | 9 | 14 | 8 | 16 | 8 | 15 | 8 | 10 | 12 | 9 | 12 | 15 | 10 | 15 | 12 | 12 | 9 | 14 | 11 | 11 | 9 | 15 | 14 | 16 | 11 | 14 | 16 | 15 | 10 | 8 | 11 | 12 | 11 | 9 | 9 | 16 | 13 | 15 | 15 | 8 | 15 | 10 | 8 | 16 | 15 | 14 | 11 | 8 | 16 | 10 | 15
446 | 77 | 48 | 104 | 142 | 185 | 233 | 274 | 325 | 375 | 420 | 476 | 525 | 583 | 627 | 16 | 9 | 10 | 13 | 14 | 15 | 13 | 14 | 8 | 10 | 10 | 10 | 15 | 10 | 10 | 8 | 9 | 13 | 11 | 15 | 10 | 8 | 12 | 11 | 13 | 9 | 15 | 14 | 12 | 9 | 13 | 16 | 15 | 10 | 11 | 9 | 13 | 14 | 16 | 13 | 12 | 10 | 16 | 11 | 13 | 16 | 14 | 15 | 9 | 10 | 10 | 15
447 | 72 | 46 | 99 | 148 | 197 | 246 | 294 | 334 | 386 | 433 | 475 | 525 | 583 | 626 | 8 | 11 | 16 | 11 | 10 | 16 | 11 | 16 | 8 | 13 | 15 | 13 | 8 | 15 | 10 | 16 | 16 | 12 | 13 | 8 | 10 | 13 | 9 | 16 | 8 | 12 | 12 | 8 | 15 | 8 | 15 | 14 | 13 | 12 | 13 | 9 | 10 | 9 | 12 | 11 | 14 | 11 | 11 | 14 | 16 | 10 | 16 | 16 | 13 | 12 | 8 | 10
448 | 68 | 46 | 95 | 149 | 205 | 256 | 306 | 349 | 395 | 446 | 493 | 544 | 592 | 647 | 12 | 14 | 9 | 11 | 10 | 12 | 12 | 15 | 12 | 15 | 16 | 11 | 16 | 15 | 13 | 12 | 9 | 16 | 14 | 12 | 9 | 16 | 15 | 10 | 11 | 11 | 12 | 9 | 9 | 11 | 10 | 16 | 13 | 10 | 15 | 13 | 9 | 12 | 10 | 16 | 13 | 12 | 15 | 11 | 16 | 12 | 8 | 12 | 16 | 8 | 15 | 16
449 | 65 | 44 | 92 | 137 | 187 | 234 | 281 | 320 | 354 | 402 | 454 | 499 | 536 | 593 | 8 | 11 | 10 | 15 | 12 | 9 | 16 | 11 | 9 | 15 | 11 | 10 | 15 | 15 | 11 | 9 | 10 | 8 | 13 | 16 | 15 | 10 | 8 | 14 | 9 | 10 | 11 | 9 | 10 | 8 | 8 | 8 | 9 | 16 | 15 | 8 | 12 | 16 | 14 | 10 | 8 | 16 | 9 | 12 | 8 | 8 | 10 | 11 | 16 | 14 | 12 | 15
450 | 61 | 38 | 88 | 131 | 177 | 220 | 262 | 312 | 354 | 398 | 451 | 497 | 558 | 605 | 9 | 8 | 13 | 8 | 10 | 13 | 14 | 13 | 14 | 11 | 9 | 9 | 12 | 11 | 13 | 10 | 11 | 9 | 12 | 11 | 8 | 13 | 13 | 8 | 13 | 13 | 12 | 12 | 11 | 12 | 11 | 8 | 15 | 9 | 12 | 8 | 14 | 11 | 13 | 15 | 13 | 12 | 10 | 11 | 16 | 13 | 16 | 16 | 10 | 13 | 9 | 15
451 | 69 | 44 | 92 | 142 | 186 | 238 | 287 | 332 | 372 | 411 | 456 | 504 | 552 | 601 | 9 | 11 | 11 | 13 | 10 | 15 | 15 | 8 | 14 | 10 | 15 | 11 | 8 | 12 | 9 | 15 | 15 | 14 | 14 | 9 | 9 | 16 | 13 | 11 | 10 | 14 | 10 | 11 | 8 | 9 | 12 | 11 | 9 | 9 | 8 | 13 | 9 | 15 | 13 | 8 | 15 | 12 | 8 | 13 | 9 | 14 | 13 | 12 | 10 | 11 | 12 | 16
452 | 79 | 56 | 96 | 137 | 181 | 234 | 284 | 330 | 373 | 422 | 467 | 515 | 564 | 607 | 13 | 15 | 13 | 15 | 10 | 13 | 9 | 8 | 10 | 8 | 10 | 13 | 15 | 12 | 8 | 9 | 11 | 15 | 12 | 15 | 9 | 16 | 12 | 13 | 12 | 14 | 11 | 9 | 12 | 9 | 8 | 14 | 15 | 11 | 15 | 8 | 9 | 11 | 15 | 10 | 10 | 12 | 12 | 14 | 13 | 13 | 12 | 11 | 11 | 9 | 9 | 14
453 | 76 | 50 | 95 | 131 | 183 | 236 | 275 | 332 | 381 | 428 | 474 | 525 | 568 | 623 | 11 | 16 | 15 | 8 | 16 | 10 | 8 | 11 | 9 | 8 | 10 | 9 | 12 | 12 | 15 | 13 | 11 | 14 | 14 | 14 | 8 | 8 | 12 | 11 | 11 | 15 | 15 | 16 | 14 | 12 | 14 | 9 | 15 | 11 | 8 | 13 | 13 | 14 | 10 | 9 | 16 | 8 | 15 | 12 | 11 | 11 | 11 | 10 | 16 | 12 | 13 | 14
454 | 65 | 44 | 93 | 129 | 174 | 223 | 274 | 322 | 364 | 403 | 447 | 490 | 533 | 572 | 8 | 13 | 13 | 10 | 11 | 10 | 14 | 14 | 8 | 8 | 9 | 11 | 9 | 14 | 10 | 12 | 8 | 12 | 14 | 15 | 10 | 15 | 10 | 16 | 8 | 14 | 13 | 13 | 12 | 10 | 12 | 8 | 10 | 10 | 10 | 9 | 12 | 12 | 9 | 11 | 9 | 11 | 15 | 8 | 8 | 12 | 9 | 14 | 9 | 13 | 9 | 8
455 | 73 | 46 | 97 | 147 | 196 | 252 | 304 | 350 | 410 | 453 | 503 | 544 | 600 | 640 | 14 | 10 | 8 | 14 | 13 | 14 | 10 | 14 | 10 | 12 | 14 | 14 | 12 | 13 | 15 | 9 | 15 | 11 | 15 | 15 | 11 | 14 | 14 | 13 | 12 | 8 | 15 | 11 | 15 | 15 | 14 | 16 | 9 | 11 | 11 | 12 | 14 | 12 | 10 | 14 | 9 | 10 | 13 | 9 | 15 | 11 | 15 | 15 | 10 | 9 | 12 | 9
456 | 68 | 48 | 90 | 137 | 186 | 230 | 276 | 315 | 366 | 412 | 466 | 517 | 560 | 612 | 10 | 11 | 13 | 14 | 11 | 9 | 8 | 14 | 10 | 13 | 14 | 10 | 13 | 12 | 9 | 15 | 11 | 14 | 8 | 11 | 13 | 9 | 12 | 12 | 8 | 9 | 10 | 12 | 14 | 12 | 14 | 11 | 15 | 11 | 11 | 9 | 16 | 9 | 15 | 14 | 13 | 13 | 13 | 12 | 11 | 8 | 16 | 8 | 15 | 13 | 11 | 13
457 | 86 | 55 | 109 | 152 | 199 | 249 | 291 | 334 | 378 | 425 | 478 | 518 | 575 | 626 | 16 | 15 | 8 | 16 | 15 | 16 | 10 | 13 | 8 | 14 | 10 | 11 | 15 | 11 | 12 | 9 | 9 | 12 | 15 | 14 | 8 | 15 | 11 | 8 | 8 | 13 | 11 | 11 | 8 | 12 | 14 | 10 | 16 | 9 | 12 | 10 | 16 | 16 | 10 | 11 | 11 | 9 | 10 | 10 | 16 | 15 | 14 | 12 | 9 | 16 | 13 | 13
458 | 70 | 52 | 89 | 125 | 165 | 211 | 266 | 317 | 361 | 411 | 455 | 508 | 562 | 611 | 15 | 11 | 16 | 10 | 8 | 10 | 11 | 8 | 9 | 8 | 9 | 10 | 8 | 10 | 8 | 14 | 14 | 9 | 9 | 14 | 11 | 16 | 12 | 16 | 10 | 14 | 15 | 12 | 12 | 14 | 9 | 9 | 10 | 16 | 14 | 10 | 9 | 10 | 16 | 9 | 16 | 13 | 8 | 16 | 8 | 16 | 14 | 16 | 12 | 14 | 11 | 12
459 | 73 | 50 | 97 | 141 | 199 | 257 | 311 | 362 | 412 | 464 | 521 | 562 | 611 | 658 | 12 | 15 | 12 | 11 | 11 | 12 | 16 | 8 | 10 | 16 | 10 | 8 | 13 | 15 | 15 | 15 | 12 | 15 | 15 | 16 | 10 | 15 | 16 | 13 | 11 | 13 | 14 | 13 | 12 | 11 | 15 | 12 | 8 | 16 | 12 | 16 | 9 | 16 | 16 | 16 | 10 | 9 | 8 | 14 | 11 | 16 | 8 | 14 | 9 | 12 | 14 | 12
460 | 79 | 55 | 102 | 147 | 194 | 246 | 291 | 332 | 383 | 435 | 486 | 543 | 602 | 652 | 12 | 15 | 14 | 14 | 14 | 10 | 14 | 9 | 11 | 13 | 12 | 9 | 11 | 12 | 11 | 13 | 13 | 12 | 12 | 15 | 12 | 12 | 12 | 9 | 9 | 8 | 16 | 8 | 9 | 11 | 16 | 15 | 10 | 15 | 12 | 15 | 14 | 9 | 16 | 12 | 15 | 13 | 14 | 15 | 13 | 15 | 15 | 16 | 8 | 14 | 14 | 14
461 | 64 | 46 | 87 | 124 | 176 | 222 | 268 | 322 | 372 | 420 | 465 | 514 | 565 | 606 | 12 | 9 | 9 | 16 | 9 | 9 | 14 | 9 | 10 | 8 | 11 | 8 | 13 | 9 | 14 | 16 | 13 | 9 | 9 | 15 | 10 | 14 | 9 | 13 | 16 | 10 | 15 | 13 | 14 | 13 | 9 | 14 | 8 | 14 | 13 | 13 | 15 | 8 | 8 | 14 | 13 | 16 | 10 | 10 | 15 | 15 | 12 | 9 | 8 | 10 | 8 | 15
462 | 77 | 50 | 101 | 145 | 204 | 246 | 296 | 347 | 399 | 454 | 497 | 542 | 588 | 626 | 8 | 12 | 15 | 15 | 12 | 15 | 16 | 8 | 14 | 11 | 11 | 8 | 16 | 15 | 15 | 13 | 10 | 15 | 8 | 9 | 10 | 12 | 13 | 15 | 12 | 15 | 14 | 10 | 16 | 12 | 16 | 8 | 11 | 15 | 16 | 13 | 11 | 10 | 11 | 11 | 8 | 16 | 10 | 11 | 16 | 10 | 9 | 11 | 11 | 9 | 9 | 9
463 | 71 | 54 | 96 | 139 | 191 | 237 | 283 | 335 | 384 | 431 | 479 | 530 | 570 | 618 | 15 | 14 | 14 | 11 | 8 | 9 | 12 | 13 | 9 | 13 | 10 | 11 | 15 | 14 | 10 | 13 | 8 | 15 | 13 | 10 | 10 | 14 | 14 | 8 | 13 | 14 | 13 | 12 | 12 | 12 | 13 | 12 | 12 | 11 | 16 | 8 | 13 | 13 | 10 | 12 | 12 | 16 | 12 | 11 | 10 | 8 | 12 | 10 | 16 | 10 | 9 | 13
464 | 71 | 46 | 103 | 140 | 184 | 227 | 281 | 329 | 377 | 428 | 463 | 511 | 547 | 595 | 16 | 8 | 12 | 10 | 12 | 13 | 16 | 16 | 10 | 8 | 11 | 8 | 13 | 12 | 11 | 8 | 9 | 10 | 14 | 10 | 9 | 15 | 14 | 16 | 9 | 11 | 15 | 13 | 15 | 16 | 8 | 9 | 12 | 16 | 12 | 11 | 9 | 8 | 8 | 10 | 13 | 15 | 9 | 11 | 11 | 9 | 8 | 8 | 11 | 13 | 14 | 10
465 | 76 | 53 | 103 | 145 | 199 | 247 | 304 | 354 | 403 | 448 | 496 | 540 | 589 | 632 | 16 | 13 | 8 | 16 | 13 | 10 | 16 | 11 | 9 | 9 | 14 | 10 | 15 | 15 | 13 | 11 | 11 | 8 | 14 | 15 | 16 | 11 | 14 | 16 | 16 | 13 | 13 | 8 | 9 | 16 | 12 | 12 | 10 | 8 | 13 | 14 | 13 | 11 | 16 | 8 | 8 | 8 | 12 | 16 | 11 | 11 | 16 | 11 | 9 | 11 | 11 | 12
466 | 71 | 51 | 98 | 139 | 184 | 236 | 281 | 329 | 384 | 428 | 480 | 524 | 571 | 621 | 13 | 15 | 13 | 10 | 8 | 12 | 15 | 12 | 8 | 13 | 11 | 9 | 11 | 8 | 14 | 12 | 14 | 15 | 13 | 10 | 13 | 10 | 9 | 13 | 11 | 15 | 13 | 9 | 15 | 15 | 11 | 14 | 16 | 9 | 9 | 10 | 13 | 12 | 14 | 13 | 11 | 9 | 14 | 10 | 12 | 11 | 16 | 8 | 15 | 12 | 12 | 11
467 | 79 | 52 | 98 | 147 | 193 | 238 | 286 | 331 | 371 | 418 | 464 | 510 | 553 | 608 | 15 | 12 | 13 | 12 | 13 | 14 | 8 | 11 | 13 | 8 | 15 | 13 | 14 | 8 | 12 | 12 | 12 | 14 | 10 | 9 | 16 | 10 | 13 | 9 | 10 | 13 | 12 | 10 | 11 | 8 | 8 | 13 | 14 | 9 | 15 | 9 | 12 | 15 | 11 | 8 | 8 | 11 | 14 | 13 | 11 | 14 | 8 | 10 | 13 | 13 | 13 | 16
468 | 70 | 52 | 89 | 140 | 187 | 229 | 269 | 321 | 371 | 419 | 466 | 512 | 559 | 601 | 11 | 10 | 15 | 16 | 8 | 10 | 10 | 9 | 15 | 12 | 8 | 16 | 8 | 8 | 15 | 16 | 11 | 8 | 8 | 15 | 9 | 15 | 8 | 8 | 12 | 14 | 14 | 12 | 16 | 15 | 10 | 9 | 8 | 16 | 11 | 13 | 16 | 12 | 11 | 8 | 16 | 9 | 12 | 9 | 12 | 9 | 14 | 12 | 9 | 15 | 10 | 8
469 | 74 | 48 | 104 | 145 | 193 | 248 | 296 | 345 | 391 | 440 | 482 | 541 | 583 | 633 | 12 | 12 | 12 | 12 | 13 | 13 | 16 | 14 | 11 | 10 | 8 | 12 | 16 | 8 | 13 | 11 | 14 | 12 | 16 | 13 | 13 | 9 | 10 | 16 | 15 | 8 | 13 | 13 | 10 | 13 | 8 | 15 | 10 | 15 | 10 | 14 | 8 | 16 | 8 | 10 | 14 | 16 | 14 | 15 | 11 | 9 | 14 | 8 | 13 | 16 | 12 | 9
470 | 72 | 45 | 103 | 147 | 189 | 234 | 285 | 331 | 374 | 425 | 471 | 517 | 572 | 619 | 15 | 11 | 8 | 11 | 16 | 11 | 15 | 16 | 14 | 10 | 10 | 10 | 8 | 11 | 11 | 12 | 8 | 13 | 12 | 12 | 16 | 15 | 9 | 11 | 10 | 11 | 15 | 10 | 10 | 10 | 10 | 13 | 11 | 11 | 15 | 14 | 8 | 15 | 11 | 12 | 14 | 13 | 11 | 8 | 16 | 12 | 11 | 16 | 11 | 12 | 12 | 12
471 | 69 | 47 | 97 | 142 | 183 | 226 | 280 | 330 | 389 | 440 | 500 | 549 | 591 | 635 | 9 | 8 | 15 | 15 | 8 | 14 | 13 | 15 | 9 | 11 | 9 | 16 | 13 | 8 | 9 | 11 | 10 | 11 | 8 | 14 | 14 | 15 | 15 | 10 | 8 | 12 | 16 | 14 | 16 | 15 | 14 | 14 | 11 | 13 | 16 | 11 | 16 | 13 | 16 | 15 | 9 | 11 | 14 | 15 | 9 | 8 | 11 | 14 | 11 | 14 | 10 | 9
472 | 71 | 44 | 94 | 139 | 188 | 242 | 280 | 333 | 376 | 418 | 471 | 526 | 582 | 634 | 14 | 10 | 8 | 12 | 12 | 15 | 11 | 12 | 9 | 13 | 12 | 11 | 9 | 15 | 11 | 14 | 15 | 12 | 14 | 13 | 12 | 10 | 8 | 8 | 14 | 11 | 13 | 15 | 16 | 8 | 8 | 11 | 12 | 12 | 8 | 10 | 15 | 13 | 14 | 11 | 13 | 13 | 16 | 13 | 16 | 13 | 14 | 13 | 15 | 12 | 16 | 9
473 | 71 | 48 | 97 | 142 | 186 | 230 | 279 | 319 | 362 | 410 | 465 | 510 | 562 | 605 | 13 | 11 | 16 | 8 | 12 | 11 | 10 | 16 | 11 | 15 | 10 | 9 | 12 | 13 | 10 | 9 | 11 | 14 | 8 | 11 | 14 | 12 | 14 | 9 | 8 | 14 | 10 | 8 | 10 | 8 | 13 | 12 | 10 | 11 | 14 | 13 | 16 | 15 | 13 | 11 | 11 | 8 | 11 | 15 | 11 | 16 | 12 | 13 | 9 | 10 | 12 | 12
474 | 75 | 53 | 100 | 151 | 195 | 244 | 296 | 356 | 398 | 444 | 499 | 554 | 598 | 647 | 10 | 16 | 13 | 14 | 14 | 8 | 12 | 13 | 11 | 16 | 16 | 8 | 11 | 15 | 10 | 8 | 9 | 9 | 15 | 16 | 14 | 13 | 14 | 11 | 15 | 15 | 16 | 14 | 10 | 10 | 11 | 11 | 10 | 9 | 13 | 14 | 15 | 13 | 13 | 14 | 14 | 9 | 16 | 16 | 9 | 13 | 11 | 11 | 8 | 15 | 14 | 12
475 | 79 | 57 | 105 | 157 | 212 | 260 | 304 | 343 | 383 | 432 | 484 | 527 | 564 | 608 | 12 | 13 | 16 | 16 | 14 | 8 | 10 | 16 | 16 | 15 | 10 | 11 | 16 | 10 | 14 | 15 | 10 | 15 | 10 | 13 | 11 | 10 | 8 | 15 | 9 | 8 | 12 | 10 | 11 | 9 | 8 | 12 | 14 | 8 | 14 | 13 | 13 | 11 | 13 | 15 | 9 | 14 | 10 | 10 | 9 | 8 | 10 | 10 | 10 | 8 | 11 | 15
476 | 75 | 51 | 102 | 149 | 203 | 253 | 302 | 352 | 399 | 453 | 500 | 547 | 595 | 646 | 9 | 14 | 15 | 13 | 11 | 13 | 16 | 11 | 12 | 8 | 12 | 15 | 13 | 16 | 11 | 14 | 14 | 16 | 11 | 9 | 15 | 10 | 12 | 12 | 13 | 13 | 10 | 14 | 12 | 10 | 15 | 10 | 16 | 13 | 10 | 15 | 16 | 8 | 9 | 14 | 11 | 10 | 14 | 12 | 14 | 8 | 14 | 12 | 13 | 13 | 9 | 16
477 | 65 | 46 | 95 | 147 | 201 | 244 | 292 | 335 | 385 | 432 | 481 | 528 | 580 | 631 | 13 | 8 | 11 | 14 | 8 | 11 | 15 | 15 | 15 | 11 | 16 | 10 | 13 | 14 | 12 | 15 | 13 | 11 | 10 | 9 | 8 | 15 | 9 | 16 | 9 | 8 | 11 | 15 | 10 | 13 | 13 | 14 | 12 | 12 | 11 | 12 | 11 | 16 | 10 | 12 | 11 | 9 | 13 | 14 | 8 | 16 | 13 | 15 | 11 | 8 | 16 | 16
478 | 81 | 55 | 100 | 147 | 193 | 244 | 296 | 355 | 408 | 452 | 508 | 556 | 607 | 649 | 14 | 16 | 10 | 15 | 11 | 15 | 10 | 9 | 11 | 9 | 16 | 11 | 8 | 9 | 16 | 13 | 10 | 16 | 11 | 14 | 14 | 11 | 16 | 11 | 15 | 15 | 14 | 15 | 14 | 14 | 14 | 11 | 12 | 12 | 9 | 11 | 13 | 16 | 13 | 14 | 12 | 14 | 9 | 13 | 10 | 12 | 16 | 13 | 9 | 13 | 10 | 10
479 | 70 | 53 | 90 | 140 | 195 | 237 | 288 | 328 | 373 | 425 | 471 | 515 | 557 | 605 | 10 | 13 | 15 | 15 | 8 | 9 | 11 | 9 | 16 | 10 | 15 | 9 | 11 | 16 | 16 | 12 | 11 | 12 | 10 | 9 | 15 | 8 | 14 | 14 | 8 | 14 | 9 | 9 | 16 | 11 | 8 | 10 | 13 | 12 | 12 | 15 | 14 | 8 | 12 | 12 | 10 | 9 | 10 | 15 | 9 | 14 | 10 | 9 | 16 | 10 | 10 | 12
480 | 64 | 42 | 84 | 128 | 181 | 235 | 284 | 330 | 372 | 420 | 474 | 526 | 573 | 621 | 11 | 10 | 11 | 10 | 14 | 8 | 12 | 8 | 9 | 14 | 13 | 8 | 15 | 14 | 10 | 14 | 14 | 15 | 11 | 14 | 11 | 15 | 14 | 9 | 12 | 8 | 16 | 10 | 11 | 8 | 11 | 12 | 11 | 13 | 16 | 8 | 14 | 16 | 13 | 11 | 12 | 16 | 10 | 14 | 11 | 12 | 14 | 10 | 13 | 8 | 16 | 11
481 | 69 | 50 | 95 | 138 | 184 | 225 | 267 | 313 | 371 | 419 | 455 | 501 | 553 | 598 | 11 | 16 | 12 | 11 | 9 | 10 | 12 | 14 | 12 | 8 | 15 | 8 | 14 | 10 | 11 | 11 | 8 | 14 | 9 | 10 | 9 | 9 | 10 | 14 | 9 | 15 | 13 | 9 | 16 | 14 | 15 | 13 | 15 | 12 | 10 | 11 | 10 | 10 | 8 | 8 | 8 | 15 | 13 | 10 | 16 | 11 | 11 | 14 | 11 | 16 | 10 | 8
482 | 64 | 38 | 84 | 125 | 169 | 216 | 261 | 313 | 357 | 404 | 455 | 511 | 560 | 606 | 8 | 11 | 8 | 11 | 13 | 13 | 12 | 8 | 12 | 11 | 10 | 8 | 14 | 13 | 9 | 8 | 12 | 9 | 11 | 15 | 15 | 8 | 10 | 12 | 12 | 16 | 10 | 14 | 8 | 16 | 11 | 9 | 10 | 14 | 15 | 8 | 16 | 16 | 10 | 9 | 13 | 15 | 15 | 13 | 11 | 14 | 16 | 8 | 12 | 13 | 10 | 11
483 | 68 | 49 | 95 | 141 | 185 | 230 | 281 | 328 | 378 | 430 | 481 | 529 | 583 | 630 | 12 | 13 | 10 | 14 | 11 | 8 | 12 | 15 | 8 | 15 | 9 | 14 | 9 | 14 | 8 | 13 | 10 | 10 | 14 | 11 | 15 | 8 | 13 | 15 | 13 | 8 | 11 | 15 | 13 | 10 | 15 | 12 | 14 | 16 | 10 | 12 | 11 | 15 | 11 | 14 | 8 | 15 | 12 | 13 | 16 | 13 | 15 | 10 | 13 | 12 | 9 | 13
484 | 66 | 42 | 90 | 130 | 174 | 222 | 267 | 311 | 361 | 407 | 451 | 503 | 552 | 601 | 9 | 8 | 9 | 16 | 13 | 11 | 9 | 15 | 11 | 8 | 9 | 12 | 9 | 16 | 11 | 8 | 10 | 15 | 9 | 14 | 9 | 16 | 11 | 9 | 10 | 13 | 13 | 8 | 12 | 12 | 12 | 14 | 11 | 12 | 9 | 14 | 11 | 11 | 11 | 11 | 12 | 14 | 15 | 11 | 13 | 12 | 10 | 14 | 12 | 14 | 11 | 12
485 | 75 | 50 | 97 | 142 | 192 | 239 | 281 | 318 | 360 | 418 | 461 | 513 | 558 | 607 | 13 | 13 | 15 | 9 | 9 | 16 | 8 | 14 | 16 | 8 | 12 | 9 | 13 | 10 | 14 | 13 | 9 | 12 | 14 | 12 | 10 | 11 | 9 | 12 | 8 | 12 | 8 | 9 | 8 | 11 | 15 | 8 | 16 | 12 | 16 | 14 | 11 | 14 | 10 | 8 | 10 | 16 | 14 | 12 | 9 | 11 | 10 | 15 | 10 | 8 | 16 | 15
486 | 69 | 46 | 93 | 143 | 179 | 228 | 274 | 327 | 378 | 418 | 453 | 506 | 555 | 597 | 11 | 14 | 11 | 10 | 14 | 9 | 8 | 16 | 10 | 12 | 16 | 12 | 8 | 12 | 8 | 8 | 13 | 13 | 12 | 11 | 10 | 10 | 16 | 10 | 13 | 12 | 15 | 13 | 15 | 13 | 10 | 13 | 13 | 9 | 8 | 10 | 8 | 9 | 10 | 8 | 14 | 13 | 16 | 10 | 15 | 9 | 11 | 14 | 14 | 8 | 8 | 12
487 | 64 | 41 | 92 | 141 | 183 | 236 | 278 | 328 | 375 | 429 | 479 | 523 | 558 | 613 | 11 | 8 | 8 | 14 | 14 | 9 | 16 | 12 | 13 | 12 | 9 | 15 | 9 | 11 | 13 | 9 | 13 | 9 | 16 | 15 | 8 | 12 | 11 | 11 | 15 | 12 | 10 | 13 | 16 | 12 | 9 | 10 | 10 | 13 | 15 | 16 | 8 | 16 | 13 | 13 | 9 | 8 | 15 | 12 | 9 | 8 | 10 | 8 | 16 | 13 | 14 | 12
488 | 74 | 50 | 95 | 140 | 182 | 231 | 274 | 324 | 371 | 426 | 470 | 512 | 553 | 604 | 14 | 12 | 13 | 11 | 8 | 16 | 10 | 11 | 12 | 8 | 16 | 9 | 9 | 16 | 9 | 8 | 10 | 13 | 10 | 16 | 10 | 8 | 13 | 12 | 15 | 8 | 13 | 14 | 8 | 11 | 14 | 14 | 15 | 15 | 15 | 10 | 8 | 10 | 11 | 15 | 11 | 13 | 9 | 9 | 8 | 8 | 10 | 15 | 12 | 15 | 8 | 16
489 | 69 | 46 | 97 | 148 | 201 | 249 | 299 | 353 | 414 | 462 | 505 | 561 | 606 | 652 | 14 | 10 | 10 | 12 | 15 | 8 | 15 | 13 | 15 | 13 | 11 | 12 | 12 | 13 | 16 | 12 | 10 | 12 | 14 | 12 | 11 | 15 | 9 | 15 | 16 | 12 | 13 | 13 | 16 | 14 | 15 | 16 | 10 | 11 | 12 | 15 | 8 | 11 | 11 | 13 | 16 | 15 | 12 | 13 | 16 | 9 | 9 | 11 | 10 | 11 | 11 | 14
490 | 65 | 46 | 93 | 137 | 189 | 240 | 291 | 336 | 379 | 423 | 466 | 518 | 556 | 615 | 8 | 12 | 14 | 12 | 9 | 10 | 16 | 12 | 9 | 13 | 9 | 13 | 13 | 16 | 10 | 13 | 13 | 14 | 16 | 8 | 15 | 11 | 15 | 10 | 14 | 12 | 11 | 8 | 14 | 12 | 8 | 9 | 15 | 11 | 8 | 10 | 10 | 9 | 10 | 14 | 14 | 15 | 9 | 14 | 8 | 9 | 10 | 11 | 15 | 15 | 13 | 16
491 | 77 | 47 | 101 | 149 | 198 | 241 | 293 | 343 | 397 | 448 | 489 | 533 | 582 | 624 | 12 | 10 | 15 | 10 | 16 | 14 | 14 | 10 | 14 | 16 | 9 | 9 | 11 | 14 | 15 | 9 | 12 | 9 | 13 | 9 | 14 | 13 | 9 | 16 | 11 | 13 | 10 | 16 | 16 | 8 | 14 | 16 | 14 | 14 | 11 | 12 | 9 | 9 | 15 | 8 | 8 | 9 | 13 | 14 | 16 | 11 | 9 | 13 | 11 | 11 | 9 | 11
492 | 84 | 62 | 112 | 167 | 218 | 278 | 324 | 366 | 411 | 461 | 515 | 559 | 607 | 656 | 16 | 15 | 15 | 16 | 9 | 13 | 12 | 16 | 14 | 16 | 12 | 13 | 15 | 14 | 12 | 10 | 16 | 15 | 15 | 14 | 13 | 14 | 8 | 11 | 10 | 11 | 10 | 11 | 9 | 12 | 8 | 16 | 13 | 14 | 11 | 12 | 13 | 14 | 12 | 15 | 8 | 8 | 14 | 14 | 13 | 8 | 14 | 13 | 14 | 13 | 8 | 14
493 | 76 | 47 | 95 | 144 | 195 | 241 | 294 | 347 | 400 | 449 | 501 | 556 | 598 | 636 | 11 | 10 | 11 | 15 | 16 | 13 | 8 | 11 | 14 | 10 | 12 | 13 | 8 | 15 | 16 | 12 | 13 | 15 | 10 | 8 | 15 | 16 | 14 | 8 | 10 | 16 | 16 | 11 | 8 | 15 | 16 | 14 | 10 | 16 | 14 | 9 | 16 | 9 | 16 | 11 | 16 | 13 | 11 | 15 | 8 | 13 | 10 | 11 | 11 | 11 | 8 | 8
494 | 72 | 50 | 94 | 149 | 200 | 250 | 303 | 353 | 398 | 451 | 501 | 544 | 597 | 645 | 9 | 16 | 11 | 14 | 12 | 10 | 10 | 12 | 15 | 15 | 14 | 11 | 15 | 9 | 11 | 16 | 16 | 14 | 11 | 9 | 16 | 11 | 12 | 14 | 11 | 16 | 15 | 8 | 8 | 15 | 10 | 12 | 10 | 16 | 14 | 13 | 12 | 8 | 15 | 15 | 13 | 10 | 10 | 10 | 15 | 13 | 9 | 16 | 10 | 12 | 16 | 10
495 | 73 | 48 | 104 | 150 | 201 | 242 | 286 | 328 | 375 | 422 | 471 | 514 | 557 | 606 | 11 | 16 | 8 | 13 | 14 | 11 | 16 | 15 | 13 | 9 | 14 | 10 | 11 | 11 | 16 | 13 | 8 | 13 | 8 | 12 | 11 | 11 | 10 | 12 | 8 | 11 | 10 | 13 | 10 | 12 | 10 | 15 | 9 | 16 | 9 | 13 | 11 | 13 | 12 | 13 | 12 | 8 | 13 | 10 | 14 | 11 | 8 | 10 | 15 | 12 | 11 | 11
496 | 80 | 53 | 107 | 152 | 204 | 256 | 300 | 346 | 400 | 451 | 499 | 549 | 589 | 637 | 15 | 16 | 9 | 13 | 16 | 11 | 15 | 12 | 14 | 8 | 11 | 12 | 12 | 15 | 9 | 16 | 10 | 16 | 15 | 11 | 11 | 8 | 11 | 14 | 15 | 13 | 9 | 9 | 14 | 13 | 14 | 13 | 14 | 15 | 12 | 10 | 14 | 9 | 15 | 10 | 12 | 11 | 14 | 13 | 8 | 14 | 10 | 8 | 10 | 10 | 13 | 15
497 | 75 | 47 | 99 | 140 | 187 | 243 | 293 | 339 | 384 | 423 | 476 | 524 | 566 | 616 | 16 | 8 | 12 | 11 | 14 | 14 | 10 | 14 | 11 | 13 | 8 | 9 | 13 | 9 | 13 | 12 | 12 | 16 | 16 | 12 | 10 | 14 | 15 | 11 | 13 | 10 | 8 | 15 | 9 | 15 | 10 | 11 | 10 | 10 | 9 | 10 | 12 | 15 | 16 | 10 | 11 | 15 | 11 | 11 | 9 | 9 | 10 | 14 | 10 | 15 | 10 | 15
498 | 86 | 56 | 112 | 155 | 205 | 248 | 291 | 342 | 395 | 441 | 491 | 540 | 602 | 647 | 16 | 13 | 14 | 13 | 14 | 16 | 12 | 14 | 9 | 13 | 8 | 13 | 10 | 9 | 16 | 15 | 13 | 8 | 10 | 12 | 8 | 10 | 16 | 9 | 11 | 16 | 11 | 13 | 16 | 15 | 13 | 9 | 15 | 14 | 8 | 9 | 16 | 10 | 12 | 12 | 12 | 13 | 12 | 12 | 16 | 16 | 14 | 16 | 9 | 10 | 15 | 11
499 | 75 | 47 | 101 | 148 | 209 | 257 | 313 | 359 | 415 | 468 | 512 | 563 | 610 | 654 | 15 | 10 | 10 | 12 | 13 | 15 | 12 | 14 | 9 | 15 | 10 | 13 | 16 | 15 | 16 | 14 | 11 | 14 | 14 | 9 | 13 | 11 | 16 | 16 | 8 | 14 | 10 | 14 | 15 | 11 | 16 | 14 | 16 | 16 | 9 | 12 | 13 | 11 | 11 | 9 | 12 | 11 | 14 | 14 | 8 | 16 | 11 | 12 | 11 | 9 | 8 | 16
500 | 77 | 54 | 105 | 155 | 203 | 257 | 294 | 351 | 403 | 451 | 499 | 542 | 593 | 639 | 12 | 15 | 11 | 16 | 11 | 12 | 13 | 15 | 16 | 13 | 11 | 10 | 15 | 10 | 10 | 13 | 11 | 14 | 15 | 14 | 8 | 11 | 9 | 9 | 12 | 16 | 16 | 13 | 16 | 14 | 10 | 12 | 15 | 9 | 13 | 11 | 16 | 11 | 10 | 11 | 11 | 9 | 13 | 10 | 13 | 13 | 11 | 14 | 13 | 9 | 14 | 10
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 56 | Sum4: 36.99; Sum8: 79; Sum12: 124; Sum16: 168; Sum20: 215.98; Sum24: 259.99; Sum28: 307.98; Sum32: 351.99; Sum36: 398; Sum40: 442.99; Sum44: 490.99; Sum48: 533.99; Sum52: 579.97
2% | 59 | Sum4: 38; Sum8: 80; Sum12: 125; Sum16: 170; Sum20: 217.98; Sum24: 261; Sum28: 309.98; Sum32: 353.98; Sum36: 400.98; Sum40: 444.98; Sum44: 493; Sum48: 538.98; Sum52: 588
3% | 60 | Sum4: 38; Sum8: 82.97; Sum12: 126.97; Sum16: 172; Sum20: 219; Sum24: 263.97; Sum28: 311.97; Sum32: 355; Sum36: 402.97; Sum40: 447.97; Sum44: 495.97; Sum48: 543.97; Sum52: 590
4% | 61 | Sum4: 39; Sum8: 83; Sum12: 128; Sum16: 173.96; Sum20: 219; Sum24: 265; Sum28: 312; Sum32: 357; Sum36: 404; Sum40: 451; Sum44: 497.96; Sum48: 547; Sum52: 592
5% | 61.95 | Sum4: 39; Sum8: 84; Sum12: 129; Sum16: 175; Sum20: 221; Sum24: 267; Sum28: 313; Sum32: 359; Sum36: 406; Sum40: 452; Sum44: 499; Sum48: 548; Sum52: 593
6% | 62 | Sum4: 40; Sum8: 85; Sum12: 129.94; Sum16: 176; Sum20: 222; Sum24: 268; Sum28: 313; Sum32: 360.94; Sum36: 407.94; Sum40: 454; Sum44: 501; Sum48: 549; Sum52: 596.94
7% | 63 | Sum4: 40; Sum8: 85; Sum12: 130; Sum16: 177; Sum20: 222.93; Sum24: 269; Sum28: 315.93; Sum32: 362; Sum36: 408; Sum40: 455; Sum44: 502.93; Sum48: 550; Sum52: 597.93
8% | 63 | Sum4: 40; Sum8: 85.92; Sum12: 131; Sum16: 178; Sum20: 223; Sum24: 270; Sum28: 316; Sum32: 362.92; Sum36: 409; Sum40: 455; Sum44: 503.92; Sum48: 551; Sum52: 599
9% | 64 | Sum4: 41; Sum8: 86; Sum12: 131; Sum16: 178; Sum20: 224; Sum24: 271; Sum28: 316; Sum32: 364; Sum36: 410; Sum40: 457; Sum44: 504; Sum48: 551.91; Sum52: 600
10% | 64 | Sum4: 41; Sum8: 87; Sum12: 131; Sum16: 179; Sum20: 224.9; Sum24: 272; Sum28: 317; Sum32: 365; Sum36: 411; Sum40: 458; Sum44: 505; Sum48: 552; Sum52: 601
11% | 64 | Sum4: 41; Sum8: 87; Sum12: 132; Sum16: 179; Sum20: 225.89; Sum24: 272; Sum28: 318; Sum32: 366; Sum36: 411.89; Sum40: 459; Sum44: 506; Sum48: 553; Sum52: 601.89
12% | 64.88 | Sum4: 41; Sum8: 88; Sum12: 132; Sum16: 180; Sum20: 226; Sum24: 272.88; Sum28: 319; Sum32: 367; Sum36: 412; Sum40: 460; Sum44: 507; Sum48: 553; Sum52: 602.88
13% | 65 | Sum4: 42; Sum8: 89; Sum12: 133; Sum16: 180; Sum20: 226; Sum24: 274; Sum28: 320; Sum32: 367; Sum36: 413; Sum40: 461; Sum44: 508; Sum48: 555; Sum52: 603
14% | 65 | Sum4: 42; Sum8: 89; Sum12: 133.86; Sum16: 181; Sum20: 227; Sum24: 274; Sum28: 320.86; Sum32: 368; Sum36: 414; Sum40: 462; Sum44: 509; Sum48: 555.86; Sum52: 604
15% | 65 | Sum4: 42; Sum8: 89; Sum12: 134; Sum16: 181; Sum20: 228; Sum24: 275; Sum28: 321; Sum32: 368; Sum36: 414.85; Sum40: 463; Sum44: 510.85; Sum48: 556; Sum52: 604
16% | 66 | Sum4: 42; Sum8: 89; Sum12: 135; Sum16: 182; Sum20: 228; Sum24: 276; Sum28: 322; Sum32: 369; Sum36: 415.84; Sum40: 463.84; Sum44: 511; Sum48: 557; Sum52: 605
17% | 66 | Sum4: 43; Sum8: 90; Sum12: 135; Sum16: 182; Sum20: 229; Sum24: 276; Sum28: 323; Sum32: 370; Sum36: 417; Sum40: 464; Sum44: 511; Sum48: 557; Sum52: 605
18% | 66 | Sum4: 43; Sum8: 90; Sum12: 136; Sum16: 182; Sum20: 229; Sum24: 277; Sum28: 324; Sum32: 371; Sum36: 418; Sum40: 465; Sum44: 512; Sum48: 558; Sum52: 606
19% | 66 | Sum4: 43; Sum8: 90; Sum12: 136; Sum16: 183; Sum20: 230; Sum24: 277; Sum28: 324; Sum32: 371; Sum36: 418; Sum40: 465; Sum44: 513; Sum48: 559; Sum52: 606
20% | 66 | Sum4: 43.8; Sum8: 90; Sum12: 136; Sum16: 183; Sum20: 230; Sum24: 277; Sum28: 325; Sum32: 372; Sum36: 419; Sum40: 466; Sum44: 514; Sum48: 559; Sum52: 607
21% | 67 | Sum4: 44; Sum8: 91; Sum12: 137; Sum16: 183; Sum20: 230; Sum24: 278; Sum28: 325; Sum32: 372; Sum36: 419; Sum40: 466.79; Sum44: 514; Sum48: 560; Sum52: 608
22% | 67 | Sum4: 44; Sum8: 91; Sum12: 137; Sum16: 183.78; Sum20: 231; Sum24: 278; Sum28: 325; Sum32: 372; Sum36: 420; Sum40: 467; Sum44: 515; Sum48: 560; Sum52: 608
23% | 67 | Sum4: 44; Sum8: 91; Sum12: 137; Sum16: 184; Sum20: 231; Sum24: 278; Sum28: 326; Sum32: 373; Sum36: 420; Sum40: 468; Sum44: 515; Sum48: 561; Sum52: 608
24% | 68 | Sum4: 44; Sum8: 91; Sum12: 137; Sum16: 184; Sum20: 232; Sum24: 279; Sum28: 326; Sum32: 373; Sum36: 420.76; Sum40: 468; Sum44: 515; Sum48: 562; Sum52: 609
25% | 68 | Sum4: 44; Sum8: 91; Sum12: 138; Sum16: 185; Sum20: 232; Sum24: 279; Sum28: 327; Sum32: 373; Sum36: 421; Sum40: 468.75; Sum44: 516; Sum48: 562; Sum52: 610
26% | 68 | Sum4: 45; Sum8: 92; Sum12: 138; Sum16: 185; Sum20: 232; Sum24: 279.74; Sum28: 328; Sum32: 374; Sum36: 421.74; Sum40: 469; Sum44: 516.74; Sum48: 563; Sum52: 611
27% | 68 | Sum4: 45; Sum8: 92; Sum12: 138; Sum16: 185; Sum20: 233; Sum24: 280; Sum28: 328; Sum32: 375; Sum36: 422; Sum40: 470; Sum44: 517; Sum48: 564; Sum52: 611
28% | 68 | Sum4: 45; Sum8: 92; Sum12: 138; Sum16: 186; Sum20: 233; Sum24: 280; Sum28: 328; Sum32: 375; Sum36: 423; Sum40: 470; Sum44: 517; Sum48: 564; Sum52: 612
29% | 69 | Sum4: 45; Sum8: 92; Sum12: 139; Sum16: 186; Sum20: 234; Sum24: 280.71; Sum28: 329; Sum32: 376; Sum36: 423; Sum40: 471; Sum44: 518; Sum48: 564.71; Sum52: 613
30% | 69 | Sum4: 45; Sum8: 92; Sum12: 139; Sum16: 186; Sum20: 234; Sum24: 281; Sum28: 329; Sum32: 376; Sum36: 424; Sum40: 471; Sum44: 518; Sum48: 565; Sum52: 613
31% | 69 | Sum4: 45; Sum8: 92; Sum12: 139; Sum16: 187; Sum20: 234; Sum24: 281; Sum28: 330; Sum32: 377; Sum36: 424; Sum40: 472; Sum44: 518.69; Sum48: 566; Sum52: 614
32% | 69 | Sum4: 45; Sum8: 92.68; Sum12: 140; Sum16: 187; Sum20: 235; Sum24: 281; Sum28: 330; Sum32: 377; Sum36: 424; Sum40: 473; Sum44: 519; Sum48: 567; Sum52: 614
33% | 70 | Sum4: 46; Sum8: 93; Sum12: 140; Sum16: 187; Sum20: 235; Sum24: 282; Sum28: 330; Sum32: 378; Sum36: 424.67; Sum40: 473; Sum44: 519; Sum48: 567.67; Sum52: 615
34% | 70 | Sum4: 46; Sum8: 93; Sum12: 140; Sum16: 187; Sum20: 235; Sum24: 282; Sum28: 331; Sum32: 378.66; Sum36: 425; Sum40: 474; Sum44: 520.66; Sum48: 568; Sum52: 616
35% | 70 | Sum4: 46; Sum8: 93; Sum12: 140; Sum16: 188; Sum20: 236; Sum24: 283; Sum28: 331; Sum32: 379; Sum36: 425; Sum40: 474; Sum44: 521; Sum48: 569; Sum52: 616.65
36% | 70 | Sum4: 46; Sum8: 93; Sum12: 141; Sum16: 188; Sum20: 236; Sum24: 283.64; Sum28: 332; Sum32: 379; Sum36: 426; Sum40: 474.64; Sum44: 522; Sum48: 570; Sum52: 618
37% | 70 | Sum4: 46; Sum8: 93; Sum12: 141; Sum16: 188; Sum20: 236; Sum24: 284; Sum28: 332; Sum32: 380; Sum36: 427; Sum40: 475; Sum44: 522; Sum48: 570.63; Sum52: 618
38% | 70 | Sum4: 46; Sum8: 94; Sum12: 141; Sum16: 188; Sum20: 237; Sum24: 284; Sum28: 332; Sum32: 380; Sum36: 428; Sum40: 476; Sum44: 523; Sum48: 571; Sum52: 619
39% | 70 | Sum4: 46; Sum8: 94; Sum12: 141; Sum16: 189; Sum20: 237; Sum24: 285; Sum28: 332; Sum32: 381; Sum36: 428; Sum40: 476; Sum44: 523.61; Sum48: 572; Sum52: 620
40% | 71 | Sum4: 46; Sum8: 94; Sum12: 142; Sum16: 189; Sum20: 237; Sum24: 285; Sum28: 333; Sum32: 381; Sum36: 429; Sum40: 477; Sum44: 524; Sum48: 572; Sum52: 620
41% | 71 | Sum4: 46; Sum8: 94; Sum12: 142; Sum16: 189; Sum20: 237; Sum24: 285; Sum28: 333; Sum32: 381; Sum36: 429; Sum40: 477; Sum44: 524; Sum48: 573; Sum52: 621
42% | 71 | Sum4: 47; Sum8: 94; Sum12: 142; Sum16: 189; Sum20: 237.58; Sum24: 285; Sum28: 334; Sum32: 382; Sum36: 429; Sum40: 478; Sum44: 525; Sum48: 574; Sum52: 621
43% | 71 | Sum4: 47; Sum8: 95; Sum12: 142; Sum16: 190; Sum20: 238; Sum24: 286; Sum28: 334; Sum32: 382; Sum36: 430; Sum40: 479; Sum44: 525.57; Sum48: 574; Sum52: 622
44% | 71 | Sum4: 47; Sum8: 95; Sum12: 142; Sum16: 190; Sum20: 238; Sum24: 286; Sum28: 334; Sum32: 383; Sum36: 430.56; Sum40: 479; Sum44: 526; Sum48: 575; Sum52: 622
45% | 71 | Sum4: 47; Sum8: 95; Sum12: 143; Sum16: 190; Sum20: 239; Sum24: 286; Sum28: 334; Sum32: 383; Sum36: 431; Sum40: 479; Sum44: 526.55; Sum48: 575; Sum52: 623
46% | 71 | Sum4: 47; Sum8: 95; Sum12: 143; Sum16: 190; Sum20: 239; Sum24: 287; Sum28: 335; Sum32: 383; Sum36: 431; Sum40: 479; Sum44: 527; Sum48: 575; Sum52: 623
47% | 72 | Sum4: 47; Sum8: 96; Sum12: 143; Sum16: 191; Sum20: 239.53; Sum24: 287; Sum28: 335; Sum32: 383.53; Sum36: 432; Sum40: 480; Sum44: 528; Sum48: 576; Sum52: 623
48% | 72 | Sum4: 47; Sum8: 96; Sum12: 143; Sum16: 191; Sum20: 240; Sum24: 287.52; Sum28: 335; Sum32: 384; Sum36: 432; Sum40: 480; Sum44: 528; Sum48: 576; Sum52: 623
49% | 72 | Sum4: 47.51; Sum8: 96; Sum12: 143; Sum16: 191; Sum20: 240; Sum24: 288; Sum28: 336; Sum32: 384; Sum36: 433; Sum40: 480; Sum44: 528; Sum48: 577; Sum52: 624
50% | 72 | Sum4: 48; Sum8: 96; Sum12: 144; Sum16: 192; Sum20: 240; Sum24: 288.5; Sum28: 336; Sum32: 385; Sum36: 433; Sum40: 481; Sum44: 529; Sum48: 577; Sum52: 624
51% | 73 | Sum4: 48; Sum8: 96; Sum12: 144; Sum16: 192; Sum20: 241; Sum24: 289; Sum28: 336; Sum32: 385; Sum36: 433; Sum40: 481; Sum44: 529; Sum48: 578; Sum52: 625
52% | 73 | Sum4: 48; Sum8: 97; Sum12: 144; Sum16: 193; Sum20: 241; Sum24: 290; Sum28: 336; Sum32: 385; Sum36: 434; Sum40: 482; Sum44: 530; Sum48: 578; Sum52: 625
53% | 73 | Sum4: 48; Sum8: 97; Sum12: 144; Sum16: 193; Sum20: 241; Sum24: 290; Sum28: 337; Sum32: 385; Sum36: 434; Sum40: 482; Sum44: 531; Sum48: 578; Sum52: 626
54% | 73 | Sum4: 48; Sum8: 97; Sum12: 145; Sum16: 193; Sum20: 242; Sum24: 290; Sum28: 337; Sum32: 386; Sum36: 435; Sum40: 482; Sum44: 531; Sum48: 579; Sum52: 626
55% | 73 | Sum4: 48; Sum8: 97; Sum12: 145; Sum16: 193; Sum20: 242; Sum24: 290; Sum28: 338; Sum32: 386; Sum36: 435; Sum40: 482; Sum44: 531.45; Sum48: 579; Sum52: 627
56% | 73 | Sum4: 48; Sum8: 97; Sum12: 145; Sum16: 194; Sum20: 242; Sum24: 291; Sum28: 338; Sum32: 386; Sum36: 435.44; Sum40: 483; Sum44: 532; Sum48: 580; Sum52: 627
57% | 73 | Sum4: 49; Sum8: 98; Sum12: 145; Sum16: 194; Sum20: 243; Sum24: 291; Sum28: 338.43; Sum32: 387; Sum36: 436; Sum40: 483; Sum44: 532; Sum48: 580; Sum52: 627
58% | 73 | Sum4: 49; Sum8: 98; Sum12: 146; Sum16: 194; Sum20: 243; Sum24: 291; Sum28: 339; Sum32: 388; Sum36: 436; Sum40: 484; Sum44: 533; Sum48: 580; Sum52: 628
59% | 74 | Sum4: 49; Sum8: 98; Sum12: 146; Sum16: 194; Sum20: 243; Sum24: 291; Sum28: 339; Sum32: 388; Sum36: 437; Sum40: 485; Sum44: 533; Sum48: 581; Sum52: 628
60% | 74 | Sum4: 49; Sum8: 98; Sum12: 146; Sum16: 195; Sum20: 243; Sum24: 292; Sum28: 340; Sum32: 388; Sum36: 437; Sum40: 485; Sum44: 533.4; Sum48: 581; Sum52: 629
61% | 74 | Sum4: 49; Sum8: 98; Sum12: 146; Sum16: 195; Sum20: 243.39; Sum24: 292; Sum28: 340; Sum32: 389; Sum36: 438; Sum40: 486; Sum44: 534; Sum48: 581.39; Sum52: 629
62% | 74 | Sum4: 50; Sum8: 99; Sum12: 147; Sum16: 195; Sum20: 244; Sum24: 293; Sum28: 341; Sum32: 389; Sum36: 438; Sum40: 486; Sum44: 535; Sum48: 582; Sum52: 630
63% | 74.37 | Sum4: 50; Sum8: 99; Sum12: 147; Sum16: 195; Sum20: 244; Sum24: 293; Sum28: 341; Sum32: 389.37; Sum36: 439; Sum40: 486.37; Sum44: 535; Sum48: 582; Sum52: 631
64% | 75 | Sum4: 50; Sum8: 99; Sum12: 147; Sum16: 196; Sum20: 244; Sum24: 293.36; Sum28: 341; Sum32: 390; Sum36: 439; Sum40: 488; Sum44: 536; Sum48: 583; Sum52: 631
65% | 75 | Sum4: 50; Sum8: 99; Sum12: 147; Sum16: 196; Sum20: 245; Sum24: 294; Sum28: 342; Sum32: 390; Sum36: 439; Sum40: 488; Sum44: 536.35; Sum48: 583; Sum52: 631
66% | 75 | Sum4: 50; Sum8: 100; Sum12: 147; Sum16: 196; Sum20: 245; Sum24: 294; Sum28: 342; Sum32: 390.34; Sum36: 439.34; Sum40: 488.34; Sum44: 537; Sum48: 583.34; Sum52: 632
67% | 75 | Sum4: 50; Sum8: 100; Sum12: 147; Sum16: 197; Sum20: 246; Sum24: 294; Sum28: 343; Sum32: 391; Sum36: 440; Sum40: 489; Sum44: 538; Sum48: 585; Sum52: 633
68% | 75 | Sum4: 51; Sum8: 100; Sum12: 148; Sum16: 197; Sum20: 246; Sum24: 295; Sum28: 343; Sum32: 392; Sum36: 440; Sum40: 489; Sum44: 538; Sum48: 586; Sum52: 634
69% | 76 | Sum4: 51; Sum8: 100; Sum12: 148; Sum16: 197.31; Sum20: 246; Sum24: 295; Sum28: 344; Sum32: 392; Sum36: 441; Sum40: 489; Sum44: 539; Sum48: 586; Sum52: 634
70% | 76 | Sum4: 51; Sum8: 100; Sum12: 148; Sum16: 198; Sum20: 247; Sum24: 296; Sum28: 344; Sum32: 392.3; Sum36: 441; Sum40: 490; Sum44: 539.3; Sum48: 587; Sum52: 635
71% | 76 | Sum4: 51; Sum8: 101; Sum12: 148; Sum16: 198; Sum20: 247; Sum24: 296; Sum28: 345; Sum32: 393; Sum36: 442; Sum40: 491; Sum44: 540; Sum48: 588; Sum52: 636
72% | 76 | Sum4: 51; Sum8: 101; Sum12: 148.28; Sum16: 198; Sum20: 247.28; Sum24: 296; Sum28: 346; Sum32: 393; Sum36: 443; Sum40: 491; Sum44: 540; Sum48: 588; Sum52: 636
73% | 76 | Sum4: 51; Sum8: 101; Sum12: 149; Sum16: 198; Sum20: 248; Sum24: 296; Sum28: 347; Sum32: 394; Sum36: 443; Sum40: 492; Sum44: 541; Sum48: 589; Sum52: 637
74% | 76.26 | Sum4: 51.26; Sum8: 101; Sum12: 149; Sum16: 199; Sum20: 248; Sum24: 297; Sum28: 347; Sum32: 395; Sum36: 444; Sum40: 492; Sum44: 541; Sum48: 589; Sum52: 638
75% | 77 | Sum4: 52; Sum8: 102; Sum12: 149.25; Sum16: 199; Sum20: 249; Sum24: 297; Sum28: 347; Sum32: 395; Sum36: 444; Sum40: 493; Sum44: 542; Sum48: 590; Sum52: 638
76% | 77 | Sum4: 52; Sum8: 102; Sum12: 150; Sum16: 199; Sum20: 249; Sum24: 298; Sum28: 348; Sum32: 396; Sum36: 445; Sum40: 493; Sum44: 542; Sum48: 591; Sum52: 638
77% | 77 | Sum4: 52; Sum8: 102; Sum12: 150; Sum16: 200; Sum20: 249; Sum24: 299; Sum28: 348; Sum32: 396.23; Sum36: 445; Sum40: 494; Sum44: 543; Sum48: 591; Sum52: 639
78% | 77 | Sum4: 53; Sum8: 102; Sum12: 150; Sum16: 200; Sum20: 250; Sum24: 299; Sum28: 349; Sum32: 397; Sum36: 445; Sum40: 495; Sum44: 543; Sum48: 592; Sum52: 639
79% | 78 | Sum4: 53; Sum8: 103; Sum12: 151; Sum16: 201; Sum20: 250; Sum24: 300; Sum28: 349; Sum32: 398; Sum36: 446; Sum40: 496; Sum44: 544; Sum48: 593; Sum52: 640
80% | 78 | Sum4: 53; Sum8: 103; Sum12: 151; Sum16: 201; Sum20: 250.2; Sum24: 300; Sum28: 350; Sum32: 398.2; Sum36: 446; Sum40: 497; Sum44: 544; Sum48: 593; Sum52: 640
81% | 78 | Sum4: 53; Sum8: 103; Sum12: 151; Sum16: 201; Sum20: 251; Sum24: 301; Sum28: 350; Sum32: 399; Sum36: 447; Sum40: 497; Sum44: 544; Sum48: 594; Sum52: 641
82% | 79 | Sum4: 53; Sum8: 104; Sum12: 152; Sum16: 202; Sum20: 252; Sum24: 301; Sum28: 350.18; Sum32: 400; Sum36: 448; Sum40: 498; Sum44: 545; Sum48: 595; Sum52: 641
83% | 79 | Sum4: 53; Sum8: 104; Sum12: 152; Sum16: 203; Sum20: 252; Sum24: 302; Sum28: 351; Sum32: 400; Sum36: 448; Sum40: 498; Sum44: 546; Sum48: 596; Sum52: 643
84% | 79 | Sum4: 54; Sum8: 104; Sum12: 153; Sum16: 203; Sum20: 253; Sum24: 302; Sum28: 352; Sum32: 401; Sum36: 449; Sum40: 499; Sum44: 547; Sum48: 597; Sum52: 644
85% | 79 | Sum4: 54; Sum8: 104; Sum12: 154; Sum16: 204; Sum20: 253; Sum24: 303; Sum28: 352; Sum32: 401; Sum36: 450.15; Sum40: 499; Sum44: 548; Sum48: 598; Sum52: 645
86% | 80 | Sum4: 54; Sum8: 104.14; Sum12: 154; Sum16: 204; Sum20: 254; Sum24: 304; Sum28: 352; Sum32: 402; Sum36: 451; Sum40: 499; Sum44: 549; Sum48: 598; Sum52: 646
87% | 80 | Sum4: 54; Sum8: 105; Sum12: 155; Sum16: 205; Sum20: 255; Sum24: 304; Sum28: 353; Sum32: 402.13; Sum36: 451; Sum40: 500; Sum44: 549; Sum48: 598; Sum52: 647
88% | 80 | Sum4: 55; Sum8: 106; Sum12: 155; Sum16: 205; Sum20: 255; Sum24: 305; Sum28: 354; Sum32: 403; Sum36: 452; Sum40: 500.12; Sum44: 550; Sum48: 599; Sum52: 648.12
89% | 81 | Sum4: 55; Sum8: 106; Sum12: 156; Sum16: 206; Sum20: 256; Sum24: 305.11; Sum28: 354; Sum32: 403.11; Sum36: 453; Sum40: 501; Sum44: 550; Sum48: 600; Sum52: 650
90% | 81 | Sum4: 55; Sum8: 106; Sum12: 156; Sum16: 207; Sum20: 257; Sum24: 306; Sum28: 354.1; Sum32: 404; Sum36: 453.1; Sum40: 502; Sum44: 552.1; Sum48: 602; Sum52: 651
91% | 82 | Sum4: 55; Sum8: 107; Sum12: 157; Sum16: 207; Sum20: 257; Sum24: 306; Sum28: 355; Sum32: 405.09; Sum36: 454; Sum40: 504; Sum44: 554; Sum48: 602; Sum52: 651
92% | 82 | Sum4: 56; Sum8: 107; Sum12: 157.08; Sum16: 207; Sum20: 258; Sum24: 307; Sum28: 356; Sum32: 406; Sum36: 455; Sum40: 505; Sum44: 555; Sum48: 603; Sum52: 652
93% | 83 | Sum4: 56; Sum8: 108; Sum12: 158; Sum16: 208; Sum20: 258; Sum24: 308; Sum28: 357; Sum32: 407; Sum36: 457; Sum40: 505; Sum44: 556; Sum48: 605; Sum52: 653.07
94% | 83 | Sum4: 57; Sum8: 108; Sum12: 159; Sum16: 208; Sum20: 259.06; Sum24: 308; Sum28: 358; Sum32: 410; Sum36: 458; Sum40: 506.06; Sum44: 557; Sum48: 606; Sum52: 655
95% | 84 | Sum4: 57; Sum8: 108; Sum12: 160; Sum16: 209; Sum20: 260; Sum24: 309; Sum28: 359; Sum32: 411; Sum36: 459; Sum40: 508.05; Sum44: 557; Sum48: 607; Sum52: 656.05
96% | 84 | Sum4: 57.04; Sum8: 109; Sum12: 160.04; Sum16: 210; Sum20: 261; Sum24: 310; Sum28: 360.04; Sum32: 411.04; Sum36: 461; Sum40: 510; Sum44: 558.04; Sum48: 608.04; Sum52: 659
97% | 85 | Sum4: 58; Sum8: 110; Sum12: 162; Sum16: 211.03; Sum20: 263; Sum24: 311; Sum28: 362; Sum32: 413.03; Sum36: 463; Sum40: 513; Sum44: 560.03; Sum48: 611; Sum52: 661
98% | 85 | Sum4: 59; Sum8: 111.02; Sum12: 162; Sum16: 213; Sum20: 264.02; Sum24: 313.04; Sum28: 363.02; Sum32: 415; Sum36: 465; Sum40: 515.02; Sum44: 563; Sum48: 612; Sum52: 663
99% | 87 | Sum4: 59; Sum8: 112; Sum12: 164; Sum16: 216; Sum20: 267.01; Sum24: 320; Sum28: 366.02; Sum32: 416; Sum36: 467; Sum40: 521; Sum44: 568; Sum48: 617.01; Sum52: 666.02
100% | 92 | Sum4: 62; Sum8: 117; Sum12: 168; Sum16: 225; Sum20: 278; Sum24: 325; Sum28: 379; Sum32: 434; Sum36: 486; Sum40: 535; Sum44: 582; Sum48: 628; Sum52: 678