## Instructions
Single Feature Forecaster or Throughput Forecaster
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
| 2 | 2018-01-17 | Refactored to support Excel 2007+ in all formulas
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). That's the odds of a coin-toss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for converting story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
About me….
I develop and teach how to use data in software development and operations teams for coaching or forecasting.
- Forecasting using Data workshop. Teach how to use these spreadsheets with practical hands-on examples based on your (and my) specific examples. Often run internally, sometimes publically.
- Data Driven Coaching workshop. Teach how to develop data driven approaches to improvement based on balancing multiple competing metrics. Often run internally, sometimes publically.
- Custom Dashboards or giving advice on your current dashboards. Take the next step in customizing our spreadsheets or deploying more advanced versions in Tableau or Power BI.
- Quantitative consulting or advice - give me a chance to answer something you need to know. I'll work with your teams in designing a prediction system or delivering a compelling visual demonstrting the issues.
Interested in chatting? Email me at troy.magennis@focusedobjective.com
Interested in stalking? Follow me on twitter @t_magennis
(best way to hear about new and improved spreadsheets like this)

## Forecast
Forecast Completion Date | [8 empty] | Results
Duration in
1. Start Date |  |  | 2019-01-01 | [5 empty] | Likelihood | 2 weeks's | Date
[9 empty] | 100% | 14 | 2019-07-16
2. How many stories are remaining to be completed? | [8 empty] | 95% | 9 | 2019-05-07
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [8 empty] | 90% | 8 | 2019-04-23
| Low guess |  | 108 |  | Highest guess |  | 108 |  | 85% | 7 | 2019-04-09
[9 empty] | 80% | 6 | 2019-03-26
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [8 empty] | 75% | 5 | 2019-03-12
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [8 empty] | 70% | 5 | 2019-03-12
| Low guess |  | 1 |  | Highest guess |  | 1 |  | 65% | 5 | 2019-03-12
[9 empty] | 60% | 4 | 2019-02-26
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [8 empty] | 55% | 4 | 2019-02-26
[9 empty] | 50% | 4 | 2019-02-26
Throughput/velocity data or estimate is for |  |  |  | 2 weeks | 14 | days |  |  | 45% | 4 | 2019-02-26
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | Sample Data Stability | 40% | 3 | 2019-02-12
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Data | 19.41% | 35% | 3 | 2019-02-12
[8 empty] | < 10% Great, < 25% Good | 30% | 3 | 2019-02-12
[9 empty] | 25% | 3 | 2019-02-12
| Low guess |  | 8 |  | Highest guess |  | 16 |  | 20% | 2 | 2019-01-29
[9 empty] | 15% | 2 | 2019-01-29
[9 empty] | 10% | 2 | 2019-01-29
[9 empty] | 5% | 2 | 2019-01-29
[9 empty] | 0% | 2 | 2019-01-29
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 2 weekss |  | Result: Total Pre-split Stories in 6 2 weekss
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 55.95
[5 empty] | 85% | 118.85 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 349
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I16: Author: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks (hidden)
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 2 weeks's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 108
30% | 10 | 15 | Server performance issues | duration at 85th P | 7
15% | 5 | 10 | Layout issues when text localized | count per period | 15.4286
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For example, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
2 | 2 | 2
71 | 1 | 5
4 | 1 | 3
79 | 2 | 6
0 | 1 | 1
40 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 5 | 3 | 3 | 0
|  |  | min | 0 | 0 | 2
|  |  | max | 79 | 71 | 79
|  |  | avg | 32.6667 | 25 | 40.3333 | -15.3333
|  |  | median | 22 | 4 | 40 | -36
|  |  | avg error |  |  |  | 15.3333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 19.41% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 2,71,4,79,0,40
|  |  | Data |  | 71 | 0 | 4 | 2 | 2 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="32.6666666666667" median="22">2,71,4,79,0,40</sip>
|  |  | Estimate |  | 8 | 13 | 8 | 9 | 9 | Distribution | <distribution name="dist" shape="fromSamples">2,71,4,79,0,40</distribution>
|  |  | Samples Or Data |  | 40 | 2 | 4 | 40 | 79
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many Samples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was captured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2019-01-29 | 101
[14 empty] | 2019-02-12 | 113
[14 empty] | 2019-02-26 | 106
[14 empty] | 2019-03-12 | 64
[14 empty] | 2019-03-26 | 40
[14 empty] | 2019-04-09 | 26
[14 empty] | 2019-04-23 | 22
[14 empty] | 2019-05-07 | 13
[14 empty] | 2019-05-21 | 7
[14 empty] | 2019-06-04 | 3
[14 empty] | 2019-06-18 | 5
[14 empty] | 2019-07-02 | 0
[14 empty] | 2019-07-16 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 2 weekss | 8 2 weekss | 12 2 weekss | 16 2 weekss | 20 2 weekss | 24 2 weekss | 28 2 weekss | 32 2 weekss | 36 2 weekss | 40 2 weekss | 44 2 weekss | 48 2 weekss | 52 2 weekss
95% | 12 | 124.95 | 212.9 | 321.85 | 430 | 538.9 | 652.9 | 740.95 | 871.45 | 1000.85 | 1111.8 | 1223.95 | 1347.6
85% | 76.85 | 166 | 283.85 | 399.7 | 497.85 | 620.55 | 742.85 | 864.85 | 980.85 | 1098.7 | 1220.55 | 1333 | 1454.85
5% | 238 | 427.1 | 583.05 | 740 | 927.1 | 1067.15 | 1213.05 | 1348.1 | 1503 | 1671.3 | 1842.45 | 1971 | 2096.5
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Remaining Stories Actuals (hidden)
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2019-01-01 | 27
2019-01-15 | 25
2019-01-29 | 20
2019-02-12 | 19
2019-02-26
2019-03-12
2019-03-26
2019-04-09
2019-04-23
2019-05-07
2019-05-21
2019-06-04
2019-06-18
2019-07-02
2019-07-16
2019-07-30
2019-08-13
2019-08-27
2019-09-10
2019-09-24
2019-10-08
2019-10-22
2019-11-05
2019-11-19
2019-12-03
2019-12-17
2019-12-31
2020-01-14
2020-01-28
2020-02-11
2020-02-25
2020-03-10
2020-03-24
2020-04-07
2020-04-21
2020-05-05
2020-05-19
2020-06-02
2020-06-16
2020-06-30
2020-07-14
2020-07-28
2020-08-11
2020-08-25
2020-09-08
2020-09-22
2020-10-06
2020-10-20
2020-11-03
2020-11-17
2020-12-01
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings (hidden)
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2019-01-01 to 2020-12-29
1 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 5 | 2019-03-12 | 108 | 104 | 25 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 7 | 2019-04-09 | 108 | 104 | 102 | 31 | 31 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 5 | 2019-03-12 | 108 | 106 | 35 | 35 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 9 | 2019-05-07 | 108 | 106 | 106 | 106 | 104 | 100 | 60 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 4 | 2019-02-26 | 108 | 106 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 4 | 2019-02-26 | 108 | 106 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 4 | 2019-02-26 | 108 | 104 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 8 | 2019-04-23 | 108 | 108 | 108 | 106 | 106 | 104 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 10 | 2019-05-21 | 108 | 68 | 66 | 64 | 24 | 20 | 18 | 18 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 3 | 2019-02-12 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 5 | 2019-03-12 | 108 | 106 | 27 | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 5 | 2019-03-12 | 108 | 108 | 106 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 5 | 2019-03-12 | 108 | 29 | 29 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 4 | 2019-02-26 | 108 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 4 | 2019-02-26 | 108 | 108 | 68 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 5 | 2019-03-12 | 108 | 108 | 104 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 4 | 2019-02-26 | 108 | 106 | 35 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 9 | 2019-05-07 | 108 | 106 | 104 | 104 | 102 | 62 | 58 | 56 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 5 | 2019-03-12 | 108 | 104 | 64 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 4 | 2019-02-26 | 108 | 37 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 14 | 2019-07-16 | 108 | 68 | 28 | 26 | 26 | 26 | 26 | 24 | 20 | 18 | 14 | 12 | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 6 | 2019-03-26 | 108 | 104 | 33 | 29 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 4 | 2019-02-26 | 108 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 5 | 2019-03-12 | 108 | 68 | 28 | 28 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 4 | 2019-02-26 | 108 | 108 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 6 | 2019-03-26 | 108 | 104 | 102 | 23 | 23 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 8 | 2019-04-23 | 108 | 108 | 108 | 37 | 37 | 37 | 35 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 6 | 2019-03-26 | 108 | 104 | 100 | 98 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 4 | 2019-02-26 | 108 | 29 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 3 | 2019-02-12 | 108 | 106 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 8 | 2019-04-23 | 108 | 104 | 64 | 62 | 58 | 54 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 4 | 2019-02-26 | 108 | 68 | 66 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 4 | 2019-02-26 | 108 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 11 | 2019-06-04 | 108 | 106 | 66 | 26 | 26 | 22 | 22 | 22 | 22 | 22 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 4 | 2019-02-26 | 108 | 104 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 3 | 2019-02-12 | 108 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 4 | 2019-02-26 | 108 | 104 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 9 | 2019-05-07 | 108 | 68 | 68 | 66 | 62 | 22 | 18 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 4 | 2019-02-26 | 108 | 104 | 100 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 3 | 2019-02-12 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 6 | 2019-03-26 | 108 | 104 | 100 | 100 | 98 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 6 | 2019-03-26 | 108 | 104 | 104 | 33 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 4 | 2019-02-26 | 108 | 37 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 5 | 2019-03-12 | 108 | 68 | 66 | 26 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 6 | 2019-03-26 | 108 | 104 | 33 | 33 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 5 | 2019-03-12 | 108 | 108 | 68 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 6 | 2019-03-26 | 108 | 104 | 102 | 102 | 62 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 4 | 2019-02-26 | 108 | 104 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 6 | 2019-03-26 | 108 | 106 | 102 | 102 | 31 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 4 | 2019-02-26 | 108 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 3 | 2019-02-12 | 108 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 4 | 2019-02-26 | 108 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 4 | 2019-02-26 | 108 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 5 | 2019-03-12 | 108 | 68 | 66 | 26 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 4 | 2019-02-26 | 108 | 104 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 10 | 2019-05-21 | 108 | 106 | 106 | 104 | 102 | 102 | 100 | 98 | 19 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 6 | 2019-03-26 | 108 | 108 | 37 | 35 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 12 | 2019-06-18 | 108 | 106 | 104 | 102 | 102 | 98 | 98 | 94 | 94 | 15 | 11 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 4 | 2019-02-26 | 108 | 29 | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 7 | 2019-04-09 | 108 | 108 | 106 | 106 | 102 | 98 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 4 | 2019-02-26 | 108 | 104 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 4 | 2019-02-26 | 108 | 29 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 3 | 2019-02-12 | 108 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 8 | 2019-04-23 | 108 | 104 | 102 | 102 | 62 | 58 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 7 | 2019-04-09 | 108 | 104 | 102 | 98 | 19 | 15 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 3 | 2019-02-12 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 3 | 2019-02-12 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 7 | 2019-04-09 | 108 | 108 | 104 | 100 | 21 | 21 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 4 | 2019-02-26 | 108 | 68 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 4 | 2019-02-26 | 108 | 104 | 102 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 8 | 2019-04-23 | 108 | 106 | 104 | 104 | 102 | 23 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 5 | 2019-03-12 | 108 | 29 | 27 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 5 | 2019-03-12 | 108 | 108 | 106 | 35 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 3 | 2019-02-12 | 108 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 4 | 2019-02-26 | 108 | 104 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 5 | 2019-03-12 | 108 | 104 | 64 | 24 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 4 | 2019-02-26 | 108 | 68 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 9 | 2019-05-07 | 108 | 108 | 104 | 104 | 102 | 102 | 102 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 7 | 2019-04-09 | 108 | 104 | 100 | 98 | 19 | 17 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 4 | 2019-02-26 | 108 | 104 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 5 | 2019-03-12 | 108 | 106 | 35 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 7 | 2019-04-09 | 108 | 104 | 104 | 104 | 100 | 96 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 5 | 2019-03-12 | 108 | 108 | 37 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 4 | 2019-02-26 | 108 | 68 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 3 | 2019-02-12 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 5 | 2019-03-12 | 108 | 68 | 64 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 4 | 2019-02-26 | 108 | 104 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 5 | 2019-03-12 | 108 | 106 | 35 | 35 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 5 | 2019-03-12 | 108 | 37 | 33 | 31 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 4 | 2019-02-26 | 108 | 106 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 3 | 2019-02-12 | 108 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 4 | 2019-02-26 | 108 | 106 | 66 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 4 | 2019-02-26 | 108 | 68 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 4 | 2019-02-26 | 108 | 29 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 5 | 2019-03-12 | 108 | 108 | 104 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 7 | 2019-04-09 | 108 | 37 | 35 | 33 | 31 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 9 | 2019-05-07 | 108 | 106 | 106 | 102 | 98 | 96 | 96 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 8 | 2019-04-23 | 108 | 108 | 106 | 35 | 31 | 29 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 5 | 2019-03-12 | 108 | 104 | 102 | 102 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 4 | 2019-02-26 | 108 | 37 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 4 | 2019-02-26 | 108 | 68 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 5 | 2019-03-12 | 108 | 106 | 106 | 102 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 6 | 2019-03-26 | 108 | 104 | 100 | 100 | 100 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 4 | 2019-02-26 | 108 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 4 | 2019-02-26 | 108 | 108 | 68 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 5 | 2019-03-12 | 108 | 104 | 64 | 62 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 3 | 2019-02-12 | 108 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 5 | 2019-03-12 | 108 | 104 | 102 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 5 | 2019-03-12 | 108 | 108 | 104 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 10 | 2019-05-21 | 108 | 108 | 104 | 100 | 100 | 60 | 60 | 60 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 5 | 2019-03-12 | 108 | 104 | 104 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 4 | 2019-02-26 | 108 | 108 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 4 | 2019-02-26 | 108 | 104 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 7 | 2019-04-09 | 108 | 104 | 102 | 62 | 60 | 56 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 7 | 2019-04-09 | 108 | 106 | 102 | 100 | 100 | 60 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 4 | 2019-02-26 | 108 | 68 | 66 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 6 | 2019-03-26 | 108 | 108 | 106 | 104 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 9 | 2019-05-07 | 108 | 108 | 104 | 25 | 23 | 21 | 21 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 5 | 2019-03-12 | 108 | 106 | 66 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 4 | 2019-02-26 | 108 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 6 | 2019-03-26 | 108 | 37 | 37 | 35 | 31 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 4 | 2019-02-26 | 108 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 4 | 2019-02-26 | 108 | 108 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 5 | 2019-03-12 | 108 | 37 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 5 | 2019-03-12 | 108 | 108 | 37 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 4 | 2019-02-26 | 108 | 68 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 8 | 2019-04-23 | 108 | 108 | 106 | 102 | 31 | 27 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 4 | 2019-02-26 | 108 | 108 | 68 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 5 | 2019-03-12 | 108 | 104 | 64 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 5 | 2019-03-12 | 108 | 29 | 25 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 3 | 2019-02-12 | 108 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 3 | 2019-02-12 | 108 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 3 | 2019-02-12 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 4 | 2019-02-26 | 108 | 37 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 4 | 2019-02-26 | 108 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 4 | 2019-02-26 | 108 | 68 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 6 | 2019-03-26 | 108 | 108 | 108 | 106 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 6 | 2019-03-26 | 108 | 104 | 100 | 96 | 92 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 4 | 2019-02-26 | 108 | 29 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 7 | 2019-04-09 | 108 | 104 | 102 | 100 | 96 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 8 | 2019-04-23 | 108 | 104 | 104 | 25 | 23 | 21 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 11 | 2019-06-04 | 108 | 106 | 106 | 106 | 106 | 102 | 31 | 29 | 25 | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 6 | 2019-03-26 | 108 | 68 | 68 | 68 | 28 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 5 | 2019-03-12 | 108 | 106 | 104 | 64 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 5 | 2019-03-12 | 108 | 104 | 64 | 24 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 4 | 2019-02-26 | 108 | 104 | 100 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 3 | 2019-02-12 | 108 | 68 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 5 | 2019-03-12 | 108 | 37 | 33 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 8 | 2019-04-23 | 108 | 104 | 104 | 102 | 62 | 62 | 60 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 4 | 2019-02-26 | 108 | 68 | 66 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 4 | 2019-02-26 | 108 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 6 | 2019-03-26 | 108 | 108 | 106 | 66 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 7 | 2019-04-09 | 108 | 108 | 106 | 104 | 100 | 98 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 8 | 2019-04-23 | 108 | 104 | 100 | 98 | 58 | 54 | 14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 7 | 2019-04-09 | 108 | 37 | 33 | 31 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 5 | 2019-03-12 | 108 | 68 | 68 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 9 | 2019-05-07 | 108 | 108 | 108 | 106 | 27 | 25 | 25 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 7 | 2019-04-09 | 108 | 106 | 102 | 102 | 98 | 98 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 5 | 2019-03-12 | 108 | 106 | 35 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 4 | 2019-02-26 | 108 | 37 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 3 | 2019-02-12 | 108 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 4 | 2019-02-26 | 108 | 106 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 3 | 2019-02-12 | 108 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 3 | 2019-02-12 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 4 | 2019-02-26 | 108 | 104 | 64 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 5 | 2019-03-12 | 108 | 108 | 104 | 100 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 5 | 2019-03-12 | 108 | 104 | 33 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 4 | 2019-02-26 | 108 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 12 | 2019-06-18 | 108 | 68 | 28 | 26 | 22 | 22 | 20 | 20 | 20 | 16 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 7 | 2019-04-09 | 108 | 104 | 104 | 102 | 102 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 10 | 2019-05-21 | 108 | 106 | 102 | 100 | 21 | 21 | 17 | 17 | 17 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 4 | 2019-02-26 | 108 | 104 | 100 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 3 | 2019-02-12 | 108 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 5 | 2019-03-12 | 108 | 108 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 4 | 2019-02-26 | 108 | 68 | 68 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 5 | 2019-03-12 | 108 | 106 | 27 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 6 | 2019-03-26 | 108 | 106 | 106 | 104 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 4 | 2019-02-26 | 108 | 68 | 28 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 5 | 2019-03-12 | 108 | 68 | 66 | 66 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 5 | 2019-03-12 | 108 | 68 | 66 | 62 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 6 | 2019-03-26 | 108 | 106 | 66 | 66 | 62 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 6 | 2019-03-26 | 108 | 106 | 66 | 62 | 62 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 10 | 2019-05-21 | 108 | 106 | 27 | 25 | 23 | 21 | 17 | 15 | 13 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 4 | 2019-02-26 | 108 | 106 | 35 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 4 | 2019-02-26 | 108 | 37 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 4 | 2019-02-26 | 108 | 106 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 4 | 2019-02-26 | 108 | 29 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 12 | 2019-06-18 | 108 | 108 | 108 | 108 | 108 | 68 | 64 | 64 | 64 | 60 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 9 | 2019-05-07 | 108 | 104 | 100 | 100 | 98 | 94 | 94 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 4 | 2019-02-26 | 108 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 6 | 2019-03-26 | 108 | 108 | 29 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 3 | 2019-02-12 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 4 | 2019-02-26 | 108 | 106 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 4 | 2019-02-26 | 108 | 37 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 5 | 2019-03-12 | 108 | 68 | 64 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 4 | 2019-02-26 | 108 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 8 | 2019-04-23 | 108 | 104 | 102 | 23 | 19 | 15 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 8 | 2019-04-23 | 108 | 106 | 106 | 104 | 100 | 98 | 94 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 4 | 2019-02-26 | 108 | 104 | 64 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 3 | 2019-02-12 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 11 | 2019-06-04 | 108 | 104 | 104 | 100 | 98 | 96 | 92 | 90 | 90 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 6 | 2019-03-26 | 108 | 108 | 108 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 6 | 2019-03-26 | 108 | 106 | 66 | 26 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 3 | 2019-02-12 | 108 | 68 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 7 | 2019-04-09 | 108 | 68 | 68 | 64 | 62 | 60 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 6 | 2019-03-26 | 108 | 104 | 102 | 102 | 31 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 3 | 2019-02-12 | 108 | 68 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 3 | 2019-02-12 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 5 | 2019-03-12 | 108 | 106 | 66 | 62 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 5 | 2019-03-12 | 108 | 108 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 6 | 2019-03-26 | 108 | 106 | 102 | 62 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 7 | 2019-04-09 | 108 | 104 | 64 | 62 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 9 | 2019-05-07 | 108 | 108 | 108 | 106 | 104 | 100 | 100 | 98 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 3 | 2019-02-12 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 8 | 2019-04-23 | 108 | 106 | 104 | 104 | 100 | 60 | 60 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 5 | 2019-03-12 | 108 | 106 | 104 | 64 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 12 | 2019-06-18 | 108 | 108 | 108 | 106 | 106 | 102 | 98 | 96 | 96 | 25 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 5 | 2019-03-12 | 108 | 106 | 104 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 3 | 2019-02-12 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 4 | 2019-02-26 | 108 | 106 | 66 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 4 | 2019-02-26 | 108 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 8 | 2019-04-23 | 108 | 104 | 104 | 104 | 104 | 102 | 100 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 5 | 2019-03-12 | 108 | 106 | 35 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 4 | 2019-02-26 | 108 | 106 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 7 | 2019-04-09 | 108 | 104 | 64 | 64 | 62 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 4 | 2019-02-26 | 108 | 29 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 9 | 2019-05-07 | 108 | 106 | 102 | 98 | 94 | 54 | 50 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 4 | 2019-02-26 | 108 | 106 | 102 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 6 | 2019-03-26 | 108 | 106 | 27 | 27 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 3 | 2019-02-12 | 108 | 104 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 5 | 2019-03-12 | 108 | 106 | 102 | 62 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 4 | 2019-02-26 | 108 | 68 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 7 | 2019-04-09 | 108 | 29 | 29 | 25 | 23 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 4 | 2019-02-26 | 108 | 104 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 6 | 2019-03-26 | 108 | 106 | 35 | 31 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 5 | 2019-03-12 | 108 | 108 | 104 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 3 | 2019-02-12 | 108 | 106 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 10 | 2019-05-21 | 108 | 106 | 102 | 102 | 102 | 100 | 100 | 100 | 98 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 5 | 2019-03-12 | 108 | 68 | 68 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 4 | 2019-02-26 | 108 | 37 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 6 | 2019-03-26 | 108 | 108 | 68 | 64 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 6 | 2019-03-26 | 108 | 106 | 106 | 106 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 4 | 2019-02-26 | 108 | 29 | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 3 | 2019-02-12 | 108 | 106 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 5 | 2019-03-12 | 108 | 108 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 5 | 2019-03-12 | 108 | 68 | 64 | 60 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 3 | 2019-02-12 | 108 | 104 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 9 | 2019-05-07 | 108 | 68 | 64 | 62 | 22 | 20 | 16 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 8 | 2019-04-23 | 108 | 108 | 106 | 66 | 64 | 60 | 56 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 8 | 2019-04-23 | 108 | 106 | 106 | 104 | 25 | 25 | 23 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 6 | 2019-03-26 | 108 | 68 | 28 | 28 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 4 | 2019-02-26 | 108 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 7 | 2019-04-09 | 108 | 106 | 27 | 23 | 19 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 5 | 2019-03-12 | 108 | 68 | 66 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 4 | 2019-02-26 | 108 | 37 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 4 | 2019-02-26 | 108 | 37 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 9 | 2019-05-07 | 108 | 104 | 102 | 98 | 58 | 56 | 56 | 52 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 8 | 2019-04-23 | 108 | 108 | 68 | 66 | 62 | 22 | 20 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 7 | 2019-04-09 | 108 | 106 | 102 | 23 | 23 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 6 | 2019-03-26 | 108 | 106 | 102 | 31 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 12 | 2019-06-18 | 108 | 104 | 64 | 62 | 60 | 56 | 16 | 12 | 10 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 4 | 2019-02-26 | 108 | 37 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 7 | 2019-04-09 | 108 | 108 | 37 | 37 | 35 | 35 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 3 | 2019-02-12 | 108 | 106 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 4 | 2019-02-26 | 108 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 4 | 2019-02-26 | 108 | 68 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 7 | 2019-04-09 | 108 | 104 | 100 | 96 | 94 | 23 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 4 | 2019-02-26 | 108 | 29 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 4 | 2019-02-26 | 108 | 37 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 4 | 2019-02-26 | 108 | 104 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 4 | 2019-02-26 | 108 | 106 | 35 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 3 | 2019-02-12 | 108 | 68 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 3 | 2019-02-12 | 108 | 106 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 6 | 2019-03-26 | 108 | 106 | 66 | 62 | 22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 4 | 2019-02-26 | 108 | 29 | 27 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 4 | 2019-02-26 | 108 | 104 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 4 | 2019-02-26 | 108 | 68 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 6 | 2019-03-26 | 108 | 104 | 104 | 102 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 4 | 2019-02-26 | 108 | 106 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 3 | 2019-02-12 | 108 | 37 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 3 | 2019-02-12 | 108 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 6 | 2019-03-26 | 108 | 68 | 66 | 62 | 58 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 4 | 2019-02-26 | 108 | 108 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 8 | 2019-04-23 | 108 | 68 | 64 | 60 | 58 | 56 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 7 | 2019-04-09 | 108 | 106 | 104 | 100 | 100 | 96 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 5 | 2019-03-12 | 108 | 108 | 68 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 4 | 2019-02-26 | 108 | 37 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 8 | 2019-04-23 | 108 | 104 | 64 | 62 | 62 | 22 | 22 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 4 | 2019-02-26 | 108 | 106 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 4 | 2019-02-26 | 108 | 37 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 5 | 2019-03-12 | 108 | 108 | 104 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 5 | 2019-03-12 | 108 | 29 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 5 | 2019-03-12 | 108 | 106 | 104 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 3 | 2019-02-12 | 108 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 5 | 2019-03-12 | 108 | 68 | 66 | 62 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 6 | 2019-03-26 | 108 | 106 | 106 | 102 | 62 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 4 | 2019-02-26 | 108 | 104 | 102 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 3 | 2019-02-12 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 3 | 2019-02-12 | 108 | 68 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 8 | 2019-04-23 | 108 | 106 | 102 | 98 | 96 | 94 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 6 | 2019-03-26 | 108 | 108 | 68 | 64 | 64 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 8 | 2019-04-23 | 108 | 106 | 106 | 102 | 31 | 29 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 6 | 2019-03-26 | 108 | 104 | 104 | 104 | 33 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 3 | 2019-02-12 | 108 | 68 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 6 | 2019-03-26 | 108 | 29 | 29 | 25 | 25 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 3 | 2019-02-12 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 4 | 2019-02-26 | 108 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 3 | 2019-02-12 | 108 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 7 | 2019-04-09 | 108 | 104 | 102 | 62 | 60 | 56 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 9 | 2019-05-07 | 108 | 104 | 100 | 98 | 98 | 58 | 54 | 54 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 6 | 2019-03-26 | 108 | 104 | 100 | 60 | 58 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 2 | 2019-01-29 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 3 | 2019-02-12 | 108 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 4 | 2019-02-26 | 108 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 6 | 2019-03-26 | 108 | 104 | 102 | 98 | 98 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 6 | 2019-03-26 | 108 | 108 | 29 | 25 | 25 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 4 | 2019-02-26 | 108 | 104 | 33 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 4 | 2019-02-26 | 108 | 104 | 102 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 7 | 2019-04-09 | 108 | 106 | 106 | 104 | 64 | 64 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 4 | 2019-02-26 | 108 | 29 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 3 | 2019-02-12 | 108 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 5 | 2019-03-12 | 108 | 104 | 33 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 4 | 2019-02-26 | 108 | 108 | 108 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 2 | 2019-01-29 | 108 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 10 | 2019-05-21 | 108 | 108 | 104 | 100 | 60 | 60 | 56 | 52 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 5 | 2019-03-12 | 108 | 106 | 104 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 3 | 2019-02-12 | 108 | 106 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 3 | 2019-02-12 | 108 | 29 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 5 | 2019-03-12 | 108 | 29 | 25 | 23 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 7 | 2019-04-09 | 108 | 104 | 104 | 104 | 102 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 5 | 2019-03-12 | 108 | 104 | 104 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 8 | 2019-04-23 | 108 | 37 | 37 | 35 | 31 | 29 | 27 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 3 | 2019-02-12 | 108 | 29 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 2 | 2019-01-29 | 108 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 4 | 2019-02-26 | 108 | 106 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 4 | 2019-02-26 | 108 | 106 | 104 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 5 | 2019-03-12 | 108 | 68 | 28 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 3 | 2019-02-12 | 108 | 37 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 166 | 85 | 249 | 479 | 553 | 717 | 729 | 982 | 1057 | 1249 | 1451 | 1606 | 1691 | 1805 | 40 | 1 | 40 | 4 | 79 | 2 | 4 | 79 | 1 | 71 | 79 | 79 | 71 | 1 | 1 | 1 | 79 | 4 | 2 | 79 | 2 | 4 | 2 | 4 | 40 | 71 | 71 | 71 | 2 | 1 | 1 | 71 | 2 | 71 | 40 | 79 | 79 | 79 | 40 | 4 | 40 | 4 | 71 | 40 | 1 | 1 | 79 | 4 | 1 | 71 | 40 | 2
2 | 237 | 233 | 356 | 434 | 479 | 600 | 680 | 871 | 1032 | 1119 | 1128 | 1359 | 1550 | 1702 | 4 | 71 | 79 | 79 | 2 | 2 | 79 | 40 | 1 | 4 | 2 | 71 | 2 | 40 | 1 | 2 | 1 | 40 | 40 | 40 | 4 | 4 | 1 | 71 | 40 | 1 | 79 | 71 | 40 | 2 | 79 | 40 | 79 | 2 | 4 | 2 | 2 | 4 | 1 | 2 | 79 | 71 | 2 | 79 | 1 | 40 | 71 | 79 | 71 | 40 | 1 | 40
3 | 168 | 163 | 249 | 296 | 529 | 612 | 764 | 849 | 1080 | 1202 | 1279 | 1470 | 1618 | 1665 | 40 | 4 | 79 | 40 | 4 | 1 | 2 | 79 | 40 | 4 | 2 | 1 | 79 | 4 | 79 | 71 | 1 | 1 | 79 | 2 | 40 | 40 | 1 | 71 | 1 | 4 | 40 | 40 | 79 | 2 | 71 | 79 | 2 | 40 | 79 | 1 | 1 | 4 | 71 | 1 | 71 | 40 | 40 | 40 | 4 | 71 | 71 | 2 | 4 | 2 | 1 | 40
4 | 271 | 160 | 275 | 389 | 545 | 744 | 826 | 1043 | 1051 | 1253 | 1407 | 1418 | 1504 | 1652 | 40 | 1 | 40 | 79 | 40 | 71 | 2 | 2 | 1 | 2 | 71 | 40 | 2 | 79 | 71 | 4 | 40 | 40 | 40 | 79 | 1 | 1 | 40 | 40 | 71 | 71 | 71 | 4 | 2 | 4 | 1 | 1 | 4 | 79 | 79 | 40 | 2 | 71 | 79 | 2 | 4 | 1 | 4 | 2 | 2 | 79 | 1 | 4 | 2 | 4 | 71 | 71
5 | 205 | 200 | 316 | 392 | 607 | 732 | 848 | 932 | 1085 | 1163 | 1355 | 1476 | 1632 | 1718 | 40 | 79 | 79 | 2 | 4 | 1 | 40 | 71 | 71 | 2 | 1 | 2 | 71 | 2 | 71 | 71 | 40 | 4 | 79 | 2 | 1 | 4 | 71 | 40 | 2 | 79 | 1 | 2 | 40 | 71 | 2 | 40 | 2 | 4 | 71 | 1 | 40 | 2 | 79 | 71 | 40 | 1 | 1 | 79 | 4 | 2 | 79 | 71 | 40 | 4 | 2 | 40
6 | 334 | 184 | 337 | 461 | 583 | 594 | 809 | 993 | 1185 | 1229 | 1240 | 1314 | 1506 | 1558 | 71 | 40 | 2 | 71 | 71 | 79 | 2 | 1 | 79 | 1 | 40 | 4 | 79 | 2 | 1 | 40 | 4 | 1 | 4 | 2 | 71 | 71 | 71 | 2 | 40 | 71 | 2 | 71 | 79 | 40 | 71 | 2 | 2 | 40 | 1 | 1 | 1 | 4 | 4 | 2 | 71 | 1 | 1 | 1 | 2 | 79 | 71 | 40 | 4 | 40 | 4 | 4
7 | 157 | 85 | 230 | 307 | 384 | 464 | 508 | 672 | 855 | 861 | 978 | 1063 | 1249 | 1396 | 1 | 79 | 4 | 1 | 71 | 1 | 71 | 2 | 71 | 1 | 4 | 1 | 71 | 4 | 1 | 1 | 71 | 4 | 4 | 1 | 2 | 1 | 1 | 40 | 4 | 2 | 79 | 79 | 71 | 1 | 71 | 40 | 1 | 1 | 2 | 2 | 40 | 2 | 4 | 71 | 1 | 4 | 1 | 79 | 71 | 4 | 71 | 40 | 4 | 71 | 1 | 71
8 | 158 | 156 | 164 | 211 | 375 | 449 | 533 | 802 | 812 | 956 | 1081 | 1275 | 1388 | 1470 | 2 | 71 | 4 | 79 | 1 | 1 | 2 | 4 | 1 | 2 | 4 | 40 | 79 | 79 | 4 | 2 | 1 | 1 | 71 | 1 | 1 | 2 | 2 | 79 | 71 | 40 | 79 | 79 | 4 | 4 | 1 | 1 | 71 | 1 | 1 | 71 | 79 | 40 | 4 | 2 | 40 | 79 | 4 | 71 | 40 | 1 | 1 | 71 | 1 | 79 | 1 | 1
9 | 325 | 253 | 328 | 488 | 718 | 794 | 800 | 1061 | 1252 | 1490 | 1574 | 1851 | 1859 | 2082 | 71 | 40 | 71 | 71 | 71 | 1 | 1 | 2 | 79 | 40 | 40 | 1 | 79 | 1 | 79 | 71 | 71 | 1 | 2 | 2 | 2 | 1 | 1 | 2 | 71 | 71 | 40 | 79 | 71 | 40 | 40 | 40 | 40 | 79 | 40 | 79 | 2 | 40 | 2 | 40 | 79 | 79 | 40 | 79 | 1 | 1 | 2 | 4 | 2 | 71 | 79 | 71
10 | 155 | 113 | 196 | 357 | 626 | 786 | 1016 | 1161 | 1325 | 1517 | 1778 | 1972 | 2194 | 2347 | 1 | 71 | 1 | 40 | 40 | 2 | 1 | 40 | 79 | 79 | 2 | 1 | 40 | 71 | 79 | 79 | 40 | 79 | 1 | 40 | 71 | 79 | 1 | 79 | 71 | 71 | 2 | 1 | 79 | 79 | 4 | 2 | 79 | 71 | 40 | 2 | 71 | 79 | 71 | 40 | 79 | 40 | 71 | 4 | 40 | 71 | 40 | 71 | 2 | 71 | 79 | 1
11 | 84 | 78 | 167 | 286 | 442 | 520 | 820 | 908 | 1146 | 1231 | 1239 | 1325 | 1339 | 1531 | 71 | 1 | 2 | 4 | 2 | 4 | 79 | 4 | 4 | 4 | 71 | 40 | 2 | 4 | 79 | 71 | 71 | 2 | 4 | 1 | 79 | 71 | 71 | 79 | 4 | 40 | 40 | 4 | 40 | 79 | 40 | 79 | 40 | 40 | 4 | 1 | 2 | 2 | 2 | 2 | 1 | 79 | 2 | 4 | 4 | 4 | 2 | 4 | 2 | 71 | 40 | 79
12 | 344 | 225 | 486 | 642 | 730 | 960 | 1043 | 1195 | 1204 | 1212 | 1404 | 1490 | 1498 | 1614 | 4 | 71 | 71 | 79 | 40 | 79 | 71 | 71 | 79 | 4 | 2 | 71 | 79 | 1 | 4 | 4 | 40 | 79 | 40 | 71 | 2 | 1 | 1 | 79 | 71 | 40 | 1 | 40 | 4 | 1 | 2 | 2 | 1 | 1 | 2 | 4 | 71 | 40 | 2 | 79 | 40 | 4 | 40 | 2 | 2 | 1 | 1 | 4 | 40 | 4 | 71 | 1
13 | 118 | 46 | 124 | 241 | 397 | 591 | 639 | 823 | 983 | 1100 | 1294 | 1519 | 1641 | 1766 | 2 | 2 | 40 | 2 | 71 | 1 | 4 | 2 | 2 | 71 | 4 | 40 | 4 | 2 | 79 | 71 | 79 | 4 | 71 | 40 | 2 | 4 | 2 | 40 | 2 | 71 | 71 | 40 | 40 | 40 | 1 | 79 | 4 | 71 | 2 | 40 | 4 | 71 | 40 | 79 | 71 | 71 | 4 | 79 | 40 | 2 | 40 | 40 | 4 | 2 | 40 | 79
14 | 55 | 50 | 166 | 366 | 513 | 589 | 741 | 815 | 896 | 1173 | 1220 | 1266 | 1460 | 1644 | 4 | 40 | 2 | 4 | 4 | 1 | 40 | 71 | 2 | 79 | 79 | 40 | 71 | 1 | 4 | 71 | 1 | 2 | 2 | 71 | 71 | 1 | 79 | 1 | 1 | 71 | 1 | 1 | 4 | 4 | 71 | 2 | 40 | 79 | 79 | 79 | 4 | 1 | 40 | 2 | 1 | 40 | 4 | 1 | 4 | 40 | 79 | 71 | 40 | 71 | 2 | 71
15 | 305 | 155 | 308 | 429 | 584 | 700 | 856 | 863 | 907 | 992 | 1114 | 1164 | 1356 | 1483 | 79 | 4 | 1 | 71 | 71 | 79 | 1 | 2 | 40 | 1 | 1 | 79 | 4 | 1 | 79 | 71 | 40 | 4 | 1 | 71 | 2 | 71 | 79 | 4 | 1 | 1 | 4 | 1 | 40 | 1 | 2 | 1 | 1 | 1 | 79 | 4 | 40 | 2 | 79 | 1 | 2 | 40 | 4 | 4 | 2 | 79 | 71 | 40 | 40 | 4 | 4 | 79
16 | 186 | 75 | 261 | 416 | 600 | 760 | 910 | 960 | 1115 | 1268 | 1351 | 1566 | 1760 | 1991 | 1 | 71 | 2 | 1 | 71 | 40 | 4 | 71 | 79 | 4 | 1 | 71 | 40 | 2 | 71 | 71 | 79 | 79 | 1 | 1 | 4 | 4 | 71 | 71 | 4 | 2 | 4 | 40 | 71 | 79 | 4 | 1 | 2 | 1 | 71 | 79 | 79 | 1 | 2 | 1 | 71 | 71 | 71 | 2 | 79 | 71 | 40 | 4 | 2 | 79 | 79 | 71
17 | 126 | 124 | 134 | 297 | 411 | 526 | 651 | 835 | 962 | 1192 | 1453 | 1644 | 1869 | 2052 | 40 | 1 | 79 | 4 | 1 | 1 | 4 | 4 | 40 | 79 | 4 | 40 | 2 | 71 | 40 | 1 | 2 | 2 | 40 | 71 | 2 | 4 | 40 | 79 | 2 | 71 | 40 | 71 | 4 | 4 | 79 | 40 | 71 | 1 | 79 | 79 | 71 | 40 | 71 | 79 | 71 | 1 | 40 | 79 | 79 | 71 | 71 | 4 | 1 | 40 | 71 | 71
18 | 357 | 238 | 399 | 562 | 644 | 877 | 951 | 1042 | 1125 | 1137 | 1264 | 1487 | 1611 | 1656 | 79 | 40 | 40 | 79 | 79 | 40 | 40 | 2 | 79 | 40 | 40 | 4 | 1 | 1 | 40 | 40 | 79 | 71 | 79 | 4 | 1 | 71 | 1 | 1 | 4 | 4 | 4 | 79 | 40 | 40 | 1 | 2 | 2 | 4 | 2 | 4 | 79 | 4 | 4 | 40 | 71 | 79 | 2 | 71 | 1 | 4 | 79 | 40 | 2 | 2 | 1 | 40
19 | 151 | 79 | 309 | 430 | 555 | 669 | 784 | 791 | 918 | 1071 | 1257 | 1372 | 1454 | 1537 | 71 | 2 | 4 | 2 | 71 | 1 | 79 | 79 | 79 | 1 | 1 | 40 | 2 | 40 | 4 | 79 | 2 | 40 | 71 | 1 | 2 | 2 | 40 | 71 | 2 | 2 | 1 | 2 | 4 | 4 | 79 | 40 | 2 | 40 | 71 | 40 | 71 | 40 | 71 | 4 | 40 | 2 | 2 | 71 | 79 | 1 | 1 | 1 | 1 | 2 | 79 | 1
20 | 313 | 194 | 455 | 617 | 695 | 708 | 794 | 872 | 955 | 1115 | 1198 | 1398 | 1592 | 1639 | 40 | 4 | 79 | 71 | 40 | 79 | 71 | 71 | 2 | 2 | 79 | 79 | 1 | 71 | 2 | 4 | 4 | 1 | 4 | 4 | 1 | 2 | 79 | 4 | 1 | 2 | 4 | 71 | 2 | 1 | 1 | 79 | 79 | 1 | 40 | 40 | 79 | 1 | 1 | 2 | 2 | 40 | 79 | 79 | 40 | 4 | 79 | 71 | 1 | 2 | 4 | 40
21 | 53 | 49 | 126 | 203 | 319 | 405 | 630 | 782 | 981 | 1027 | 1250 | 1337 | 1500 | 1624 | 1 | 4 | 40 | 4 | 2 | 2 | 2 | 71 | 4 | 1 | 71 | 1 | 71 | 1 | 4 | 40 | 40 | 40 | 4 | 2 | 79 | 71 | 4 | 71 | 40 | 71 | 1 | 40 | 40 | 1 | 79 | 79 | 4 | 1 | 40 | 1 | 71 | 2 | 79 | 71 | 2 | 2 | 4 | 79 | 79 | 4 | 40 | 40 | 4 | 1 | 79 | 40
22 | 228 | 153 | 236 | 453 | 645 | 800 | 847 | 1163 | 1311 | 1316 | 1510 | 1740 | 1903 | 2056 | 71 | 79 | 2 | 1 | 4 | 71 | 4 | 4 | 4 | 71 | 71 | 71 | 40 | 2 | 79 | 71 | 4 | 71 | 79 | 1 | 40 | 1 | 4 | 2 | 79 | 79 | 79 | 79 | 2 | 71 | 4 | 71 | 1 | 1 | 1 | 2 | 79 | 4 | 40 | 71 | 71 | 79 | 79 | 1 | 79 | 79 | 1 | 4 | 40 | 2 | 40 | 71
23 | 227 | 85 | 230 | 318 | 510 | 594 | 827 | 943 | 1127 | 1242 | 1388 | 1540 | 1700 | 1902 | 4 | 1 | 79 | 1 | 71 | 71 | 1 | 2 | 4 | 1 | 79 | 4 | 2 | 79 | 71 | 40 | 79 | 2 | 1 | 2 | 79 | 71 | 4 | 79 | 1 | 71 | 40 | 4 | 71 | 2 | 40 | 71 | 40 | 2 | 71 | 2 | 71 | 2 | 2 | 71 | 1 | 71 | 79 | 1 | 1 | 79 | 40 | 40 | 79 | 4 | 40 | 79
24 | 159 | 117 | 278 | 438 | 590 | 673 | 756 | 995 | 1117 | 1201 | 1284 | 1406 | 1522 | 1783 | 71 | 4 | 40 | 2 | 40 | 2 | 79 | 40 | 79 | 1 | 40 | 40 | 1 | 71 | 40 | 40 | 71 | 4 | 4 | 4 | 40 | 2 | 1 | 40 | 79 | 2 | 79 | 79 | 79 | 2 | 1 | 40 | 40 | 2 | 40 | 2 | 40 | 40 | 2 | 1 | 2 | 1 | 40 | 79 | 4 | 71 | 40 | 1 | 40 | 71 | 71 | 79
25 | 233 | 153 | 344 | 528 | 691 | 772 | 922 | 1047 | 1246 | 1409 | 1494 | 1571 | 1687 | 1917 | 79 | 1 | 71 | 2 | 1 | 79 | 71 | 40 | 71 | 71 | 2 | 40 | 4 | 79 | 79 | 1 | 4 | 2 | 4 | 71 | 4 | 71 | 71 | 4 | 2 | 79 | 40 | 4 | 79 | 1 | 79 | 40 | 40 | 79 | 40 | 4 | 1 | 4 | 40 | 40 | 1 | 1 | 4 | 71 | 4 | 40 | 71 | 1 | 40 | 40 | 71 | 79
26 | 333 | 292 | 452 | 577 | 740 | 867 | 1050 | 1214 | 1290 | 1445 | 1608 | 1614 | 1738 | 1821 | 71 | 71 | 79 | 71 | 1 | 40 | 79 | 40 | 40 | 2 | 79 | 4 | 79 | 40 | 4 | 40 | 79 | 4 | 4 | 40 | 1 | 71 | 40 | 71 | 2 | 4 | 79 | 79 | 2 | 1 | 2 | 71 | 40 | 4 | 71 | 40 | 40 | 79 | 4 | 40 | 1 | 2 | 2 | 1 | 1 | 4 | 79 | 40 | 4 | 4 | 71 | 4
27 | 305 | 155 | 416 | 493 | 615 | 623 | 748 | 872 | 1020 | 1214 | 1367 | 1598 | 1681 | 1728 | 71 | 4 | 1 | 79 | 79 | 71 | 71 | 40 | 2 | 71 | 2 | 2 | 2 | 40 | 1 | 79 | 2 | 1 | 1 | 4 | 4 | 40 | 79 | 2 | 79 | 40 | 4 | 1 | 71 | 71 | 2 | 4 | 40 | 79 | 4 | 71 | 40 | 40 | 2 | 71 | 79 | 71 | 2 | 79 | 1 | 79 | 2 | 1 | 2 | 1 | 40 | 4
28 | 255 | 183 | 405 | 522 | 605 | 760 | 951 | 1032 | 1147 | 1346 | 1470 | 1548 | 1670 | 1822 | 71 | 40 | 1 | 71 | 1 | 71 | 79 | 71 | 4 | 2 | 71 | 40 | 40 | 1 | 2 | 40 | 4 | 71 | 79 | 1 | 1 | 71 | 79 | 40 | 2 | 71 | 4 | 4 | 71 | 40 | 2 | 2 | 1 | 40 | 79 | 79 | 40 | 4 | 40 | 40 | 71 | 1 | 2 | 4 | 40 | 1 | 79 | 2 | 40 | 40 | 71 | 1
29 | 156 | 115 | 198 | 353 | 360 | 510 | 629 | 745 | 936 | 1022 | 1174 | 1368 | 1591 | 1813 | 71 | 40 | 2 | 2 | 1 | 40 | 2 | 40 | 1 | 71 | 79 | 4 | 1 | 1 | 1 | 4 | 71 | 4 | 4 | 71 | 4 | 40 | 71 | 4 | 4 | 71 | 40 | 1 | 1 | 79 | 40 | 71 | 40 | 4 | 2 | 40 | 1 | 1 | 71 | 79 | 4 | 40 | 71 | 79 | 2 | 79 | 71 | 71 | 71 | 1 | 71 | 79
30 | 334 | 184 | 407 | 563 | 688 | 804 | 881 | 1142 | 1264 | 1533 | 1724 | 1805 | 1932 | 2056 | 2 | 71 | 71 | 40 | 71 | 79 | 71 | 2 | 79 | 4 | 2 | 71 | 40 | 2 | 79 | 4 | 1 | 4 | 40 | 71 | 71 | 2 | 2 | 2 | 71 | 40 | 71 | 79 | 2 | 1 | 40 | 79 | 71 | 40 | 79 | 79 | 40 | 71 | 40 | 40 | 71 | 4 | 2 | 4 | 4 | 79 | 40 | 4 | 1 | 4 | 40 | 79
31 | 166 | 85 | 208 | 321 | 504 | 659 | 820 | 981 | 1129 | 1175 | 1333 | 1417 | 1464 | 1587 | 40 | 40 | 1 | 4 | 79 | 2 | 2 | 40 | 1 | 1 | 71 | 40 | 1 | 40 | 71 | 71 | 1 | 4 | 79 | 71 | 79 | 2 | 1 | 79 | 2 | 40 | 79 | 40 | 2 | 4 | 71 | 71 | 4 | 1 | 1 | 40 | 79 | 71 | 4 | 4 | 79 | 2 | 1 | 2 | 1 | 2 | 40 | 4 | 40 | 2 | 79 | 2
32 | 160 | 80 | 162 | 307 | 393 | 478 | 555 | 566 | 721 | 767 | 776 | 929 | 1015 | 1129 | 4 | 4 | 71 | 1 | 40 | 40 | 1 | 1 | 2 | 71 | 71 | 1 | 2 | 1 | 79 | 4 | 79 | 1 | 4 | 1 | 1 | 71 | 4 | 1 | 4 | 2 | 4 | 1 | 1 | 79 | 71 | 4 | 4 | 1 | 40 | 1 | 2 | 1 | 2 | 4 | 40 | 2 | 40 | 71 | 79 | 4 | 1 | 2 | 1 | 2 | 40 | 71
33 | 159 | 87 | 301 | 418 | 540 | 693 | 857 | 1059 | 1282 | 1438 | 1585 | 1671 | 1752 | 1827 | 2 | 4 | 2 | 79 | 1 | 71 | 71 | 71 | 2 | 40 | 4 | 71 | 40 | 1 | 2 | 79 | 40 | 40 | 71 | 2 | 79 | 4 | 2 | 79 | 79 | 4 | 79 | 40 | 2 | 71 | 79 | 71 | 2 | 4 | 71 | 79 | 71 | 4 | 71 | 1 | 4 | 1 | 2 | 79 | 71 | 2 | 4 | 4 | 1 | 2 | 71 | 1
34 | 242 | 162 | 322 | 505 | 699 | 851 | 895 | 1053 | 1275 | 1430 | 1655 | 1839 | 1915 | 2068 | 79 | 2 | 2 | 79 | 79 | 1 | 79 | 1 | 1 | 71 | 71 | 40 | 40 | 79 | 71 | 4 | 71 | 1 | 1 | 79 | 1 | 1 | 40 | 2 | 71 | 4 | 79 | 4 | 79 | 1 | 71 | 71 | 79 | 71 | 1 | 4 | 4 | 79 | 71 | 71 | 71 | 2 | 71 | 40 | 2 | 2 | 71 | 1 | 40 | 71 | 40 | 2
35 | 274 | 163 | 357 | 556 | 833 | 993 | 1215 | 1330 | 1529 | 1715 | 1799 | 1885 | 1971 | 2050 | 79 | 1 | 79 | 4 | 71 | 40 | 79 | 4 | 40 | 40 | 79 | 40 | 79 | 79 | 79 | 40 | 40 | 40 | 40 | 40 | 1 | 71 | 71 | 79 | 71 | 2 | 40 | 2 | 40 | 40 | 79 | 40 | 40 | 71 | 71 | 4 | 2 | 1 | 2 | 79 | 2 | 4 | 79 | 1 | 1 | 2 | 79 | 4 | 2 | 71 | 4 | 2
36 | 295 | 214 | 299 | 377 | 646 | 840 | 1070 | 1295 | 1412 | 1456 | 1609 | 1731 | 2023 | 2140 | 71 | 71 | 1 | 71 | 2 | 79 | 2 | 2 | 2 | 4 | 71 | 1 | 71 | 79 | 79 | 40 | 40 | 71 | 4 | 79 | 40 | 79 | 40 | 71 | 79 | 71 | 71 | 4 | 2 | 4 | 40 | 71 | 40 | 1 | 1 | 2 | 2 | 40 | 71 | 40 | 1 | 2 | 40 | 79 | 79 | 71 | 71 | 71 | 40 | 2 | 4 | 71
37 | 244 | 125 | 316 | 325 | 337 | 570 | 697 | 740 | 749 | 915 | 1001 | 1185 | 1309 | 1358 | 4 | 79 | 2 | 40 | 79 | 40 | 1 | 71 | 1 | 2 | 4 | 2 | 2 | 2 | 4 | 4 | 79 | 71 | 4 | 79 | 4 | 40 | 4 | 79 | 40 | 1 | 1 | 1 | 4 | 2 | 1 | 2 | 79 | 79 | 4 | 4 | 1 | 4 | 79 | 2 | 2 | 40 | 71 | 71 | 79 | 1 | 40 | 4 | 4 | 4 | 1 | 40
38 | 91 | 87 | 163 | 208 | 485 | 671 | 720 | 911 | 1035 | 1180 | 1296 | 1449 | 1576 | 1659 | 2 | 4 | 2 | 79 | 2 | 2 | 71 | 1 | 40 | 2 | 1 | 2 | 40 | 79 | 79 | 79 | 40 | 71 | 4 | 71 | 4 | 40 | 4 | 1 | 1 | 79 | 40 | 71 | 4 | 1 | 40 | 79 | 71 | 71 | 2 | 1 | 4 | 40 | 1 | 71 | 79 | 1 | 2 | 71 | 4 | 4 | 40 | 79 | 1 | 2 | 40 | 40
39 | 127 | 16 | 207 | 320 | 364 | 416 | 571 | 657 | 841 | 1033 | 1120 | 1206 | 1436 | 1484 | 4 | 4 | 4 | 4 | 71 | 40 | 40 | 40 | 1 | 71 | 1 | 40 | 1 | 1 | 40 | 2 | 40 | 4 | 4 | 4 | 1 | 79 | 4 | 71 | 1 | 4 | 79 | 2 | 2 | 71 | 40 | 71 | 2 | 71 | 79 | 40 | 4 | 2 | 2 | 79 | 4 | 2 | 1 | 79 | 71 | 40 | 40 | 79 | 2 | 40 | 2 | 4
40 | 153 | 150 | 195 | 312 | 437 | 558 | 564 | 756 | 837 | 922 | 1047 | 1200 | 1211 | 1333 | 71 | 4 | 71 | 4 | 2 | 1 | 40 | 2 | 2 | 4 | 71 | 40 | 2 | 4 | 79 | 40 | 1 | 79 | 40 | 1 | 2 | 1 | 2 | 1 | 79 | 40 | 2 | 71 | 4 | 71 | 2 | 4 | 2 | 2 | 79 | 2 | 40 | 2 | 79 | 4 | 1 | 2 | 79 | 71 | 4 | 1 | 4 | 2 | 40 | 40 | 40 | 2
41 | 127 | 52 | 129 | 295 | 440 | 553 | 775 | 931 | 937 | 1162 | 1286 | 1555 | 1702 | 1857 | 40 | 4 | 4 | 4 | 71 | 4 | 1 | 1 | 79 | 4 | 79 | 4 | 71 | 1 | 2 | 71 | 40 | 1 | 71 | 1 | 71 | 71 | 79 | 1 | 79 | 4 | 2 | 71 | 1 | 1 | 2 | 2 | 4 | 79 | 71 | 71 | 4 | 40 | 1 | 79 | 79 | 71 | 40 | 79 | 71 | 71 | 4 | 1 | 4 | 40 | 71 | 40
42 | 126 | 45 | 170 | 247 | 441 | 596 | 750 | 758 | 941 | 989 | 994 | 1177 | 1264 | 1417 | 40 | 2 | 2 | 1 | 2 | 79 | 4 | 40 | 1 | 1 | 4 | 71 | 4 | 40 | 71 | 79 | 40 | 71 | 4 | 40 | 2 | 71 | 79 | 2 | 4 | 1 | 2 | 1 | 40 | 1 | 71 | 71 | 40 | 4 | 2 | 2 | 1 | 2 | 1 | 1 | 71 | 71 | 1 | 40 | 79 | 4 | 2 | 2 | 71 | 79 | 2 | 1
43 | 52 | 46 | 163 | 362 | 561 | 715 | 860 | 945 | 1029 | 1221 | 1384 | 1506 | 1627 | 1715 | 1 | 40 | 4 | 1 | 2 | 4 | 71 | 40 | 79 | 40 | 79 | 1 | 40 | 79 | 79 | 1 | 71 | 2 | 2 | 79 | 71 | 2 | 1 | 71 | 4 | 40 | 1 | 40 | 40 | 2 | 2 | 40 | 2 | 40 | 79 | 71 | 40 | 79 | 4 | 40 | 2 | 40 | 79 | 1 | 79 | 1 | 1 | 40 | 79 | 4 | 4 | 1
44 | 124 | 83 | 274 | 430 | 580 | 743 | 857 | 1056 | 1204 | 1351 | 1474 | 1558 | 1636 | 1889 | 40 | 2 | 1 | 40 | 40 | 1 | 79 | 71 | 79 | 4 | 71 | 2 | 71 | 4 | 71 | 4 | 40 | 40 | 4 | 79 | 71 | 2 | 1 | 40 | 40 | 40 | 40 | 79 | 71 | 2 | 4 | 71 | 71 | 4 | 71 | 1 | 2 | 2 | 40 | 79 | 40 | 2 | 40 | 2 | 1 | 4 | 2 | 71 | 71 | 71 | 40 | 71
45 | 233 | 83 | 313 | 427 | 546 | 593 | 680 | 794 | 1019 | 1205 | 1330 | 1416 | 1499 | 1652 | 40 | 1 | 2 | 40 | 71 | 79 | 79 | 1 | 2 | 40 | 71 | 1 | 4 | 4 | 40 | 71 | 1 | 2 | 40 | 4 | 4 | 2 | 2 | 79 | 40 | 71 | 2 | 1 | 71 | 79 | 4 | 71 | 40 | 4 | 71 | 71 | 2 | 40 | 4 | 79 | 79 | 4 | 2 | 1 | 2 | 40 | 40 | 1 | 2 | 1 | 79 | 71
46 | 87 | 14 | 167 | 214 | 262 | 415 | 536 | 649 | 734 | 821 | 873 | 921 | 1112 | 1266 | 2 | 4 | 4 | 4 | 71 | 2 | 1 | 79 | 40 | 1 | 4 | 2 | 4 | 40 | 2 | 2 | 2 | 1 | 71 | 79 | 79 | 40 | 1 | 1 | 71 | 1 | 1 | 40 | 40 | 4 | 40 | 1 | 2 | 2 | 4 | 79 | 40 | 4 | 4 | 4 | 40 | 4 | 2 | 2 | 71 | 40 | 1 | 79 | 2 | 2 | 71 | 79
47 | 244 | 86 | 402 | 519 | 675 | 836 | 960 | 965 | 1048 | 1134 | 1251 | 1407 | 1454 | 1654 | 79 | 2 | 1 | 4 | 79 | 79 | 79 | 79 | 40 | 2 | 4 | 71 | 4 | 71 | 2 | 79 | 2 | 1 | 79 | 79 | 40 | 1 | 4 | 79 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 79 | 79 | 2 | 4 | 1 | 40 | 71 | 4 | 2 | 2 | 71 | 4 | 79 | 4 | 1 | 40 | 2 | 2 | 79 | 40 | 79
48 | 168 | 124 | 248 | 363 | 518 | 567 | 614 | 837 | 922 | 1070 | 1153 | 1375 | 1461 | 1505 | 40 | 79 | 1 | 4 | 4 | 40 | 79 | 1 | 40 | 2 | 2 | 71 | 1 | 79 | 71 | 4 | 4 | 1 | 40 | 4 | 4 | 2 | 40 | 1 | 79 | 71 | 2 | 71 | 4 | 1 | 79 | 1 | 71 | 2 | 4 | 71 | 79 | 2 | 1 | 1 | 71 | 71 | 79 | 1 | 4 | 2 | 40 | 40 | 2 | 1 | 1 | 40
49 | 158 | 78 | 308 | 461 | 536 | 652 | 815 | 968 | 1159 | 1312 | 1439 | 1563 | 1755 | 1915 | 1 | 4 | 2 | 71 | 1 | 79 | 79 | 71 | 40 | 2 | 40 | 71 | 1 | 2 | 71 | 1 | 4 | 40 | 71 | 1 | 40 | 4 | 40 | 79 | 79 | 1 | 2 | 71 | 1 | 79 | 71 | 40 | 71 | 2 | 1 | 79 | 4 | 4 | 79 | 40 | 79 | 40 | 1 | 4 | 2 | 79 | 40 | 71 | 1 | 40 | 79 | 40
50 | 93 | 85 | 137 | 254 | 369 | 452 | 605 | 730 | 778 | 861 | 1022 | 1108 | 1191 | 1352 | 40 | 4 | 40 | 1 | 4 | 4 | 4 | 40 | 4 | 71 | 2 | 40 | 2 | 2 | 40 | 71 | 1 | 2 | 79 | 1 | 2 | 1 | 79 | 71 | 79 | 4 | 40 | 2 | 2 | 4 | 2 | 40 | 40 | 40 | 1 | 2 | 40 | 79 | 2 | 40 | 2 | 79 | 4 | 1 | 79 | 1 | 2 | 1 | 40 | 79 | 40 | 2
51 | 164 | 161 | 283 | 360 | 546 | 740 | 826 | 870 | 956 | 964 | 1050 | 1171 | 1247 | 1360 | 1 | 79 | 79 | 2 | 1 | 2 | 79 | 40 | 2 | 2 | 2 | 71 | 40 | 4 | 71 | 71 | 79 | 71 | 4 | 40 | 2 | 40 | 40 | 4 | 2 | 1 | 1 | 40 | 4 | 2 | 79 | 1 | 1 | 1 | 4 | 2 | 1 | 2 | 4 | 79 | 79 | 1 | 40 | 1 | 2 | 2 | 71 | 1 | 1 | 40 | 71 | 1
52 | 302 | 191 | 382 | 542 | 655 | 732 | 817 | 1039 | 1118 | 1301 | 1495 | 1728 | 1845 | 1930 | 1 | 79 | 40 | 71 | 71 | 40 | 1 | 79 | 40 | 1 | 40 | 79 | 1 | 40 | 71 | 1 | 71 | 4 | 1 | 1 | 1 | 79 | 1 | 4 | 71 | 40 | 40 | 71 | 2 | 2 | 4 | 71 | 71 | 71 | 1 | 40 | 79 | 71 | 40 | 4 | 79 | 4 | 79 | 71 | 4 | 71 | 2 | 40 | 1 | 79 | 4 | 1
53 | 275 | 194 | 358 | 434 | 558 | 636 | 796 | 921 | 1074 | 1155 | 1207 | 1257 | 1443 | 1674 | 79 | 4 | 71 | 40 | 79 | 2 | 79 | 4 | 71 | 2 | 1 | 2 | 1 | 40 | 79 | 4 | 4 | 71 | 1 | 2 | 79 | 79 | 1 | 1 | 40 | 2 | 79 | 4 | 1 | 2 | 71 | 79 | 4 | 2 | 71 | 4 | 4 | 4 | 4 | 40 | 4 | 40 | 4 | 2 | 71 | 71 | 40 | 4 | 79 | 71 | 2 | 79
54 | 189 | 114 | 347 | 423 | 545 | 592 | 678 | 834 | 988 | 1133 | 1179 | 1396 | 1474 | 1599 | 2 | 40 | 1 | 71 | 71 | 4 | 79 | 79 | 71 | 2 | 2 | 1 | 1 | 2 | 40 | 79 | 40 | 2 | 4 | 1 | 1 | 2 | 79 | 4 | 4 | 71 | 79 | 2 | 2 | 71 | 79 | 2 | 1 | 71 | 71 | 2 | 4 | 40 | 1 | 1 | 71 | 71 | 4 | 71 | 2 | 1 | 71 | 4 | 4 | 2 | 40 | 79
55 | 190 | 117 | 194 | 317 | 401 | 516 | 631 | 722 | 874 | 1027 | 1144 | 1151 | 1265 | 1348 | 40 | 2 | 71 | 4 | 71 | 2 | 2 | 2 | 40 | 2 | 79 | 2 | 2 | 1 | 2 | 79 | 40 | 2 | 2 | 71 | 40 | 2 | 71 | 2 | 4 | 79 | 4 | 4 | 1 | 71 | 1 | 79 | 2 | 71 | 79 | 1 | 4 | 71 | 2 | 40 | 1 | 4 | 1 | 1 | 40 | 1 | 71 | 2 | 40 | 2 | 1 | 40
56 | 196 | 85 | 346 | 510 | 633 | 794 | 948 | 1034 | 1267 | 1389 | 1658 | 1782 | 1829 | 1915 | 79 | 2 | 2 | 2 | 71 | 40 | 71 | 79 | 2 | 79 | 79 | 4 | 40 | 79 | 2 | 2 | 40 | 79 | 40 | 2 | 2 | 71 | 79 | 2 | 2 | 40 | 40 | 4 | 71 | 79 | 4 | 79 | 1 | 2 | 79 | 40 | 79 | 79 | 71 | 40 | 1 | 40 | 4 | 79 | 1 | 2 | 4 | 40 | 4 | 1 | 79 | 2
57 | 375 | 225 | 486 | 600 | 800 | 810 | 926 | 1050 | 1350 | 1434 | 1634 | 1856 | 1970 | 2014 | 71 | 79 | 4 | 71 | 71 | 79 | 40 | 71 | 1 | 2 | 40 | 71 | 40 | 2 | 79 | 79 | 4 | 4 | 1 | 1 | 4 | 40 | 71 | 1 | 79 | 1 | 40 | 4 | 71 | 79 | 79 | 71 | 79 | 2 | 2 | 1 | 2 | 79 | 79 | 40 | 1 | 71 | 71 | 79 | 40 | 2 | 1 | 71 | 40 | 2 | 1 | 1
58 | 157 | 154 | 163 | 290 | 450 | 649 | 725 | 886 | 1070 | 1184 | 1307 | 1388 | 1465 | 1648 | 2 | 79 | 2 | 71 | 1 | 2 | 4 | 2 | 79 | 4 | 4 | 40 | 1 | 40 | 79 | 40 | 40 | 40 | 79 | 40 | 2 | 1 | 2 | 71 | 40 | 79 | 2 | 40 | 71 | 2 | 40 | 71 | 71 | 2 | 1 | 40 | 40 | 79 | 2 | 2 | 4 | 2 | 4 | 71 | 1 | 71 | 1 | 4 | 71 | 71 | 40 | 1
59 | 119 | 113 | 238 | 401 | 561 | 708 | 939 | 1063 | 1190 | 1309 | 1542 | 1617 | 1731 | 1954 | 1 | 71 | 1 | 40 | 4 | 2 | 40 | 79 | 40 | 40 | 4 | 79 | 79 | 1 | 79 | 1 | 1 | 71 | 4 | 71 | 79 | 71 | 2 | 79 | 1 | 4 | 40 | 79 | 4 | 40 | 79 | 4 | 71 | 4 | 40 | 4 | 71 | 4 | 79 | 79 | 71 | 1 | 1 | 2 | 71 | 40 | 1 | 2 | 71 | 79 | 71 | 2
60 | 237 | 164 | 281 | 366 | 446 | 599 | 609 | 689 | 872 | 920 | 1076 | 1267 | 1415 | 1500 | 79 | 2 | 4 | 79 | 2 | 71 | 4 | 40 | 79 | 4 | 1 | 1 | 4 | 4 | 71 | 1 | 40 | 40 | 2 | 71 | 1 | 1 | 4 | 4 | 1 | 71 | 4 | 4 | 40 | 71 | 1 | 71 | 4 | 2 | 2 | 40 | 79 | 4 | 2 | 71 | 79 | 71 | 40 | 1 | 4 | 71 | 71 | 2 | 1 | 1 | 4 | 79
61 | 306 | 164 | 387 | 573 | 806 | 927 | 1010 | 1098 | 1253 | 1407 | 1630 | 1716 | 1838 | 1982 | 79 | 2 | 79 | 4 | 71 | 71 | 79 | 2 | 71 | 4 | 40 | 71 | 79 | 4 | 71 | 79 | 1 | 1 | 40 | 79 | 40 | 2 | 40 | 1 | 40 | 4 | 4 | 40 | 71 | 1 | 79 | 4 | 2 | 2 | 71 | 79 | 79 | 2 | 71 | 71 | 2 | 1 | 4 | 79 | 79 | 2 | 40 | 1 | 1 | 1 | 71 | 71
62 | 271 | 121 | 275 | 352 | 475 | 556 | 642 | 721 | 952 | 1026 | 1072 | 1194 | 1347 | 1390 | 40 | 1 | 40 | 40 | 79 | 71 | 2 | 2 | 71 | 1 | 4 | 1 | 2 | 40 | 2 | 79 | 4 | 2 | 4 | 71 | 4 | 2 | 40 | 40 | 2 | 2 | 4 | 71 | 79 | 71 | 2 | 79 | 71 | 1 | 1 | 1 | 2 | 2 | 2 | 40 | 40 | 79 | 2 | 1 | 1 | 71 | 2 | 79 | 1 | 1 | 40 | 1
63 | 56 | 12 | 206 | 319 | 482 | 526 | 641 | 721 | 843 | 1076 | 1159 | 1240 | 1356 | 1403 | 2 | 2 | 4 | 4 | 40 | 4 | 79 | 71 | 1 | 1 | 40 | 71 | 1 | 79 | 4 | 79 | 1 | 40 | 1 | 2 | 40 | 2 | 71 | 2 | 4 | 71 | 4 | 1 | 40 | 2 | 79 | 1 | 79 | 71 | 4 | 79 | 1 | 40 | 40 | 2 | 2 | 4 | 4 | 71 | 40 | 1 | 4 | 71 | 1 | 2 | 40 | 4
64 | 313 | 202 | 354 | 499 | 655 | 803 | 1095 | 1251 | 1396 | 1552 | 1813 | 2082 | 2351 | 2361 | 4 | 79 | 40 | 79 | 71 | 40 | 40 | 1 | 2 | 71 | 1 | 71 | 71 | 2 | 79 | 4 | 71 | 4 | 71 | 2 | 71 | 79 | 71 | 71 | 2 | 4 | 71 | 79 | 71 | 2 | 71 | 1 | 71 | 4 | 79 | 2 | 71 | 40 | 71 | 79 | 79 | 71 | 79 | 40 | 40 | 71 | 79 | 79 | 4 | 4 | 1 | 1
65 | 312 | 231 | 320 | 472 | 589 | 711 | 942 | 1102 | 1257 | 1457 | 1643 | 1724 | 1808 | 1932 | 71 | 2 | 79 | 79 | 2 | 79 | 4 | 4 | 1 | 71 | 79 | 1 | 2 | 4 | 71 | 40 | 2 | 40 | 79 | 1 | 79 | 2 | 79 | 71 | 1 | 1 | 79 | 79 | 71 | 40 | 4 | 40 | 2 | 40 | 79 | 79 | 71 | 71 | 4 | 40 | 4 | 2 | 71 | 4 | 2 | 40 | 40 | 2 | 40 | 40 | 4 | 40
66 | 226 | 154 | 337 | 347 | 616 | 816 | 966 | 1049 | 1126 | 1359 | 1520 | 1683 | 1906 | 1956 | 71 | 2 | 79 | 2 | 1 | 71 | 71 | 40 | 2 | 2 | 4 | 2 | 71 | 79 | 79 | 40 | 2 | 40 | 79 | 79 | 71 | 71 | 4 | 4 | 2 | 40 | 1 | 40 | 2 | 2 | 71 | 2 | 71 | 4 | 79 | 79 | 79 | 40 | 2 | 40 | 79 | 4 | 40 | 40 | 71 | 2 | 71 | 79 | 4 | 40 | 4 | 2
67 | 255 | 183 | 338 | 417 | 466 | 552 | 708 | 830 | 1061 | 1252 | 1407 | 1590 | 1713 | 1868 | 71 | 40 | 71 | 1 | 1 | 71 | 79 | 4 | 4 | 71 | 2 | 2 | 1 | 40 | 4 | 4 | 2 | 1 | 4 | 79 | 2 | 4 | 79 | 71 | 1 | 40 | 79 | 2 | 71 | 2 | 79 | 79 | 40 | 1 | 71 | 79 | 4 | 40 | 71 | 40 | 1 | 71 | 40 | 71 | 2 | 79 | 40 | 2 | 71 | 79 | 4 | 1
68 | 51 | 9 | 55 | 100 | 217 | 294 | 563 | 855 | 1046 | 1168 | 1284 | 1428 | 1622 | 1778 | 1 | 2 | 2 | 4 | 40 | 2 | 2 | 2 | 1 | 2 | 40 | 2 | 4 | 40 | 2 | 71 | 1 | 71 | 4 | 1 | 71 | 79 | 79 | 40 | 71 | 71 | 71 | 79 | 71 | 1 | 79 | 40 | 2 | 79 | 1 | 40 | 40 | 1 | 71 | 4 | 71 | 1 | 1 | 71 | 71 | 4 | 79 | 40 | 4 | 79 | 71 | 2
69 | 192 | 150 | 264 | 418 | 505 | 660 | 782 | 976 | 1167 | 1366 | 1596 | 1752 | 1912 | 1994 | 4 | 71 | 4 | 71 | 2 | 40 | 71 | 1 | 2 | 71 | 2 | 79 | 2 | 4 | 2 | 79 | 71 | 4 | 40 | 40 | 2 | 79 | 40 | 1 | 40 | 79 | 71 | 4 | 71 | 40 | 79 | 1 | 40 | 79 | 79 | 1 | 79 | 71 | 1 | 79 | 79 | 2 | 71 | 4 | 40 | 1 | 40 | 79 | 1 | 1 | 1 | 79
70 | 310 | 199 | 429 | 545 | 552 | 712 | 867 | 989 | 1034 | 1187 | 1332 | 1381 | 1468 | 1634 | 40 | 79 | 79 | 1 | 71 | 40 | 40 | 79 | 4 | 1 | 40 | 71 | 2 | 2 | 2 | 1 | 79 | 40 | 1 | 40 | 71 | 4 | 79 | 1 | 40 | 40 | 2 | 40 | 2 | 1 | 40 | 2 | 79 | 1 | 71 | 2 | 71 | 71 | 1 | 2 | 1 | 4 | 4 | 40 | 2 | 79 | 2 | 4 | 79 | 79 | 4 | 4
71 | 236 | 163 | 238 | 287 | 404 | 454 | 679 | 728 | 920 | 928 | 1006 | 1128 | 1320 | 1475 | 79 | 4 | 40 | 40 | 2 | 71 | 1 | 1 | 4 | 1 | 4 | 40 | 4 | 2 | 40 | 71 | 4 | 2 | 4 | 40 | 71 | 4 | 71 | 79 | 4 | 40 | 1 | 4 | 79 | 71 | 2 | 40 | 2 | 2 | 2 | 2 | 4 | 2 | 1 | 71 | 2 | 1 | 40 | 79 | 71 | 40 | 79 | 2 | 79 | 1 | 4 | 71
72 | 169 | 127 | 244 | 397 | 550 | 781 | 980 | 1068 | 1282 | 1429 | 1613 | 1777 | 1853 | 2016 | 40 | 4 | 4 | 79 | 2 | 40 | 71 | 4 | 1 | 71 | 2 | 79 | 71 | 79 | 2 | 1 | 2 | 79 | 79 | 71 | 40 | 79 | 79 | 1 | 4 | 4 | 79 | 1 | 71 | 1 | 71 | 71 | 71 | 4 | 1 | 71 | 71 | 40 | 71 | 2 | 79 | 4 | 2 | 79 | 2 | 71 | 1 | 2 | 4 | 1 | 79 | 79
73 | 83 | 79 | 158 | 234 | 387 | 610 | 812 | 965 | 1121 | 1248 | 1404 | 1482 | 1493 | 1612 | 4 | 71 | 2 | 2 | 2 | 2 | 71 | 4 | 1 | 71 | 2 | 2 | 79 | 2 | 71 | 1 | 79 | 71 | 71 | 2 | 4 | 79 | 79 | 40 | 79 | 71 | 2 | 1 | 79 | 71 | 2 | 4 | 40 | 4 | 79 | 4 | 2 | 79 | 4 | 71 | 4 | 71 | 1 | 2 | 4 | 2 | 4 | 1 | 4 | 4 | 40 | 71
74 | 207 | 202 | 213 | 412 | 572 | 727 | 958 | 1034 | 1150 | 1226 | 1456 | 1505 | 1658 | 1783 | 40 | 4 | 79 | 79 | 1 | 4 | 4 | 2 | 40 | 1 | 79 | 79 | 1 | 40 | 79 | 40 | 71 | 1 | 79 | 4 | 79 | 71 | 2 | 79 | 2 | 2 | 71 | 1 | 4 | 40 | 71 | 1 | 2 | 1 | 2 | 71 | 71 | 1 | 79 | 79 | 1 | 40 | 4 | 4 | 2 | 71 | 79 | 1 | 2 | 4 | 40 | 79
75 | 118 | 76 | 193 | 348 | 504 | 659 | 778 | 931 | 1018 | 1220 | 1414 | 1461 | 1614 | 1875 | 2 | 1 | 2 | 71 | 2 | 40 | 4 | 71 | 40 | 4 | 71 | 40 | 4 | 79 | 2 | 71 | 71 | 4 | 40 | 40 | 4 | 4 | 71 | 40 | 2 | 40 | 71 | 40 | 79 | 2 | 4 | 2 | 79 | 79 | 4 | 40 | 71 | 79 | 4 | 40 | 1 | 4 | 2 | 40 | 2 | 71 | 79 | 1 | 71 | 71 | 79 | 40
76 | 82 | 9 | 155 | 310 | 540 | 773 | 1042 | 1131 | 1210 | 1254 | 1378 | 1530 | 1657 | 1704 | 2 | 2 | 4 | 1 | 71 | 2 | 2 | 71 | 71 | 4 | 1 | 79 | 79 | 79 | 71 | 1 | 79 | 79 | 4 | 71 | 79 | 40 | 79 | 71 | 2 | 4 | 4 | 79 | 4 | 2 | 71 | 2 | 1 | 2 | 40 | 1 | 1 | 4 | 40 | 79 | 71 | 1 | 1 | 79 | 40 | 4 | 79 | 4 | 4 | 2 | 40 | 1
77 | 272 | 161 | 352 | 471 | 779 | 970 | 980 | 1099 | 1332 | 1523 | 1761 | 1906 | 2023 | 2140 | 2 | 79 | 1 | 79 | 71 | 40 | 40 | 40 | 4 | 71 | 4 | 40 | 79 | 79 | 79 | 71 | 79 | 40 | 1 | 71 | 2 | 2 | 4 | 2 | 40 | 4 | 71 | 4 | 79 | 79 | 4 | 71 | 71 | 40 | 79 | 1 | 79 | 79 | 1 | 79 | 71 | 1 | 71 | 2 | 2 | 71 | 4 | 40 | 2 | 40 | 4 | 71
78 | 155 | 153 | 197 | 321 | 398 | 512 | 586 | 894 | 943 | 1099 | 1182 | 1415 | 1528 | 1722 | 71 | 2 | 40 | 40 | 1 | 1 | 40 | 2 | 40 | 79 | 1 | 4 | 71 | 4 | 1 | 1 | 2 | 40 | 1 | 71 | 1 | 1 | 71 | 1 | 79 | 79 | 79 | 71 | 4 | 4 | 1 | 40 | 2 | 71 | 4 | 79 | 1 | 1 | 2 | 79 | 79 | 79 | 4 | 71 | 1 | 40 | 71 | 1 | 71 | 79 | 40 | 4
79 | 91 | 11 | 99 | 290 | 445 | 607 | 693 | 703 | 792 | 950 | 998 | 1114 | 1383 | 1505 | 4 | 2 | 4 | 1 | 40 | 40 | 4 | 4 | 79 | 71 | 40 | 1 | 4 | 79 | 71 | 1 | 2 | 79 | 79 | 2 | 40 | 40 | 4 | 2 | 2 | 2 | 4 | 2 | 4 | 79 | 2 | 4 | 71 | 4 | 79 | 4 | 40 | 4 | 2 | 2 | 1 | 40 | 71 | 4 | 79 | 79 | 40 | 71 | 40 | 1 | 79 | 2
80 | 158 | 83 | 163 | 363 | 586 | 595 | 826 | 987 | 1112 | 1197 | 1353 | 1477 | 1594 | 1710 | 2 | 1 | 79 | 1 | 71 | 4 | 4 | 1 | 79 | 40 | 79 | 2 | 79 | 71 | 2 | 71 | 2 | 1 | 4 | 2 | 71 | 79 | 79 | 2 | 40 | 40 | 2 | 79 | 2 | 40 | 79 | 4 | 1 | 1 | 79 | 4 | 2 | 71 | 4 | 79 | 40 | 4 | 40 | 40 | 2 | 4 | 71 | 40 | 71 | 1 | 40 | 4
81 | 188 | 46 | 338 | 427 | 549 | 593 | 643 | 691 | 740 | 971 | 978 | 1132 | 1254 | 1448 | 1 | 40 | 1 | 4 | 71 | 71 | 71 | 79 | 4 | 79 | 2 | 4 | 2 | 1 | 79 | 40 | 1 | 2 | 1 | 40 | 4 | 4 | 40 | 2 | 2 | 4 | 40 | 2 | 4 | 1 | 40 | 4 | 2 | 71 | 79 | 79 | 4 | 1 | 1 | 1 | 71 | 2 | 79 | 2 | 40 | 79 | 1 | 2 | 4 | 71 | 79 | 40
82 | 235 | 230 | 277 | 433 | 521 | 746 | 870 | 1030 | 1180 | 1266 | 1427 | 1593 | 1603 | 1758 | 79 | 1 | 79 | 71 | 1 | 4 | 2 | 40 | 71 | 4 | 2 | 79 | 4 | 79 | 1 | 4 | 71 | 71 | 79 | 4 | 4 | 79 | 1 | 40 | 79 | 40 | 1 | 40 | 4 | 71 | 71 | 4 | 4 | 2 | 79 | 1 | 79 | 2 | 40 | 40 | 4 | 79 | 79 | 4 | 2 | 2 | 2 | 4 | 71 | 4 | 1 | 79
83 | 305 | 261 | 349 | 470 | 661 | 775 | 791 | 944 | 1096 | 1282 | 1404 | 1559 | 1567 | 1751 | 40 | 71 | 79 | 71 | 40 | 4 | 4 | 40 | 40 | 40 | 1 | 40 | 1 | 79 | 40 | 71 | 1 | 40 | 2 | 71 | 4 | 4 | 4 | 4 | 2 | 40 | 71 | 40 | 1 | 71 | 1 | 79 | 71 | 4 | 71 | 40 | 40 | 79 | 1 | 2 | 79 | 4 | 71 | 1 | 2 | 2 | 2 | 2 | 71 | 71 | 2 | 40
84 | 158 | 78 | 233 | 387 | 617 | 706 | 715 | 798 | 915 | 1068 | 1291 | 1483 | 1564 | 1789 | 4 | 2 | 1 | 71 | 79 | 1 | 4 | 71 | 71 | 2 | 79 | 2 | 71 | 79 | 1 | 79 | 4 | 4 | 2 | 79 | 1 | 2 | 4 | 2 | 40 | 40 | 1 | 2 | 40 | 2 | 4 | 71 | 71 | 2 | 40 | 40 | 71 | 79 | 2 | 71 | 71 | 79 | 40 | 2 | 4 | 71 | 4 | 2 | 71 | 4 | 79 | 71
85 | 313 | 202 | 316 | 476 | 562 | 575 | 730 | 844 | 959 | 1005 | 1126 | 1203 | 1428 | 1620 | 40 | 4 | 79 | 79 | 71 | 40 | 1 | 2 | 79 | 40 | 1 | 40 | 40 | 2 | 40 | 4 | 1 | 4 | 4 | 4 | 4 | 79 | 71 | 1 | 71 | 1 | 40 | 2 | 2 | 40 | 2 | 71 | 1 | 40 | 4 | 1 | 1 | 79 | 40 | 1 | 71 | 1 | 4 | 1 | 71 | 79 | 71 | 4 | 71 | 40 | 2 | 79
86 | 195 | 153 | 236 | 317 | 393 | 474 | 636 | 836 | 1066 | 1250 | 1475 | 1590 | 1675 | 1861 | 40 | 40 | 2 | 71 | 2 | 40 | 40 | 1 | 71 | 2 | 4 | 4 | 2 | 2 | 71 | 1 | 2 | 4 | 71 | 4 | 79 | 79 | 2 | 2 | 79 | 2 | 40 | 79 | 40 | 79 | 40 | 71 | 71 | 71 | 40 | 2 | 71 | 71 | 4 | 79 | 40 | 2 | 2 | 71 | 1 | 40 | 4 | 40 | 71 | 71 | 4 | 40
87 | 199 | 124 | 271 | 320 | 444 | 450 | 603 | 678 | 831 | 883 | 1082 | 1197 | 1352 | 1400 | 40 | 79 | 4 | 1 | 71 | 4 | 1 | 71 | 40 | 4 | 1 | 4 | 40 | 40 | 4 | 40 | 2 | 1 | 1 | 2 | 40 | 71 | 40 | 2 | 2 | 1 | 71 | 1 | 1 | 2 | 79 | 71 | 40 | 4 | 4 | 4 | 40 | 1 | 79 | 79 | 2 | 71 | 40 | 2 | 79 | 1 | 4 | 71 | 40 | 4 | 2 | 2
88 | 168 | 85 | 173 | 259 | 419 | 497 | 643 | 799 | 1068 | 1115 | 1159 | 1243 | 1443 | 1565 | 4 | 1 | 1 | 79 | 4 | 79 | 4 | 1 | 4 | 40 | 40 | 2 | 1 | 79 | 40 | 40 | 2 | 4 | 1 | 71 | 71 | 2 | 2 | 71 | 79 | 4 | 71 | 2 | 71 | 79 | 79 | 40 | 1 | 2 | 40 | 4 | 40 | 2 | 1 | 1 | 79 | 2 | 1 | 2 | 79 | 79 | 2 | 40 | 1 | 79 | 2 | 40
89 | 123 | 117 | 198 | 246 | 294 | 535 | 766 | 843 | 962 | 1087 | 1242 | 1356 | 1503 | 1702 | 4 | 71 | 2 | 40 | 4 | 2 | 71 | 4 | 2 | 2 | 40 | 4 | 2 | 40 | 2 | 4 | 79 | 79 | 4 | 79 | 79 | 2 | 79 | 71 | 71 | 1 | 1 | 4 | 71 | 40 | 4 | 4 | 4 | 2 | 79 | 40 | 40 | 40 | 4 | 71 | 2 | 1 | 71 | 40 | 1 | 4 | 71 | 71 | 1 | 40 | 79 | 79
90 | 236 | 117 | 386 | 398 | 512 | 665 | 714 | 792 | 919 | 1040 | 1293 | 1302 | 1429 | 1584 | 71 | 40 | 4 | 2 | 40 | 79 | 71 | 79 | 4 | 2 | 2 | 4 | 2 | 40 | 1 | 71 | 40 | 2 | 40 | 71 | 40 | 1 | 4 | 4 | 1 | 71 | 4 | 2 | 79 | 4 | 4 | 40 | 79 | 40 | 1 | 1 | 71 | 40 | 71 | 71 | 2 | 2 | 1 | 4 | 4 | 4 | 40 | 79 | 4 | 79 | 71 | 1
91 | 279 | 199 | 284 | 289 | 442 | 524 | 602 | 765 | 810 | 893 | 1038 | 1124 | 1249 | 1441 | 40 | 79 | 79 | 1 | 1 | 79 | 1 | 4 | 2 | 1 | 1 | 1 | 79 | 1 | 71 | 2 | 1 | 1 | 40 | 40 | 2 | 4 | 71 | 1 | 79 | 4 | 40 | 40 | 2 | 2 | 1 | 40 | 1 | 79 | 1 | 2 | 71 | 1 | 2 | 71 | 40 | 40 | 4 | 2 | 40 | 2 | 79 | 4 | 79 | 71 | 40 | 2
92 | 261 | 186 | 305 | 420 | 495 | 572 | 755 | 938 | 1161 | 1321 | 1371 | 1493 | 1570 | 1734 | 4 | 40 | 71 | 71 | 4 | 71 | 40 | 4 | 2 | 40 | 71 | 2 | 1 | 2 | 1 | 71 | 71 | 4 | 1 | 1 | 71 | 71 | 40 | 1 | 71 | 71 | 40 | 1 | 71 | 71 | 79 | 2 | 1 | 79 | 79 | 1 | 4 | 2 | 4 | 40 | 79 | 1 | 2 | 40 | 1 | 71 | 1 | 4 | 2 | 79 | 4 | 79
93 | 349 | 269 | 393 | 469 | 660 | 782 | 942 | 1067 | 1228 | 1412 | 1495 | 1647 | 1733 | 1924 | 79 | 71 | 79 | 40 | 40 | 40 | 40 | 4 | 71 | 2 | 2 | 1 | 71 | 40 | 79 | 1 | 1 | 2 | 40 | 79 | 40 | 79 | 40 | 1 | 2 | 40 | 79 | 4 | 79 | 40 | 40 | 2 | 71 | 40 | 2 | 71 | 71 | 4 | 4 | 4 | 1 | 71 | 1 | 79 | 2 | 1 | 79 | 4 | 79 | 1 | 40 | 71
94 | 147 | 74 | 266 | 277 | 469 | 513 | 660 | 745 | 822 | 833 | 978 | 1178 | 1264 | 1340 | 1 | 1 | 1 | 71 | 2 | 71 | 79 | 40 | 2 | 1 | 4 | 4 | 40 | 79 | 2 | 71 | 40 | 1 | 1 | 2 | 71 | 1 | 71 | 4 | 2 | 79 | 2 | 2 | 4 | 71 | 1 | 1 | 4 | 1 | 2 | 4 | 1 | 2 | 71 | 71 | 79 | 79 | 40 | 2 | 2 | 79 | 1 | 4 | 2 | 71 | 1 | 2
95 | 16 | 10 | 18 | 103 | 305 | 453 | 637 | 837 | 995 | 1004 | 1079 | 1166 | 1249 | 1331 | 4 | 2 | 2 | 2 | 4 | 2 | 1 | 1 | 79 | 1 | 4 | 1 | 79 | 79 | 4 | 40 | 2 | 71 | 4 | 71 | 71 | 2 | 40 | 71 | 79 | 79 | 2 | 40 | 4 | 4 | 71 | 79 | 2 | 4 | 2 | 1 | 1 | 71 | 2 | 1 | 4 | 2 | 2 | 79 | 40 | 40 | 1 | 2 | 1 | 1 | 1 | 79
96 | 171 | 13 | 174 | 435 | 596 | 742 | 828 | 982 | 1196 | 1312 | 1467 | 1547 | 1558 | 1639 | 4 | 1 | 4 | 4 | 79 | 79 | 2 | 1 | 40 | 79 | 71 | 71 | 40 | 79 | 2 | 40 | 71 | 2 | 2 | 71 | 79 | 1 | 4 | 2 | 79 | 2 | 2 | 71 | 71 | 1 | 71 | 71 | 1 | 4 | 40 | 71 | 79 | 4 | 71 | 1 | 1 | 4 | 71 | 4 | 4 | 4 | 2 | 1 | 2 | 71 | 4 | 4
97 | 123 | 115 | 126 | 286 | 477 | 633 | 750 | 863 | 941 | 1141 | 1266 | 1489 | 1616 | 1701 | 2 | 2 | 71 | 40 | 4 | 4 | 2 | 1 | 79 | 1 | 40 | 40 | 40 | 79 | 1 | 71 | 79 | 2 | 71 | 4 | 40 | 4 | 71 | 2 | 1 | 40 | 1 | 71 | 4 | 71 | 1 | 2 | 40 | 79 | 2 | 79 | 4 | 79 | 2 | 40 | 2 | 71 | 79 | 71 | 40 | 4 | 79 | 4 | 2 | 2 | 2 | 79
98 | 117 | 114 | 192 | 280 | 358 | 402 | 562 | 754 | 945 | 992 | 1070 | 1287 | 1362 | 1447 | 1 | 2 | 40 | 71 | 1 | 2 | 71 | 4 | 79 | 1 | 4 | 4 | 1 | 71 | 2 | 4 | 1 | 40 | 1 | 2 | 1 | 79 | 40 | 40 | 2 | 40 | 71 | 79 | 40 | 79 | 71 | 1 | 4 | 1 | 2 | 40 | 2 | 1 | 4 | 71 | 4 | 71 | 71 | 71 | 1 | 1 | 2 | 71 | 1 | 79 | 4 | 1
99 | 86 | 83 | 94 | 247 | 449 | 526 | 650 | 774 | 921 | 1143 | 1309 | 1353 | 1536 | 1616 | 79 | 1 | 2 | 1 | 1 | 2 | 4 | 4 | 71 | 2 | 79 | 1 | 79 | 4 | 40 | 79 | 1 | 4 | 1 | 71 | 4 | 40 | 40 | 40 | 79 | 4 | 1 | 40 | 4 | 71 | 1 | 71 | 1 | 71 | 71 | 79 | 4 | 79 | 79 | 4 | 2 | 40 | 1 | 1 | 1 | 71 | 40 | 71 | 4 | 71 | 1 | 4
100 | 187 | 183 | 195 | 358 | 444 | 519 | 636 | 819 | 1041 | 1233 | 1386 | 1472 | 1551 | 1598 | 71 | 71 | 1 | 40 | 2 | 2 | 4 | 4 | 4 | 40 | 79 | 40 | 2 | 4 | 1 | 79 | 1 | 2 | 71 | 1 | 2 | 4 | 40 | 71 | 1 | 40 | 71 | 71 | 71 | 1 | 79 | 71 | 2 | 40 | 71 | 79 | 2 | 79 | 1 | 71 | 4 | 1 | 2 | 79 | 71 | 4 | 2 | 2 | 40 | 2 | 1 | 4
101 | 349 | 199 | 355 | 434 | 617 | 739 | 1039 | 1160 | 1352 | 1479 | 1626 | 1779 | 2048 | 2163 | 40 | 79 | 79 | 1 | 79 | 71 | 4 | 2 | 71 | 4 | 2 | 2 | 71 | 71 | 1 | 40 | 40 | 40 | 40 | 2 | 79 | 71 | 79 | 71 | 1 | 40 | 79 | 1 | 71 | 79 | 40 | 2 | 4 | 4 | 40 | 79 | 71 | 71 | 4 | 1 | 2 | 1 | 79 | 71 | 40 | 71 | 79 | 79 | 71 | 2 | 2 | 40
102 | 204 | 124 | 279 | 479 | 639 | 647 | 725 | 956 | 1036 | 1202 | 1327 | 1493 | 1576 | 1624 | 4 | 1 | 40 | 79 | 79 | 1 | 71 | 4 | 79 | 40 | 79 | 2 | 79 | 79 | 1 | 1 | 1 | 4 | 2 | 1 | 1 | 2 | 4 | 71 | 71 | 79 | 2 | 79 | 1 | 71 | 4 | 4 | 4 | 79 | 79 | 4 | 79 | 40 | 4 | 2 | 4 | 79 | 79 | 4 | 4 | 4 | 71 | 4 | 2 | 4 | 2 | 40
103 | 161 | 11 | 242 | 326 | 371 | 562 | 723 | 846 | 1040 | 1157 | 1235 | 1389 | 1536 | 1805 | 1 | 2 | 4 | 4 | 79 | 71 | 2 | 79 | 40 | 2 | 40 | 2 | 1 | 40 | 2 | 2 | 71 | 40 | 1 | 79 | 40 | 2 | 40 | 79 | 2 | 79 | 40 | 2 | 79 | 71 | 4 | 40 | 71 | 2 | 40 | 4 | 1 | 2 | 4 | 71 | 2 | 79 | 71 | 2 | 71 | 1 | 71 | 4 | 79 | 40 | 71 | 79
104 | 207 | 199 | 249 | 449 | 690 | 959 | 1189 | 1350 | 1552 | 1708 | 1754 | 1839 | 1844 | 1851 | 79 | 40 | 79 | 1 | 4 | 4 | 40 | 2 | 79 | 40 | 2 | 79 | 79 | 4 | 79 | 79 | 40 | 71 | 79 | 79 | 1 | 79 | 79 | 71 | 1 | 79 | 79 | 2 | 79 | 4 | 40 | 79 | 2 | 4 | 79 | 71 | 1 | 40 | 1 | 4 | 4 | 40 | 1 | 40 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 2
105 | 125 | 45 | 206 | 330 | 408 | 607 | 720 | 953 | 999 | 1159 | 1361 | 1439 | 1553 | 1783 | 1 | 2 | 40 | 2 | 1 | 79 | 2 | 79 | 40 | 4 | 40 | 40 | 1 | 71 | 2 | 4 | 40 | 1 | 79 | 79 | 1 | 71 | 1 | 40 | 4 | 79 | 79 | 71 | 4 | 40 | 1 | 1 | 40 | 40 | 40 | 40 | 79 | 4 | 40 | 79 | 2 | 1 | 71 | 4 | 1 | 2 | 71 | 40 | 40 | 71 | 40 | 79
106 | 174 | 166 | 254 | 370 | 415 | 638 | 832 | 1073 | 1304 | 1425 | 1581 | 1664 | 1903 | 2055 | 4 | 4 | 79 | 79 | 4 | 4 | 79 | 1 | 71 | 1 | 4 | 40 | 40 | 2 | 1 | 2 | 2 | 71 | 71 | 79 | 4 | 79 | 40 | 71 | 79 | 79 | 4 | 79 | 79 | 71 | 2 | 79 | 40 | 1 | 40 | 40 | 2 | 4 | 71 | 79 | 40 | 1 | 40 | 2 | 2 | 79 | 79 | 79 | 79 | 1 | 1 | 71
107 | 235 | 194 | 279 | 367 | 558 | 683 | 831 | 917 | 1072 | 1333 | 1602 | 1609 | 1732 | 1884 | 40 | 4 | 71 | 79 | 40 | 1 | 40 | 4 | 4 | 4 | 1 | 79 | 79 | 1 | 40 | 71 | 40 | 4 | 79 | 2 | 71 | 2 | 4 | 71 | 2 | 40 | 4 | 40 | 79 | 1 | 4 | 71 | 71 | 79 | 71 | 40 | 79 | 71 | 79 | 40 | 1 | 2 | 2 | 2 | 79 | 2 | 2 | 40 | 79 | 1 | 71 | 1
108 | 95 | 89 | 245 | 408 | 497 | 506 | 554 | 707 | 753 | 872 | 1036 | 1112 | 1265 | 1418 | 4 | 4 | 79 | 2 | 4 | 2 | 71 | 79 | 79 | 40 | 4 | 40 | 2 | 4 | 4 | 79 | 2 | 1 | 2 | 4 | 2 | 4 | 2 | 40 | 40 | 2 | 71 | 40 | 40 | 1 | 4 | 1 | 40 | 71 | 4 | 4 | 79 | 2 | 4 | 79 | 2 | 71 | 1 | 2 | 2 | 40 | 71 | 40 | 79 | 2 | 71 | 1
109 | 304 | 300 | 446 | 570 | 862 | 1062 | 1148 | 1194 | 1471 | 1702 | 1860 | 1871 | 1950 | 2072 | 79 | 71 | 79 | 71 | 2 | 2 | 71 | 71 | 40 | 79 | 1 | 4 | 71 | 71 | 71 | 79 | 79 | 79 | 40 | 2 | 1 | 2 | 79 | 4 | 4 | 40 | 1 | 1 | 79 | 79 | 79 | 40 | 2 | 71 | 79 | 79 | 71 | 79 | 4 | 4 | 4 | 1 | 4 | 2 | 4 | 2 | 2 | 71 | 2 | 40 | 79 | 1
110 | 341 | 191 | 343 | 426 | 437 | 512 | 714 | 913 | 1071 | 1219 | 1403 | 1561 | 1610 | 1699 | 71 | 79 | 1 | 40 | 71 | 79 | 1 | 1 | 40 | 1 | 40 | 2 | 4 | 2 | 4 | 1 | 1 | 2 | 71 | 1 | 40 | 4 | 79 | 79 | 40 | 79 | 79 | 1 | 79 | 4 | 71 | 4 | 71 | 71 | 4 | 2 | 40 | 71 | 2 | 71 | 4 | 79 | 71 | 4 | 4 | 4 | 40 | 1 | 4 | 79 | 2 | 4
111 | 280 | 122 | 321 | 475 | 659 | 806 | 854 | 1123 | 1240 | 1325 | 1410 | 1632 | 1720 | 1730 | 40 | 79 | 1 | 2 | 79 | 79 | 1 | 40 | 71 | 79 | 2 | 2 | 71 | 71 | 2 | 40 | 71 | 71 | 1 | 4 | 4 | 2 | 40 | 2 | 79 | 40 | 71 | 79 | 2 | 4 | 40 | 71 | 4 | 1 | 40 | 40 | 1 | 4 | 40 | 40 | 71 | 79 | 71 | 1 | 40 | 4 | 40 | 4 | 1 | 4 | 4 | 1
112 | 165 | 161 | 238 | 325 | 411 | 492 | 608 | 693 | 916 | 963 | 1050 | 1100 | 1256 | 1378 | 40 | 40 | 79 | 2 | 2 | 2 | 2 | 71 | 79 | 2 | 2 | 4 | 1 | 79 | 4 | 2 | 4 | 71 | 4 | 2 | 40 | 71 | 4 | 1 | 79 | 1 | 1 | 4 | 71 | 71 | 2 | 79 | 1 | 4 | 40 | 2 | 4 | 2 | 2 | 79 | 2 | 40 | 4 | 4 | 4 | 79 | 2 | 71 | 1 | 79 | 2 | 40
113 | 160 | 85 | 165 | 171 | 463 | 547 | 708 | 832 | 1026 | 1145 | 1298 | 1412 | 1559 | 1715 | 1 | 40 | 40 | 4 | 4 | 71 | 4 | 1 | 2 | 2 | 1 | 1 | 71 | 79 | 71 | 71 | 2 | 40 | 2 | 40 | 40 | 40 | 79 | 2 | 1 | 40 | 79 | 4 | 40 | 4 | 71 | 79 | 4 | 4 | 40 | 71 | 2 | 1 | 71 | 79 | 71 | 2 | 40 | 1 | 71 | 4 | 1 | 71 | 79 | 71 | 2 | 4
114 | 305 | 186 | 424 | 469 | 625 | 635 | 720 | 873 | 1023 | 1069 | 1291 | 1407 | 1522 | 1643 | 71 | 4 | 40 | 71 | 40 | 79 | 79 | 40 | 2 | 2 | 40 | 1 | 2 | 4 | 71 | 79 | 1 | 4 | 1 | 4 | 2 | 2 | 2 | 79 | 1 | 2 | 71 | 79 | 4 | 71 | 71 | 4 | 2 | 2 | 40 | 2 | 71 | 71 | 79 | 1 | 40 | 71 | 1 | 4 | 2 | 71 | 40 | 2 | 1 | 1 | 79 | 40
115 | 129 | 123 | 248 | 447 | 685 | 798 | 913 | 999 | 1087 | 1348 | 1433 | 1549 | 1709 | 1759 | 2 | 2 | 79 | 40 | 4 | 2 | 79 | 40 | 40 | 40 | 79 | 40 | 79 | 79 | 79 | 1 | 71 | 1 | 1 | 40 | 2 | 71 | 2 | 40 | 2 | 79 | 4 | 1 | 79 | 1 | 4 | 4 | 71 | 71 | 79 | 40 | 4 | 1 | 40 | 40 | 1 | 71 | 40 | 4 | 40 | 79 | 40 | 1 | 40 | 2 | 4 | 4
116 | 194 | 192 | 236 | 400 | 410 | 563 | 715 | 763 | 771 | 857 | 1012 | 1139 | 1333 | 1563 | 2 | 40 | 79 | 71 | 1 | 1 | 40 | 2 | 79 | 2 | 4 | 79 | 2 | 4 | 2 | 2 | 40 | 2 | 71 | 40 | 79 | 71 | 1 | 1 | 2 | 40 | 2 | 4 | 1 | 1 | 4 | 2 | 40 | 4 | 40 | 2 | 4 | 79 | 71 | 1 | 40 | 4 | 79 | 4 | 4 | 71 | 79 | 40 | 71 | 40 | 40 | 79
117 | 159 | 86 | 203 | 250 | 405 | 489 | 613 | 815 | 942 | 1025 | 1111 | 1158 | 1202 | 1354 | 40 | 4 | 40 | 2 | 2 | 71 | 4 | 40 | 4 | 40 | 1 | 2 | 71 | 79 | 4 | 1 | 79 | 2 | 2 | 1 | 4 | 79 | 1 | 40 | 79 | 79 | 4 | 40 | 40 | 79 | 4 | 4 | 2 | 1 | 1 | 79 | 4 | 79 | 2 | 1 | 4 | 2 | 40 | 1 | 2 | 40 | 1 | 1 | 79 | 1 | 71 | 1
118 | 91 | 47 | 166 | 249 | 296 | 380 | 501 | 615 | 622 | 813 | 821 | 896 | 1049 | 1240 | 40 | 4 | 1 | 2 | 40 | 4 | 4 | 71 | 4 | 71 | 4 | 4 | 1 | 40 | 2 | 4 | 2 | 79 | 1 | 2 | 1 | 79 | 40 | 1 | 2 | 1 | 71 | 40 | 4 | 1 | 1 | 1 | 79 | 71 | 1 | 40 | 1 | 1 | 4 | 2 | 1 | 71 | 1 | 2 | 71 | 40 | 2 | 40 | 71 | 40 | 40 | 40
119 | 227 | 222 | 308 | 353 | 363 | 452 | 608 | 831 | 1025 | 1150 | 1238 | 1429 | 1515 | 1631 | 1 | 79 | 71 | 71 | 1 | 4 | 79 | 2 | 1 | 40 | 2 | 2 | 2 | 2 | 4 | 2 | 79 | 4 | 4 | 2 | 2 | 4 | 79 | 71 | 2 | 71 | 79 | 71 | 71 | 40 | 4 | 79 | 40 | 79 | 4 | 2 | 1 | 4 | 4 | 79 | 79 | 1 | 40 | 71 | 2 | 1 | 79 | 4 | 40 | 71 | 4 | 1
120 | 272 | 153 | 313 | 390 | 504 | 618 | 781 | 983 | 1139 | 1188 | 1421 | 1582 | 1658 | 1744 | 1 | 79 | 2 | 71 | 79 | 40 | 1 | 40 | 71 | 1 | 4 | 1 | 2 | 71 | 40 | 1 | 2 | 40 | 1 | 71 | 40 | 4 | 40 | 79 | 79 | 79 | 4 | 40 | 79 | 71 | 4 | 2 | 4 | 40 | 4 | 1 | 71 | 4 | 79 | 79 | 2 | 40 | 40 | 79 | 71 | 2 | 2 | 1 | 1 | 79 | 2 | 4
121 | 336 | 194 | 378 | 505 | 554 | 639 | 756 | 842 | 922 | 1075 | 1229 | 1376 | 1567 | 1614 | 4 | 40 | 79 | 71 | 71 | 71 | 40 | 2 | 4 | 79 | 40 | 4 | 4 | 4 | 40 | 1 | 79 | 4 | 1 | 1 | 2 | 71 | 40 | 4 | 2 | 1 | 79 | 4 | 4 | 1 | 4 | 71 | 71 | 2 | 79 | 1 | 79 | 71 | 2 | 2 | 1 | 71 | 4 | 71 | 71 | 79 | 1 | 40 | 1 | 40 | 2 | 4
122 | 305 | 155 | 385 | 618 | 742 | 983 | 1146 | 1309 | 1464 | 1551 | 1699 | 1826 | 1986 | 2109 | 71 | 4 | 1 | 79 | 71 | 79 | 79 | 1 | 4 | 79 | 71 | 79 | 1 | 40 | 79 | 4 | 79 | 79 | 79 | 4 | 4 | 40 | 79 | 40 | 4 | 79 | 40 | 40 | 71 | 1 | 4 | 79 | 2 | 2 | 79 | 4 | 4 | 71 | 71 | 2 | 79 | 4 | 40 | 4 | 1 | 1 | 79 | 79 | 2 | 2 | 79 | 40
123 | 95 | 87 | 97 | 183 | 366 | 453 | 464 | 666 | 787 | 979 | 1101 | 1370 | 1564 | 1712 | 4 | 79 | 2 | 2 | 4 | 4 | 1 | 1 | 4 | 79 | 2 | 1 | 1 | 71 | 71 | 40 | 2 | 4 | 79 | 2 | 4 | 4 | 1 | 2 | 40 | 4 | 79 | 79 | 40 | 1 | 40 | 40 | 2 | 40 | 71 | 79 | 2 | 40 | 79 | 1 | 79 | 40 | 79 | 71 | 4 | 79 | 40 | 71 | 2 | 4 | 71 | 71
124 | 169 | 50 | 172 | 296 | 557 | 710 | 795 | 808 | 1002 | 1127 | 1211 | 1327 | 1557 | 1810 | 4 | 40 | 4 | 2 | 40 | 79 | 1 | 2 | 79 | 40 | 1 | 4 | 71 | 79 | 71 | 40 | 1 | 2 | 79 | 71 | 2 | 2 | 2 | 79 | 4 | 4 | 1 | 4 | 4 | 79 | 40 | 71 | 40 | 4 | 79 | 2 | 2 | 79 | 2 | 1 | 40 | 1 | 71 | 4 | 71 | 79 | 79 | 1 | 71 | 71 | 40 | 71
125 | 84 | 82 | 242 | 247 | 364 | 516 | 632 | 753 | 911 | 1103 | 1286 | 1441 | 1625 | 1809 | 1 | 1 | 40 | 40 | 1 | 1 | 79 | 79 | 1 | 1 | 1 | 2 | 40 | 4 | 2 | 71 | 1 | 40 | 71 | 40 | 71 | 40 | 1 | 4 | 1 | 40 | 79 | 1 | 4 | 4 | 71 | 79 | 71 | 2 | 79 | 40 | 40 | 71 | 1 | 71 | 4 | 79 | 1 | 71 | 2 | 71 | 40 | 71 | 71 | 40 | 71 | 2
126 | 197 | 47 | 203 | 363 | 412 | 556 | 647 | 838 | 849 | 858 | 1080 | 1232 | 1356 | 1517 | 1 | 40 | 4 | 2 | 71 | 79 | 2 | 4 | 79 | 79 | 1 | 1 | 40 | 4 | 4 | 1 | 71 | 1 | 1 | 71 | 4 | 4 | 79 | 4 | 40 | 1 | 71 | 79 | 4 | 1 | 4 | 2 | 4 | 1 | 2 | 2 | 79 | 71 | 1 | 71 | 40 | 71 | 1 | 40 | 1 | 40 | 79 | 4 | 1 | 79 | 2 | 79
127 | 231 | 81 | 381 | 545 | 624 | 854 | 899 | 1013 | 1126 | 1215 | 1407 | 1606 | 1883 | 1997 | 2 | 4 | 71 | 4 | 79 | 71 | 79 | 71 | 79 | 79 | 4 | 2 | 71 | 2 | 4 | 2 | 71 | 79 | 1 | 79 | 2 | 40 | 2 | 1 | 40 | 1 | 2 | 71 | 1 | 40 | 1 | 71 | 79 | 4 | 2 | 4 | 2 | 40 | 79 | 71 | 40 | 1 | 79 | 79 | 79 | 79 | 40 | 79 | 2 | 40 | 71 | 1
128 | 318 | 199 | 359 | 628 | 827 | 952 | 1076 | 1123 | 1325 | 1439 | 1630 | 1852 | 1969 | 2261 | 79 | 79 | 40 | 1 | 40 | 79 | 1 | 40 | 71 | 40 | 79 | 79 | 79 | 40 | 79 | 1 | 40 | 4 | 79 | 2 | 40 | 79 | 1 | 4 | 2 | 4 | 40 | 1 | 4 | 79 | 40 | 79 | 1 | 71 | 2 | 40 | 40 | 40 | 71 | 40 | 71 | 79 | 1 | 71 | 2 | 71 | 40 | 4 | 71 | 71 | 71 | 79
129 | 232 | 152 | 351 | 397 | 409 | 572 | 864 | 942 | 1092 | 1214 | 1413 | 1605 | 1766 | 1983 | 1 | 71 | 79 | 1 | 79 | 1 | 79 | 40 | 2 | 2 | 2 | 40 | 4 | 4 | 2 | 2 | 4 | 40 | 40 | 79 | 71 | 79 | 71 | 71 | 71 | 2 | 4 | 1 | 71 | 4 | 71 | 4 | 40 | 2 | 79 | 1 | 40 | 40 | 40 | 79 | 71 | 79 | 2 | 40 | 2 | 40 | 79 | 40 | 71 | 71 | 71 | 4
130 | 159 | 155 | 309 | 398 | 519 | 666 | 712 | 859 | 1014 | 1161 | 1355 | 1539 | 1622 | 1739 | 1 | 71 | 4 | 79 | 2 | 2 | 71 | 79 | 79 | 4 | 4 | 2 | 40 | 40 | 1 | 40 | 71 | 4 | 1 | 71 | 40 | 2 | 2 | 2 | 4 | 71 | 71 | 1 | 4 | 1 | 79 | 71 | 1 | 71 | 71 | 4 | 79 | 71 | 4 | 40 | 40 | 71 | 2 | 71 | 79 | 2 | 1 | 1 | 2 | 4 | 40 | 71
131 | 226 | 222 | 309 | 389 | 476 | 714 | 906 | 1147 | 1263 | 1377 | 1389 | 1473 | 1704 | 1903 | 40 | 71 | 40 | 71 | 2 | 2 | 79 | 4 | 4 | 1 | 4 | 71 | 2 | 2 | 4 | 79 | 1 | 79 | 79 | 79 | 2 | 79 | 40 | 71 | 79 | 4 | 79 | 79 | 4 | 1 | 71 | 40 | 40 | 2 | 1 | 71 | 4 | 2 | 4 | 2 | 40 | 2 | 40 | 2 | 71 | 79 | 79 | 2 | 79 | 40 | 79 | 1
132 | 199 | 88 | 280 | 360 | 438 | 554 | 715 | 803 | 964 | 1080 | 1155 | 1318 | 1396 | 1595 | 40 | 4 | 40 | 4 | 40 | 71 | 79 | 2 | 4 | 1 | 71 | 4 | 71 | 2 | 4 | 1 | 1 | 71 | 40 | 4 | 2 | 79 | 40 | 40 | 4 | 4 | 79 | 1 | 2 | 79 | 40 | 40 | 1 | 4 | 40 | 71 | 2 | 1 | 1 | 71 | 4 | 40 | 40 | 79 | 2 | 1 | 71 | 4 | 79 | 1 | 40 | 79
133 | 204 | 160 | 287 | 364 | 448 | 494 | 568 | 615 | 730 | 813 | 1113 | 1268 | 1421 | 1567 | 40 | 1 | 40 | 79 | 40 | 4 | 79 | 4 | 71 | 4 | 1 | 1 | 79 | 2 | 2 | 1 | 40 | 4 | 1 | 1 | 1 | 1 | 1 | 71 | 2 | 4 | 1 | 40 | 2 | 40 | 71 | 2 | 79 | 1 | 2 | 1 | 79 | 71 | 79 | 71 | 4 | 40 | 71 | 40 | 40 | 2 | 71 | 40 | 71 | 71 | 2 | 2
134 | 155 | 83 | 266 | 313 | 497 | 611 | 694 | 740 | 906 | 984 | 1207 | 1360 | 1449 | 1532 | 4 | 4 | 71 | 4 | 1 | 71 | 40 | 71 | 4 | 40 | 1 | 2 | 71 | 40 | 71 | 2 | 71 | 40 | 2 | 1 | 40 | 40 | 1 | 2 | 1 | 1 | 40 | 4 | 4 | 4 | 79 | 79 | 1 | 2 | 71 | 4 | 71 | 71 | 79 | 2 | 2 | 79 | 1 | 71 | 4 | 79 | 4 | 2 | 40 | 1 | 40 | 2
135 | 235 | 191 | 310 | 426 | 649 | 805 | 1030 | 1157 | 1235 | 1390 | 1543 | 1745 | 1819 | 1830 | 1 | 40 | 71 | 79 | 40 | 4 | 4 | 71 | 1 | 4 | 71 | 40 | 79 | 2 | 71 | 71 | 2 | 71 | 79 | 4 | 79 | 71 | 71 | 4 | 4 | 79 | 40 | 4 | 2 | 1 | 71 | 4 | 79 | 71 | 4 | 1 | 71 | 79 | 2 | 1 | 79 | 79 | 4 | 40 | 1 | 1 | 71 | 1 | 4 | 2 | 4 | 1
136 | 197 | 86 | 277 | 285 | 408 | 716 | 830 | 877 | 922 | 1161 | 1288 | 1335 | 1535 | 1693 | 79 | 4 | 2 | 1 | 71 | 40 | 40 | 40 | 1 | 2 | 1 | 4 | 2 | 79 | 2 | 40 | 79 | 71 | 79 | 79 | 2 | 1 | 40 | 71 | 40 | 2 | 1 | 4 | 2 | 1 | 2 | 40 | 79 | 79 | 79 | 2 | 4 | 4 | 40 | 79 | 40 | 4 | 1 | 2 | 40 | 79 | 79 | 2 | 4 | 4 | 79 | 71
137 | 118 | 43 | 276 | 361 | 560 | 638 | 763 | 813 | 969 | 1060 | 1137 | 1292 | 1414 | 1675 | 1 | 1 | 40 | 1 | 71 | 4 | 79 | 79 | 1 | 40 | 40 | 4 | 79 | 40 | 40 | 40 | 1 | 4 | 71 | 2 | 2 | 4 | 79 | 40 | 4 | 2 | 4 | 40 | 71 | 4 | 2 | 79 | 4 | 4 | 4 | 79 | 71 | 1 | 1 | 4 | 40 | 71 | 40 | 4 | 1 | 79 | 2 | 40 | 71 | 79 | 71 | 40
138 | 52 | 50 | 133 | 213 | 265 | 353 | 444 | 530 | 791 | 1024 | 1182 | 1229 | 1307 | 1429 | 2 | 40 | 4 | 4 | 1 | 1 | 79 | 2 | 4 | 1 | 71 | 4 | 4 | 4 | 4 | 40 | 40 | 4 | 4 | 40 | 4 | 4 | 79 | 4 | 79 | 4 | 2 | 1 | 71 | 79 | 71 | 40 | 71 | 4 | 79 | 79 | 71 | 4 | 79 | 4 | 1 | 4 | 2 | 40 | 71 | 2 | 1 | 4 | 1 | 40 | 79 | 2
139 | 200 | 117 | 280 | 403 | 597 | 789 | 794 | 880 | 930 | 1168 | 1331 | 1523 | 1709 | 1714 | 2 | 71 | 4 | 40 | 79 | 4 | 79 | 1 | 2 | 2 | 40 | 79 | 71 | 4 | 79 | 40 | 40 | 71 | 79 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 79 | 4 | 4 | 4 | 2 | 40 | 1 | 79 | 79 | 79 | 1 | 79 | 4 | 79 | 40 | 79 | 71 | 2 | 71 | 40 | 4 | 71 | 1 | 1 | 1 | 2
140 | 166 | 161 | 208 | 252 | 368 | 528 | 745 | 959 | 1159 | 1284 | 1369 | 1591 | 1641 | 1754 | 79 | 2 | 1 | 79 | 1 | 4 | 2 | 40 | 2 | 1 | 1 | 40 | 40 | 1 | 71 | 4 | 79 | 1 | 40 | 40 | 71 | 4 | 71 | 71 | 71 | 71 | 71 | 1 | 79 | 40 | 2 | 79 | 4 | 79 | 40 | 2 | 1 | 40 | 40 | 4 | 1 | 71 | 71 | 79 | 40 | 2 | 4 | 4 | 1 | 1 | 71 | 40
141 | 133 | 127 | 175 | 328 | 442 | 518 | 671 | 827 | 879 | 1112 | 1264 | 1416 | 1716 | 1762 | 40 | 4 | 79 | 4 | 4 | 2 | 40 | 2 | 40 | 71 | 40 | 2 | 40 | 2 | 1 | 71 | 2 | 2 | 1 | 71 | 40 | 2 | 71 | 40 | 2 | 71 | 79 | 4 | 4 | 4 | 4 | 40 | 79 | 4 | 79 | 71 | 1 | 1 | 71 | 79 | 1 | 1 | 71 | 79 | 71 | 79 | 71 | 79 | 2 | 2 | 40 | 2
142 | 271 | 199 | 276 | 281 | 357 | 472 | 557 | 782 | 792 | 1023 | 1331 | 1340 | 1456 | 1503 | 1 | 79 | 40 | 79 | 71 | 1 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 71 | 2 | 2 | 2 | 40 | 71 | 79 | 4 | 1 | 1 | 4 | 71 | 71 | 79 | 4 | 2 | 2 | 2 | 71 | 79 | 2 | 79 | 79 | 79 | 79 | 71 | 1 | 2 | 2 | 4 | 40 | 1 | 4 | 71 | 4 | 40 | 2 | 1
143 | 233 | 230 | 313 | 396 | 480 | 491 | 615 | 737 | 821 | 934 | 1134 | 1328 | 1452 | 1497 | 79 | 40 | 71 | 40 | 2 | 1 | 1 | 79 | 4 | 4 | 4 | 71 | 79 | 2 | 2 | 1 | 4 | 1 | 4 | 2 | 4 | 79 | 1 | 40 | 2 | 40 | 1 | 79 | 1 | 2 | 79 | 2 | 1 | 1 | 40 | 71 | 40 | 2 | 79 | 79 | 4 | 40 | 79 | 71 | 1 | 4 | 40 | 79 | 1 | 2 | 2 | 40
144 | 160 | 152 | 240 | 325 | 339 | 347 | 435 | 626 | 741 | 750 | 975 | 1123 | 1275 | 1400 | 71 | 1 | 40 | 40 | 4 | 4 | 1 | 79 | 1 | 40 | 4 | 40 | 4 | 4 | 4 | 2 | 1 | 1 | 4 | 2 | 4 | 1 | 79 | 4 | 1 | 40 | 79 | 71 | 2 | 40 | 71 | 2 | 2 | 4 | 2 | 1 | 71 | 71 | 4 | 79 | 2 | 71 | 4 | 71 | 1 | 40 | 40 | 71 | 79 | 4 | 2 | 40
145 | 202 | 121 | 285 | 363 | 444 | 568 | 652 | 738 | 859 | 1022 | 1107 | 1156 | 1163 | 1349 | 40 | 40 | 1 | 40 | 79 | 2 | 4 | 79 | 2 | 71 | 1 | 4 | 71 | 4 | 2 | 4 | 1 | 4 | 40 | 79 | 40 | 2 | 40 | 2 | 79 | 1 | 4 | 2 | 1 | 79 | 1 | 40 | 79 | 40 | 40 | 4 | 1 | 4 | 1 | 79 | 4 | 40 | 1 | 4 | 2 | 2 | 2 | 1 | 71 | 71 | 4 | 40
146 | 166 | 122 | 241 | 247 | 402 | 594 | 640 | 794 | 918 | 1004 | 1198 | 1400 | 1517 | 1747 | 2 | 79 | 1 | 40 | 4 | 40 | 4 | 71 | 1 | 1 | 2 | 2 | 1 | 79 | 71 | 4 | 71 | 2 | 79 | 40 | 4 | 1 | 40 | 1 | 71 | 2 | 2 | 79 | 79 | 1 | 40 | 4 | 40 | 40 | 2 | 4 | 79 | 4 | 40 | 71 | 79 | 79 | 4 | 40 | 2 | 4 | 40 | 71 | 40 | 79 | 40 | 71
147 | 271 | 160 | 382 | 581 | 666 | 896 | 1049 | 1197 | 1352 | 1506 | 1728 | 1775 | 1824 | 2008 | 79 | 1 | 79 | 1 | 71 | 40 | 71 | 40 | 79 | 40 | 1 | 79 | 40 | 1 | 40 | 4 | 40 | 71 | 40 | 79 | 40 | 71 | 40 | 2 | 71 | 2 | 71 | 4 | 4 | 1 | 79 | 71 | 71 | 79 | 2 | 2 | 71 | 71 | 1 | 79 | 4 | 1 | 2 | 40 | 40 | 4 | 4 | 1 | 40 | 71 | 2 | 71
148 | 193 | 82 | 273 | 436 | 636 | 721 | 837 | 1029 | 1306 | 1394 | 1671 | 1819 | 1941 | 2095 | 40 | 40 | 1 | 1 | 40 | 71 | 79 | 1 | 40 | 40 | 4 | 79 | 79 | 79 | 2 | 40 | 40 | 40 | 1 | 4 | 40 | 1 | 71 | 4 | 40 | 79 | 71 | 2 | 79 | 40 | 79 | 79 | 4 | 40 | 4 | 40 | 79 | 79 | 40 | 79 | 2 | 4 | 71 | 71 | 40 | 2 | 1 | 79 | 2 | 2 | 79 | 71
149 | 169 | 163 | 211 | 411 | 526 | 603 | 727 | 843 | 1073 | 1227 | 1421 | 1615 | 1837 | 1920 | 79 | 4 | 40 | 40 | 4 | 2 | 2 | 40 | 79 | 40 | 2 | 79 | 2 | 2 | 71 | 40 | 1 | 71 | 4 | 1 | 40 | 4 | 1 | 79 | 40 | 71 | 4 | 1 | 79 | 71 | 40 | 40 | 79 | 2 | 71 | 2 | 71 | 79 | 4 | 40 | 4 | 40 | 71 | 79 | 1 | 71 | 79 | 71 | 40 | 40 | 2 | 1
150 | 350 | 269 | 508 | 519 | 671 | 826 | 950 | 1144 | 1191 | 1354 | 1473 | 1703 | 1855 | 1977 | 40 | 79 | 79 | 71 | 79 | 2 | 79 | 79 | 1 | 2 | 4 | 4 | 71 | 1 | 79 | 1 | 71 | 4 | 40 | 40 | 40 | 1 | 4 | 79 | 4 | 40 | 79 | 71 | 4 | 2 | 1 | 40 | 79 | 4 | 40 | 40 | 4 | 4 | 40 | 71 | 1 | 79 | 71 | 79 | 1 | 1 | 79 | 71 | 79 | 2 | 1 | 40
151 | 224 | 144 | 299 | 424 | 615 | 662 | 740 | 855 | 863 | 946 | 1022 | 1338 | 1423 | 1509 | 1 | 1 | 71 | 71 | 79 | 1 | 4 | 71 | 2 | 4 | 40 | 79 | 79 | 40 | 71 | 1 | 1 | 2 | 4 | 40 | 2 | 1 | 4 | 71 | 71 | 2 | 2 | 40 | 2 | 4 | 1 | 1 | 1 | 2 | 1 | 79 | 2 | 1 | 2 | 71 | 79 | 79 | 79 | 79 | 2 | 2 | 79 | 2 | 79 | 1 | 2 | 4
152 | 275 | 164 | 358 | 541 | 704 | 851 | 1112 | 1203 | 1279 | 1365 | 1481 | 1711 | 1903 | 2050 | 2 | 79 | 4 | 79 | 71 | 40 | 79 | 4 | 40 | 71 | 71 | 1 | 40 | 79 | 4 | 40 | 71 | 4 | 71 | 1 | 71 | 71 | 40 | 79 | 79 | 4 | 4 | 4 | 2 | 71 | 2 | 1 | 1 | 79 | 4 | 2 | 1 | 4 | 40 | 71 | 40 | 79 | 40 | 71 | 79 | 40 | 71 | 2 | 4 | 71 | 1 | 71
153 | 264 | 122 | 270 | 283 | 360 | 474 | 595 | 673 | 718 | 909 | 998 | 1122 | 1305 | 1426 | 40 | 2 | 79 | 1 | 71 | 71 | 4 | 2 | 4 | 4 | 4 | 1 | 71 | 1 | 4 | 1 | 2 | 71 | 1 | 40 | 40 | 1 | 79 | 1 | 71 | 4 | 1 | 2 | 2 | 40 | 1 | 2 | 40 | 79 | 71 | 1 | 4 | 2 | 79 | 4 | 40 | 1 | 4 | 79 | 71 | 1 | 71 | 40 | 1 | 1 | 79 | 40
154 | 127 | 44 | 135 | 221 | 307 | 548 | 600 | 822 | 941 | 1171 | 1217 | 1223 | 1423 | 1547 | 2 | 1 | 40 | 1 | 79 | 4 | 4 | 4 | 79 | 4 | 1 | 2 | 40 | 2 | 40 | 4 | 79 | 79 | 4 | 79 | 40 | 4 | 4 | 4 | 71 | 40 | 40 | 71 | 4 | 71 | 4 | 40 | 1 | 79 | 71 | 79 | 2 | 40 | 2 | 2 | 2 | 2 | 1 | 1 | 40 | 79 | 2 | 79 | 4 | 40 | 1 | 79
155 | 236 | 153 | 244 | 474 | 627 | 752 | 827 | 949 | 954 | 1079 | 1271 | 1355 | 1541 | 1617 | 79 | 71 | 1 | 2 | 79 | 4 | 4 | 4 | 79 | 71 | 40 | 40 | 40 | 2 | 40 | 71 | 79 | 2 | 40 | 4 | 1 | 71 | 2 | 1 | 40 | 40 | 40 | 2 | 1 | 2 | 1 | 1 | 4 | 79 | 40 | 2 | 40 | 2 | 79 | 71 | 2 | 1 | 2 | 79 | 71 | 40 | 71 | 4 | 2 | 2 | 1 | 71
156 | 226 | 184 | 298 | 385 | 463 | 657 | 887 | 970 | 1161 | 1244 | 1293 | 1445 | 1493 | 1582 | 40 | 71 | 71 | 2 | 40 | 2 | 71 | 1 | 2 | 79 | 2 | 4 | 71 | 4 | 2 | 1 | 4 | 79 | 71 | 40 | 79 | 71 | 79 | 1 | 1 | 79 | 1 | 2 | 71 | 1 | 79 | 40 | 1 | 2 | 40 | 40 | 4 | 1 | 40 | 4 | 1 | 79 | 1 | 71 | 40 | 2 | 4 | 2 | 4 | 79 | 2 | 4
157 | 87 | 84 | 198 | 364 | 445 | 670 | 720 | 835 | 948 | 1111 | 1333 | 1485 | 1570 | 1792 | 40 | 2 | 2 | 40 | 1 | 2 | 71 | 40 | 79 | 79 | 4 | 4 | 71 | 4 | 4 | 2 | 71 | 4 | 71 | 79 | 4 | 40 | 2 | 4 | 40 | 2 | 71 | 2 | 40 | 71 | 1 | 1 | 79 | 79 | 1 | 4 | 1 | 71 | 71 | 79 | 40 | 71 | 1 | 40 | 40 | 40 | 1 | 4 | 71 | 71 | 79 | 1
158 | 196 | 155 | 199 | 283 | 292 | 413 | 504 | 659 | 814 | 899 | 1015 | 1217 | 1265 | 1426 | 71 | 40 | 4 | 40 | 1 | 40 | 1 | 2 | 40 | 2 | 40 | 2 | 1 | 4 | 2 | 2 | 1 | 1 | 79 | 40 | 4 | 4 | 79 | 4 | 4 | 79 | 71 | 1 | 4 | 71 | 40 | 40 | 79 | 4 | 1 | 1 | 4 | 40 | 71 | 1 | 40 | 4 | 79 | 79 | 40 | 2 | 2 | 4 | 79 | 1 | 79 | 2
159 | 313 | 155 | 396 | 618 | 778 | 825 | 1056 | 1240 | 1356 | 1501 | 1623 | 1740 | 1890 | 2046 | 79 | 1 | 4 | 71 | 79 | 79 | 4 | 79 | 71 | 79 | 71 | 1 | 1 | 40 | 79 | 40 | 40 | 2 | 1 | 4 | 79 | 79 | 71 | 2 | 2 | 71 | 71 | 40 | 1 | 71 | 4 | 40 | 71 | 71 | 2 | 1 | 40 | 40 | 40 | 2 | 40 | 2 | 4 | 71 | 4 | 71 | 4 | 71 | 2 | 71 | 79 | 4
160 | 373 | 231 | 453 | 577 | 661 | 845 | 1003 | 1156 | 1348 | 1428 | 1513 | 1590 | 1784 | 1796 | 79 | 79 | 71 | 2 | 71 | 71 | 79 | 1 | 79 | 40 | 1 | 4 | 1 | 2 | 2 | 79 | 71 | 71 | 40 | 2 | 79 | 4 | 4 | 71 | 71 | 1 | 2 | 79 | 79 | 71 | 2 | 40 | 4 | 71 | 1 | 4 | 79 | 1 | 1 | 4 | 2 | 71 | 2 | 2 | 71 | 79 | 4 | 40 | 2 | 2 | 4 | 4
161 | 79 | 75 | 160 | 315 | 361 | 519 | 667 | 755 | 911 | 1180 | 1293 | 1459 | 1506 | 1690 | 1 | 71 | 1 | 2 | 2 | 2 | 79 | 2 | 79 | 4 | 71 | 1 | 40 | 2 | 2 | 2 | 4 | 71 | 79 | 4 | 71 | 71 | 2 | 4 | 4 | 1 | 4 | 79 | 71 | 4 | 2 | 79 | 71 | 79 | 40 | 79 | 71 | 1 | 40 | 1 | 79 | 79 | 4 | 4 | 1 | 4 | 40 | 2 | 71 | 40 | 71 | 2
162 | 318 | 199 | 468 | 552 | 707 | 790 | 945 | 1108 | 1224 | 1457 | 1541 | 1616 | 1766 | 1816 | 40 | 40 | 40 | 79 | 79 | 40 | 79 | 71 | 40 | 2 | 2 | 40 | 71 | 79 | 1 | 4 | 79 | 1 | 1 | 2 | 4 | 40 | 71 | 40 | 4 | 79 | 1 | 79 | 4 | 71 | 40 | 1 | 4 | 79 | 71 | 79 | 1 | 2 | 79 | 2 | 1 | 2 | 1 | 71 | 4 | 71 | 71 | 4 | 2 | 4 | 40 | 4
163 | 194 | 152 | 336 | 453 | 462 | 615 | 731 | 914 | 966 | 1119 | 1127 | 1136 | 1336 | 1535 | 40 | 1 | 71 | 40 | 2 | 40 | 71 | 71 | 2 | 71 | 4 | 40 | 2 | 1 | 2 | 4 | 40 | 2 | 40 | 71 | 40 | 1 | 4 | 71 | 40 | 71 | 1 | 71 | 40 | 4 | 4 | 4 | 71 | 2 | 1 | 79 | 1 | 2 | 1 | 4 | 2 | 2 | 1 | 4 | 40 | 2 | 79 | 79 | 40 | 79 | 1 | 79
164 | 267 | 192 | 347 | 538 | 815 | 1084 | 1284 | 1409 | 1600 | 1763 | 1839 | 1960 | 2177 | 2485 | 79 | 40 | 2 | 71 | 4 | 71 | 40 | 40 | 79 | 40 | 71 | 1 | 79 | 79 | 79 | 40 | 71 | 79 | 79 | 40 | 40 | 2 | 79 | 79 | 79 | 2 | 4 | 40 | 71 | 1 | 40 | 79 | 4 | 40 | 79 | 40 | 1 | 2 | 2 | 71 | 40 | 1 | 79 | 1 | 71 | 4 | 71 | 71 | 79 | 79 | 71 | 79
165 | 227 | 155 | 230 | 384 | 472 | 597 | 827 | 980 | 1097 | 1143 | 1265 | 1427 | 1590 | 1634 | 79 | 1 | 4 | 71 | 1 | 71 | 1 | 2 | 71 | 2 | 2 | 79 | 4 | 1 | 4 | 79 | 2 | 79 | 4 | 40 | 40 | 79 | 40 | 71 | 71 | 2 | 79 | 1 | 2 | 4 | 71 | 40 | 4 | 1 | 40 | 1 | 79 | 1 | 2 | 40 | 79 | 2 | 2 | 79 | 79 | 79 | 1 | 4 | 40 | 1 | 1 | 2
166 | 87 | 84 | 128 | 405 | 565 | 690 | 853 | 1092 | 1173 | 1220 | 1381 | 1673 | 1756 | 1979 | 1 | 2 | 79 | 2 | 2 | 1 | 40 | 1 | 79 | 79 | 79 | 40 | 1 | 79 | 40 | 40 | 2 | 79 | 4 | 40 | 40 | 40 | 4 | 79 | 79 | 2 | 79 | 79 | 4 | 71 | 4 | 2 | 1 | 40 | 4 | 2 | 40 | 79 | 2 | 40 | 71 | 79 | 71 | 71 | 40 | 40 | 1 | 2 | 71 | 2 | 79 | 71
167 | 349 | 230 | 355 | 511 | 556 | 634 | 759 | 914 | 1069 | 1263 | 1488 | 1536 | 1618 | 1810 | 1 | 71 | 79 | 79 | 40 | 79 | 2 | 4 | 71 | 4 | 79 | 2 | 1 | 2 | 2 | 40 | 71 | 2 | 4 | 1 | 4 | 40 | 79 | 2 | 4 | 71 | 79 | 1 | 1 | 71 | 79 | 4 | 4 | 71 | 40 | 79 | 4 | 79 | 71 | 71 | 2 | 40 | 2 | 4 | 1 | 1 | 79 | 1 | 79 | 71 | 2 | 40
168 | 264 | 145 | 383 | 505 | 619 | 663 | 854 | 1004 | 1190 | 1265 | 1465 | 1587 | 1670 | 1717 | 71 | 1 | 2 | 71 | 40 | 79 | 79 | 40 | 79 | 2 | 40 | 1 | 1 | 71 | 2 | 40 | 1 | 40 | 1 | 2 | 40 | 79 | 71 | 1 | 71 | 71 | 4 | 4 | 40 | 71 | 4 | 71 | 71 | 1 | 1 | 2 | 79 | 2 | 40 | 79 | 2 | 1 | 40 | 79 | 1 | 2 | 79 | 1 | 1 | 4 | 2 | 40
169 | 123 | 117 | 129 | 142 | 225 | 377 | 499 | 544 | 621 | 913 | 1040 | 1123 | 1289 | 1372 | 71 | 40 | 2 | 4 | 2 | 4 | 2 | 4 | 4 | 1 | 4 | 4 | 4 | 4 | 71 | 4 | 1 | 40 | 40 | 71 | 1 | 79 | 40 | 2 | 2 | 2 | 40 | 1 | 1 | 4 | 1 | 71 | 71 | 71 | 71 | 79 | 4 | 4 | 79 | 40 | 1 | 40 | 2 | 40 | 79 | 4 | 79 | 4 | 1 | 79 | 2 | 1
170 | 308 | 150 | 391 | 507 | 760 | 768 | 889 | 974 | 1099 | 1252 | 1299 | 1305 | 1497 | 1611 | 4 | 4 | 71 | 71 | 79 | 79 | 4 | 79 | 71 | 1 | 40 | 4 | 71 | 40 | 71 | 71 | 1 | 1 | 2 | 4 | 40 | 1 | 40 | 40 | 79 | 4 | 1 | 1 | 79 | 40 | 4 | 2 | 1 | 2 | 79 | 71 | 4 | 40 | 1 | 2 | 2 | 1 | 1 | 2 | 40 | 2 | 71 | 79 | 71 | 1 | 2 | 40
171 | 11 | 6 | 169 | 394 | 521 | 743 | 895 | 1125 | 1211 | 1367 | 1600 | 1725 | 1916 | 2071 | 2 | 1 | 1 | 2 | 1 | 4 | 79 | 79 | 79 | 4 | 71 | 71 | 4 | 79 | 40 | 4 | 71 | 1 | 71 | 79 | 71 | 79 | 1 | 1 | 79 | 71 | 79 | 1 | 2 | 79 | 4 | 1 | 79 | 4 | 2 | 71 | 4 | 79 | 71 | 79 | 2 | 4 | 40 | 79 | 40 | 71 | 40 | 40 | 79 | 1 | 4 | 71
172 | 165 | 123 | 171 | 373 | 459 | 538 | 654 | 661 | 875 | 953 | 962 | 1118 | 1281 | 1481 | 2 | 2 | 79 | 40 | 2 | 40 | 4 | 2 | 40 | 79 | 4 | 79 | 2 | 4 | 40 | 40 | 4 | 2 | 71 | 2 | 4 | 71 | 1 | 40 | 2 | 2 | 2 | 1 | 1 | 71 | 71 | 71 | 1 | 71 | 2 | 4 | 2 | 1 | 4 | 2 | 71 | 2 | 4 | 79 | 40 | 79 | 40 | 4 | 79 | 79 | 2 | 40
173 | 199 | 124 | 310 | 435 | 512 | 672 | 820 | 908 | 1071 | 1293 | 1369 | 1454 | 1537 | 1806 | 79 | 40 | 1 | 4 | 71 | 4 | 71 | 40 | 79 | 4 | 2 | 40 | 1 | 1 | 4 | 71 | 40 | 1 | 79 | 40 | 4 | 71 | 2 | 71 | 4 | 4 | 1 | 79 | 79 | 79 | 1 | 4 | 1 | 71 | 71 | 79 | 2 | 1 | 2 | 71 | 79 | 4 | 1 | 1 | 40 | 2 | 40 | 1 | 40 | 71 | 79 | 79
174 | 234 | 161 | 307 | 429 | 659 | 774 | 935 | 1019 | 1026 | 1111 | 1118 | 1270 | 1433 | 1580 | 2 | 79 | 40 | 40 | 2 | 71 | 2 | 71 | 1 | 40 | 2 | 79 | 40 | 79 | 71 | 40 | 2 | 40 | 71 | 2 | 79 | 2 | 79 | 1 | 2 | 40 | 2 | 40 | 2 | 1 | 2 | 2 | 1 | 4 | 79 | 1 | 2 | 2 | 1 | 2 | 1 | 71 | 40 | 40 | 79 | 4 | 1 | 79 | 4 | 71 | 1 | 71
175 | 313 | 233 | 386 | 580 | 693 | 772 | 927 | 1080 | 1088 | 1241 | 1368 | 1609 | 1870 | 1947 | 79 | 79 | 71 | 4 | 79 | 1 | 2 | 71 | 71 | 79 | 40 | 4 | 71 | 40 | 1 | 1 | 2 | 4 | 2 | 71 | 71 | 79 | 1 | 4 | 2 | 71 | 40 | 40 | 4 | 2 | 1 | 1 | 40 | 40 | 71 | 2 | 4 | 4 | 40 | 79 | 79 | 79 | 79 | 4 | 71 | 71 | 40 | 79 | 4 | 71 | 1 | 1
176 | 160 | 85 | 302 | 388 | 474 | 588 | 779 | 903 | 1048 | 1204 | 1281 | 1367 | 1376 | 1421 | 4 | 40 | 1 | 40 | 4 | 71 | 71 | 71 | 4 | 1 | 79 | 2 | 79 | 4 | 1 | 2 | 2 | 71 | 40 | 1 | 79 | 1 | 40 | 71 | 40 | 40 | 40 | 4 | 1 | 71 | 2 | 71 | 2 | 71 | 79 | 4 | 4 | 1 | 71 | 1 | 79 | 2 | 1 | 4 | 2 | 2 | 4 | 1 | 40 | 1 | 2 | 2
177 | 15 | 12 | 98 | 108 | 322 | 439 | 524 | 573 | 658 | 880 | 1113 | 1228 | 1303 | 1426 | 2 | 4 | 4 | 2 | 1 | 2 | 4 | 79 | 4 | 1 | 4 | 1 | 71 | 71 | 71 | 1 | 71 | 2 | 4 | 40 | 40 | 4 | 40 | 1 | 4 | 40 | 4 | 1 | 40 | 4 | 40 | 1 | 40 | 71 | 40 | 71 | 71 | 79 | 4 | 79 | 40 | 71 | 2 | 2 | 71 | 2 | 1 | 1 | 40 | 2 | 79 | 2
178 | 195 | 153 | 270 | 493 | 573 | 767 | 961 | 1238 | 1468 | 1518 | 1718 | 1872 | 2095 | 2142 | 2 | 1 | 71 | 79 | 2 | 40 | 4 | 71 | 2 | 71 | 71 | 79 | 1 | 4 | 4 | 71 | 79 | 71 | 4 | 40 | 4 | 40 | 79 | 71 | 79 | 40 | 79 | 79 | 79 | 79 | 1 | 71 | 2 | 4 | 4 | 40 | 40 | 79 | 79 | 2 | 79 | 71 | 2 | 2 | 71 | 79 | 2 | 71 | 4 | 40 | 2 | 1
179 | 269 | 158 | 272 | 463 | 619 | 767 | 894 | 1077 | 1155 | 1234 | 1495 | 1619 | 1668 | 1862 | 4 | 79 | 4 | 71 | 71 | 40 | 1 | 2 | 71 | 40 | 79 | 1 | 79 | 4 | 71 | 2 | 71 | 4 | 2 | 71 | 40 | 4 | 79 | 4 | 1 | 40 | 71 | 71 | 1 | 4 | 71 | 2 | 2 | 2 | 71 | 4 | 79 | 71 | 40 | 71 | 4 | 79 | 40 | 1 | 4 | 40 | 4 | 1 | 4 | 79 | 40 | 71
180 | 197 | 194 | 270 | 393 | 440 | 670 | 797 | 1019 | 1108 | 1156 | 1347 | 1495 | 1620 | 1706 | 4 | 71 | 79 | 40 | 2 | 1 | 2 | 71 | 79 | 2 | 2 | 40 | 40 | 4 | 2 | 1 | 71 | 79 | 40 | 40 | 4 | 40 | 4 | 79 | 71 | 79 | 71 | 1 | 4 | 79 | 2 | 4 | 2 | 4 | 40 | 2 | 1 | 71 | 79 | 40 | 4 | 71 | 71 | 2 | 2 | 40 | 4 | 79 | 2 | 1 | 79 | 4
181 | 264 | 153 | 383 | 461 | 616 | 740 | 895 | 943 | 1029 | 1106 | 1151 | 1306 | 1531 | 1545 | 2 | 71 | 79 | 1 | 71 | 40 | 40 | 79 | 71 | 4 | 1 | 2 | 4 | 1 | 79 | 71 | 40 | 40 | 4 | 40 | 71 | 4 | 40 | 40 | 2 | 4 | 2 | 40 | 4 | 40 | 2 | 40 | 4 | 71 | 1 | 1 | 2 | 2 | 40 | 1 | 71 | 4 | 79 | 1 | 71 | 71 | 79 | 4 | 4 | 2 | 4 | 4
182 | 207 | 124 | 357 | 367 | 608 | 683 | 802 | 965 | 1148 | 1293 | 1418 | 1501 | 1576 | 1693 | 40 | 4 | 1 | 79 | 4 | 79 | 71 | 79 | 1 | 4 | 1 | 4 | 79 | 79 | 79 | 4 | 2 | 1 | 1 | 71 | 4 | 4 | 40 | 71 | 4 | 1 | 79 | 79 | 40 | 71 | 1 | 71 | 1 | 71 | 71 | 2 | 40 | 79 | 2 | 4 | 2 | 1 | 1 | 79 | 71 | 1 | 2 | 1 | 2 | 40 | 4 | 71
183 | 313 | 233 | 354 | 398 | 475 | 744 | 860 | 1052 | 1102 | 1216 | 1222 | 1388 | 1471 | 1478 | 79 | 79 | 71 | 4 | 79 | 1 | 40 | 1 | 40 | 1 | 1 | 2 | 2 | 2 | 2 | 71 | 40 | 79 | 71 | 79 | 40 | 71 | 1 | 4 | 40 | 2 | 79 | 71 | 2 | 4 | 4 | 40 | 71 | 1 | 2 | 40 | 1 | 2 | 2 | 1 | 79 | 79 | 4 | 4 | 79 | 1 | 2 | 1 | 2 | 2 | 2 | 1
184 | 166 | 163 | 316 | 541 | 588 | 597 | 797 | 921 | 1143 | 1229 | 1373 | 1573 | 1803 | 1995 | 1 | 4 | 79 | 79 | 1 | 2 | 71 | 79 | 71 | 79 | 4 | 71 | 2 | 4 | 1 | 40 | 2 | 2 | 1 | 4 | 2 | 79 | 40 | 79 | 40 | 1 | 4 | 79 | 71 | 71 | 40 | 40 | 2 | 79 | 4 | 1 | 71 | 71 | 1 | 1 | 40 | 2 | 79 | 79 | 79 | 1 | 79 | 71 | 40 | 79 | 71 | 2
185 | 198 | 87 | 239 | 364 | 519 | 749 | 827 | 948 | 1067 | 1359 | 1444 | 1591 | 1754 | 1915 | 2 | 4 | 79 | 2 | 71 | 40 | 1 | 40 | 40 | 2 | 4 | 79 | 4 | 71 | 40 | 40 | 71 | 79 | 1 | 79 | 2 | 1 | 71 | 4 | 79 | 1 | 1 | 40 | 71 | 4 | 4 | 40 | 71 | 71 | 79 | 71 | 40 | 1 | 4 | 40 | 1 | 71 | 71 | 4 | 1 | 79 | 79 | 4 | 79 | 2 | 40 | 40
186 | 50 | 8 | 200 | 286 | 369 | 451 | 537 | 623 | 823 | 976 | 1022 | 1103 | 1225 | 1301 | 2 | 4 | 1 | 1 | 40 | 2 | 79 | 71 | 4 | 1 | 79 | 2 | 1 | 1 | 2 | 79 | 1 | 1 | 79 | 1 | 2 | 79 | 4 | 1 | 2 | 4 | 1 | 79 | 40 | 79 | 79 | 2 | 2 | 79 | 71 | 1 | 1 | 4 | 1 | 40 | 2 | 4 | 71 | 4 | 40 | 2 | 79 | 1 | 1 | 71 | 2 | 2
187 | 380 | 230 | 385 | 429 | 505 | 551 | 636 | 684 | 878 | 955 | 1002 | 1225 | 1350 | 1542 | 79 | 40 | 40 | 71 | 79 | 71 | 4 | 1 | 2 | 1 | 1 | 40 | 2 | 71 | 2 | 1 | 1 | 1 | 4 | 40 | 1 | 79 | 4 | 1 | 4 | 40 | 2 | 2 | 4 | 71 | 40 | 79 | 2 | 2 | 71 | 2 | 4 | 1 | 40 | 2 | 79 | 2 | 71 | 71 | 4 | 79 | 40 | 2 | 71 | 40 | 2 | 79
188 | 194 | 152 | 198 | 346 | 432 | 548 | 693 | 780 | 971 | 981 | 1108 | 1221 | 1338 | 1530 | 71 | 1 | 40 | 40 | 2 | 40 | 2 | 2 | 4 | 2 | 71 | 71 | 2 | 79 | 1 | 4 | 71 | 40 | 1 | 4 | 1 | 71 | 71 | 2 | 4 | 79 | 2 | 2 | 71 | 1 | 79 | 40 | 4 | 1 | 4 | 1 | 79 | 4 | 4 | 40 | 1 | 71 | 1 | 40 | 4 | 40 | 2 | 71 | 40 | 2 | 71 | 79
189 | 277 | 158 | 427 | 543 | 555 | 676 | 875 | 952 | 1115 | 1239 | 1315 | 1325 | 1472 | 1482 | 79 | 71 | 4 | 4 | 79 | 40 | 79 | 71 | 4 | 1 | 40 | 71 | 2 | 4 | 2 | 4 | 1 | 40 | 40 | 40 | 79 | 79 | 40 | 1 | 1 | 1 | 4 | 71 | 1 | 79 | 4 | 79 | 1 | 40 | 4 | 79 | 2 | 71 | 2 | 1 | 4 | 4 | 1 | 1 | 71 | 1 | 71 | 4 | 2 | 4 | 2 | 2
190 | 84 | 76 | 156 | 317 | 400 | 630 | 705 | 821 | 864 | 1094 | 1217 | 1339 | 1422 | 1426 | 2 | 71 | 2 | 1 | 4 | 4 | 1 | 71 | 2 | 40 | 79 | 40 | 4 | 4 | 71 | 4 | 79 | 1 | 79 | 71 | 1 | 2 | 71 | 1 | 71 | 40 | 4 | 1 | 1 | 1 | 40 | 1 | 79 | 79 | 71 | 1 | 2 | 2 | 40 | 79 | 1 | 2 | 40 | 79 | 40 | 1 | 40 | 2 | 1 | 1 | 1 | 1
191 | 411 | 261 | 417 | 656 | 817 | 944 | 1107 | 1222 | 1269 | 1347 | 1394 | 1478 | 1703 | 1710 | 40 | 79 | 71 | 71 | 71 | 79 | 2 | 4 | 79 | 79 | 79 | 2 | 79 | 2 | 1 | 79 | 4 | 4 | 40 | 79 | 79 | 79 | 4 | 1 | 71 | 2 | 40 | 2 | 1 | 4 | 2 | 40 | 2 | 71 | 1 | 4 | 4 | 2 | 40 | 1 | 2 | 2 | 1 | 79 | 79 | 71 | 4 | 71 | 1 | 2 | 2 | 2
192 | 83 | 79 | 158 | 282 | 481 | 566 | 610 | 688 | 776 | 824 | 1008 | 1210 | 1223 | 1309 | 2 | 71 | 2 | 4 | 2 | 2 | 4 | 71 | 1 | 79 | 40 | 4 | 79 | 1 | 40 | 79 | 40 | 40 | 4 | 1 | 1 | 2 | 1 | 40 | 2 | 71 | 1 | 4 | 1 | 4 | 79 | 4 | 2 | 4 | 2 | 40 | 40 | 71 | 2 | 71 | 40 | 79 | 79 | 4 | 4 | 4 | 1 | 4 | 79 | 1 | 2 | 4
193 | 158 | 86 | 166 | 388 | 536 | 622 | 847 | 968 | 1014 | 1131 | 1246 | 1468 | 1553 | 1753 | 2 | 79 | 4 | 1 | 71 | 1 | 4 | 4 | 79 | 71 | 71 | 1 | 2 | 71 | 4 | 71 | 79 | 4 | 1 | 2 | 79 | 4 | 71 | 71 | 40 | 40 | 1 | 40 | 40 | 4 | 1 | 1 | 71 | 2 | 4 | 40 | 2 | 71 | 2 | 40 | 71 | 40 | 40 | 71 | 1 | 79 | 4 | 1 | 79 | 40 | 79 | 2
194 | 283 | 202 | 285 | 438 | 490 | 565 | 687 | 736 | 821 | 904 | 986 | 1066 | 1220 | 1305 | 40 | 79 | 79 | 4 | 79 | 2 | 1 | 1 | 79 | 71 | 1 | 2 | 4 | 4 | 4 | 40 | 2 | 1 | 1 | 71 | 40 | 79 | 1 | 2 | 4 | 1 | 40 | 4 | 40 | 4 | 40 | 1 | 40 | 1 | 2 | 40 | 40 | 1 | 1 | 40 | 4 | 1 | 71 | 4 | 79 | 71 | 2 | 2 | 4 | 40 | 40 | 1
195 | 352 | 269 | 355 | 632 | 711 | 832 | 945 | 1253 | 1484 | 1645 | 1772 | 2033 | 2158 | 2350 | 79 | 40 | 71 | 79 | 79 | 4 | 2 | 1 | 79 | 79 | 79 | 40 | 2 | 71 | 2 | 4 | 40 | 1 | 40 | 40 | 1 | 71 | 1 | 40 | 79 | 71 | 79 | 79 | 2 | 79 | 79 | 71 | 79 | 2 | 79 | 1 | 4 | 4 | 40 | 79 | 71 | 71 | 79 | 40 | 4 | 79 | 40 | 2 | 40 | 79 | 2 | 71
196 | 127 | 124 | 238 | 324 | 477 | 622 | 705 | 850 | 1073 | 1264 | 1388 | 1551 | 1706 | 1825 | 79 | 4 | 40 | 1 | 1 | 2 | 40 | 71 | 40 | 40 | 4 | 2 | 40 | 2 | 40 | 71 | 71 | 1 | 2 | 71 | 79 | 1 | 1 | 2 | 71 | 1 | 2 | 71 | 71 | 2 | 79 | 71 | 40 | 79 | 1 | 71 | 40 | 40 | 40 | 4 | 79 | 1 | 79 | 4 | 1 | 79 | 4 | 71 | 4 | 4 | 71 | 40
197 | 302 | 152 | 343 | 468 | 512 | 704 | 921 | 1121 | 1304 | 1392 | 1545 | 1770 | 1856 | 1970 | 40 | 1 | 71 | 40 | 71 | 79 | 1 | 40 | 40 | 4 | 79 | 2 | 1 | 1 | 40 | 2 | 79 | 40 | 71 | 2 | 4 | 71 | 71 | 71 | 40 | 79 | 2 | 79 | 1 | 71 | 71 | 40 | 4 | 4 | 79 | 1 | 40 | 71 | 40 | 2 | 4 | 79 | 71 | 71 | 4 | 1 | 79 | 2 | 2 | 40 | 71 | 1
198 | 83 | 80 | 86 | 234 | 351 | 430 | 578 | 695 | 889 | 1111 | 1294 | 1380 | 1532 | 1723 | 4 | 71 | 1 | 4 | 2 | 1 | 2 | 1 | 71 | 2 | 71 | 4 | 71 | 40 | 2 | 4 | 2 | 2 | 4 | 71 | 71 | 4 | 2 | 71 | 40 | 2 | 71 | 4 | 79 | 4 | 71 | 40 | 79 | 71 | 71 | 1 | 40 | 1 | 71 | 71 | 79 | 4 | 2 | 1 | 1 | 1 | 79 | 71 | 1 | 79 | 71 | 40
199 | 191 | 183 | 341 | 424 | 541 | 549 | 556 | 778 | 865 | 1018 | 1103 | 1230 | 1460 | 1620 | 71 | 1 | 40 | 71 | 4 | 4 | 79 | 71 | 40 | 40 | 2 | 1 | 4 | 71 | 40 | 2 | 2 | 4 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 71 | 71 | 79 | 4 | 79 | 2 | 2 | 79 | 2 | 71 | 1 | 4 | 40 | 40 | 1 | 4 | 4 | 40 | 79 | 79 | 71 | 40 | 40 | 79 | 1 | 1 | 79
200 | 165 | 84 | 173 | 326 | 481 | 773 | 823 | 871 | 1057 | 1138 | 1215 | 1378 | 1525 | 1802 | 79 | 2 | 2 | 1 | 79 | 2 | 4 | 4 | 1 | 2 | 71 | 79 | 4 | 1 | 71 | 79 | 71 | 79 | 71 | 71 | 4 | 4 | 40 | 2 | 2 | 4 | 2 | 40 | 40 | 4 | 71 | 71 | 4 | 2 | 4 | 71 | 1 | 1 | 4 | 71 | 79 | 1 | 79 | 4 | 1 | 71 | 71 | 4 | 79 | 79 | 79 | 40
201 | 91 | 86 | 164 | 387 | 431 | 625 | 894 | 980 | 1027 | 1079 | 1239 | 1328 | 1380 | 1566 | 40 | 40 | 2 | 4 | 4 | 1 | 2 | 71 | 79 | 71 | 2 | 71 | 2 | 1 | 1 | 40 | 4 | 71 | 40 | 79 | 79 | 40 | 79 | 71 | 1 | 4 | 79 | 2 | 40 | 4 | 1 | 2 | 4 | 4 | 4 | 40 | 1 | 40 | 79 | 40 | 79 | 2 | 4 | 4 | 4 | 4 | 40 | 4 | 71 | 71 | 4 | 40
202 | 225 | 153 | 305 | 394 | 444 | 605 | 767 | 920 | 1064 | 1186 | 1308 | 1389 | 1606 | 1792 | 40 | 71 | 2 | 40 | 71 | 1 | 79 | 1 | 79 | 4 | 4 | 2 | 4 | 4 | 40 | 2 | 79 | 1 | 79 | 2 | 2 | 79 | 2 | 79 | 79 | 2 | 71 | 1 | 71 | 1 | 71 | 1 | 1 | 40 | 2 | 79 | 2 | 1 | 40 | 79 | 4 | 71 | 2 | 4 | 4 | 71 | 71 | 71 | 4 | 71 | 40 | 71
203 | 166 | 125 | 285 | 401 | 492 | 500 | 584 | 767 | 815 | 968 | 1121 | 1281 | 1359 | 1438 | 2 | 40 | 79 | 4 | 40 | 1 | 40 | 79 | 71 | 1 | 40 | 4 | 4 | 4 | 4 | 79 | 2 | 1 | 4 | 1 | 2 | 40 | 40 | 2 | 40 | 1 | 71 | 71 | 40 | 2 | 2 | 4 | 40 | 2 | 40 | 71 | 2 | 71 | 40 | 40 | 40 | 79 | 1 | 40 | 1 | 71 | 2 | 4 | 2 | 4 | 71 | 2
204 | 117 | 114 | 189 | 313 | 426 | 430 | 476 | 706 | 821 | 906 | 1051 | 1137 | 1216 | 1302 | 71 | 40 | 1 | 2 | 1 | 2 | 71 | 1 | 1 | 79 | 40 | 4 | 1 | 40 | 71 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 40 | 71 | 79 | 79 | 1 | 71 | 2 | 40 | 2 | 1 | 79 | 4 | 1 | 71 | 1 | 71 | 2 | 4 | 40 | 2 | 40 | 71 | 4 | 2 | 2 | 1 | 2 | 4 | 79
205 | 198 | 194 | 340 | 351 | 573 | 694 | 888 | 1003 | 1119 | 1202 | 1432 | 1585 | 1732 | 1926 | 4 | 79 | 71 | 40 | 2 | 2 | 71 | 71 | 1 | 2 | 4 | 4 | 71 | 71 | 1 | 79 | 40 | 1 | 79 | 1 | 40 | 79 | 71 | 4 | 40 | 2 | 71 | 2 | 40 | 1 | 4 | 71 | 4 | 71 | 4 | 4 | 40 | 79 | 40 | 71 | 1 | 79 | 2 | 71 | 1 | 4 | 71 | 71 | 71 | 79 | 4 | 40
206 | 263 | 152 | 374 | 451 | 642 | 759 | 942 | 1144 | 1192 | 1391 | 1516 | 1669 | 1747 | 1823 | 71 | 1 | 1 | 79 | 71 | 40 | 71 | 40 | 71 | 4 | 1 | 1 | 79 | 1 | 71 | 40 | 71 | 40 | 2 | 4 | 1 | 71 | 71 | 40 | 40 | 4 | 79 | 79 | 2 | 4 | 40 | 2 | 1 | 79 | 79 | 40 | 2 | 4 | 40 | 79 | 79 | 71 | 1 | 2 | 71 | 4 | 2 | 1 | 71 | 2 | 1 | 2
207 | 267 | 117 | 269 | 346 | 471 | 521 | 665 | 742 | 925 | 1008 | 1123 | 1314 | 1399 | 1559 | 40 | 71 | 4 | 2 | 79 | 71 | 1 | 1 | 4 | 1 | 1 | 71 | 4 | 2 | 40 | 79 | 4 | 2 | 4 | 40 | 71 | 1 | 1 | 71 | 2 | 2 | 71 | 2 | 40 | 1 | 71 | 71 | 1 | 79 | 1 | 2 | 40 | 71 | 2 | 2 | 1 | 71 | 79 | 40 | 1 | 4 | 1 | 79 | 79 | 79 | 1 | 1
208 | 204 | 163 | 210 | 372 | 463 | 578 | 692 | 813 | 892 | 983 | 991 | 1077 | 1318 | 1396 | 40 | 40 | 79 | 4 | 1 | 40 | 2 | 4 | 2 | 79 | 79 | 2 | 4 | 4 | 4 | 79 | 2 | 71 | 40 | 2 | 40 | 2 | 1 | 71 | 79 | 40 | 1 | 1 | 2 | 4 | 71 | 2 | 4 | 4 | 79 | 4 | 2 | 4 | 1 | 1 | 79 | 4 | 2 | 1 | 4 | 79 | 79 | 79 | 4 | 71 | 2 | 1
209 | 150 | 145 | 194 | 427 | 665 | 865 | 878 | 994 | 1072 | 1263 | 1486 | 1599 | 1685 | 1877 | 2 | 71 | 1 | 71 | 1 | 4 | 4 | 40 | 79 | 4 | 71 | 79 | 79 | 79 | 40 | 40 | 2 | 79 | 79 | 40 | 4 | 4 | 4 | 1 | 71 | 4 | 40 | 1 | 1 | 71 | 4 | 2 | 40 | 71 | 40 | 40 | 71 | 2 | 79 | 71 | 1 | 1 | 71 | 40 | 4 | 79 | 1 | 2 | 79 | 2 | 71 | 40
210 | 127 | 124 | 208 | 333 | 408 | 571 | 578 | 663 | 817 | 830 | 1122 | 1414 | 1570 | 1733 | 40 | 79 | 4 | 1 | 2 | 1 | 79 | 2 | 2 | 4 | 79 | 40 | 1 | 2 | 71 | 1 | 40 | 79 | 40 | 4 | 1 | 2 | 2 | 2 | 4 | 40 | 40 | 1 | 2 | 71 | 2 | 79 | 4 | 1 | 4 | 4 | 71 | 79 | 71 | 71 | 79 | 71 | 71 | 71 | 79 | 4 | 71 | 2 | 40 | 40 | 4 | 79
211 | 158 | 83 | 241 | 394 | 472 | 705 | 782 | 976 | 1026 | 1226 | 1232 | 1395 | 1594 | 1863 | 1 | 1 | 79 | 2 | 71 | 4 | 4 | 79 | 2 | 79 | 71 | 1 | 71 | 1 | 4 | 2 | 79 | 4 | 79 | 71 | 2 | 71 | 2 | 2 | 79 | 71 | 4 | 40 | 4 | 40 | 2 | 4 | 79 | 79 | 40 | 2 | 2 | 1 | 1 | 2 | 1 | 4 | 79 | 79 | 40 | 79 | 79 | 1 | 79 | 71 | 79 | 40
212 | 271 | 199 | 276 | 428 | 547 | 808 | 820 | 1004 | 1160 | 1239 | 1469 | 1632 | 1639 | 1831 | 40 | 1 | 79 | 79 | 71 | 1 | 1 | 4 | 1 | 79 | 1 | 71 | 4 | 71 | 4 | 40 | 79 | 71 | 40 | 71 | 2 | 4 | 2 | 4 | 2 | 71 | 71 | 40 | 2 | 79 | 4 | 71 | 4 | 71 | 2 | 2 | 71 | 1 | 79 | 79 | 79 | 79 | 4 | 1 | 1 | 2 | 2 | 2 | 40 | 71 | 2 | 79
213 | 349 | 269 | 357 | 517 | 708 | 931 | 1094 | 1178 | 1256 | 1301 | 1464 | 1578 | 1819 | 2044 | 40 | 79 | 71 | 79 | 40 | 40 | 4 | 4 | 79 | 40 | 40 | 1 | 40 | 71 | 79 | 1 | 2 | 71 | 79 | 71 | 4 | 40 | 79 | 40 | 79 | 2 | 1 | 2 | 2 | 4 | 71 | 1 | 40 | 2 | 1 | 2 | 79 | 4 | 79 | 1 | 71 | 1 | 2 | 40 | 79 | 79 | 4 | 79 | 4 | 71 | 71 | 79
214 | 372 | 230 | 453 | 636 | 797 | 953 | 1106 | 1227 | 1343 | 1460 | 1662 | 1856 | 1934 | 1977 | 40 | 71 | 40 | 79 | 71 | 71 | 79 | 2 | 71 | 40 | 71 | 1 | 40 | 40 | 2 | 79 | 79 | 71 | 4 | 2 | 1 | 71 | 2 | 79 | 79 | 1 | 1 | 40 | 1 | 40 | 71 | 4 | 2 | 71 | 40 | 4 | 79 | 79 | 4 | 40 | 4 | 71 | 40 | 79 | 71 | 1 | 2 | 4 | 40 | 1 | 1 | 1
215 | 233 | 230 | 275 | 399 | 477 | 604 | 727 | 773 | 887 | 975 | 1139 | 1322 | 1407 | 1531 | 79 | 71 | 40 | 40 | 1 | 2 | 40 | 2 | 4 | 40 | 79 | 1 | 71 | 1 | 2 | 4 | 4 | 40 | 4 | 79 | 2 | 40 | 2 | 79 | 1 | 4 | 40 | 1 | 2 | 71 | 40 | 1 | 4 | 4 | 1 | 79 | 79 | 79 | 4 | 2 | 1 | 71 | 71 | 40 | 2 | 2 | 79 | 2 | 40 | 40 | 40 | 4
216 | 89 | 47 | 130 | 363 | 480 | 596 | 752 | 873 | 1057 | 1171 | 1215 | 1445 | 1603 | 1727 | 2 | 40 | 4 | 1 | 2 | 40 | 1 | 40 | 71 | 79 | 4 | 79 | 4 | 71 | 2 | 40 | 1 | 40 | 71 | 4 | 2 | 79 | 4 | 71 | 40 | 40 | 40 | 1 | 40 | 2 | 71 | 71 | 71 | 40 | 2 | 1 | 1 | 40 | 2 | 1 | 79 | 1 | 79 | 71 | 4 | 79 | 4 | 71 | 1 | 40 | 79 | 4
217 | 349 | 230 | 391 | 510 | 588 | 669 | 892 | 1055 | 1216 | 1407 | 1450 | 1611 | 1656 | 1699 | 71 | 40 | 40 | 79 | 79 | 40 | 2 | 40 | 40 | 4 | 71 | 4 | 2 | 1 | 71 | 4 | 4 | 2 | 4 | 71 | 2 | 71 | 71 | 79 | 40 | 4 | 79 | 40 | 2 | 79 | 1 | 79 | 79 | 1 | 40 | 71 | 1 | 1 | 40 | 1 | 40 | 79 | 2 | 40 | 1 | 2 | 40 | 2 | 1 | 1 | 1 | 40
218 | 84 | 12 | 88 | 134 | 140 | 264 | 386 | 577 | 663 | 710 | 902 | 1063 | 1188 | 1352 | 4 | 2 | 2 | 4 | 71 | 1 | 2 | 2 | 1 | 4 | 40 | 1 | 1 | 2 | 2 | 1 | 1 | 79 | 40 | 4 | 40 | 1 | 2 | 79 | 79 | 1 | 40 | 71 | 2 | 1 | 4 | 79 | 2 | 40 | 1 | 4 | 40 | 2 | 79 | 71 | 1 | 79 | 2 | 79 | 40 | 4 | 79 | 2 | 79 | 4 | 79 | 2
219 | 86 | 44 | 158 | 302 | 457 | 609 | 767 | 776 | 890 | 938 | 1024 | 1104 | 1334 | 1409 | 1 | 1 | 40 | 2 | 40 | 2 | 71 | 1 | 1 | 1 | 71 | 71 | 1 | 79 | 4 | 71 | 1 | 71 | 79 | 1 | 79 | 71 | 4 | 4 | 2 | 1 | 4 | 2 | 1 | 2 | 40 | 71 | 40 | 2 | 2 | 4 | 2 | 40 | 4 | 40 | 4 | 4 | 71 | 1 | 40 | 79 | 40 | 71 | 2 | 1 | 71 | 1
220 | 306 | 156 | 417 | 609 | 840 | 1063 | 1138 | 1265 | 1344 | 1431 | 1615 | 1876 | 2040 | 2159 | 79 | 4 | 2 | 71 | 79 | 71 | 40 | 71 | 71 | 2 | 79 | 40 | 79 | 2 | 71 | 79 | 2 | 71 | 71 | 79 | 1 | 2 | 71 | 1 | 40 | 79 | 4 | 4 | 2 | 71 | 2 | 4 | 4 | 2 | 79 | 2 | 40 | 2 | 71 | 71 | 71 | 71 | 40 | 79 | 79 | 4 | 2 | 79 | 71 | 4 | 40 | 4
221 | 153 | 78 | 233 | 319 | 471 | 588 | 888 | 1048 | 1123 | 1237 | 1398 | 1667 | 1822 | 1905 | 2 | 71 | 4 | 1 | 71 | 4 | 1 | 79 | 4 | 1 | 2 | 79 | 79 | 1 | 71 | 1 | 2 | 40 | 4 | 71 | 71 | 71 | 79 | 79 | 79 | 1 | 40 | 40 | 1 | 71 | 2 | 1 | 40 | 1 | 2 | 71 | 40 | 40 | 2 | 79 | 71 | 79 | 79 | 40 | 79 | 4 | 1 | 71 | 1 | 2 | 40 | 40
222 | 233 | 153 | 277 | 360 | 668 | 821 | 869 | 1169 | 1330 | 1453 | 1461 | 1470 | 1693 | 1846 | 1 | 2 | 79 | 71 | 40 | 40 | 40 | 4 | 4 | 71 | 4 | 4 | 79 | 71 | 79 | 79 | 71 | 40 | 40 | 2 | 2 | 4 | 2 | 40 | 79 | 71 | 79 | 71 | 2 | 40 | 40 | 79 | 2 | 79 | 2 | 40 | 2 | 1 | 4 | 1 | 2 | 2 | 4 | 1 | 71 | 71 | 79 | 2 | 2 | 1 | 71 | 79
223 | 367 | 292 | 448 | 534 | 717 | 764 | 849 | 1004 | 1120 | 1312 | 1537 | 1651 | 1796 | 1956 | 71 | 71 | 71 | 79 | 71 | 4 | 79 | 2 | 1 | 79 | 4 | 2 | 1 | 71 | 71 | 40 | 1 | 4 | 2 | 40 | 4 | 40 | 40 | 1 | 1 | 79 | 71 | 4 | 4 | 71 | 40 | 1 | 71 | 79 | 2 | 40 | 71 | 4 | 79 | 71 | 1 | 2 | 40 | 71 | 71 | 2 | 1 | 71 | 1 | 1 | 79 | 79
224 | 206 | 125 | 212 | 367 | 592 | 679 | 873 | 1031 | 1080 | 1197 | 1344 | 1507 | 1660 | 1875 | 40 | 2 | 4 | 79 | 79 | 2 | 2 | 4 | 40 | 40 | 4 | 71 | 71 | 71 | 79 | 4 | 2 | 4 | 2 | 79 | 40 | 4 | 71 | 79 | 71 | 4 | 4 | 79 | 4 | 4 | 1 | 40 | 40 | 2 | 4 | 71 | 4 | 1 | 71 | 71 | 1 | 79 | 4 | 79 | 71 | 2 | 79 | 1 | 71 | 71 | 71 | 2
225 | 158 | 86 | 199 | 210 | 260 | 498 | 611 | 660 | 710 | 796 | 801 | 926 | 1109 | 1261 | 1 | 2 | 79 | 4 | 1 | 71 | 1 | 40 | 2 | 4 | 1 | 4 | 4 | 4 | 2 | 40 | 79 | 1 | 79 | 79 | 1 | 1 | 71 | 40 | 1 | 4 | 4 | 40 | 40 | 4 | 4 | 2 | 4 | 40 | 40 | 2 | 1 | 2 | 1 | 1 | 79 | 40 | 4 | 2 | 71 | 40 | 71 | 1 | 79 | 71 | 1 | 1
226 | 51 | 9 | 59 | 243 | 360 | 407 | 530 | 582 | 628 | 859 | 1012 | 1090 | 1100 | 1183 | 2 | 4 | 2 | 1 | 2 | 40 | 4 | 4 | 71 | 71 | 2 | 40 | 4 | 2 | 40 | 71 | 2 | 40 | 4 | 1 | 2 | 79 | 2 | 40 | 40 | 4 | 4 | 4 | 40 | 4 | 1 | 1 | 79 | 79 | 2 | 71 | 1 | 79 | 2 | 71 | 4 | 71 | 2 | 1 | 2 | 2 | 4 | 2 | 79 | 1 | 2 | 1
227 | 352 | 233 | 435 | 652 | 800 | 1025 | 1219 | 1519 | 1674 | 1865 | 2025 | 2188 | 2305 | 2353 | 79 | 4 | 71 | 79 | 40 | 79 | 4 | 79 | 4 | 71 | 71 | 71 | 71 | 2 | 71 | 4 | 71 | 4 | 79 | 71 | 4 | 79 | 40 | 71 | 79 | 71 | 79 | 71 | 79 | 71 | 4 | 1 | 71 | 40 | 40 | 40 | 1 | 79 | 79 | 1 | 79 | 4 | 40 | 40 | 2 | 40 | 71 | 4 | 40 | 2 | 2 | 4
228 | 157 | 152 | 315 | 322 | 544 | 744 | 754 | 909 | 1028 | 1172 | 1405 | 1591 | 1743 | 1904 | 40 | 40 | 71 | 1 | 4 | 1 | 79 | 79 | 1 | 1 | 1 | 4 | 79 | 71 | 1 | 71 | 2 | 40 | 79 | 79 | 4 | 1 | 4 | 1 | 79 | 1 | 71 | 4 | 4 | 4 | 71 | 40 | 1 | 71 | 1 | 71 | 4 | 79 | 79 | 71 | 71 | 71 | 4 | 40 | 1 | 71 | 79 | 1 | 79 | 79 | 2 | 1
229 | 197 | 114 | 241 | 257 | 334 | 564 | 640 | 651 | 694 | 850 | 1041 | 1121 | 1274 | 1428 | 40 | 71 | 1 | 2 | 4 | 79 | 4 | 40 | 4 | 4 | 4 | 4 | 1 | 71 | 4 | 1 | 40 | 40 | 71 | 79 | 1 | 2 | 71 | 2 | 4 | 4 | 1 | 2 | 1 | 1 | 1 | 40 | 79 | 2 | 71 | 4 | 40 | 79 | 71 | 1 | 4 | 1 | 4 | 71 | 71 | 1 | 79 | 2 | 79 | 2 | 2 | 71
230 | 227 | 183 | 233 | 360 | 521 | 607 | 723 | 883 | 1006 | 1151 | 1160 | 1238 | 1471 | 1618 | 71 | 71 | 1 | 40 | 40 | 4 | 2 | 4 | 79 | 4 | 4 | 40 | 2 | 1 | 79 | 79 | 4 | 1 | 79 | 2 | 40 | 1 | 71 | 4 | 1 | 40 | 40 | 79 | 2 | 2 | 79 | 40 | 71 | 1 | 71 | 2 | 1 | 2 | 4 | 2 | 2 | 1 | 71 | 4 | 71 | 4 | 79 | 79 | 4 | 1 | 71 | 71
231 | 283 | 164 | 291 | 375 | 539 | 694 | 772 | 857 | 1009 | 1056 | 1173 | 1325 | 1472 | 1664 | 2 | 79 | 79 | 4 | 40 | 79 | 4 | 4 | 1 | 79 | 2 | 2 | 2 | 79 | 79 | 4 | 40 | 4 | 40 | 71 | 2 | 4 | 1 | 71 | 1 | 40 | 4 | 40 | 71 | 1 | 40 | 40 | 4 | 2 | 1 | 40 | 2 | 71 | 40 | 4 | 1 | 71 | 1 | 79 | 71 | 4 | 71 | 1 | 2 | 79 | 40 | 71
232 | 160 | 88 | 168 | 316 | 533 | 686 | 802 | 965 | 1159 | 1306 | 1469 | 1631 | 1822 | 1985 | 79 | 1 | 4 | 4 | 1 | 71 | 4 | 4 | 2 | 71 | 71 | 4 | 71 | 71 | 71 | 4 | 1 | 79 | 2 | 71 | 40 | 1 | 71 | 4 | 1 | 4 | 79 | 79 | 79 | 40 | 4 | 71 | 71 | 71 | 1 | 4 | 4 | 79 | 79 | 1 | 79 | 2 | 2 | 79 | 79 | 71 | 1 | 40 | 79 | 79 | 4 | 1
233 | 204 | 160 | 354 | 479 | 561 | 608 | 694 | 878 | 1028 | 1035 | 1304 | 1382 | 1468 | 1581 | 40 | 1 | 79 | 40 | 40 | 4 | 79 | 71 | 40 | 79 | 2 | 4 | 1 | 1 | 40 | 40 | 2 | 4 | 1 | 40 | 1 | 2 | 79 | 4 | 40 | 2 | 71 | 71 | 4 | 71 | 4 | 71 | 2 | 2 | 1 | 2 | 40 | 71 | 79 | 79 | 2 | 4 | 71 | 1 | 2 | 4 | 1 | 79 | 1 | 71 | 40 | 1
234 | 204 | 85 | 346 | 430 | 518 | 598 | 609 | 765 | 926 | 1195 | 1243 | 1289 | 1369 | 1529 | 40 | 40 | 1 | 4 | 79 | 40 | 71 | 71 | 2 | 1 | 79 | 2 | 4 | 4 | 1 | 79 | 1 | 71 | 4 | 4 | 4 | 1 | 4 | 2 | 79 | 71 | 4 | 2 | 1 | 79 | 79 | 2 | 79 | 71 | 79 | 40 | 2 | 4 | 40 | 2 | 2 | 40 | 2 | 2 | 1 | 4 | 4 | 71 | 1 | 79 | 40 | 40
235 | 236 | 86 | 244 | 467 | 552 | 844 | 888 | 1043 | 1165 | 1312 | 1433 | 1578 | 1769 | 1921 | 40 | 40 | 2 | 4 | 79 | 71 | 4 | 4 | 79 | 2 | 71 | 71 | 1 | 1 | 79 | 4 | 71 | 79 | 71 | 71 | 40 | 1 | 2 | 1 | 79 | 4 | 71 | 1 | 79 | 40 | 1 | 2 | 4 | 71 | 1 | 71 | 40 | 1 | 1 | 79 | 71 | 1 | 71 | 2 | 1 | 79 | 40 | 71 | 40 | 40 | 71 | 1
236 | 54 | 10 | 58 | 182 | 335 | 491 | 575 | 688 | 879 | 957 | 1035 | 1116 | 1165 | 1388 | 1 | 1 | 4 | 4 | 4 | 40 | 2 | 2 | 79 | 4 | 1 | 40 | 2 | 40 | 40 | 71 | 79 | 71 | 2 | 4 | 2 | 40 | 2 | 40 | 71 | 40 | 1 | 1 | 40 | 79 | 1 | 71 | 1 | 4 | 71 | 2 | 1 | 4 | 71 | 2 | 71 | 4 | 2 | 4 | 4 | 4 | 1 | 40 | 79 | 2 | 71 | 71
237 | 165 | 123 | 276 | 498 | 728 | 811 | 889 | 1042 | 1236 | 1384 | 1430 | 1621 | 1634 | 1639 | 40 | 2 | 79 | 2 | 2 | 40 | 71 | 40 | 40 | 71 | 71 | 40 | 79 | 71 | 40 | 40 | 4 | 71 | 4 | 4 | 2 | 71 | 4 | 1 | 79 | 2 | 71 | 1 | 71 | 4 | 40 | 79 | 71 | 71 | 4 | 2 | 40 | 2 | 2 | 2 | 1 | 79 | 71 | 40 | 4 | 4 | 1 | 4 | 1 | 2 | 1 | 1
238 | 275 | 125 | 386 | 541 | 658 | 812 | 1051 | 1205 | 1505 | 1590 | 1679 | 1802 | 1963 | 2043 | 79 | 2 | 4 | 40 | 71 | 79 | 71 | 40 | 1 | 79 | 4 | 71 | 4 | 2 | 71 | 40 | 2 | 79 | 71 | 2 | 2 | 79 | 79 | 79 | 2 | 79 | 71 | 2 | 71 | 79 | 79 | 71 | 1 | 79 | 4 | 1 | 4 | 2 | 79 | 4 | 2 | 2 | 79 | 40 | 2 | 40 | 79 | 40 | 4 | 4 | 1 | 71
239 | 155 | 152 | 274 | 422 | 644 | 731 | 819 | 903 | 991 | 1074 | 1124 | 1276 | 1398 | 1515 | 1 | 79 | 71 | 1 | 1 | 2 | 40 | 79 | 2 | 4 | 71 | 71 | 1 | 79 | 71 | 71 | 4 | 2 | 2 | 79 | 4 | 79 | 1 | 4 | 40 | 40 | 2 | 2 | 4 | 4 | 79 | 1 | 1 | 40 | 40 | 2 | 4 | 4 | 2 | 40 | 1 | 1 | 71 | 79 | 1 | 40 | 2 | 79 | 71 | 2 | 4 | 40
240 | 169 | 125 | 210 | 224 | 302 | 312 | 426 | 476 | 590 | 753 | 899 | 1012 | 1057 | 1223 | 2 | 4 | 40 | 79 | 4 | 40 | 40 | 1 | 4 | 4 | 4 | 2 | 1 | 4 | 2 | 71 | 4 | 4 | 1 | 1 | 2 | 71 | 1 | 40 | 2 | 4 | 4 | 40 | 1 | 40 | 2 | 71 | 4 | 40 | 40 | 79 | 2 | 2 | 71 | 71 | 40 | 1 | 1 | 71 | 1 | 2 | 40 | 2 | 79 | 79 | 4 | 4
241 | 208 | 202 | 288 | 442 | 664 | 786 | 903 | 982 | 1067 | 1181 | 1193 | 1277 | 1507 | 1655 | 40 | 79 | 79 | 4 | 4 | 2 | 1 | 79 | 71 | 2 | 79 | 2 | 71 | 71 | 1 | 79 | 79 | 2 | 1 | 40 | 2 | 71 | 4 | 40 | 2 | 4 | 71 | 2 | 40 | 1 | 4 | 40 | 40 | 1 | 2 | 71 | 4 | 2 | 4 | 2 | 40 | 2 | 40 | 2 | 40 | 71 | 40 | 79 | 4 | 71 | 71 | 2
242 | 235 | 85 | 377 | 524 | 674 | 801 | 1032 | 1111 | 1263 | 1417 | 1619 | 1911 | 2036 | 2163 | 40 | 40 | 1 | 4 | 79 | 71 | 71 | 71 | 1 | 71 | 71 | 4 | 71 | 4 | 4 | 71 | 4 | 79 | 4 | 40 | 79 | 71 | 79 | 2 | 2 | 2 | 71 | 4 | 40 | 71 | 40 | 1 | 2 | 71 | 79 | 2 | 79 | 4 | 79 | 40 | 71 | 71 | 79 | 71 | 4 | 2 | 79 | 40 | 79 | 40 | 4 | 4
243 | 204 | 124 | 246 | 332 | 445 | 532 | 655 | 702 | 850 | 1119 | 1202 | 1355 | 1368 | 1483 | 4 | 1 | 40 | 79 | 79 | 1 | 2 | 40 | 1 | 2 | 79 | 4 | 40 | 1 | 1 | 71 | 2 | 2 | 79 | 4 | 2 | 79 | 2 | 40 | 2 | 4 | 40 | 1 | 71 | 71 | 4 | 2 | 79 | 40 | 71 | 79 | 1 | 2 | 79 | 1 | 79 | 1 | 71 | 2 | 4 | 4 | 4 | 1 | 2 | 2 | 40 | 71
244 | 306 | 231 | 350 | 542 | 591 | 747 | 941 | 1024 | 1140 | 1300 | 1425 | 1579 | 1732 | 1880 | 79 | 79 | 2 | 71 | 71 | 4 | 4 | 40 | 71 | 79 | 2 | 40 | 4 | 4 | 40 | 1 | 2 | 71 | 4 | 79 | 79 | 4 | 40 | 71 | 4 | 4 | 71 | 4 | 1 | 71 | 4 | 40 | 40 | 40 | 79 | 1 | 4 | 40 | 79 | 2 | 71 | 2 | 2 | 79 | 2 | 1 | 71 | 79 | 71 | 4 | 2 | 71
245 | 265 | 184 | 337 | 425 | 547 | 692 | 703 | 857 | 976 | 988 | 1135 | 1179 | 1417 | 1501 | 71 | 2 | 71 | 40 | 79 | 2 | 71 | 1 | 4 | 1 | 79 | 4 | 79 | 1 | 40 | 2 | 2 | 1 | 71 | 71 | 2 | 1 | 4 | 4 | 79 | 71 | 2 | 2 | 4 | 71 | 40 | 4 | 4 | 4 | 2 | 2 | 1 | 4 | 71 | 71 | 1 | 2 | 40 | 1 | 40 | 79 | 79 | 40 | 2 | 2 | 40 | 40
246 | 364 | 214 | 506 | 590 | 714 | 761 | 960 | 1073 | 1188 | 1307 | 1385 | 1510 | 1701 | 1901 | 71 | 1 | 71 | 71 | 79 | 71 | 71 | 71 | 40 | 2 | 40 | 2 | 79 | 4 | 40 | 1 | 2 | 40 | 1 | 4 | 79 | 1 | 40 | 79 | 71 | 1 | 40 | 1 | 2 | 2 | 71 | 40 | 40 | 71 | 4 | 4 | 71 | 2 | 1 | 4 | 40 | 4 | 79 | 2 | 79 | 1 | 71 | 40 | 79 | 40 | 79 | 2
247 | 158 | 155 | 238 | 321 | 406 | 492 | 613 | 693 | 704 | 787 | 794 | 942 | 1024 | 1218 | 79 | 1 | 71 | 4 | 1 | 2 | 1 | 79 | 1 | 79 | 1 | 2 | 79 | 1 | 4 | 1 | 2 | 79 | 4 | 1 | 1 | 40 | 40 | 40 | 4 | 4 | 1 | 71 | 1 | 4 | 4 | 2 | 2 | 79 | 1 | 1 | 2 | 2 | 2 | 1 | 71 | 2 | 71 | 4 | 40 | 1 | 1 | 40 | 71 | 79 | 4 | 40
248 | 204 | 199 | 315 | 437 | 515 | 673 | 761 | 877 | 965 | 1087 | 1243 | 1388 | 1440 | 1526 | 40 | 79 | 79 | 1 | 4 | 1 | 71 | 40 | 40 | 1 | 2 | 79 | 2 | 1 | 71 | 4 | 79 | 4 | 4 | 71 | 79 | 1 | 4 | 4 | 71 | 40 | 4 | 1 | 40 | 40 | 4 | 4 | 1 | 40 | 79 | 2 | 79 | 4 | 71 | 2 | 1 | 71 | 2 | 71 | 4 | 4 | 4 | 40 | 40 | 4 | 2 | 40
249 | 274 | 155 | 416 | 532 | 654 | 892 | 1008 | 1123 | 1203 | 1363 | 1487 | 1686 | 1772 | 1849 | 1 | 71 | 4 | 79 | 40 | 79 | 71 | 71 | 71 | 1 | 40 | 4 | 40 | 1 | 79 | 2 | 79 | 40 | 40 | 79 | 4 | 71 | 40 | 1 | 2 | 71 | 2 | 40 | 4 | 1 | 71 | 4 | 1 | 79 | 79 | 1 | 79 | 4 | 40 | 1 | 79 | 40 | 40 | 40 | 4 | 2 | 79 | 1 | 1 | 71 | 4 | 1
250 | 166 | 164 | 172 | 403 | 603 | 758 | 983 | 1169 | 1371 | 1449 | 1562 | 1792 | 1876 | 1884 | 79 | 79 | 2 | 4 | 1 | 1 | 2 | 4 | 79 | 2 | 71 | 79 | 79 | 40 | 79 | 2 | 71 | 4 | 40 | 40 | 79 | 71 | 4 | 71 | 71 | 71 | 40 | 4 | 79 | 79 | 40 | 4 | 71 | 4 | 1 | 2 | 40 | 71 | 1 | 1 | 79 | 1 | 71 | 79 | 40 | 2 | 40 | 2 | 1 | 2 | 4 | 1
251 | 350 | 277 | 392 | 547 | 669 | 938 | 1102 | 1255 | 1334 | 1482 | 1723 | 1877 | 2038 | 2204 | 79 | 79 | 40 | 79 | 71 | 2 | 40 | 2 | 4 | 71 | 40 | 40 | 2 | 40 | 40 | 40 | 79 | 40 | 71 | 79 | 79 | 2 | 4 | 79 | 71 | 40 | 2 | 40 | 2 | 2 | 4 | 71 | 4 | 71 | 2 | 71 | 4 | 79 | 79 | 79 | 2 | 79 | 2 | 71 | 1 | 2 | 79 | 79 | 4 | 79 | 4 | 79
252 | 126 | 43 | 199 | 352 | 468 | 584 | 629 | 774 | 1007 | 1160 | 1352 | 1465 | 1579 | 1657 | 40 | 1 | 1 | 1 | 79 | 4 | 71 | 2 | 2 | 79 | 1 | 71 | 71 | 1 | 4 | 40 | 4 | 1 | 40 | 71 | 40 | 2 | 2 | 1 | 71 | 1 | 2 | 71 | 79 | 79 | 4 | 71 | 79 | 2 | 1 | 71 | 79 | 2 | 40 | 71 | 40 | 71 | 1 | 1 | 71 | 2 | 40 | 1 | 2 | 4 | 71 | 1
253 | 269 | 127 | 311 | 495 | 695 | 848 | 1011 | 1213 | 1298 | 1383 | 1506 | 1581 | 1744 | 1828 | 4 | 4 | 40 | 79 | 71 | 71 | 40 | 2 | 40 | 71 | 2 | 71 | 79 | 2 | 40 | 79 | 79 | 2 | 71 | 1 | 79 | 4 | 1 | 79 | 79 | 79 | 4 | 40 | 2 | 2 | 2 | 79 | 79 | 1 | 4 | 1 | 2 | 2 | 79 | 40 | 1 | 71 | 2 | 1 | 40 | 4 | 79 | 40 | 2 | 1 | 2 | 79
254 | 208 | 202 | 289 | 450 | 600 | 677 | 726 | 773 | 820 | 942 | 1102 | 1229 | 1318 | 1327 | 40 | 4 | 79 | 79 | 4 | 2 | 2 | 79 | 79 | 1 | 2 | 79 | 71 | 71 | 4 | 4 | 1 | 1 | 4 | 71 | 40 | 4 | 1 | 4 | 2 | 4 | 1 | 40 | 1 | 4 | 40 | 2 | 1 | 79 | 2 | 40 | 1 | 40 | 40 | 79 | 4 | 79 | 40 | 4 | 2 | 4 | 79 | 4 | 1 | 2 | 4 | 2
255 | 91 | 47 | 202 | 463 | 587 | 733 | 935 | 1058 | 1137 | 1183 | 1232 | 1355 | 1366 | 1480 | 40 | 2 | 1 | 4 | 4 | 40 | 40 | 71 | 71 | 79 | 71 | 40 | 79 | 40 | 4 | 1 | 71 | 71 | 2 | 2 | 4 | 40 | 79 | 79 | 2 | 2 | 79 | 40 | 71 | 2 | 4 | 2 | 40 | 1 | 1 | 4 | 1 | 4 | 40 | 4 | 79 | 2 | 40 | 2 | 4 | 4 | 1 | 2 | 71 | 2 | 40 | 1
256 | 135 | 52 | 254 | 339 | 500 | 583 | 774 | 924 | 1046 | 1230 | 1383 | 1536 | 1652 | 1663 | 40 | 4 | 4 | 4 | 79 | 4 | 79 | 40 | 4 | 40 | 40 | 1 | 40 | 40 | 79 | 2 | 2 | 40 | 40 | 1 | 40 | 71 | 1 | 79 | 4 | 4 | 71 | 71 | 1 | 79 | 2 | 40 | 2 | 71 | 40 | 71 | 79 | 71 | 2 | 1 | 71 | 1 | 79 | 2 | 40 | 71 | 1 | 4 | 4 | 4 | 1 | 2
257 | 196 | 194 | 238 | 362 | 475 | 635 | 865 | 911 | 989 | 1145 | 1267 | 1356 | 1547 | 1662 | 71 | 40 | 4 | 79 | 1 | 1 | 2 | 40 | 4 | 40 | 40 | 40 | 40 | 1 | 71 | 1 | 40 | 1 | 79 | 40 | 79 | 40 | 71 | 40 | 40 | 1 | 4 | 1 | 1 | 2 | 71 | 4 | 4 | 2 | 79 | 71 | 40 | 40 | 40 | 2 | 4 | 4 | 79 | 2 | 71 | 40 | 40 | 40 | 40 | 2 | 71 | 2
258 | 241 | 233 | 285 | 500 | 738 | 929 | 1077 | 1190 | 1268 | 1451 | 1498 | 1581 | 1775 | 1890 | 79 | 4 | 71 | 79 | 4 | 4 | 40 | 4 | 2 | 71 | 71 | 71 | 1 | 79 | 79 | 79 | 71 | 79 | 40 | 1 | 71 | 2 | 4 | 71 | 40 | 1 | 1 | 71 | 2 | 71 | 4 | 1 | 71 | 1 | 71 | 40 | 4 | 40 | 2 | 1 | 2 | 1 | 40 | 40 | 79 | 71 | 4 | 40 | 2 | 40 | 2 | 71
259 | 230 | 150 | 380 | 564 | 576 | 693 | 704 | 751 | 904 | 986 | 1067 | 1258 | 1338 | 1490 | 4 | 4 | 71 | 71 | 79 | 1 | 79 | 71 | 40 | 71 | 2 | 71 | 2 | 4 | 2 | 4 | 40 | 2 | 4 | 71 | 1 | 2 | 4 | 4 | 2 | 4 | 1 | 40 | 1 | 79 | 71 | 2 | 1 | 40 | 40 | 1 | 4 | 4 | 71 | 2 | 40 | 1 | 71 | 79 | 4 | 71 | 4 | 1 | 40 | 71 | 40 | 1
260 | 391 | 241 | 466 | 583 | 782 | 898 | 1090 | 1331 | 1522 | 1608 | 1808 | 1889 | 2050 | 2096 | 79 | 4 | 79 | 79 | 79 | 71 | 71 | 4 | 71 | 2 | 40 | 4 | 79 | 40 | 40 | 40 | 1 | 4 | 71 | 40 | 2 | 79 | 71 | 40 | 4 | 79 | 79 | 79 | 79 | 40 | 1 | 71 | 4 | 1 | 79 | 2 | 79 | 40 | 79 | 2 | 2 | 71 | 4 | 4 | 40 | 2 | 79 | 40 | 4 | 40 | 1 | 1
261 | 153 | 80 | 236 | 360 | 369 | 485 | 707 | 946 | 1065 | 1225 | 1419 | 1535 | 1729 | 1774 | 1 | 71 | 4 | 4 | 71 | 2 | 79 | 4 | 79 | 1 | 4 | 40 | 4 | 2 | 2 | 1 | 71 | 1 | 4 | 40 | 71 | 79 | 1 | 71 | 79 | 79 | 79 | 2 | 71 | 40 | 4 | 4 | 79 | 1 | 40 | 40 | 71 | 79 | 40 | 4 | 1 | 40 | 71 | 4 | 40 | 71 | 4 | 79 | 2 | 40 | 2 | 1
262 | 208 | 164 | 213 | 368 | 457 | 543 | 662 | 786 | 908 | 986 | 1172 | 1328 | 1453 | 1605 | 79 | 4 | 2 | 79 | 4 | 40 | 1 | 4 | 4 | 71 | 1 | 79 | 4 | 2 | 4 | 79 | 4 | 2 | 40 | 40 | 4 | 71 | 40 | 4 | 1 | 40 | 79 | 4 | 40 | 40 | 2 | 40 | 2 | 71 | 4 | 1 | 4 | 40 | 71 | 71 | 2 | 4 | 71 | 79 | 2 | 79 | 4 | 40 | 1 | 40 | 71 | 40
263 | 333 | 222 | 491 | 580 | 657 | 771 | 1002 | 1193 | 1271 | 1384 | 1539 | 1587 | 1711 | 1864 | 1 | 79 | 71 | 71 | 40 | 71 | 79 | 79 | 79 | 4 | 2 | 4 | 71 | 1 | 4 | 1 | 40 | 2 | 71 | 1 | 71 | 2 | 79 | 79 | 79 | 1 | 40 | 71 | 1 | 4 | 71 | 2 | 40 | 71 | 1 | 1 | 71 | 1 | 4 | 79 | 2 | 40 | 2 | 4 | 40 | 40 | 4 | 40 | 71 | 2 | 1 | 79
264 | 204 | 163 | 284 | 333 | 496 | 540 | 657 | 737 | 900 | 975 | 1097 | 1260 | 1334 | 1411 | 1 | 79 | 79 | 4 | 1 | 40 | 40 | 40 | 1 | 40 | 4 | 4 | 40 | 4 | 79 | 40 | 2 | 40 | 1 | 1 | 4 | 71 | 40 | 2 | 71 | 4 | 1 | 4 | 79 | 79 | 4 | 1 | 71 | 2 | 1 | 1 | 40 | 40 | 2 | 40 | 1 | 79 | 4 | 79 | 1 | 1 | 71 | 1 | 1 | 4 | 1 | 71
265 | 90 | 9 | 163 | 321 | 446 | 606 | 800 | 921 | 1144 | 1224 | 1516 | 1733 | 1971 | 2119 | 2 | 1 | 4 | 2 | 2 | 79 | 2 | 71 | 79 | 4 | 4 | 71 | 40 | 79 | 4 | 2 | 1 | 79 | 79 | 1 | 71 | 40 | 79 | 4 | 1 | 79 | 1 | 40 | 71 | 2 | 79 | 71 | 1 | 4 | 71 | 4 | 71 | 79 | 71 | 71 | 71 | 71 | 71 | 4 | 79 | 79 | 40 | 40 | 71 | 2 | 71 | 4
266 | 305 | 155 | 378 | 461 | 584 | 728 | 778 | 933 | 1155 | 1238 | 1316 | 1515 | 1604 | 1865 | 79 | 71 | 1 | 4 | 79 | 71 | 71 | 2 | 79 | 1 | 2 | 1 | 79 | 2 | 40 | 2 | 71 | 71 | 1 | 1 | 4 | 4 | 40 | 2 | 4 | 1 | 79 | 71 | 1 | 71 | 71 | 79 | 4 | 71 | 4 | 4 | 71 | 4 | 2 | 1 | 79 | 79 | 1 | 40 | 4 | 4 | 2 | 79 | 71 | 71 | 79 | 40
267 | 88 | 8 | 90 | 244 | 428 | 433 | 625 | 824 | 910 | 990 | 1066 | 1291 | 1513 | 1521 | 4 | 2 | 1 | 1 | 1 | 79 | 1 | 1 | 79 | 71 | 2 | 2 | 71 | 71 | 40 | 2 | 1 | 2 | 1 | 1 | 40 | 71 | 2 | 79 | 40 | 40 | 79 | 40 | 4 | 40 | 2 | 40 | 4 | 1 | 71 | 4 | 71 | 2 | 1 | 2 | 4 | 79 | 71 | 71 | 1 | 71 | 71 | 79 | 2 | 1 | 1 | 4
268 | 82 | 80 | 232 | 320 | 445 | 629 | 712 | 758 | 989 | 1065 | 1179 | 1373 | 1450 | 1611 | 1 | 4 | 71 | 4 | 1 | 1 | 71 | 79 | 79 | 4 | 4 | 1 | 40 | 79 | 4 | 2 | 71 | 40 | 2 | 71 | 2 | 1 | 79 | 1 | 1 | 1 | 4 | 40 | 79 | 79 | 2 | 71 | 2 | 1 | 2 | 71 | 2 | 1 | 40 | 71 | 40 | 71 | 4 | 79 | 2 | 71 | 2 | 2 | 2 | 79 | 40 | 40
269 | 199 | 155 | 357 | 512 | 598 | 837 | 958 | 1080 | 1272 | 1424 | 1587 | 1672 | 1718 | 1920 | 1 | 4 | 71 | 79 | 40 | 4 | 79 | 79 | 4 | 79 | 71 | 1 | 79 | 4 | 1 | 2 | 2 | 79 | 79 | 79 | 79 | 1 | 40 | 1 | 1 | 2 | 79 | 40 | 2 | 79 | 71 | 40 | 71 | 40 | 1 | 40 | 1 | 79 | 4 | 79 | 4 | 79 | 1 | 1 | 1 | 4 | 40 | 1 | 40 | 4 | 79 | 79
270 | 193 | 113 | 312 | 320 | 403 | 414 | 683 | 764 | 844 | 932 | 1095 | 1216 | 1302 | 1349 | 1 | 71 | 1 | 40 | 79 | 1 | 79 | 40 | 2 | 2 | 2 | 2 | 2 | 1 | 79 | 1 | 1 | 4 | 2 | 4 | 71 | 79 | 79 | 40 | 4 | 4 | 71 | 2 | 1 | 4 | 71 | 4 | 4 | 40 | 40 | 4 | 40 | 40 | 4 | 79 | 40 | 1 | 79 | 1 | 40 | 40 | 4 | 2 | 40 | 4 | 1 | 2
271 | 233 | 114 | 306 | 567 | 689 | 958 | 1082 | 1299 | 1482 | 1637 | 1762 | 1885 | 2001 | 2084 | 1 | 40 | 71 | 2 | 79 | 40 | 71 | 2 | 71 | 40 | 79 | 71 | 2 | 40 | 1 | 79 | 71 | 79 | 79 | 40 | 4 | 79 | 1 | 40 | 71 | 71 | 71 | 4 | 1 | 71 | 71 | 40 | 4 | 71 | 1 | 79 | 4 | 2 | 79 | 40 | 79 | 2 | 40 | 2 | 1 | 4 | 40 | 71 | 40 | 2 | 1 | 40
272 | 311 | 230 | 430 | 586 | 741 | 757 | 807 | 1032 | 1117 | 1127 | 1175 | 1322 | 1367 | 1589 | 79 | 79 | 1 | 71 | 2 | 79 | 79 | 40 | 79 | 4 | 71 | 2 | 71 | 40 | 4 | 40 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 2 | 4 | 71 | 71 | 79 | 79 | 4 | 1 | 1 | 4 | 1 | 1 | 4 | 4 | 2 | 2 | 40 | 4 | 71 | 71 | 1 | 2 | 40 | 1 | 2 | 79 | 71 | 1 | 71
273 | 427 | 269 | 508 | 593 | 678 | 764 | 918 | 1032 | 1043 | 1198 | 1285 | 1407 | 1571 | 1655 | 40 | 79 | 71 | 79 | 79 | 79 | 2 | 79 | 1 | 40 | 4 | 40 | 4 | 79 | 1 | 1 | 2 | 1 | 79 | 4 | 79 | 71 | 2 | 2 | 40 | 2 | 71 | 1 | 4 | 1 | 4 | 2 | 79 | 1 | 4 | 71 | 2 | 79 | 2 | 4 | 2 | 40 | 79 | 1 | 79 | 79 | 4 | 2 | 2 | 40 | 40 | 2
274 | 305 | 233 | 346 | 432 | 512 | 773 | 926 | 1151 | 1304 | 1596 | 1757 | 1771 | 1818 | 2032 | 4 | 71 | 79 | 79 | 1 | 71 | 1 | 40 | 4 | 40 | 2 | 40 | 4 | 71 | 4 | 1 | 71 | 79 | 71 | 40 | 71 | 79 | 1 | 2 | 71 | 4 | 71 | 79 | 1 | 71 | 2 | 79 | 71 | 79 | 71 | 71 | 79 | 79 | 2 | 1 | 2 | 4 | 4 | 4 | 4 | 2 | 1 | 40 | 71 | 71 | 1 | 71
275 | 89 | 83 | 162 | 209 | 439 | 599 | 712 | 833 | 1048 | 1133 | 1209 | 1365 | 1525 | 1646 | 1 | 2 | 1 | 79 | 4 | 2 | 2 | 71 | 1 | 4 | 40 | 2 | 79 | 40 | 40 | 71 | 40 | 79 | 40 | 1 | 1 | 40 | 71 | 1 | 79 | 1 | 40 | 1 | 71 | 71 | 71 | 2 | 40 | 4 | 40 | 1 | 2 | 1 | 2 | 71 | 4 | 2 | 79 | 71 | 40 | 40 | 79 | 1 | 40 | 40 | 40 | 1
276 | 12 | 6 | 123 | 129 | 284 | 409 | 417 | 495 | 617 | 858 | 1060 | 1246 | 1329 | 1410 | 1 | 2 | 2 | 1 | 4 | 2 | 71 | 40 | 1 | 2 | 1 | 2 | 40 | 40 | 4 | 71 | 79 | 4 | 40 | 2 | 4 | 1 | 1 | 2 | 4 | 2 | 1 | 71 | 1 | 2 | 79 | 40 | 79 | 79 | 79 | 4 | 79 | 40 | 4 | 79 | 71 | 4 | 40 | 71 | 2 | 40 | 40 | 1 | 2 | 4 | 4 | 71
277 | 128 | 86 | 208 | 430 | 660 | 823 | 909 | 1062 | 1331 | 1608 | 1766 | 1922 | 2037 | 2087 | 2 | 4 | 1 | 79 | 40 | 2 | 40 | 40 | 40 | 71 | 71 | 40 | 40 | 40 | 79 | 71 | 40 | 79 | 4 | 40 | 4 | 2 | 1 | 79 | 79 | 2 | 1 | 71 | 71 | 79 | 79 | 40 | 40 | 79 | 79 | 79 | 71 | 79 | 4 | 4 | 4 | 71 | 79 | 2 | 71 | 2 | 40 | 2 | 4 | 40 | 2 | 4
278 | 238 | 80 | 243 | 442 | 564 | 708 | 716 | 910 | 1140 | 1263 | 1384 | 1500 | 1702 | 1715 | 4 | 1 | 4 | 71 | 79 | 79 | 1 | 4 | 79 | 1 | 79 | 40 | 40 | 2 | 79 | 1 | 1 | 71 | 71 | 1 | 2 | 1 | 1 | 4 | 71 | 40 | 79 | 4 | 40 | 40 | 71 | 79 | 2 | 40 | 2 | 79 | 1 | 40 | 1 | 79 | 1 | 71 | 4 | 40 | 4 | 40 | 79 | 79 | 4 | 1 | 4 | 4
279 | 269 | 225 | 388 | 510 | 590 | 714 | 859 | 909 | 1062 | 1276 | 1398 | 1515 | 1667 | 1792 | 79 | 71 | 71 | 4 | 40 | 4 | 79 | 40 | 40 | 40 | 40 | 2 | 4 | 71 | 4 | 1 | 4 | 40 | 40 | 40 | 71 | 2 | 1 | 71 | 4 | 40 | 2 | 4 | 79 | 1 | 71 | 2 | 71 | 1 | 71 | 71 | 1 | 79 | 40 | 2 | 71 | 4 | 2 | 40 | 1 | 40 | 71 | 40 | 79 | 4 | 2 | 40
280 | 247 | 166 | 250 | 372 | 446 | 612 | 796 | 920 | 995 | 1006 | 1091 | 1175 | 1323 | 1366 | 4 | 79 | 79 | 4 | 2 | 79 | 2 | 1 | 40 | 2 | 40 | 40 | 71 | 1 | 1 | 1 | 79 | 79 | 4 | 4 | 40 | 2 | 71 | 71 | 1 | 40 | 4 | 79 | 71 | 1 | 1 | 2 | 4 | 2 | 1 | 4 | 2 | 79 | 2 | 2 | 2 | 40 | 40 | 2 | 71 | 71 | 4 | 2 | 1 | 1 | 1 | 40
281 | 130 | 86 | 213 | 329 | 473 | 589 | 858 | 1089 | 1235 | 1320 | 1503 | 1618 | 1703 | 1749 | 40 | 40 | 2 | 4 | 4 | 40 | 4 | 79 | 71 | 1 | 40 | 4 | 71 | 1 | 1 | 71 | 1 | 4 | 71 | 40 | 71 | 79 | 79 | 40 | 79 | 71 | 2 | 79 | 2 | 71 | 71 | 2 | 40 | 1 | 40 | 4 | 1 | 71 | 40 | 71 | 40 | 2 | 2 | 71 | 1 | 40 | 40 | 4 | 40 | 1 | 4 | 1
282 | 236 | 156 | 239 | 362 | 443 | 529 | 676 | 801 | 956 | 964 | 1158 | 1274 | 1489 | 1639 | 4 | 79 | 71 | 2 | 79 | 1 | 1 | 2 | 79 | 40 | 2 | 2 | 4 | 2 | 4 | 71 | 4 | 79 | 2 | 1 | 1 | 4 | 71 | 71 | 2 | 40 | 4 | 79 | 4 | 40 | 40 | 71 | 4 | 1 | 1 | 2 | 79 | 4 | 71 | 40 | 40 | 71 | 4 | 1 | 2 | 71 | 71 | 71 | 71 | 4 | 71 | 4
283 | 199 | 124 | 282 | 404 | 493 | 715 | 832 | 915 | 994 | 1119 | 1271 | 1416 | 1426 | 1550 | 4 | 40 | 1 | 79 | 4 | 71 | 4 | 79 | 1 | 2 | 79 | 40 | 79 | 4 | 4 | 2 | 40 | 71 | 71 | 40 | 40 | 2 | 4 | 71 | 4 | 71 | 4 | 4 | 2 | 4 | 2 | 71 | 40 | 2 | 79 | 4 | 1 | 71 | 40 | 40 | 71 | 71 | 2 | 1 | 4 | 4 | 1 | 1 | 40 | 79 | 1 | 4
284 | 280 | 161 | 322 | 474 | 622 | 777 | 894 | 1124 | 1209 | 1354 | 1546 | 1709 | 1853 | 1974 | 2 | 79 | 1 | 79 | 40 | 79 | 2 | 40 | 1 | 40 | 71 | 40 | 4 | 71 | 2 | 71 | 79 | 1 | 71 | 4 | 2 | 40 | 71 | 4 | 1 | 79 | 71 | 79 | 4 | 79 | 1 | 1 | 71 | 1 | 71 | 2 | 2 | 79 | 40 | 71 | 4 | 79 | 1 | 79 | 1 | 71 | 71 | 1 | 1 | 1 | 79 | 40
285 | 235 | 160 | 315 | 390 | 612 | 736 | 744 | 900 | 1056 | 1270 | 1318 | 1548 | 1665 | 1820 | 79 | 79 | 1 | 1 | 71 | 4 | 1 | 79 | 1 | 71 | 2 | 1 | 40 | 71 | 71 | 40 | 79 | 1 | 40 | 4 | 1 | 1 | 2 | 4 | 79 | 4 | 2 | 71 | 79 | 2 | 71 | 4 | 71 | 71 | 71 | 1 | 4 | 2 | 2 | 40 | 79 | 79 | 71 | 1 | 40 | 71 | 4 | 2 | 40 | 4 | 40 | 71
286 | 159 | 78 | 239 | 317 | 540 | 762 | 773 | 965 | 1051 | 1204 | 1254 | 1376 | 1637 | 1646 | 71 | 1 | 2 | 4 | 2 | 79 | 79 | 1 | 4 | 2 | 1 | 71 | 71 | 79 | 71 | 2 | 40 | 40 | 71 | 71 | 4 | 1 | 2 | 4 | 71 | 40 | 79 | 2 | 40 | 4 | 2 | 40 | 71 | 79 | 1 | 2 | 2 | 40 | 4 | 4 | 40 | 40 | 2 | 40 | 71 | 71 | 79 | 40 | 2 | 2 | 1 | 4
287 | 131 | 87 | 250 | 374 | 537 | 582 | 736 | 744 | 930 | 1122 | 1422 | 1585 | 1807 | 1999 | 2 | 79 | 4 | 2 | 40 | 4 | 79 | 40 | 4 | 40 | 1 | 79 | 4 | 40 | 79 | 40 | 2 | 40 | 2 | 1 | 2 | 79 | 2 | 71 | 4 | 1 | 2 | 1 | 71 | 4 | 71 | 40 | 71 | 40 | 79 | 2 | 79 | 71 | 71 | 79 | 79 | 79 | 1 | 4 | 71 | 1 | 79 | 71 | 40 | 79 | 2 | 71
288 | 127 | 86 | 238 | 320 | 514 | 592 | 680 | 692 | 807 | 1021 | 1251 | 1414 | 1535 | 1690 | 4 | 79 | 1 | 2 | 1 | 40 | 40 | 71 | 40 | 1 | 1 | 40 | 71 | 4 | 40 | 79 | 2 | 71 | 1 | 4 | 1 | 4 | 79 | 4 | 4 | 2 | 4 | 2 | 2 | 2 | 71 | 40 | 71 | 71 | 71 | 1 | 79 | 71 | 1 | 79 | 79 | 4 | 40 | 40 | 1 | 40 | 40 | 40 | 40 | 4 | 71 | 40
289 | 234 | 84 | 345 | 354 | 476 | 667 | 859 | 1050 | 1164 | 1464 | 1655 | 1737 | 1899 | 1975 | 2 | 1 | 2 | 79 | 79 | 71 | 71 | 40 | 2 | 4 | 2 | 1 | 2 | 79 | 1 | 40 | 1 | 79 | 40 | 71 | 79 | 40 | 71 | 2 | 40 | 79 | 1 | 71 | 2 | 1 | 71 | 40 | 79 | 71 | 79 | 71 | 79 | 71 | 40 | 1 | 1 | 1 | 79 | 1 | 2 | 2 | 79 | 79 | 1 | 71 | 2 | 2
290 | 230 | 155 | 341 | 464 | 511 | 589 | 635 | 827 | 951 | 1104 | 1231 | 1319 | 1396 | 1541 | 79 | 4 | 1 | 71 | 71 | 4 | 40 | 71 | 2 | 79 | 2 | 40 | 2 | 4 | 40 | 1 | 2 | 71 | 1 | 4 | 40 | 2 | 2 | 2 | 71 | 2 | 40 | 79 | 79 | 1 | 4 | 40 | 2 | 79 | 71 | 1 | 40 | 79 | 4 | 4 | 1 | 79 | 4 | 4 | 1 | 71 | 1 | 4 | 1 | 71 | 2 | 71
291 | 197 | 153 | 202 | 346 | 462 | 695 | 925 | 971 | 1050 | 1272 | 1394 | 1405 | 1565 | 1765 | 1 | 2 | 79 | 71 | 40 | 4 | 1 | 4 | 1 | 1 | 71 | 71 | 40 | 71 | 4 | 1 | 79 | 4 | 71 | 79 | 79 | 71 | 40 | 40 | 40 | 1 | 4 | 1 | 4 | 2 | 2 | 71 | 40 | 71 | 71 | 40 | 2 | 1 | 40 | 79 | 1 | 4 | 4 | 2 | 40 | 79 | 1 | 40 | 79 | 40 | 79 | 2
292 | 235 | 116 | 385 | 638 | 907 | 1023 | 1067 | 1219 | 1346 | 1463 | 1547 | 1674 | 1796 | 1987 | 71 | 4 | 40 | 1 | 79 | 40 | 79 | 71 | 40 | 71 | 71 | 71 | 79 | 71 | 40 | 79 | 40 | 71 | 1 | 4 | 40 | 1 | 2 | 1 | 1 | 40 | 71 | 40 | 40 | 79 | 4 | 4 | 71 | 4 | 2 | 40 | 79 | 2 | 2 | 1 | 40 | 4 | 79 | 4 | 79 | 2 | 40 | 1 | 1 | 71 | 40 | 79
293 | 218 | 146 | 290 | 445 | 637 | 758 | 981 | 1131 | 1142 | 1187 | 1276 | 1319 | 1482 | 1603 | 71 | 2 | 71 | 2 | 1 | 71 | 71 | 1 | 71 | 4 | 79 | 1 | 79 | 2 | 40 | 71 | 1 | 1 | 79 | 40 | 71 | 71 | 79 | 2 | 4 | 71 | 4 | 71 | 4 | 2 | 1 | 4 | 1 | 2 | 2 | 40 | 4 | 4 | 79 | 2 | 1 | 1 | 1 | 40 | 4 | 40 | 79 | 40 | 1 | 79 | 40 | 1
294 | 237 | 164 | 279 | 540 | 731 | 962 | 1037 | 1162 | 1239 | 1438 | 1661 | 1710 | 1940 | 2022 | 79 | 2 | 4 | 79 | 71 | 2 | 40 | 2 | 79 | 40 | 71 | 71 | 1 | 71 | 40 | 79 | 79 | 79 | 2 | 71 | 2 | 1 | 71 | 1 | 40 | 2 | 4 | 79 | 2 | 71 | 2 | 2 | 79 | 40 | 1 | 79 | 79 | 71 | 71 | 2 | 4 | 4 | 1 | 40 | 79 | 71 | 1 | 79 | 1 | 40 | 40 | 1
295 | 244 | 164 | 319 | 482 | 567 | 683 | 806 | 997 | 1118 | 1195 | 1340 | 1532 | 1684 | 1772 | 79 | 4 | 2 | 79 | 79 | 1 | 71 | 4 | 40 | 4 | 40 | 79 | 1 | 79 | 1 | 4 | 71 | 1 | 4 | 40 | 79 | 40 | 2 | 2 | 1 | 79 | 40 | 71 | 40 | 79 | 1 | 1 | 71 | 4 | 1 | 1 | 2 | 71 | 71 | 1 | 79 | 2 | 71 | 40 | 71 | 79 | 1 | 1 | 4 | 1 | 79 | 4
296 | 380 | 261 | 499 | 624 | 779 | 978 | 1247 | 1410 | 1565 | 1648 | 1725 | 1919 | 2041 | 2196 | 71 | 79 | 71 | 40 | 79 | 40 | 79 | 40 | 40 | 4 | 79 | 2 | 71 | 4 | 79 | 1 | 79 | 40 | 40 | 40 | 71 | 79 | 79 | 40 | 79 | 4 | 79 | 1 | 1 | 4 | 71 | 79 | 40 | 2 | 1 | 40 | 2 | 71 | 2 | 2 | 71 | 4 | 40 | 79 | 2 | 40 | 1 | 79 | 4 | 79 | 1 | 71
297 | 244 | 86 | 286 | 442 | 589 | 600 | 794 | 994 | 1076 | 1242 | 1328 | 1414 | 1647 | 1947 | 2 | 1 | 4 | 79 | 79 | 79 | 2 | 40 | 4 | 2 | 79 | 71 | 71 | 4 | 1 | 71 | 4 | 2 | 4 | 1 | 71 | 40 | 79 | 4 | 40 | 2 | 79 | 79 | 1 | 40 | 40 | 1 | 79 | 4 | 79 | 4 | 1 | 4 | 2 | 79 | 2 | 79 | 4 | 1 | 79 | 71 | 79 | 4 | 71 | 79 | 79 | 71
298 | 121 | 80 | 279 | 394 | 546 | 709 | 723 | 801 | 875 | 1027 | 1180 | 1380 | 1633 | 1894 | 1 | 4 | 4 | 71 | 40 | 1 | 79 | 79 | 2 | 2 | 40 | 71 | 71 | 1 | 79 | 1 | 79 | 4 | 40 | 40 | 2 | 4 | 4 | 4 | 4 | 1 | 2 | 71 | 71 | 1 | 1 | 1 | 71 | 1 | 1 | 79 | 40 | 40 | 71 | 2 | 2 | 79 | 40 | 79 | 71 | 40 | 71 | 71 | 71 | 79 | 40 | 71
299 | 84 | 80 | 125 | 210 | 425 | 581 | 589 | 742 | 889 | 1112 | 1303 | 1416 | 1607 | 1657 | 4 | 4 | 1 | 71 | 2 | 2 | 1 | 40 | 1 | 1 | 4 | 79 | 2 | 71 | 71 | 71 | 71 | 79 | 2 | 4 | 1 | 1 | 4 | 2 | 2 | 40 | 40 | 71 | 71 | 1 | 4 | 71 | 2 | 71 | 79 | 71 | 40 | 71 | 1 | 79 | 1 | 40 | 1 | 71 | 40 | 79 | 71 | 1 | 4 | 4 | 2 | 40
300 | 122 | 50 | 194 | 417 | 496 | 687 | 840 | 959 | 1153 | 1242 | 1389 | 1542 | 1695 | 1774 | 2 | 4 | 40 | 4 | 71 | 1 | 71 | 1 | 2 | 79 | 71 | 71 | 71 | 2 | 2 | 4 | 79 | 40 | 71 | 1 | 1 | 79 | 2 | 71 | 40 | 4 | 71 | 4 | 71 | 79 | 4 | 40 | 4 | 79 | 2 | 4 | 71 | 71 | 1 | 4 | 71 | 1 | 2 | 79 | 2 | 79 | 71 | 1 | 4 | 2 | 2 | 71
301 | 241 | 158 | 321 | 483 | 705 | 826 | 901 | 1123 | 1131 | 1219 | 1342 | 1536 | 1652 | 1810 | 71 | 79 | 4 | 4 | 4 | 79 | 79 | 1 | 2 | 79 | 2 | 79 | 71 | 1 | 71 | 79 | 1 | 40 | 79 | 1 | 1 | 71 | 2 | 1 | 40 | 71 | 71 | 40 | 1 | 4 | 2 | 1 | 4 | 1 | 4 | 79 | 2 | 79 | 2 | 40 | 71 | 79 | 4 | 40 | 4 | 71 | 1 | 40 | 71 | 4 | 79 | 4
302 | 233 | 158 | 236 | 311 | 433 | 632 | 753 | 764 | 773 | 964 | 1042 | 1197 | 1319 | 1442 | 79 | 4 | 4 | 71 | 4 | 71 | 2 | 1 | 71 | 1 | 2 | 1 | 40 | 1 | 79 | 2 | 40 | 40 | 79 | 40 | 1 | 40 | 1 | 79 | 4 | 2 | 1 | 4 | 2 | 1 | 4 | 2 | 1 | 79 | 40 | 71 | 2 | 71 | 1 | 4 | 1 | 71 | 79 | 4 | 1 | 2 | 40 | 79 | 2 | 2 | 79 | 40
303 | 344 | 261 | 347 | 564 | 730 | 1022 | 1252 | 1337 | 1462 | 1547 | 1671 | 1835 | 2065 | 2148 | 71 | 71 | 40 | 79 | 4 | 79 | 2 | 1 | 4 | 71 | 71 | 71 | 4 | 4 | 79 | 79 | 71 | 71 | 71 | 79 | 79 | 40 | 71 | 40 | 40 | 40 | 1 | 4 | 40 | 79 | 4 | 2 | 40 | 1 | 4 | 40 | 4 | 1 | 79 | 40 | 2 | 79 | 4 | 79 | 79 | 40 | 40 | 71 | 79 | 2 | 1 | 1
304 | 303 | 230 | 308 | 390 | 475 | 675 | 867 | 953 | 1041 | 1188 | 1340 | 1601 | 1787 | 1981 | 79 | 71 | 40 | 40 | 71 | 2 | 4 | 1 | 1 | 1 | 1 | 79 | 79 | 1 | 4 | 1 | 79 | 79 | 40 | 2 | 71 | 40 | 79 | 2 | 1 | 79 | 4 | 2 | 79 | 4 | 1 | 4 | 4 | 71 | 71 | 1 | 79 | 1 | 1 | 71 | 40 | 71 | 71 | 79 | 71 | 71 | 4 | 40 | 4 | 71 | 40 | 79
305 | 49 | 47 | 129 | 290 | 440 | 642 | 723 | 962 | 1114 | 1189 | 1303 | 1456 | 1500 | 1511 | 1 | 2 | 40 | 4 | 1 | 1 | 1 | 79 | 40 | 2 | 40 | 79 | 4 | 71 | 4 | 71 | 79 | 40 | 4 | 79 | 4 | 2 | 4 | 71 | 79 | 2 | 79 | 79 | 40 | 1 | 40 | 71 | 71 | 1 | 1 | 2 | 71 | 2 | 1 | 40 | 71 | 2 | 1 | 79 | 1 | 1 | 2 | 40 | 4 | 1 | 4 | 2
306 | 388 | 308 | 499 | 693 | 838 | 955 | 1004 | 1281 | 1365 | 1634 | 1714 | 1866 | 1911 | 2227 | 79 | 79 | 79 | 71 | 79 | 1 | 40 | 71 | 40 | 4 | 79 | 71 | 71 | 1 | 2 | 71 | 2 | 4 | 71 | 40 | 4 | 1 | 40 | 4 | 79 | 79 | 40 | 79 | 2 | 2 | 79 | 1 | 79 | 40 | 79 | 71 | 1 | 71 | 4 | 4 | 1 | 1 | 71 | 79 | 40 | 2 | 1 | 2 | 79 | 79 | 79 | 79
307 | 169 | 163 | 213 | 335 | 452 | 606 | 867 | 1067 | 1077 | 1163 | 1308 | 1352 | 1435 | 1519 | 4 | 79 | 1 | 79 | 4 | 2 | 4 | 40 | 40 | 1 | 79 | 2 | 2 | 40 | 4 | 71 | 79 | 2 | 2 | 71 | 40 | 71 | 71 | 79 | 2 | 40 | 79 | 79 | 1 | 4 | 4 | 1 | 40 | 40 | 2 | 4 | 2 | 1 | 71 | 71 | 1 | 40 | 1 | 2 | 40 | 2 | 40 | 1 | 40 | 2 | 2 | 40
308 | 228 | 184 | 339 | 389 | 475 | 713 | 904 | 1062 | 1214 | 1437 | 1585 | 1735 | 1935 | 2080 | 71 | 40 | 2 | 71 | 40 | 4 | 71 | 40 | 4 | 2 | 4 | 40 | 79 | 4 | 1 | 2 | 40 | 79 | 40 | 79 | 1 | 71 | 40 | 79 | 79 | 71 | 4 | 4 | 40 | 40 | 71 | 1 | 2 | 79 | 71 | 71 | 4 | 71 | 71 | 2 | 71 | 4 | 71 | 4 | 79 | 79 | 2 | 40 | 2 | 71 | 1 | 71
309 | 263 | 183 | 266 | 421 | 574 | 690 | 912 | 1066 | 1143 | 1306 | 1430 | 1442 | 1526 | 1533 | 71 | 71 | 1 | 40 | 1 | 79 | 1 | 2 | 79 | 4 | 1 | 71 | 79 | 1 | 2 | 71 | 71 | 4 | 1 | 40 | 71 | 40 | 40 | 71 | 2 | 71 | 79 | 2 | 1 | 71 | 1 | 4 | 4 | 40 | 79 | 40 | 4 | 1 | 79 | 40 | 2 | 2 | 4 | 4 | 2 | 2 | 79 | 1 | 2 | 2 | 1 | 2
310 | 89 | 84 | 92 | 174 | 366 | 550 | 734 | 856 | 942 | 1025 | 1208 | 1431 | 1556 | 1599 | 40 | 40 | 2 | 2 | 1 | 4 | 1 | 2 | 79 | 1 | 1 | 1 | 40 | 71 | 2 | 79 | 71 | 71 | 2 | 40 | 40 | 71 | 71 | 2 | 1 | 2 | 79 | 40 | 40 | 4 | 40 | 2 | 1 | 40 | 2 | 40 | 40 | 1 | 71 | 71 | 71 | 79 | 2 | 71 | 40 | 4 | 79 | 2 | 1 | 1 | 40 | 1
311 | 190 | 148 | 234 | 418 | 579 | 809 | 887 | 1048 | 1165 | 1286 | 1364 | 1485 | 1638 | 1799 | 71 | 4 | 2 | 71 | 2 | 40 | 4 | 40 | 40 | 71 | 71 | 2 | 79 | 2 | 1 | 79 | 1 | 79 | 71 | 79 | 1 | 2 | 4 | 71 | 40 | 79 | 40 | 2 | 40 | 4 | 2 | 71 | 1 | 1 | 40 | 79 | 4 | 1 | 71 | 2 | 1 | 79 | 1 | 40 | 79 | 71 | 2 | 1 | 2 | 1 | 79 | 79
312 | 197 | 122 | 316 | 440 | 603 | 686 | 734 | 809 | 992 | 1041 | 1341 | 1422 | 1503 | 1555 | 1 | 40 | 79 | 2 | 4 | 71 | 40 | 79 | 40 | 79 | 1 | 4 | 1 | 79 | 79 | 4 | 4 | 4 | 4 | 71 | 4 | 2 | 2 | 40 | 1 | 71 | 2 | 1 | 71 | 1 | 71 | 40 | 4 | 40 | 4 | 1 | 71 | 71 | 79 | 79 | 4 | 2 | 4 | 71 | 4 | 71 | 4 | 2 | 4 | 40 | 4 | 4
313 | 275 | 156 | 386 | 469 | 513 | 589 | 673 | 723 | 801 | 848 | 1032 | 1195 | 1319 | 1519 | 71 | 2 | 79 | 4 | 79 | 40 | 71 | 40 | 1 | 1 | 79 | 2 | 1 | 40 | 1 | 2 | 2 | 1 | 71 | 2 | 2 | 2 | 79 | 1 | 4 | 4 | 40 | 2 | 71 | 4 | 1 | 2 | 1 | 40 | 2 | 4 | 71 | 71 | 40 | 2 | 40 | 40 | 4 | 79 | 1 | 4 | 79 | 40 | 79 | 40 | 2 | 79
314 | 196 | 115 | 346 | 510 | 662 | 668 | 752 | 904 | 947 | 1111 | 1302 | 1346 | 1507 | 1592 | 2 | 71 | 2 | 40 | 2 | 79 | 71 | 79 | 79 | 79 | 2 | 4 | 71 | 79 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 79 | 2 | 2 | 71 | 1 | 1 | 79 | 1 | 1 | 40 | 1 | 2 | 4 | 79 | 79 | 71 | 1 | 79 | 40 | 2 | 1 | 40 | 1 | 2 | 40 | 40 | 79 | 79 | 1 | 1 | 4
315 | 89 | 81 | 93 | 249 | 474 | 636 | 790 | 982 | 1028 | 1180 | 1307 | 1506 | 1661 | 1816 | 4 | 4 | 71 | 2 | 4 | 4 | 2 | 2 | 2 | 79 | 71 | 4 | 71 | 79 | 71 | 4 | 79 | 2 | 79 | 2 | 71 | 2 | 79 | 2 | 71 | 2 | 40 | 79 | 40 | 2 | 2 | 2 | 71 | 1 | 1 | 79 | 4 | 40 | 79 | 4 | 40 | 1 | 79 | 79 | 4 | 79 | 1 | 71 | 4 | 79 | 71 | 1
316 | 169 | 164 | 171 | 258 | 372 | 491 | 579 | 665 | 811 | 1033 | 1180 | 1341 | 1493 | 1570 | 79 | 79 | 2 | 4 | 4 | 1 | 1 | 1 | 2 | 2 | 79 | 4 | 40 | 1 | 71 | 2 | 4 | 71 | 40 | 4 | 4 | 79 | 1 | 4 | 1 | 79 | 4 | 2 | 71 | 2 | 2 | 71 | 40 | 71 | 71 | 40 | 4 | 71 | 1 | 71 | 2 | 79 | 1 | 79 | 1 | 71 | 79 | 1 | 2 | 71 | 2 | 2
317 | 306 | 156 | 386 | 463 | 468 | 584 | 740 | 887 | 1048 | 1239 | 1360 | 1551 | 1665 | 1740 | 71 | 79 | 2 | 4 | 79 | 71 | 79 | 1 | 4 | 1 | 1 | 71 | 1 | 1 | 1 | 2 | 1 | 4 | 71 | 40 | 4 | 79 | 2 | 71 | 4 | 1 | 71 | 71 | 2 | 40 | 79 | 40 | 40 | 71 | 1 | 79 | 40 | 40 | 1 | 40 | 1 | 79 | 40 | 71 | 1 | 40 | 2 | 71 | 71 | 2 | 1 | 1
318 | 344 | 233 | 455 | 471 | 623 | 738 | 968 | 1081 | 1265 | 1311 | 1433 | 1518 | 1702 | 1782 | 79 | 4 | 71 | 79 | 40 | 71 | 40 | 71 | 4 | 4 | 4 | 4 | 79 | 1 | 1 | 71 | 40 | 71 | 2 | 2 | 79 | 1 | 79 | 71 | 1 | 1 | 71 | 40 | 40 | 71 | 71 | 2 | 4 | 1 | 40 | 1 | 40 | 2 | 79 | 1 | 2 | 2 | 2 | 79 | 2 | 40 | 71 | 71 | 1 | 4 | 71 | 4
319 | 155 | 113 | 197 | 311 | 503 | 655 | 847 | 894 | 1010 | 1062 | 1177 | 1299 | 1382 | 1465 | 1 | 40 | 1 | 71 | 2 | 40 | 40 | 2 | 1 | 71 | 2 | 40 | 79 | 2 | 71 | 40 | 79 | 1 | 71 | 1 | 79 | 2 | 40 | 71 | 1 | 4 | 2 | 40 | 1 | 71 | 4 | 40 | 4 | 4 | 40 | 4 | 2 | 2 | 71 | 40 | 79 | 40 | 2 | 1 | 2 | 40 | 1 | 40 | 1 | 2 | 1 | 79
320 | 234 | 231 | 384 | 584 | 661 | 775 | 781 | 906 | 1030 | 1042 | 1124 | 1290 | 1373 | 1382 | 71 | 79 | 2 | 79 | 2 | 1 | 71 | 79 | 79 | 40 | 79 | 2 | 71 | 1 | 1 | 4 | 40 | 1 | 71 | 2 | 1 | 1 | 2 | 2 | 40 | 2 | 79 | 4 | 40 | 79 | 1 | 4 | 4 | 2 | 2 | 4 | 40 | 1 | 40 | 1 | 4 | 79 | 79 | 4 | 40 | 2 | 40 | 1 | 4 | 1 | 2 | 2
321 | 198 | 192 | 200 | 492 | 683 | 767 | 922 | 1152 | 1202 | 1329 | 1528 | 1653 | 1814 | 1998 | 79 | 2 | 40 | 71 | 4 | 2 | 1 | 1 | 71 | 79 | 71 | 71 | 79 | 71 | 1 | 40 | 2 | 40 | 40 | 2 | 71 | 4 | 1 | 79 | 71 | 40 | 40 | 79 | 40 | 4 | 2 | 4 | 4 | 79 | 4 | 40 | 40 | 79 | 1 | 79 | 40 | 79 | 2 | 4 | 79 | 79 | 2 | 1 | 71 | 71 | 2 | 40
322 | 124 | 116 | 132 | 257 | 382 | 496 | 659 | 823 | 948 | 1248 | 1509 | 1701 | 1822 | 1902 | 71 | 40 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 40 | 2 | 79 | 79 | 4 | 2 | 40 | 2 | 1 | 71 | 40 | 40 | 79 | 4 | 40 | 79 | 4 | 79 | 2 | 40 | 4 | 2 | 79 | 71 | 71 | 79 | 79 | 79 | 71 | 40 | 71 | 71 | 2 | 79 | 40 | 1 | 40 | 40 | 40 | 4 | 71 | 1 | 4
323 | 296 | 223 | 368 | 529 | 541 | 841 | 918 | 1003 | 1091 | 1208 | 1461 | 1507 | 1671 | 1873 | 71 | 79 | 2 | 71 | 71 | 2 | 1 | 71 | 40 | 79 | 2 | 40 | 4 | 2 | 2 | 4 | 79 | 71 | 79 | 71 | 2 | 2 | 2 | 71 | 2 | 79 | 2 | 2 | 1 | 4 | 4 | 79 | 4 | 71 | 40 | 2 | 71 | 71 | 71 | 40 | 1 | 4 | 1 | 40 | 2 | 79 | 79 | 4 | 79 | 4 | 79 | 40
324 | 151 | 147 | 301 | 418 | 532 | 537 | 701 | 822 | 871 | 880 | 966 | 1124 | 1206 | 1297 | 4 | 1 | 71 | 71 | 2 | 2 | 79 | 71 | 40 | 71 | 2 | 4 | 40 | 1 | 71 | 2 | 2 | 1 | 1 | 1 | 79 | 2 | 79 | 4 | 79 | 1 | 40 | 1 | 40 | 4 | 4 | 1 | 2 | 1 | 4 | 2 | 2 | 4 | 79 | 1 | 71 | 79 | 4 | 4 | 1 | 1 | 1 | 79 | 4 | 4 | 4 | 79
325 | 403 | 261 | 478 | 739 | 931 | 974 | 1205 | 1318 | 1556 | 1747 | 1908 | 2141 | 2307 | 2386 | 71 | 40 | 79 | 71 | 71 | 71 | 71 | 4 | 79 | 40 | 71 | 71 | 71 | 40 | 2 | 79 | 40 | 1 | 1 | 1 | 2 | 79 | 71 | 79 | 1 | 40 | 1 | 71 | 79 | 1 | 79 | 79 | 1 | 79 | 40 | 71 | 79 | 79 | 1 | 2 | 71 | 4 | 79 | 79 | 4 | 4 | 79 | 79 | 4 | 2 | 2 | 71
326 | 272 | 199 | 274 | 357 | 441 | 596 | 787 | 934 | 1009 | 1131 | 1216 | 1408 | 1524 | 1678 | 79 | 40 | 79 | 1 | 71 | 2 | 1 | 1 | 79 | 2 | 1 | 1 | 1 | 2 | 79 | 2 | 79 | 71 | 1 | 4 | 71 | 1 | 79 | 40 | 71 | 71 | 4 | 1 | 1 | 1 | 2 | 71 | 79 | 2 | 1 | 40 | 1 | 79 | 1 | 4 | 40 | 71 | 2 | 79 | 40 | 4 | 71 | 1 | 2 | 71 | 2 | 79
327 | 265 | 192 | 270 | 316 | 363 | 518 | 639 | 864 | 980 | 1030 | 1079 | 1164 | 1317 | 1547 | 2 | 71 | 40 | 79 | 71 | 2 | 4 | 1 | 2 | 2 | 40 | 2 | 2 | 4 | 40 | 1 | 40 | 4 | 40 | 71 | 40 | 79 | 1 | 1 | 71 | 4 | 79 | 71 | 40 | 71 | 1 | 4 | 4 | 2 | 4 | 40 | 40 | 4 | 1 | 4 | 40 | 40 | 4 | 1 | 2 | 1 | 79 | 71 | 79 | 1 | 79 | 71
328 | 244 | 125 | 317 | 396 | 552 | 710 | 862 | 1062 | 1224 | 1268 | 1426 | 1473 | 1628 | 1820 | 2 | 79 | 4 | 40 | 40 | 79 | 71 | 2 | 2 | 4 | 71 | 2 | 2 | 4 | 79 | 71 | 4 | 79 | 71 | 4 | 1 | 40 | 40 | 71 | 40 | 79 | 2 | 79 | 79 | 79 | 2 | 2 | 40 | 1 | 2 | 1 | 4 | 79 | 71 | 4 | 40 | 1 | 2 | 4 | 79 | 4 | 71 | 1 | 71 | 79 | 40 | 2
329 | 274 | 194 | 355 | 444 | 566 | 719 | 799 | 959 | 1038 | 1152 | 1235 | 1312 | 1395 | 1473 | 4 | 71 | 40 | 79 | 40 | 40 | 79 | 2 | 79 | 4 | 4 | 2 | 79 | 2 | 40 | 1 | 71 | 1 | 79 | 2 | 1 | 71 | 4 | 4 | 40 | 40 | 1 | 79 | 71 | 4 | 2 | 2 | 1 | 40 | 2 | 71 | 1 | 2 | 1 | 79 | 71 | 2 | 2 | 2 | 2 | 40 | 40 | 1 | 4 | 2 | 1 | 71
330 | 303 | 192 | 422 | 536 | 548 | 632 | 756 | 844 | 931 | 1047 | 1172 | 1332 | 1496 | 1618 | 2 | 40 | 71 | 79 | 40 | 71 | 79 | 40 | 40 | 71 | 2 | 1 | 4 | 2 | 4 | 2 | 79 | 2 | 1 | 2 | 40 | 4 | 79 | 1 | 40 | 40 | 4 | 4 | 4 | 79 | 2 | 2 | 40 | 71 | 1 | 4 | 2 | 79 | 40 | 4 | 40 | 79 | 1 | 40 | 4 | 2 | 79 | 79 | 40 | 2 | 40 | 40
331 | 130 | 50 | 249 | 332 | 554 | 638 | 793 | 1062 | 1148 | 1236 | 1322 | 1333 | 1485 | 1754 | 4 | 4 | 2 | 40 | 40 | 40 | 40 | 79 | 71 | 4 | 4 | 4 | 71 | 79 | 71 | 1 | 1 | 2 | 79 | 2 | 1 | 71 | 4 | 79 | 40 | 71 | 79 | 79 | 40 | 40 | 2 | 4 | 79 | 4 | 4 | 1 | 4 | 79 | 2 | 1 | 4 | 1 | 2 | 4 | 40 | 40 | 1 | 71 | 40 | 71 | 79 | 79
332 | 272 | 230 | 276 | 323 | 438 | 638 | 754 | 834 | 995 | 1078 | 1191 | 1241 | 1316 | 1469 | 71 | 79 | 1 | 79 | 2 | 40 | 2 | 2 | 4 | 40 | 1 | 2 | 2 | 2 | 40 | 71 | 79 | 40 | 2 | 79 | 1 | 71 | 4 | 40 | 4 | 71 | 1 | 4 | 79 | 1 | 79 | 2 | 71 | 4 | 4 | 4 | 1 | 1 | 71 | 40 | 4 | 40 | 4 | 2 | 1 | 71 | 2 | 1 | 2 | 79 | 1 | 71
333 | 239 | 158 | 322 | 614 | 697 | 810 | 931 | 1122 | 1321 | 1435 | 1556 | 1672 | 1680 | 1771 | 4 | 79 | 4 | 71 | 79 | 2 | 79 | 4 | 71 | 71 | 71 | 79 | 79 | 2 | 1 | 1 | 40 | 71 | 1 | 1 | 40 | 1 | 1 | 79 | 79 | 40 | 1 | 71 | 79 | 1 | 79 | 40 | 40 | 1 | 71 | 2 | 40 | 79 | 1 | 1 | 40 | 1 | 4 | 71 | 4 | 2 | 1 | 1 | 4 | 79 | 4 | 4
334 | 88 | 47 | 130 | 135 | 220 | 445 | 603 | 649 | 727 | 889 | 976 | 1028 | 1181 | 1302 | 1 | 40 | 2 | 4 | 1 | 40 | 40 | 2 | 1 | 1 | 2 | 1 | 4 | 1 | 1 | 79 | 4 | 79 | 71 | 71 | 71 | 79 | 4 | 4 | 4 | 1 | 1 | 40 | 71 | 1 | 4 | 2 | 2 | 79 | 2 | 79 | 4 | 2 | 2 | 79 | 40 | 4 | 4 | 4 | 71 | 1 | 79 | 2 | 1 | 1 | 40 | 79
335 | 302 | 230 | 385 | 389 | 551 | 601 | 723 | 917 | 1000 | 1050 | 1244 | 1392 | 1508 | 1591 | 71 | 1 | 79 | 79 | 71 | 1 | 79 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | 79 | 79 | 40 | 4 | 4 | 2 | 2 | 1 | 79 | 40 | 71 | 40 | 4 | 79 | 1 | 40 | 40 | 2 | 4 | 40 | 4 | 2 | 4 | 71 | 79 | 40 | 4 | 71 | 2 | 71 | 71 | 4 | 40 | 1 | 79 | 2 | 1 | 1
336 | 127 | 83 | 269 | 355 | 519 | 605 | 729 | 895 | 1055 | 1134 | 1212 | 1298 | 1531 | 1644 | 4 | 4 | 4 | 71 | 40 | 4 | 71 | 71 | 1 | 4 | 79 | 2 | 4 | 79 | 79 | 2 | 1 | 4 | 79 | 2 | 40 | 40 | 4 | 40 | 79 | 4 | 4 | 79 | 40 | 79 | 40 | 1 | 71 | 4 | 2 | 2 | 1 | 2 | 4 | 71 | 2 | 4 | 40 | 40 | 79 | 4 | 79 | 71 | 1 | 1 | 71 | 40
337 | 235 | 191 | 385 | 538 | 776 | 959 | 1076 | 1190 | 1315 | 1473 | 1519 | 1641 | 1727 | 1736 | 79 | 40 | 1 | 71 | 4 | 40 | 71 | 79 | 2 | 71 | 40 | 40 | 40 | 79 | 79 | 40 | 71 | 1 | 71 | 40 | 71 | 4 | 2 | 40 | 40 | 1 | 2 | 71 | 79 | 4 | 2 | 40 | 71 | 79 | 4 | 4 | 1 | 4 | 40 | 1 | 40 | 1 | 79 | 2 | 1 | 79 | 4 | 2 | 2 | 2 | 1 | 4
338 | 202 | 160 | 243 | 396 | 477 | 707 | 793 | 917 | 1001 | 1045 | 1198 | 1315 | 1437 | 1589 | 40 | 1 | 79 | 40 | 2 | 40 | 1 | 40 | 71 | 2 | 79 | 1 | 2 | 4 | 4 | 71 | 40 | 79 | 40 | 71 | 4 | 79 | 1 | 2 | 1 | 79 | 40 | 4 | 2 | 79 | 1 | 2 | 1 | 40 | 2 | 1 | 71 | 40 | 2 | 40 | 71 | 2 | 40 | 4 | 40 | 2 | 1 | 79 | 1 | 79 | 1 | 71
339 | 263 | 113 | 346 | 353 | 427 | 590 | 604 | 653 | 875 | 1077 | 1237 | 1320 | 1403 | 1478 | 1 | 71 | 1 | 40 | 79 | 71 | 79 | 4 | 1 | 1 | 1 | 4 | 1 | 1 | 71 | 1 | 4 | 40 | 79 | 40 | 2 | 4 | 4 | 4 | 1 | 40 | 4 | 4 | 71 | 40 | 40 | 71 | 40 | 4 | 79 | 79 | 1 | 1 | 79 | 79 | 1 | 79 | 1 | 2 | 4 | 4 | 71 | 4 | 1 | 2 | 1 | 71
340 | 238 | 166 | 243 | 368 | 377 | 387 | 503 | 578 | 694 | 916 | 1141 | 1218 | 1448 | 1531 | 4 | 79 | 79 | 4 | 1 | 71 | 1 | 4 | 4 | 2 | 40 | 79 | 2 | 4 | 2 | 1 | 4 | 1 | 4 | 1 | 40 | 4 | 1 | 71 | 71 | 1 | 2 | 1 | 71 | 1 | 40 | 4 | 40 | 71 | 40 | 71 | 71 | 4 | 71 | 79 | 4 | 1 | 1 | 71 | 79 | 71 | 1 | 79 | 1 | 40 | 40 | 2
341 | 164 | 83 | 244 | 319 | 550 | 749 | 874 | 1096 | 1288 | 1452 | 1577 | 1627 | 1810 | 1934 | 1 | 2 | 40 | 40 | 79 | 2 | 40 | 40 | 2 | 71 | 1 | 1 | 2 | 79 | 71 | 79 | 40 | 79 | 40 | 40 | 79 | 4 | 2 | 40 | 71 | 40 | 71 | 40 | 79 | 2 | 71 | 40 | 4 | 79 | 2 | 79 | 2 | 79 | 4 | 40 | 4 | 2 | 40 | 4 | 71 | 71 | 1 | 40 | 1 | 4 | 40 | 79
342 | 264 | 261 | 339 | 500 | 549 | 673 | 865 | 1013 | 1096 | 1182 | 1338 | 1504 | 1551 | 1634 | 79 | 71 | 40 | 71 | 2 | 1 | 71 | 4 | 79 | 1 | 79 | 2 | 40 | 4 | 1 | 4 | 1 | 40 | 4 | 79 | 79 | 71 | 40 | 2 | 2 | 4 | 71 | 71 | 4 | 71 | 4 | 4 | 4 | 2 | 40 | 40 | 2 | 79 | 4 | 71 | 79 | 4 | 79 | 4 | 1 | 40 | 4 | 2 | 1 | 40 | 40 | 2
343 | 227 | 85 | 308 | 499 | 665 | 851 | 898 | 1090 | 1246 | 1407 | 1524 | 1746 | 1898 | 2131 | 2 | 79 | 2 | 2 | 71 | 71 | 2 | 79 | 79 | 1 | 40 | 71 | 79 | 4 | 79 | 4 | 71 | 71 | 40 | 4 | 40 | 4 | 1 | 2 | 40 | 71 | 79 | 2 | 71 | 4 | 2 | 79 | 2 | 79 | 40 | 40 | 40 | 4 | 2 | 71 | 71 | 1 | 71 | 79 | 1 | 1 | 71 | 79 | 79 | 71 | 4 | 79
344 | 199 | 155 | 202 | 318 | 403 | 527 | 654 | 818 | 933 | 1135 | 1213 | 1335 | 1529 | 1691 | 1 | 71 | 4 | 79 | 40 | 4 | 1 | 2 | 1 | 4 | 71 | 40 | 40 | 40 | 4 | 1 | 40 | 4 | 1 | 79 | 79 | 4 | 4 | 40 | 4 | 2 | 79 | 79 | 2 | 71 | 40 | 2 | 79 | 40 | 79 | 4 | 71 | 2 | 4 | 1 | 79 | 1 | 2 | 40 | 79 | 40 | 4 | 71 | 2 | 79 | 79 | 2
345 | 242 | 162 | 284 | 329 | 414 | 541 | 691 | 916 | 1100 | 1112 | 1276 | 1326 | 1484 | 1567 | 79 | 2 | 79 | 2 | 40 | 40 | 2 | 40 | 2 | 1 | 2 | 40 | 1 | 1 | 4 | 79 | 40 | 4 | 79 | 4 | 4 | 4 | 71 | 71 | 79 | 71 | 71 | 4 | 71 | 40 | 71 | 2 | 2 | 4 | 2 | 4 | 4 | 79 | 2 | 79 | 40 | 4 | 4 | 2 | 79 | 4 | 4 | 71 | 2 | 1 | 1 | 79
346 | 228 | 148 | 234 | 347 | 492 | 570 | 801 | 887 | 1148 | 1332 | 1379 | 1496 | 1545 | 1625 | 2 | 71 | 4 | 71 | 1 | 79 | 2 | 4 | 71 | 40 | 1 | 1 | 71 | 2 | 71 | 1 | 4 | 2 | 1 | 71 | 79 | 71 | 79 | 2 | 79 | 4 | 1 | 2 | 71 | 71 | 40 | 79 | 2 | 40 | 71 | 71 | 2 | 40 | 1 | 4 | 71 | 2 | 40 | 4 | 4 | 4 | 1 | 40 | 4 | 71 | 4 | 1
347 | 381 | 231 | 386 | 541 | 696 | 880 | 1113 | 1238 | 1351 | 1503 | 1658 | 1958 | 1969 | 2045 | 2 | 79 | 79 | 71 | 71 | 79 | 4 | 1 | 71 | 1 | 79 | 4 | 71 | 4 | 1 | 79 | 40 | 2 | 71 | 71 | 79 | 79 | 71 | 4 | 2 | 79 | 4 | 40 | 1 | 40 | 1 | 71 | 71 | 1 | 40 | 40 | 71 | 40 | 4 | 40 | 71 | 79 | 71 | 79 | 1 | 4 | 4 | 2 | 1 | 71 | 2 | 2
348 | 160 | 85 | 310 | 460 | 471 | 617 | 706 | 781 | 827 | 911 | 995 | 1225 | 1304 | 1391 | 1 | 1 | 79 | 4 | 4 | 71 | 71 | 79 | 71 | 71 | 4 | 4 | 1 | 4 | 2 | 4 | 71 | 2 | 2 | 71 | 4 | 2 | 4 | 79 | 2 | 71 | 1 | 1 | 1 | 40 | 4 | 1 | 1 | 2 | 2 | 79 | 2 | 1 | 79 | 2 | 79 | 40 | 40 | 71 | 2 | 4 | 2 | 71 | 4 | 2 | 79 | 2
349 | 318 | 238 | 401 | 559 | 607 | 760 | 913 | 992 | 1183 | 1330 | 1455 | 1580 | 1772 | 2003 | 79 | 79 | 79 | 1 | 1 | 79 | 79 | 4 | 4 | 4 | 71 | 79 | 40 | 2 | 4 | 2 | 40 | 2 | 40 | 71 | 71 | 40 | 2 | 40 | 2 | 4 | 71 | 2 | 79 | 71 | 1 | 40 | 71 | 1 | 4 | 71 | 2 | 40 | 4 | 79 | 2 | 79 | 40 | 4 | 2 | 79 | 71 | 40 | 79 | 79 | 71 | 2
350 | 82 | 77 | 162 | 353 | 366 | 635 | 679 | 835 | 990 | 1079 | 1273 | 1387 | 1394 | 1547 | 71 | 1 | 4 | 1 | 4 | 1 | 79 | 1 | 40 | 71 | 40 | 40 | 1 | 4 | 4 | 4 | 79 | 40 | 71 | 79 | 40 | 1 | 1 | 2 | 4 | 2 | 79 | 71 | 71 | 40 | 4 | 40 | 2 | 4 | 4 | 79 | 40 | 79 | 4 | 71 | 40 | 71 | 1 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 79 | 71
351 | 225 | 75 | 344 | 535 | 696 | 812 | 939 | 1018 | 1093 | 1168 | 1320 | 1400 | 1631 | 1756 | 1 | 1 | 71 | 2 | 79 | 71 | 40 | 79 | 1 | 71 | 40 | 79 | 79 | 40 | 2 | 40 | 71 | 4 | 1 | 40 | 40 | 4 | 4 | 79 | 71 | 2 | 4 | 2 | 1 | 2 | 71 | 1 | 2 | 1 | 71 | 1 | 40 | 71 | 1 | 40 | 4 | 4 | 71 | 1 | 71 | 79 | 79 | 2 | 4 | 2 | 40 | 79
352 | 82 | 79 | 193 | 338 | 532 | 615 | 767 | 884 | 897 | 984 | 1144 | 1343 | 1428 | 1547 | 71 | 2 | 2 | 4 | 2 | 1 | 40 | 71 | 71 | 2 | 1 | 71 | 40 | 71 | 79 | 4 | 1 | 1 | 2 | 79 | 1 | 1 | 71 | 79 | 71 | 40 | 2 | 4 | 1 | 4 | 4 | 4 | 79 | 4 | 2 | 2 | 79 | 1 | 79 | 1 | 79 | 1 | 40 | 79 | 79 | 4 | 1 | 1 | 40 | 4 | 71 | 4
353 | 150 | 75 | 233 | 282 | 476 | 524 | 613 | 765 | 931 | 1044 | 1238 | 1312 | 1399 | 1518 | 71 | 1 | 1 | 2 | 4 | 71 | 79 | 4 | 40 | 4 | 1 | 4 | 79 | 71 | 40 | 4 | 2 | 4 | 40 | 2 | 4 | 79 | 4 | 2 | 71 | 1 | 40 | 40 | 79 | 4 | 4 | 79 | 1 | 40 | 71 | 1 | 4 | 71 | 40 | 79 | 1 | 1 | 71 | 1 | 2 | 2 | 79 | 4 | 4 | 71 | 40 | 4
354 | 84 | 11 | 128 | 216 | 330 | 379 | 425 | 678 | 869 | 955 | 1208 | 1368 | 1451 | 1566 | 2 | 1 | 4 | 4 | 71 | 2 | 40 | 4 | 4 | 40 | 4 | 40 | 1 | 71 | 2 | 40 | 4 | 1 | 4 | 40 | 1 | 4 | 40 | 1 | 40 | 71 | 71 | 71 | 1 | 40 | 71 | 79 | 2 | 40 | 40 | 4 | 71 | 71 | 40 | 71 | 40 | 1 | 79 | 40 | 2 | 1 | 79 | 1 | 2 | 71 | 40 | 2
355 | 129 | 85 | 209 | 295 | 339 | 417 | 539 | 762 | 987 | 1150 | 1194 | 1347 | 1433 | 1508 | 1 | 4 | 79 | 1 | 40 | 4 | 1 | 79 | 4 | 79 | 2 | 1 | 1 | 40 | 1 | 2 | 4 | 71 | 2 | 1 | 1 | 2 | 40 | 79 | 71 | 2 | 71 | 79 | 4 | 71 | 79 | 71 | 79 | 79 | 1 | 4 | 2 | 40 | 1 | 1 | 40 | 71 | 40 | 2 | 2 | 4 | 79 | 1 | 1 | 2 | 1 | 71
356 | 123 | 79 | 206 | 431 | 594 | 718 | 880 | 1063 | 1215 | 1370 | 1449 | 1533 | 1686 | 1771 | 2 | 71 | 2 | 4 | 4 | 40 | 4 | 79 | 71 | 79 | 4 | 71 | 79 | 1 | 79 | 4 | 1 | 79 | 40 | 4 | 79 | 79 | 2 | 2 | 71 | 1 | 40 | 71 | 1 | 79 | 71 | 1 | 71 | 4 | 40 | 40 | 2 | 4 | 71 | 2 | 1 | 79 | 2 | 2 | 2 | 71 | 79 | 1 | 1 | 1 | 79 | 4
357 | 238 | 127 | 313 | 324 | 445 | 497 | 546 | 628 | 636 | 752 | 906 | 994 | 1224 | 1382 | 4 | 4 | 40 | 79 | 40 | 71 | 71 | 4 | 4 | 1 | 4 | 2 | 1 | 40 | 1 | 79 | 4 | 4 | 40 | 4 | 40 | 1 | 4 | 4 | 1 | 1 | 40 | 40 | 4 | 2 | 1 | 1 | 71 | 1 | 40 | 4 | 79 | 71 | 2 | 2 | 1 | 4 | 79 | 4 | 1 | 79 | 71 | 79 | 79 | 71 | 4 | 4
358 | 51 | 46 | 56 | 144 | 298 | 489 | 647 | 655 | 872 | 1125 | 1250 | 1261 | 1346 | 1538 | 4 | 1 | 40 | 1 | 1 | 4 | 4 | 1 | 4 | 79 | 4 | 1 | 2 | 2 | 79 | 71 | 40 | 71 | 79 | 1 | 71 | 4 | 79 | 4 | 2 | 2 | 2 | 2 | 71 | 4 | 71 | 71 | 71 | 40 | 71 | 71 | 40 | 79 | 4 | 2 | 2 | 1 | 4 | 4 | 4 | 1 | 79 | 1 | 40 | 71 | 2 | 79
359 | 258 | 186 | 338 | 422 | 433 | 578 | 703 | 933 | 1164 | 1255 | 1380 | 1468 | 1582 | 1707 | 4 | 71 | 71 | 40 | 71 | 1 | 1 | 79 | 2 | 2 | 1 | 79 | 4 | 2 | 1 | 4 | 71 | 71 | 2 | 1 | 2 | 40 | 79 | 4 | 40 | 79 | 40 | 71 | 79 | 71 | 2 | 79 | 4 | 4 | 79 | 4 | 40 | 2 | 4 | 79 | 4 | 79 | 4 | 1 | 2 | 1 | 40 | 71 | 79 | 4 | 2 | 40
360 | 232 | 121 | 276 | 506 | 623 | 667 | 677 | 756 | 940 | 1084 | 1270 | 1351 | 1573 | 1692 | 1 | 1 | 40 | 79 | 71 | 40 | 4 | 40 | 40 | 79 | 40 | 71 | 4 | 40 | 2 | 71 | 1 | 2 | 1 | 40 | 1 | 1 | 4 | 4 | 71 | 2 | 4 | 2 | 71 | 40 | 2 | 71 | 71 | 1 | 1 | 71 | 71 | 40 | 71 | 4 | 2 | 4 | 4 | 71 | 40 | 71 | 71 | 40 | 4 | 4 | 40 | 71
361 | 236 | 153 | 239 | 324 | 407 | 640 | 688 | 841 | 926 | 1078 | 1203 | 1355 | 1511 | 1772 | 40 | 40 | 2 | 71 | 79 | 4 | 2 | 1 | 4 | 40 | 1 | 40 | 79 | 1 | 1 | 2 | 4 | 71 | 79 | 79 | 4 | 40 | 2 | 2 | 40 | 2 | 71 | 40 | 4 | 1 | 79 | 1 | 1 | 79 | 71 | 1 | 4 | 79 | 40 | 2 | 71 | 79 | 1 | 1 | 79 | 4 | 2 | 71 | 71 | 71 | 40 | 79
362 | 226 | 222 | 228 | 273 | 428 | 572 | 693 | 810 | 819 | 1002 | 1158 | 1322 | 1475 | 1600 | 1 | 71 | 71 | 79 | 2 | 2 | 1 | 1 | 1 | 40 | 2 | 2 | 4 | 79 | 71 | 1 | 1 | 71 | 71 | 1 | 1 | 40 | 79 | 1 | 4 | 71 | 40 | 2 | 2 | 4 | 2 | 1 | 71 | 1 | 71 | 40 | 79 | 2 | 71 | 4 | 2 | 79 | 4 | 79 | 79 | 2 | 71 | 1 | 79 | 40 | 2 | 4
363 | 236 | 161 | 317 | 517 | 708 | 854 | 1010 | 1310 | 1399 | 1622 | 1738 | 1827 | 1913 | 2028 | 79 | 1 | 79 | 2 | 71 | 4 | 2 | 79 | 79 | 2 | 79 | 40 | 40 | 71 | 79 | 1 | 2 | 71 | 2 | 71 | 79 | 2 | 71 | 4 | 79 | 79 | 71 | 71 | 4 | 79 | 2 | 4 | 71 | 71 | 2 | 79 | 1 | 40 | 4 | 71 | 4 | 4 | 2 | 79 | 79 | 2 | 1 | 4 | 2 | 71 | 2 | 40
364 | 169 | 163 | 175 | 367 | 484 | 676 | 799 | 923 | 1079 | 1340 | 1648 | 1871 | 1959 | 2109 | 1 | 79 | 4 | 79 | 4 | 2 | 4 | 2 | 2 | 71 | 79 | 40 | 71 | 4 | 40 | 2 | 40 | 2 | 79 | 71 | 40 | 2 | 79 | 2 | 79 | 40 | 1 | 4 | 79 | 71 | 2 | 4 | 79 | 71 | 40 | 71 | 71 | 79 | 79 | 79 | 71 | 2 | 79 | 71 | 4 | 79 | 1 | 4 | 4 | 4 | 71 | 71
365 | 267 | 194 | 347 | 624 | 640 | 684 | 698 | 774 | 896 | 980 | 1026 | 1104 | 1319 | 1433 | 79 | 71 | 40 | 4 | 71 | 2 | 1 | 79 | 40 | 79 | 79 | 79 | 4 | 4 | 4 | 4 | 1 | 1 | 2 | 40 | 4 | 4 | 2 | 4 | 71 | 2 | 1 | 2 | 79 | 1 | 40 | 2 | 79 | 2 | 1 | 2 | 1 | 1 | 4 | 40 | 2 | 4 | 71 | 1 | 71 | 71 | 71 | 2 | 71 | 2 | 40 | 1
366 | 236 | 231 | 239 | 387 | 434 | 525 | 609 | 808 | 966 | 1165 | 1387 | 1578 | 1723 | 1915 | 79 | 79 | 71 | 2 | 1 | 4 | 1 | 2 | 71 | 2 | 71 | 4 | 2 | 1 | 4 | 40 | 4 | 79 | 4 | 4 | 2 | 2 | 40 | 40 | 79 | 79 | 1 | 40 | 79 | 71 | 4 | 4 | 79 | 40 | 1 | 79 | 71 | 71 | 79 | 1 | 40 | 71 | 40 | 40 | 71 | 71 | 2 | 1 | 40 | 71 | 79 | 2
367 | 313 | 163 | 318 | 509 | 662 | 816 | 929 | 937 | 1214 | 1400 | 1484 | 1492 | 1684 | 1840 | 40 | 4 | 79 | 40 | 79 | 71 | 4 | 1 | 1 | 71 | 40 | 79 | 71 | 79 | 1 | 2 | 71 | 2 | 79 | 2 | 1 | 40 | 71 | 1 | 4 | 1 | 1 | 2 | 79 | 79 | 79 | 40 | 71 | 71 | 40 | 4 | 2 | 1 | 2 | 79 | 1 | 1 | 4 | 2 | 79 | 71 | 40 | 2 | 4 | 71 | 79 | 2
368 | 235 | 124 | 243 | 404 | 604 | 682 | 690 | 913 | 1107 | 1191 | 1385 | 1539 | 1652 | 1739 | 79 | 4 | 1 | 40 | 40 | 71 | 4 | 4 | 1 | 79 | 79 | 2 | 40 | 79 | 2 | 79 | 1 | 4 | 2 | 71 | 2 | 1 | 4 | 1 | 71 | 79 | 2 | 71 | 40 | 79 | 4 | 71 | 79 | 2 | 1 | 2 | 71 | 79 | 4 | 40 | 79 | 2 | 71 | 2 | 1 | 1 | 40 | 71 | 2 | 79 | 2 | 4
369 | 53 | 12 | 126 | 356 | 403 | 516 | 640 | 863 | 909 | 1031 | 1122 | 1208 | 1400 | 1615 | 4 | 4 | 2 | 2 | 1 | 40 | 71 | 2 | 40 | 79 | 71 | 40 | 40 | 1 | 4 | 2 | 1 | 40 | 1 | 71 | 40 | 79 | 1 | 4 | 79 | 71 | 2 | 71 | 1 | 40 | 4 | 1 | 40 | 2 | 79 | 1 | 4 | 4 | 4 | 79 | 4 | 79 | 2 | 1 | 71 | 79 | 40 | 2 | 2 | 71 | 71 | 71
370 | 310 | 152 | 313 | 394 | 406 | 554 | 642 | 833 | 956 | 1039 | 1300 | 1463 | 1547 | 1633 | 40 | 40 | 71 | 1 | 79 | 79 | 2 | 1 | 2 | 71 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 71 | 2 | 71 | 4 | 4 | 40 | 40 | 1 | 40 | 71 | 79 | 79 | 2 | 2 | 40 | 1 | 2 | 1 | 79 | 40 | 71 | 71 | 79 | 4 | 40 | 79 | 40 | 2 | 2 | 79 | 1 | 40 | 4 | 40 | 2
371 | 313 | 238 | 386 | 431 | 553 | 675 | 869 | 953 | 1183 | 1452 | 1610 | 1804 | 2034 | 2233 | 79 | 40 | 40 | 79 | 71 | 4 | 71 | 2 | 1 | 2 | 2 | 40 | 2 | 79 | 40 | 1 | 40 | 2 | 1 | 79 | 79 | 71 | 4 | 40 | 2 | 2 | 1 | 79 | 40 | 71 | 40 | 79 | 79 | 79 | 71 | 40 | 4 | 4 | 79 | 71 | 4 | 71 | 79 | 40 | 40 | 40 | 79 | 71 | 79 | 1 | 79 | 40
372 | 190 | 184 | 271 | 532 | 649 | 727 | 805 | 969 | 1207 | 1437 | 1558 | 1712 | 1867 | 1990 | 40 | 71 | 71 | 2 | 4 | 2 | 2 | 79 | 71 | 40 | 71 | 79 | 2 | 71 | 40 | 4 | 4 | 2 | 71 | 1 | 1 | 4 | 2 | 71 | 4 | 2 | 79 | 79 | 40 | 79 | 40 | 79 | 40 | 40 | 79 | 71 | 40 | 1 | 1 | 79 | 2 | 2 | 79 | 71 | 40 | 40 | 71 | 4 | 2 | 79 | 40 | 2
373 | 188 | 113 | 269 | 453 | 567 | 713 | 904 | 1096 | 1182 | 1257 | 1345 | 1394 | 1439 | 1530 | 40 | 71 | 1 | 1 | 4 | 71 | 2 | 79 | 40 | 71 | 71 | 2 | 2 | 40 | 1 | 71 | 71 | 2 | 71 | 2 | 71 | 1 | 40 | 79 | 71 | 2 | 40 | 79 | 4 | 79 | 1 | 2 | 1 | 2 | 1 | 71 | 79 | 4 | 1 | 4 | 40 | 4 | 4 | 1 | 1 | 2 | 40 | 2 | 4 | 4 | 4 | 79
374 | 118 | 74 | 199 | 476 | 626 | 779 | 786 | 969 | 1049 | 1099 | 1213 | 1295 | 1517 | 1703 | 71 | 1 | 1 | 1 | 4 | 40 | 79 | 2 | 40 | 79 | 79 | 79 | 4 | 4 | 71 | 71 | 2 | 79 | 1 | 71 | 4 | 1 | 1 | 1 | 40 | 71 | 71 | 1 | 4 | 71 | 1 | 4 | 4 | 2 | 4 | 40 | 1 | 40 | 2 | 71 | 1 | 40 | 1 | 40 | 79 | 71 | 71 | 1 | 40 | 71 | 4 | 71
375 | 155 | 83 | 274 | 360 | 522 | 602 | 729 | 816 | 1047 | 1174 | 1368 | 1451 | 1501 | 1695 | 4 | 4 | 71 | 4 | 1 | 71 | 40 | 79 | 4 | 1 | 2 | 79 | 79 | 79 | 2 | 2 | 4 | 71 | 4 | 1 | 79 | 4 | 40 | 4 | 4 | 2 | 79 | 2 | 71 | 79 | 79 | 2 | 4 | 40 | 79 | 4 | 71 | 4 | 40 | 79 | 4 | 71 | 4 | 4 | 4 | 4 | 40 | 2 | 79 | 40 | 4 | 71
376 | 133 | 127 | 216 | 292 | 416 | 497 | 611 | 700 | 899 | 1015 | 1168 | 1293 | 1449 | 1574 | 4 | 79 | 4 | 40 | 4 | 2 | 79 | 4 | 2 | 1 | 2 | 71 | 79 | 40 | 1 | 4 | 4 | 71 | 2 | 4 | 40 | 2 | 1 | 71 | 4 | 2 | 4 | 79 | 79 | 40 | 1 | 79 | 40 | 71 | 4 | 1 | 71 | 2 | 1 | 79 | 2 | 4 | 40 | 79 | 4 | 79 | 71 | 2 | 79 | 4 | 2 | 40
377 | 169 | 127 | 242 | 459 | 583 | 777 | 862 | 951 | 1112 | 1298 | 1415 | 1499 | 1507 | 1626 | 40 | 79 | 4 | 4 | 2 | 40 | 71 | 2 | 4 | 71 | 71 | 71 | 1 | 4 | 40 | 79 | 71 | 4 | 40 | 79 | 40 | 1 | 40 | 4 | 79 | 2 | 4 | 4 | 79 | 1 | 2 | 79 | 4 | 40 | 71 | 71 | 2 | 4 | 71 | 40 | 2 | 40 | 40 | 2 | 2 | 2 | 2 | 2 | 40 | 4 | 4 | 71
378 | 352 | 241 | 360 | 520 | 567 | 686 | 838 | 993 | 1107 | 1228 | 1430 | 1544 | 1730 | 1890 | 79 | 79 | 4 | 79 | 71 | 40 | 4 | 4 | 79 | 79 | 1 | 1 | 1 | 2 | 4 | 40 | 40 | 71 | 4 | 4 | 1 | 1 | 71 | 79 | 71 | 40 | 40 | 4 | 71 | 1 | 40 | 2 | 1 | 1 | 40 | 79 | 40 | 79 | 79 | 4 | 1 | 71 | 2 | 40 | 71 | 40 | 4 | 71 | 79 | 1 | 79 | 1
379 | 235 | 191 | 239 | 462 | 469 | 660 | 823 | 910 | 1026 | 1033 | 1077 | 1232 | 1385 | 1510 | 40 | 1 | 71 | 79 | 40 | 4 | 2 | 2 | 79 | 2 | 71 | 71 | 2 | 2 | 2 | 1 | 40 | 79 | 71 | 1 | 40 | 79 | 4 | 40 | 4 | 79 | 2 | 2 | 71 | 40 | 4 | 1 | 4 | 1 | 1 | 1 | 40 | 2 | 1 | 1 | 4 | 71 | 79 | 1 | 2 | 40 | 71 | 40 | 2 | 79 | 40 | 4
380 | 228 | 86 | 234 | 390 | 536 | 699 | 778 | 826 | 979 | 1204 | 1351 | 1498 | 1584 | 1629 | 4 | 2 | 40 | 40 | 71 | 71 | 2 | 4 | 79 | 71 | 2 | 4 | 71 | 2 | 71 | 2 | 4 | 40 | 40 | 79 | 71 | 2 | 4 | 2 | 40 | 2 | 2 | 4 | 71 | 2 | 40 | 40 | 71 | 71 | 4 | 79 | 71 | 71 | 4 | 1 | 71 | 1 | 4 | 71 | 2 | 40 | 4 | 40 | 40 | 2 | 2 | 1
381 | 264 | 114 | 414 | 575 | 736 | 824 | 872 | 951 | 1064 | 1217 | 1381 | 1504 | 1552 | 1702 | 71 | 40 | 1 | 2 | 71 | 79 | 71 | 79 | 1 | 2 | 79 | 79 | 40 | 2 | 79 | 40 | 79 | 4 | 4 | 1 | 4 | 40 | 2 | 2 | 2 | 71 | 2 | 4 | 71 | 1 | 1 | 40 | 1 | 2 | 79 | 71 | 2 | 79 | 79 | 4 | 40 | 2 | 2 | 79 | 2 | 40 | 4 | 2 | 4 | 71 | 71 | 4
382 | 341 | 230 | 491 | 607 | 694 | 737 | 929 | 1005 | 1151 | 1365 | 1626 | 1673 | 1756 | 1955 | 71 | 79 | 40 | 40 | 40 | 71 | 71 | 79 | 71 | 1 | 40 | 4 | 2 | 2 | 79 | 4 | 1 | 1 | 40 | 1 | 2 | 79 | 40 | 71 | 2 | 1 | 71 | 2 | 2 | 71 | 2 | 71 | 71 | 71 | 1 | 71 | 79 | 40 | 71 | 71 | 1 | 2 | 4 | 40 | 1 | 2 | 1 | 79 | 1 | 79 | 79 | 40
383 | 189 | 78 | 192 | 308 | 456 | 536 | 621 | 820 | 1006 | 1159 | 1280 | 1471 | 1670 | 1831 | 4 | 1 | 2 | 71 | 40 | 71 | 1 | 2 | 4 | 40 | 71 | 1 | 2 | 71 | 4 | 71 | 71 | 4 | 1 | 4 | 4 | 1 | 40 | 40 | 79 | 79 | 1 | 40 | 4 | 71 | 71 | 40 | 2 | 71 | 40 | 40 | 1 | 40 | 79 | 1 | 40 | 71 | 79 | 1 | 40 | 79 | 1 | 79 | 2 | 1 | 79 | 79
384 | 160 | 88 | 318 | 328 | 489 | 689 | 888 | 1043 | 1164 | 1247 | 1366 | 1415 | 1539 | 1683 | 40 | 40 | 4 | 4 | 71 | 1 | 79 | 79 | 2 | 2 | 2 | 4 | 2 | 1 | 79 | 79 | 79 | 79 | 2 | 40 | 79 | 40 | 40 | 40 | 40 | 71 | 40 | 4 | 1 | 40 | 79 | 1 | 40 | 40 | 2 | 1 | 71 | 4 | 4 | 40 | 40 | 4 | 1 | 4 | 40 | 4 | 1 | 79 | 1 | 71 | 1 | 71
385 | 264 | 184 | 336 | 499 | 613 | 827 | 1010 | 1134 | 1287 | 1373 | 1421 | 1612 | 1729 | 1846 | 40 | 71 | 71 | 2 | 40 | 40 | 71 | 1 | 4 | 1 | 79 | 79 | 1 | 71 | 2 | 40 | 71 | 71 | 71 | 1 | 71 | 40 | 1 | 71 | 1 | 40 | 4 | 79 | 40 | 40 | 2 | 71 | 40 | 2 | 40 | 4 | 2 | 4 | 40 | 2 | 40 | 71 | 1 | 79 | 40 | 71 | 2 | 4 | 4 | 40 | 2 | 71
386 | 189 | 116 | 347 | 472 | 522 | 747 | 930 | 1083 | 1204 | 1465 | 1590 | 1599 | 1752 | 1879 | 4 | 40 | 1 | 71 | 71 | 2 | 79 | 79 | 4 | 2 | 79 | 40 | 40 | 4 | 2 | 4 | 4 | 71 | 71 | 79 | 71 | 71 | 1 | 40 | 2 | 79 | 71 | 1 | 40 | 1 | 79 | 1 | 40 | 79 | 71 | 71 | 2 | 4 | 40 | 79 | 2 | 2 | 1 | 4 | 40 | 71 | 2 | 40 | 79 | 4 | 4 | 40
387 | 233 | 152 | 277 | 469 | 591 | 829 | 912 | 997 | 1160 | 1209 | 1259 | 1384 | 1539 | 1662 | 71 | 40 | 1 | 40 | 79 | 2 | 40 | 4 | 79 | 71 | 40 | 2 | 2 | 40 | 40 | 40 | 79 | 79 | 40 | 40 | 1 | 2 | 40 | 40 | 79 | 1 | 1 | 4 | 1 | 4 | 79 | 79 | 4 | 1 | 40 | 4 | 2 | 4 | 40 | 4 | 2 | 40 | 4 | 79 | 71 | 40 | 4 | 40 | 2 | 79 | 40 | 2
388 | 235 | 85 | 377 | 530 | 541 | 655 | 819 | 977 | 1101 | 1146 | 1223 | 1346 | 1431 | 1586 | 79 | 1 | 4 | 1 | 71 | 79 | 71 | 71 | 71 | 2 | 40 | 40 | 4 | 2 | 4 | 1 | 2 | 40 | 71 | 1 | 79 | 4 | 79 | 2 | 71 | 4 | 4 | 79 | 1 | 79 | 40 | 4 | 1 | 2 | 40 | 2 | 2 | 71 | 2 | 2 | 2 | 79 | 40 | 2 | 4 | 1 | 79 | 1 | 79 | 4 | 1 | 71
389 | 13 | 11 | 93 | 171 | 256 | 439 | 599 | 726 | 910 | 989 | 1078 | 1233 | 1350 | 1436 | 4 | 4 | 2 | 1 | 1 | 1 | 79 | 1 | 71 | 1 | 4 | 2 | 2 | 2 | 79 | 2 | 40 | 71 | 71 | 1 | 79 | 1 | 79 | 1 | 4 | 40 | 79 | 4 | 2 | 71 | 40 | 71 | 2 | 4 | 71 | 2 | 2 | 79 | 4 | 4 | 1 | 71 | 4 | 79 | 71 | 2 | 40 | 4 | 2 | 79 | 1 | 4
390 | 88 | 84 | 96 | 248 | 403 | 602 | 686 | 908 | 1062 | 1153 | 1196 | 1248 | 1332 | 1448 | 40 | 40 | 2 | 2 | 2 | 2 | 4 | 4 | 71 | 1 | 1 | 79 | 1 | 79 | 71 | 4 | 79 | 40 | 79 | 1 | 2 | 1 | 79 | 2 | 79 | 1 | 71 | 71 | 2 | 2 | 79 | 71 | 4 | 4 | 4 | 79 | 1 | 40 | 1 | 1 | 4 | 4 | 40 | 4 | 40 | 40 | 2 | 2 | 40 | 1 | 71 | 4
391 | 197 | 191 | 316 | 546 | 671 | 825 | 980 | 1055 | 1140 | 1264 | 1447 | 1603 | 1682 | 1797 | 79 | 40 | 71 | 1 | 2 | 4 | 79 | 40 | 1 | 79 | 71 | 79 | 79 | 2 | 4 | 40 | 71 | 79 | 2 | 2 | 1 | 71 | 4 | 79 | 1 | 1 | 71 | 2 | 1 | 40 | 4 | 40 | 4 | 40 | 79 | 1 | 71 | 1 | 71 | 40 | 71 | 79 | 4 | 2 | 2 | 4 | 71 | 2 | 71 | 2 | 40 | 2
392 | 133 | 125 | 206 | 397 | 524 | 739 | 749 | 904 | 1052 | 1062 | 1264 | 1314 | 1438 | 1596 | 2 | 4 | 40 | 79 | 4 | 4 | 71 | 2 | 1 | 71 | 79 | 40 | 40 | 4 | 4 | 79 | 71 | 2 | 71 | 71 | 2 | 2 | 4 | 2 | 79 | 4 | 1 | 71 | 71 | 4 | 2 | 71 | 1 | 4 | 4 | 1 | 79 | 40 | 4 | 79 | 40 | 2 | 4 | 4 | 40 | 40 | 40 | 4 | 79 | 4 | 4 | 71
393 | 375 | 292 | 486 | 493 | 659 | 819 | 933 | 1047 | 1162 | 1400 | 1594 | 1718 | 1796 | 1960 | 71 | 71 | 79 | 71 | 79 | 4 | 40 | 71 | 2 | 2 | 1 | 2 | 79 | 4 | 79 | 4 | 40 | 1 | 40 | 79 | 40 | 71 | 1 | 2 | 2 | 71 | 1 | 40 | 2 | 40 | 71 | 2 | 40 | 79 | 79 | 40 | 4 | 79 | 40 | 71 | 79 | 40 | 1 | 4 | 1 | 71 | 4 | 2 | 79 | 2 | 79 | 4
394 | 199 | 124 | 205 | 359 | 436 | 557 | 603 | 764 | 919 | 1035 | 1121 | 1315 | 1473 | 1520 | 4 | 1 | 40 | 79 | 4 | 71 | 4 | 2 | 2 | 2 | 71 | 79 | 1 | 71 | 1 | 4 | 79 | 40 | 1 | 1 | 2 | 2 | 2 | 40 | 79 | 79 | 2 | 1 | 71 | 40 | 4 | 40 | 40 | 71 | 1 | 4 | 4 | 2 | 79 | 1 | 4 | 71 | 40 | 79 | 4 | 79 | 71 | 4 | 1 | 4 | 40 | 2
395 | 200 | 156 | 206 | 369 | 453 | 617 | 733 | 849 | 1012 | 1166 | 1216 | 1382 | 1509 | 1700 | 79 | 4 | 2 | 71 | 40 | 4 | 2 | 4 | 40 | 79 | 40 | 4 | 79 | 2 | 1 | 2 | 2 | 79 | 4 | 79 | 40 | 71 | 1 | 4 | 40 | 71 | 4 | 1 | 79 | 4 | 1 | 79 | 2 | 2 | 79 | 71 | 4 | 2 | 4 | 40 | 4 | 4 | 79 | 79 | 79 | 4 | 40 | 4 | 1 | 40 | 79 | 71
396 | 51 | 47 | 123 | 286 | 298 | 419 | 507 | 699 | 854 | 1085 | 1164 | 1213 | 1297 | 1453 | 1 | 4 | 2 | 40 | 2 | 2 | 1 | 71 | 79 | 79 | 1 | 4 | 2 | 4 | 4 | 2 | 1 | 40 | 40 | 40 | 40 | 4 | 40 | 4 | 71 | 2 | 40 | 79 | 4 | 79 | 1 | 71 | 79 | 2 | 79 | 71 | 4 | 2 | 2 | 71 | 4 | 1 | 40 | 4 | 2 | 79 | 1 | 2 | 4 | 79 | 2 | 71
397 | 224 | 74 | 297 | 558 | 680 | 757 | 948 | 1108 | 1193 | 1270 | 1500 | 1646 | 1907 | 2106 | 1 | 71 | 1 | 1 | 71 | 79 | 71 | 2 | 79 | 71 | 71 | 40 | 40 | 2 | 40 | 40 | 71 | 2 | 2 | 2 | 79 | 40 | 71 | 1 | 40 | 40 | 79 | 1 | 79 | 1 | 4 | 1 | 1 | 71 | 1 | 4 | 1 | 79 | 71 | 79 | 71 | 71 | 2 | 2 | 71 | 79 | 40 | 71 | 79 | 79 | 40 | 1
398 | 52 | 47 | 202 | 284 | 439 | 561 | 650 | 730 | 929 | 1090 | 1315 | 1437 | 1562 | 1573 | 4 | 2 | 1 | 40 | 1 | 4 | 71 | 79 | 1 | 40 | 40 | 1 | 1 | 79 | 4 | 71 | 79 | 1 | 40 | 2 | 4 | 2 | 79 | 4 | 71 | 4 | 1 | 4 | 40 | 40 | 40 | 79 | 79 | 2 | 40 | 40 | 71 | 4 | 79 | 71 | 79 | 40 | 2 | 1 | 2 | 79 | 4 | 40 | 4 | 2 | 1 | 4
399 | 200 | 156 | 208 | 353 | 441 | 666 | 711 | 905 | 982 | 1138 | 1184 | 1298 | 1458 | 1462 | 79 | 4 | 2 | 71 | 4 | 40 | 4 | 4 | 71 | 1 | 71 | 2 | 79 | 4 | 1 | 4 | 4 | 71 | 79 | 71 | 40 | 1 | 2 | 2 | 71 | 40 | 4 | 79 | 71 | 2 | 2 | 2 | 4 | 79 | 71 | 2 | 1 | 40 | 4 | 1 | 71 | 1 | 40 | 2 | 40 | 79 | 1 | 40 | 1 | 1 | 1 | 1
400 | 205 | 161 | 288 | 480 | 741 | 827 | 948 | 1034 | 1189 | 1381 | 1529 | 1644 | 1689 | 1873 | 40 | 79 | 40 | 2 | 4 | 40 | 79 | 4 | 40 | 2 | 79 | 71 | 40 | 79 | 71 | 71 | 40 | 4 | 40 | 2 | 40 | 40 | 40 | 1 | 2 | 4 | 40 | 40 | 71 | 40 | 40 | 4 | 79 | 40 | 2 | 71 | 2 | 4 | 71 | 71 | 71 | 2 | 40 | 2 | 40 | 1 | 2 | 2 | 40 | 2 | 71 | 71
401 | 119 | 78 | 160 | 313 | 363 | 555 | 710 | 864 | 1012 | 1166 | 1435 | 1634 | 1848 | 2050 | 4 | 2 | 71 | 1 | 40 | 1 | 1 | 40 | 79 | 1 | 71 | 2 | 4 | 2 | 4 | 40 | 71 | 40 | 2 | 79 | 40 | 40 | 71 | 4 | 2 | 79 | 2 | 71 | 2 | 71 | 71 | 4 | 79 | 2 | 71 | 2 | 79 | 71 | 40 | 79 | 40 | 1 | 79 | 79 | 71 | 71 | 1 | 71 | 79 | 40 | 79 | 4
402 | 344 | 194 | 349 | 543 | 701 | 750 | 873 | 956 | 1083 | 1230 | 1421 | 1496 | 1659 | 1746 | 40 | 79 | 4 | 71 | 71 | 79 | 1 | 4 | 71 | 4 | 79 | 40 | 4 | 71 | 4 | 79 | 1 | 40 | 4 | 4 | 2 | 2 | 79 | 40 | 2 | 40 | 1 | 40 | 79 | 4 | 40 | 4 | 71 | 71 | 1 | 4 | 79 | 40 | 1 | 71 | 71 | 1 | 1 | 2 | 1 | 79 | 79 | 4 | 4 | 2 | 79 | 2
403 | 344 | 194 | 349 | 472 | 588 | 743 | 821 | 904 | 1049 | 1233 | 1471 | 1518 | 1671 | 1746 | 71 | 79 | 4 | 40 | 79 | 71 | 4 | 1 | 2 | 2 | 79 | 40 | 1 | 71 | 4 | 40 | 79 | 4 | 1 | 71 | 2 | 4 | 1 | 71 | 2 | 1 | 40 | 40 | 1 | 71 | 2 | 71 | 2 | 71 | 40 | 71 | 40 | 79 | 40 | 79 | 4 | 1 | 2 | 40 | 71 | 40 | 40 | 2 | 1 | 71 | 1 | 2
404 | 287 | 214 | 360 | 371 | 418 | 464 | 655 | 857 | 1049 | 1095 | 1325 | 1471 | 1665 | 1778 | 1 | 71 | 71 | 71 | 2 | 71 | 2 | 71 | 2 | 4 | 4 | 1 | 1 | 2 | 40 | 4 | 2 | 2 | 2 | 40 | 79 | 40 | 1 | 71 | 79 | 79 | 40 | 4 | 71 | 79 | 40 | 2 | 40 | 4 | 1 | 1 | 40 | 40 | 79 | 71 | 71 | 71 | 2 | 2 | 40 | 79 | 4 | 71 | 1 | 71 | 40 | 1
405 | 202 | 161 | 282 | 292 | 380 | 469 | 555 | 643 | 935 | 1126 | 1271 | 1318 | 1549 | 1748 | 40 | 40 | 79 | 2 | 40 | 1 | 40 | 40 | 2 | 2 | 4 | 2 | 4 | 1 | 4 | 79 | 4 | 4 | 2 | 79 | 79 | 1 | 2 | 4 | 4 | 1 | 79 | 4 | 71 | 71 | 71 | 79 | 40 | 1 | 71 | 79 | 1 | 71 | 71 | 2 | 4 | 2 | 1 | 40 | 79 | 71 | 2 | 79 | 1 | 79 | 40 | 79
406 | 155 | 114 | 230 | 276 | 392 | 468 | 668 | 752 | 967 | 1055 | 1208 | 1332 | 1416 | 1600 | 40 | 1 | 71 | 2 | 1 | 40 | 71 | 4 | 4 | 1 | 40 | 1 | 71 | 40 | 4 | 1 | 71 | 1 | 2 | 2 | 79 | 40 | 2 | 79 | 2 | 40 | 40 | 2 | 2 | 71 | 71 | 71 | 79 | 4 | 4 | 1 | 2 | 79 | 1 | 71 | 1 | 40 | 4 | 79 | 2 | 40 | 2 | 40 | 2 | 71 | 71 | 40
407 | 13 | 8 | 86 | 203 | 214 | 299 | 384 | 500 | 663 | 739 | 980 | 1063 | 1143 | 1298 | 4 | 2 | 1 | 1 | 4 | 1 | 2 | 71 | 40 | 2 | 4 | 71 | 2 | 4 | 4 | 1 | 4 | 1 | 40 | 40 | 40 | 4 | 1 | 40 | 1 | 71 | 4 | 40 | 4 | 1 | 79 | 79 | 2 | 2 | 1 | 71 | 79 | 79 | 4 | 79 | 40 | 2 | 40 | 1 | 71 | 1 | 4 | 4 | 40 | 40 | 71 | 4
408 | 13 | 10 | 55 | 142 | 194 | 396 | 595 | 711 | 799 | 1091 | 1243 | 1399 | 1549 | 1634 | 4 | 1 | 4 | 1 | 2 | 1 | 2 | 40 | 2 | 2 | 4 | 79 | 40 | 4 | 4 | 4 | 4 | 40 | 79 | 79 | 79 | 1 | 79 | 40 | 4 | 40 | 71 | 1 | 1 | 4 | 4 | 79 | 71 | 71 | 79 | 71 | 1 | 79 | 1 | 71 | 2 | 79 | 71 | 4 | 4 | 4 | 71 | 71 | 79 | 2 | 2 | 2
409 | 194 | 122 | 313 | 504 | 698 | 775 | 930 | 1054 | 1245 | 1475 | 1602 | 1679 | 1757 | 1873 | 2 | 79 | 40 | 1 | 1 | 71 | 79 | 40 | 71 | 1 | 40 | 79 | 4 | 71 | 40 | 79 | 71 | 1 | 4 | 1 | 79 | 1 | 4 | 71 | 79 | 40 | 1 | 4 | 40 | 1 | 79 | 71 | 71 | 79 | 1 | 79 | 4 | 40 | 4 | 79 | 71 | 1 | 4 | 1 | 1 | 2 | 4 | 71 | 71 | 40 | 4 | 1
410 | 158 | 114 | 233 | 399 | 559 | 713 | 799 | 921 | 1113 | 1158 | 1313 | 1432 | 1556 | 1681 | 71 | 2 | 1 | 40 | 40 | 4 | 71 | 4 | 4 | 4 | 79 | 79 | 1 | 79 | 79 | 1 | 71 | 2 | 79 | 2 | 40 | 4 | 2 | 40 | 79 | 1 | 40 | 2 | 40 | 79 | 71 | 2 | 2 | 40 | 2 | 1 | 4 | 79 | 1 | 71 | 71 | 4 | 40 | 4 | 79 | 40 | 1 | 4 | 2 | 40 | 79 | 4
411 | 132 | 88 | 274 | 504 | 665 | 859 | 1004 | 1198 | 1320 | 1503 | 1512 | 1664 | 1780 | 1933 | 4 | 79 | 1 | 4 | 4 | 40 | 71 | 71 | 79 | 1 | 71 | 79 | 2 | 79 | 40 | 40 | 40 | 71 | 79 | 4 | 1 | 71 | 71 | 2 | 79 | 4 | 40 | 71 | 1 | 79 | 2 | 40 | 71 | 40 | 71 | 1 | 4 | 1 | 2 | 2 | 71 | 40 | 1 | 40 | 71 | 4 | 40 | 1 | 40 | 40 | 2 | 71
412 | 167 | 125 | 169 | 247 | 293 | 415 | 684 | 829 | 989 | 1172 | 1216 | 1261 | 1269 | 1281 | 4 | 79 | 40 | 2 | 40 | 2 | 1 | 1 | 71 | 1 | 2 | 4 | 4 | 40 | 1 | 1 | 79 | 2 | 40 | 1 | 71 | 79 | 79 | 40 | 2 | 71 | 1 | 71 | 1 | 1 | 79 | 79 | 1 | 40 | 71 | 71 | 1 | 1 | 2 | 40 | 1 | 2 | 40 | 2 | 2 | 2 | 2 | 2 | 4 | 2 | 2 | 4
413 | 125 | 84 | 129 | 213 | 376 | 465 | 590 | 743 | 867 | 948 | 1029 | 1108 | 1118 | 1128 | 1 | 79 | 2 | 2 | 1 | 40 | 2 | 2 | 2 | 40 | 2 | 40 | 79 | 40 | 40 | 4 | 2 | 79 | 4 | 4 | 4 | 40 | 79 | 2 | 40 | 40 | 2 | 71 | 40 | 79 | 4 | 1 | 4 | 4 | 2 | 71 | 71 | 4 | 2 | 4 | 2 | 2 | 4 | 71 | 4 | 4 | 1 | 1 | 2 | 4 | 2 | 2
414 | 344 | 194 | 416 | 538 | 729 | 810 | 1009 | 1093 | 1100 | 1188 | 1403 | 1528 | 1644 | 1690 | 4 | 71 | 40 | 79 | 79 | 71 | 1 | 71 | 1 | 79 | 40 | 2 | 71 | 79 | 40 | 1 | 4 | 2 | 71 | 4 | 79 | 1 | 79 | 40 | 2 | 79 | 2 | 1 | 1 | 2 | 2 | 2 | 4 | 1 | 79 | 4 | 2 | 71 | 71 | 71 | 79 | 2 | 4 | 40 | 1 | 71 | 40 | 4 | 40 | 4 | 1 | 1
415 | 232 | 152 | 276 | 392 | 547 | 694 | 808 | 960 | 1077 | 1156 | 1237 | 1323 | 1334 | 1455 | 1 | 40 | 40 | 71 | 40 | 40 | 4 | 40 | 71 | 4 | 1 | 40 | 40 | 4 | 71 | 40 | 71 | 1 | 71 | 4 | 2 | 40 | 71 | 1 | 79 | 71 | 1 | 1 | 4 | 40 | 2 | 71 | 2 | 71 | 2 | 4 | 4 | 2 | 71 | 4 | 1 | 2 | 79 | 4 | 1 | 2 | 4 | 4 | 79 | 1 | 1 | 40
416 | 16 | 8 | 166 | 253 | 331 | 485 | 777 | 857 | 903 | 990 | 1145 | 1153 | 1308 | 1546 | 1 | 2 | 4 | 1 | 4 | 4 | 71 | 79 | 4 | 2 | 2 | 79 | 1 | 4 | 71 | 2 | 2 | 79 | 2 | 71 | 71 | 71 | 79 | 71 | 1 | 4 | 4 | 71 | 1 | 40 | 1 | 4 | 2 | 79 | 4 | 2 | 79 | 71 | 4 | 1 | 1 | 4 | 2 | 1 | 4 | 71 | 79 | 1 | 79 | 40 | 79 | 40
417 | 157 | 77 | 160 | 166 | 215 | 515 | 628 | 680 | 725 | 811 | 995 | 1082 | 1274 | 1356 | 71 | 1 | 1 | 4 | 1 | 79 | 1 | 2 | 1 | 2 | 1 | 2 | 4 | 1 | 40 | 4 | 79 | 79 | 71 | 71 | 71 | 40 | 1 | 1 | 4 | 4 | 4 | 40 | 2 | 40 | 2 | 1 | 4 | 2 | 40 | 40 | 2 | 40 | 71 | 71 | 2 | 4 | 79 | 2 | 2 | 71 | 40 | 79 | 40 | 1 | 1 | 40
418 | 202 | 122 | 208 | 368 | 522 | 641 | 874 | 1035 | 1343 | 1387 | 1543 | 1586 | 1746 | 1932 | 79 | 1 | 40 | 2 | 40 | 40 | 4 | 2 | 79 | 1 | 1 | 79 | 2 | 2 | 71 | 79 | 40 | 4 | 4 | 71 | 79 | 71 | 4 | 79 | 2 | 79 | 1 | 79 | 79 | 79 | 79 | 71 | 1 | 2 | 40 | 1 | 4 | 79 | 71 | 2 | 1 | 1 | 40 | 1 | 79 | 1 | 40 | 40 | 4 | 40 | 71 | 71
419 | 128 | 86 | 200 | 278 | 361 | 439 | 554 | 748 | 756 | 769 | 935 | 1098 | 1219 | 1413 | 2 | 1 | 79 | 4 | 40 | 2 | 1 | 71 | 2 | 71 | 4 | 1 | 1 | 2 | 40 | 40 | 2 | 1 | 71 | 4 | 2 | 71 | 2 | 40 | 71 | 4 | 79 | 40 | 1 | 1 | 2 | 4 | 4 | 4 | 1 | 4 | 79 | 4 | 79 | 4 | 40 | 40 | 4 | 79 | 1 | 40 | 1 | 79 | 4 | 40 | 71 | 79
420 | 16 | 11 | 22 | 105 | 335 | 488 | 644 | 689 | 736 | 889 | 970 | 1084 | 1169 | 1258 | 4 | 1 | 4 | 2 | 1 | 4 | 4 | 2 | 2 | 1 | 40 | 40 | 71 | 40 | 40 | 79 | 79 | 71 | 1 | 2 | 71 | 4 | 79 | 2 | 2 | 1 | 2 | 40 | 2 | 4 | 40 | 1 | 2 | 71 | 40 | 40 | 4 | 4 | 71 | 2 | 2 | 40 | 71 | 1 | 40 | 40 | 1 | 4 | 2 | 4 | 4 | 79
421 | 159 | 86 | 200 | 285 | 440 | 639 | 719 | 874 | 987 | 1108 | 1338 | 1383 | 1528 | 1675 | 2 | 1 | 4 | 79 | 71 | 2 | 40 | 1 | 4 | 79 | 1 | 1 | 71 | 1 | 79 | 4 | 79 | 40 | 1 | 79 | 4 | 4 | 71 | 1 | 79 | 1 | 4 | 71 | 1 | 40 | 71 | 1 | 40 | 79 | 1 | 1 | 79 | 1 | 71 | 79 | 2 | 1 | 40 | 2 | 71 | 2 | 71 | 1 | 4 | 71 | 71 | 1
422 | 130 | 124 | 210 | 363 | 601 | 682 | 693 | 887 | 1071 | 1162 | 1174 | 1226 | 1374 | 1526 | 4 | 79 | 1 | 40 | 4 | 2 | 1 | 79 | 79 | 71 | 2 | 1 | 40 | 79 | 79 | 40 | 4 | 2 | 71 | 4 | 4 | 2 | 1 | 4 | 79 | 4 | 71 | 40 | 71 | 71 | 40 | 2 | 4 | 4 | 4 | 79 | 4 | 2 | 4 | 2 | 4 | 4 | 4 | 40 | 2 | 71 | 71 | 4 | 71 | 40 | 40 | 1
423 | 342 | 184 | 484 | 645 | 690 | 850 | 933 | 1019 | 1107 | 1332 | 1495 | 1643 | 1729 | 1998 | 71 | 71 | 40 | 2 | 79 | 79 | 71 | 71 | 79 | 2 | 79 | 1 | 2 | 40 | 1 | 2 | 1 | 79 | 1 | 79 | 79 | 1 | 1 | 2 | 1 | 4 | 2 | 79 | 79 | 4 | 1 | 4 | 4 | 71 | 79 | 71 | 1 | 79 | 79 | 4 | 2 | 71 | 71 | 4 | 2 | 1 | 79 | 4 | 79 | 79 | 71 | 40
424 | 53 | 9 | 211 | 334 | 422 | 616 | 730 | 1014 | 1169 | 1255 | 1380 | 1426 | 1504 | 1590 | 4 | 2 | 2 | 1 | 4 | 40 | 79 | 79 | 2 | 79 | 40 | 2 | 40 | 40 | 4 | 4 | 71 | 4 | 40 | 79 | 40 | 2 | 71 | 1 | 71 | 71 | 71 | 71 | 1 | 4 | 71 | 79 | 40 | 4 | 40 | 2 | 2 | 4 | 79 | 40 | 1 | 1 | 4 | 40 | 71 | 2 | 1 | 4 | 2 | 4 | 79 | 1
425 | 217 | 145 | 225 | 232 | 278 | 444 | 530 | 616 | 701 | 962 | 1154 | 1315 | 1470 | 1516 | 1 | 71 | 2 | 71 | 71 | 1 | 4 | 4 | 2 | 2 | 1 | 2 | 1 | 1 | 4 | 40 | 79 | 4 | 79 | 4 | 4 | 2 | 1 | 79 | 4 | 79 | 2 | 1 | 40 | 40 | 1 | 4 | 71 | 79 | 40 | 71 | 79 | 40 | 71 | 2 | 79 | 79 | 2 | 1 | 79 | 4 | 71 | 1 | 1 | 40 | 4 | 1
426 | 204 | 160 | 277 | 287 | 434 | 664 | 886 | 966 | 1114 | 1163 | 1241 | 1317 | 1475 | 1588 | 1 | 1 | 79 | 79 | 4 | 40 | 2 | 71 | 4 | 1 | 1 | 4 | 1 | 4 | 71 | 71 | 40 | 79 | 40 | 71 | 71 | 79 | 1 | 71 | 4 | 1 | 71 | 4 | 71 | 4 | 71 | 2 | 4 | 4 | 40 | 1 | 71 | 4 | 2 | 1 | 71 | 1 | 2 | 2 | 4 | 71 | 4 | 79 | 1 | 71 | 1 | 40
427 | 85 | 79 | 165 | 434 | 590 | 742 | 786 | 1008 | 1095 | 1141 | 1371 | 1554 | 1704 | 1859 | 71 | 2 | 4 | 2 | 2 | 4 | 1 | 79 | 79 | 40 | 71 | 79 | 79 | 71 | 2 | 4 | 79 | 1 | 1 | 71 | 2 | 40 | 1 | 1 | 71 | 71 | 1 | 79 | 79 | 4 | 2 | 2 | 1 | 40 | 4 | 1 | 79 | 40 | 40 | 71 | 71 | 71 | 40 | 1 | 4 | 71 | 4 | 71 | 79 | 1 | 4 | 71
428 | 200 | 119 | 203 | 361 | 480 | 605 | 681 | 942 | 1105 | 1289 | 1519 | 1635 | 1904 | 2029 | 4 | 4 | 40 | 71 | 2 | 79 | 1 | 2 | 79 | 4 | 71 | 4 | 4 | 4 | 71 | 40 | 2 | 40 | 79 | 4 | 2 | 2 | 71 | 1 | 71 | 40 | 71 | 79 | 40 | 40 | 4 | 79 | 40 | 71 | 2 | 71 | 1 | 71 | 79 | 79 | 1 | 4 | 71 | 40 | 71 | 40 | 79 | 79 | 40 | 79 | 4 | 2
429 | 161 | 88 | 272 | 394 | 594 | 718 | 768 | 852 | 861 | 939 | 1178 | 1223 | 1386 | 1578 | 79 | 4 | 4 | 1 | 71 | 2 | 40 | 71 | 40 | 40 | 2 | 40 | 79 | 40 | 2 | 79 | 1 | 79 | 4 | 40 | 40 | 4 | 2 | 4 | 2 | 79 | 2 | 1 | 4 | 1 | 2 | 2 | 2 | 1 | 4 | 71 | 79 | 79 | 79 | 2 | 40 | 1 | 2 | 2 | 40 | 4 | 79 | 40 | 2 | 40 | 71 | 79
430 | 124 | 82 | 274 | 396 | 559 | 650 | 888 | 1012 | 1168 | 1321 | 1412 | 1564 | 1841 | 1994 | 1 | 40 | 40 | 1 | 2 | 40 | 79 | 71 | 2 | 79 | 40 | 1 | 4 | 1 | 79 | 79 | 4 | 4 | 79 | 4 | 1 | 79 | 79 | 79 | 40 | 4 | 40 | 40 | 79 | 71 | 2 | 4 | 71 | 79 | 1 | 2 | 4 | 79 | 4 | 4 | 1 | 79 | 1 | 71 | 79 | 40 | 79 | 79 | 2 | 1 | 79 | 71
431 | 197 | 86 | 269 | 469 | 660 | 785 | 901 | 912 | 1025 | 1175 | 1299 | 1493 | 1651 | 1729 | 2 | 4 | 40 | 40 | 40 | 71 | 1 | 71 | 79 | 79 | 2 | 40 | 71 | 40 | 1 | 79 | 79 | 2 | 4 | 40 | 4 | 71 | 40 | 1 | 2 | 4 | 4 | 1 | 71 | 40 | 1 | 1 | 71 | 4 | 71 | 4 | 4 | 79 | 40 | 1 | 71 | 79 | 40 | 4 | 71 | 4 | 79 | 4 | 71 | 2 | 1 | 4
432 | 122 | 47 | 126 | 242 | 328 | 445 | 631 | 752 | 841 | 955 | 1078 | 1261 | 1306 | 1454 | 40 | 1 | 4 | 2 | 4 | 71 | 2 | 2 | 4 | 71 | 1 | 40 | 1 | 79 | 2 | 4 | 4 | 71 | 40 | 2 | 40 | 4 | 71 | 71 | 40 | 40 | 1 | 40 | 2 | 79 | 4 | 4 | 71 | 1 | 40 | 2 | 2 | 2 | 40 | 79 | 71 | 71 | 1 | 40 | 2 | 2 | 1 | 40 | 2 | 71 | 71 | 4
433 | 277 | 194 | 358 | 480 | 485 | 643 | 731 | 852 | 934 | 1134 | 1213 | 1443 | 1568 | 1647 | 40 | 71 | 4 | 79 | 79 | 4 | 2 | 79 | 2 | 40 | 40 | 40 | 1 | 1 | 2 | 1 | 79 | 4 | 4 | 71 | 4 | 1 | 4 | 79 | 40 | 1 | 40 | 40 | 40 | 1 | 1 | 40 | 2 | 79 | 79 | 40 | 4 | 2 | 2 | 71 | 71 | 79 | 79 | 1 | 2 | 40 | 4 | 79 | 71 | 2 | 2 | 4
434 | 236 | 163 | 319 | 482 | 629 | 714 | 797 | 919 | 1005 | 1199 | 1246 | 1430 | 1544 | 1666 | 40 | 40 | 79 | 4 | 71 | 2 | 4 | 79 | 40 | 4 | 79 | 40 | 1 | 71 | 4 | 71 | 1 | 1 | 4 | 79 | 40 | 40 | 2 | 1 | 40 | 1 | 79 | 2 | 2 | 79 | 1 | 4 | 40 | 4 | 79 | 71 | 40 | 1 | 2 | 4 | 71 | 40 | 71 | 2 | 71 | 1 | 40 | 2 | 40 | 2 | 40 | 40
435 | 256 | 114 | 258 | 460 | 546 | 632 | 870 | 913 | 995 | 1041 | 1130 | 1204 | 1323 | 1467 | 40 | 1 | 71 | 2 | 71 | 71 | 1 | 1 | 40 | 79 | 4 | 79 | 1 | 79 | 2 | 4 | 4 | 79 | 1 | 2 | 40 | 40 | 79 | 79 | 1 | 1 | 40 | 1 | 1 | 40 | 1 | 40 | 2 | 2 | 40 | 2 | 79 | 4 | 2 | 4 | 1 | 1 | 1 | 71 | 71 | 40 | 4 | 4 | 71 | 71 | 1 | 1
436 | 280 | 161 | 399 | 598 | 836 | 960 | 970 | 1051 | 1061 | 1143 | 1151 | 1198 | 1398 | 1589 | 79 | 40 | 40 | 2 | 40 | 79 | 79 | 40 | 1 | 40 | 79 | 79 | 79 | 79 | 40 | 40 | 40 | 79 | 1 | 4 | 4 | 4 | 1 | 1 | 2 | 71 | 4 | 4 | 4 | 4 | 1 | 1 | 1 | 1 | 79 | 1 | 2 | 4 | 1 | 1 | 4 | 40 | 2 | 1 | 79 | 2 | 40 | 79 | 79 | 1 | 40 | 71
437 | 158 | 85 | 308 | 531 | 613 | 765 | 811 | 1111 | 1294 | 1407 | 1495 | 1541 | 1705 | 1850 | 2 | 2 | 2 | 79 | 2 | 71 | 79 | 71 | 71 | 79 | 2 | 71 | 40 | 1 | 1 | 40 | 71 | 40 | 1 | 40 | 2 | 2 | 2 | 40 | 79 | 79 | 71 | 71 | 40 | 71 | 71 | 1 | 1 | 40 | 1 | 71 | 4 | 4 | 40 | 40 | 1 | 4 | 40 | 1 | 79 | 4 | 2 | 79 | 2 | 1 | 71 | 71
438 | 157 | 85 | 198 | 490 | 692 | 813 | 857 | 1012 | 1131 | 1181 | 1230 | 1386 | 1390 | 1574 | 1 | 79 | 4 | 1 | 1 | 71 | 40 | 1 | 79 | 71 | 71 | 71 | 79 | 4 | 79 | 40 | 79 | 1 | 40 | 1 | 40 | 1 | 2 | 1 | 1 | 79 | 71 | 4 | 4 | 71 | 4 | 40 | 4 | 2 | 4 | 40 | 40 | 4 | 4 | 1 | 79 | 2 | 4 | 71 | 1 | 1 | 1 | 1 | 71 | 2 | 71 | 40
439 | 227 | 85 | 338 | 529 | 539 | 702 | 866 | 1016 | 1179 | 1229 | 1462 | 1547 | 1697 | 1744 | 4 | 1 | 1 | 79 | 71 | 71 | 40 | 71 | 79 | 1 | 40 | 71 | 1 | 4 | 1 | 4 | 40 | 4 | 40 | 79 | 2 | 79 | 79 | 4 | 4 | 4 | 71 | 71 | 79 | 1 | 79 | 4 | 2 | 4 | 4 | 40 | 4 | 79 | 71 | 79 | 1 | 40 | 40 | 4 | 4 | 4 | 71 | 71 | 40 | 1 | 4 | 2
440 | 236 | 86 | 319 | 549 | 673 | 754 | 899 | 1051 | 1099 | 1285 | 1371 | 1498 | 1576 | 1698 | 40 | 4 | 2 | 40 | 71 | 79 | 79 | 4 | 79 | 71 | 40 | 40 | 79 | 4 | 40 | 1 | 2 | 4 | 4 | 71 | 71 | 71 | 1 | 2 | 1 | 71 | 1 | 79 | 2 | 40 | 4 | 2 | 40 | 71 | 4 | 71 | 2 | 40 | 40 | 4 | 4 | 40 | 4 | 79 | 4 | 71 | 2 | 1 | 1 | 40 | 2 | 79
441 | 232 | 191 | 237 | 285 | 430 | 622 | 786 | 949 | 1148 | 1233 | 1358 | 1583 | 1749 | 1826 | 71 | 79 | 1 | 40 | 1 | 40 | 4 | 1 | 2 | 40 | 2 | 4 | 71 | 1 | 2 | 71 | 2 | 71 | 79 | 40 | 2 | 79 | 4 | 79 | 40 | 79 | 40 | 4 | 79 | 40 | 79 | 1 | 1 | 4 | 40 | 40 | 40 | 79 | 4 | 2 | 71 | 4 | 71 | 79 | 4 | 4 | 79 | 79 | 1 | 4 | 1 | 71
442 | 156 | 114 | 236 | 402 | 635 | 711 | 833 | 958 | 1150 | 1306 | 1317 | 1539 | 1624 | 1709 | 71 | 2 | 1 | 40 | 2 | 40 | 1 | 79 | 4 | 79 | 4 | 79 | 4 | 79 | 79 | 71 | 1 | 2 | 71 | 2 | 2 | 40 | 40 | 40 | 2 | 79 | 40 | 4 | 79 | 40 | 71 | 2 | 4 | 71 | 2 | 79 | 2 | 4 | 4 | 1 | 79 | 71 | 71 | 1 | 1 | 4 | 40 | 40 | 1 | 40 | 40 | 4
443 | 130 | 50 | 213 | 367 | 449 | 495 | 503 | 630 | 708 | 949 | 1068 | 1079 | 1164 | 1250 | 2 | 4 | 4 | 40 | 79 | 1 | 79 | 4 | 2 | 79 | 2 | 71 | 1 | 1 | 79 | 1 | 1 | 4 | 40 | 1 | 4 | 1 | 1 | 2 | 4 | 40 | 79 | 4 | 1 | 2 | 4 | 71 | 79 | 79 | 4 | 79 | 4 | 71 | 4 | 40 | 1 | 2 | 4 | 4 | 79 | 2 | 2 | 2 | 1 | 4 | 2 | 79
444 | 155 | 114 | 266 | 350 | 505 | 627 | 740 | 856 | 1050 | 1280 | 1358 | 1441 | 1672 | 1680 | 2 | 71 | 40 | 1 | 1 | 40 | 71 | 40 | 2 | 2 | 40 | 40 | 40 | 40 | 4 | 71 | 79 | 1 | 40 | 2 | 1 | 40 | 1 | 71 | 71 | 4 | 1 | 40 | 71 | 4 | 79 | 40 | 79 | 71 | 79 | 1 | 1 | 71 | 2 | 4 | 40 | 2 | 40 | 1 | 79 | 2 | 71 | 79 | 1 | 1 | 4 | 2
445 | 195 | 153 | 276 | 460 | 690 | 734 | 856 | 864 | 1030 | 1105 | 1152 | 1413 | 1501 | 1693 | 2 | 71 | 79 | 1 | 2 | 40 | 2 | 79 | 2 | 71 | 40 | 71 | 40 | 79 | 40 | 71 | 1 | 1 | 40 | 2 | 79 | 40 | 2 | 1 | 4 | 2 | 1 | 1 | 4 | 79 | 4 | 79 | 2 | 1 | 71 | 1 | 40 | 2 | 4 | 1 | 71 | 79 | 40 | 71 | 1 | 4 | 4 | 79 | 40 | 71 | 79 | 2
446 | 120 | 47 | 192 | 407 | 528 | 642 | 766 | 920 | 996 | 1187 | 1303 | 1381 | 1573 | 1689 | 1 | 4 | 2 | 40 | 71 | 2 | 1 | 71 | 71 | 71 | 2 | 71 | 1 | 40 | 79 | 1 | 2 | 1 | 40 | 71 | 79 | 4 | 40 | 1 | 2 | 79 | 2 | 71 | 2 | 71 | 1 | 2 | 79 | 71 | 1 | 40 | 40 | 71 | 1 | 4 | 4 | 1 | 2 | 71 | 79 | 71 | 2 | 40 | 1 | 4 | 40 | 71
447 | 160 | 88 | 165 | 250 | 403 | 450 | 611 | 834 | 1018 | 1171 | 1373 | 1450 | 1680 | 1882 | 79 | 4 | 4 | 1 | 71 | 1 | 1 | 4 | 1 | 4 | 1 | 79 | 1 | 71 | 2 | 79 | 1 | 4 | 40 | 2 | 79 | 2 | 40 | 40 | 79 | 2 | 71 | 71 | 71 | 71 | 40 | 2 | 40 | 71 | 2 | 40 | 40 | 79 | 79 | 4 | 1 | 1 | 4 | 71 | 79 | 79 | 1 | 71 | 79 | 40 | 79 | 4
448 | 297 | 222 | 370 | 416 | 464 | 619 | 805 | 1030 | 1157 | 1319 | 1408 | 1608 | 1807 | 1926 | 40 | 40 | 71 | 71 | 71 | 4 | 71 | 2 | 1 | 1 | 40 | 4 | 40 | 2 | 2 | 4 | 4 | 1 | 71 | 79 | 71 | 40 | 71 | 4 | 4 | 79 | 71 | 71 | 40 | 4 | 79 | 4 | 2 | 2 | 79 | 79 | 2 | 4 | 4 | 79 | 2 | 79 | 79 | 40 | 1 | 79 | 40 | 79 | 71 | 4 | 40 | 4
449 | 200 | 192 | 208 | 257 | 384 | 433 | 552 | 707 | 823 | 903 | 1136 | 1149 | 1340 | 1415 | 2 | 71 | 79 | 40 | 4 | 4 | 4 | 4 | 4 | 40 | 4 | 1 | 4 | 4 | 79 | 40 | 4 | 4 | 40 | 1 | 71 | 4 | 4 | 40 | 71 | 1 | 4 | 79 | 4 | 40 | 71 | 1 | 71 | 1 | 4 | 4 | 4 | 71 | 79 | 79 | 4 | 4 | 4 | 1 | 71 | 79 | 40 | 1 | 1 | 1 | 71 | 2
450 | 169 | 127 | 280 | 440 | 709 | 795 | 997 | 1002 | 1081 | 1169 | 1221 | 1235 | 1243 | 1320 | 40 | 4 | 4 | 79 | 2 | 40 | 71 | 40 | 79 | 40 | 1 | 40 | 40 | 79 | 71 | 79 | 79 | 1 | 4 | 2 | 79 | 79 | 40 | 4 | 1 | 1 | 2 | 1 | 4 | 2 | 71 | 2 | 1 | 79 | 4 | 4 | 40 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 1 | 4 | 2 | 1 | 1 | 71 | 4 | 1
451 | 233 | 122 | 383 | 468 | 553 | 602 | 618 | 773 | 850 | 1041 | 1045 | 1193 | 1279 | 1357 | 40 | 1 | 2 | 79 | 71 | 40 | 71 | 79 | 4 | 1 | 1 | 79 | 2 | 2 | 2 | 79 | 4 | 40 | 1 | 4 | 4 | 4 | 4 | 4 | 79 | 1 | 71 | 4 | 2 | 2 | 71 | 2 | 40 | 40 | 71 | 40 | 1 | 1 | 1 | 1 | 71 | 71 | 4 | 2 | 79 | 4 | 2 | 1 | 4 | 2 | 1 | 71
452 | 311 | 238 | 391 | 551 | 557 | 684 | 769 | 891 | 976 | 1175 | 1262 | 1386 | 1570 | 1654 | 79 | 40 | 40 | 79 | 71 | 2 | 79 | 1 | 1 | 40 | 40 | 79 | 1 | 2 | 2 | 1 | 4 | 40 | 4 | 79 | 40 | 1 | 4 | 40 | 40 | 40 | 40 | 2 | 1 | 1 | 79 | 4 | 40 | 40 | 40 | 79 | 4 | 79 | 2 | 2 | 79 | 1 | 4 | 40 | 40 | 71 | 2 | 71 | 2 | 40 | 2 | 40
453 | 207 | 163 | 288 | 376 | 529 | 760 | 837 | 914 | 1000 | 1009 | 1165 | 1251 | 1512 | 1706 | 79 | 40 | 40 | 4 | 4 | 40 | 2 | 79 | 79 | 4 | 4 | 1 | 71 | 79 | 2 | 1 | 79 | 71 | 2 | 79 | 1 | 4 | 71 | 1 | 71 | 1 | 4 | 1 | 2 | 79 | 1 | 4 | 2 | 4 | 1 | 2 | 79 | 2 | 71 | 4 | 1 | 2 | 79 | 4 | 71 | 40 | 71 | 79 | 71 | 79 | 40 | 4
454 | 225 | 114 | 267 | 342 | 506 | 591 | 666 | 818 | 904 | 990 | 1215 | 1296 | 1458 | 1575 | 1 | 71 | 2 | 40 | 71 | 40 | 40 | 2 | 1 | 2 | 71 | 1 | 79 | 2 | 4 | 79 | 4 | 79 | 1 | 1 | 2 | 1 | 1 | 71 | 40 | 71 | 1 | 40 | 4 | 40 | 2 | 40 | 2 | 1 | 79 | 4 | 4 | 71 | 71 | 79 | 2 | 4 | 4 | 71 | 79 | 2 | 79 | 2 | 71 | 2 | 40 | 4
455 | 295 | 153 | 301 | 570 | 731 | 886 | 972 | 1055 | 1064 | 1188 | 1427 | 1551 | 1812 | 1897 | 71 | 79 | 1 | 2 | 71 | 71 | 4 | 2 | 79 | 79 | 40 | 71 | 79 | 1 | 79 | 2 | 71 | 79 | 1 | 4 | 1 | 2 | 79 | 4 | 2 | 1 | 79 | 1 | 4 | 2 | 1 | 2 | 79 | 1 | 4 | 40 | 2 | 79 | 79 | 79 | 1 | 40 | 79 | 4 | 71 | 40 | 79 | 71 | 40 | 4 | 1 | 40
456 | 274 | 155 | 316 | 392 | 607 | 762 | 839 | 1070 | 1264 | 1342 | 1428 | 1620 | 1626 | 1706 | 79 | 71 | 4 | 1 | 79 | 40 | 40 | 2 | 2 | 71 | 2 | 1 | 2 | 71 | 71 | 71 | 1 | 79 | 4 | 71 | 1 | 71 | 4 | 1 | 2 | 79 | 71 | 79 | 79 | 71 | 40 | 4 | 4 | 2 | 71 | 1 | 79 | 1 | 2 | 4 | 2 | 71 | 40 | 79 | 1 | 2 | 2 | 1 | 1 | 71 | 4 | 4
457 | 161 | 155 | 165 | 248 | 465 | 474 | 627 | 888 | 964 | 1050 | 1099 | 1178 | 1263 | 1385 | 4 | 1 | 71 | 79 | 2 | 4 | 2 | 2 | 1 | 40 | 2 | 40 | 71 | 71 | 4 | 71 | 4 | 1 | 2 | 2 | 71 | 1 | 2 | 79 | 71 | 40 | 79 | 71 | 2 | 1 | 2 | 71 | 79 | 1 | 2 | 4 | 1 | 4 | 40 | 4 | 71 | 4 | 2 | 2 | 40 | 40 | 4 | 1 | 40 | 1 | 2 | 79
458 | 205 | 86 | 278 | 431 | 584 | 709 | 822 | 830 | 986 | 1200 | 1347 | 1423 | 1581 | 1705 | 2 | 4 | 1 | 79 | 40 | 79 | 2 | 71 | 71 | 1 | 79 | 2 | 40 | 71 | 40 | 2 | 40 | 79 | 2 | 4 | 40 | 71 | 1 | 1 | 1 | 1 | 4 | 2 | 79 | 4 | 2 | 71 | 71 | 71 | 71 | 1 | 71 | 4 | 71 | 1 | 1 | 71 | 2 | 2 | 79 | 4 | 71 | 4 | 40 | 4 | 79 | 1
459 | 121 | 10 | 240 | 442 | 634 | 818 | 970 | 1133 | 1221 | 1338 | 1429 | 1587 | 1743 | 1901 | 2 | 2 | 4 | 2 | 40 | 71 | 79 | 40 | 4 | 79 | 79 | 40 | 71 | 79 | 40 | 2 | 40 | 71 | 2 | 71 | 1 | 71 | 79 | 1 | 4 | 79 | 79 | 1 | 4 | 79 | 1 | 4 | 2 | 4 | 40 | 71 | 79 | 4 | 4 | 4 | 79 | 4 | 4 | 71 | 4 | 71 | 2 | 79 | 4 | 79 | 71 | 4
460 | 285 | 241 | 360 | 514 | 605 | 727 | 806 | 1075 | 1230 | 1422 | 1546 | 1554 | 1670 | 1794 | 79 | 79 | 4 | 79 | 40 | 4 | 4 | 71 | 2 | 71 | 2 | 79 | 4 | 79 | 4 | 4 | 79 | 40 | 1 | 2 | 4 | 71 | 2 | 2 | 79 | 40 | 71 | 79 | 4 | 1 | 71 | 79 | 79 | 2 | 71 | 40 | 79 | 40 | 4 | 1 | 4 | 2 | 1 | 1 | 40 | 4 | 71 | 1 | 79 | 40 | 4 | 1
461 | 225 | 222 | 267 | 422 | 502 | 582 | 874 | 1022 | 1031 | 1155 | 1302 | 1426 | 1473 | 1597 | 1 | 71 | 79 | 71 | 2 | 1 | 40 | 2 | 4 | 40 | 71 | 40 | 4 | 1 | 71 | 4 | 1 | 4 | 71 | 4 | 71 | 71 | 71 | 79 | 4 | 2 | 71 | 71 | 2 | 1 | 4 | 2 | 79 | 1 | 4 | 40 | 71 | 4 | 71 | 1 | 40 | 79 | 4 | 1 | 2 | 4 | 40 | 1 | 40 | 1 | 4 | 79
462 | 88 | 47 | 207 | 290 | 376 | 492 | 606 | 766 | 950 | 1103 | 1255 | 1493 | 1570 | 1831 | 1 | 2 | 40 | 4 | 40 | 1 | 40 | 79 | 2 | 1 | 79 | 1 | 4 | 1 | 2 | 79 | 71 | 4 | 40 | 1 | 71 | 1 | 40 | 2 | 40 | 79 | 1 | 40 | 71 | 2 | 71 | 40 | 2 | 79 | 71 | 1 | 1 | 79 | 1 | 71 | 79 | 79 | 79 | 1 | 1 | 4 | 71 | 1 | 40 | 71 | 79 | 71
463 | 164 | 161 | 237 | 282 | 290 | 301 | 425 | 733 | 925 | 1047 | 1264 | 1310 | 1433 | 1518 | 79 | 2 | 1 | 79 | 2 | 1 | 2 | 71 | 2 | 40 | 2 | 1 | 4 | 1 | 2 | 1 | 4 | 1 | 4 | 2 | 40 | 4 | 79 | 1 | 79 | 79 | 79 | 71 | 71 | 40 | 79 | 2 | 79 | 40 | 1 | 2 | 71 | 4 | 71 | 71 | 1 | 4 | 1 | 40 | 79 | 40 | 2 | 2 | 4 | 1 | 1 | 79
464 | 156 | 153 | 159 | 169 | 324 | 448 | 492 | 614 | 764 | 886 | 1155 | 1274 | 1324 | 1402 | 79 | 71 | 1 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 2 | 4 | 79 | 1 | 71 | 4 | 40 | 4 | 79 | 1 | 1 | 1 | 2 | 40 | 1 | 40 | 79 | 2 | 71 | 4 | 71 | 4 | 2 | 40 | 40 | 40 | 71 | 79 | 40 | 79 | 71 | 4 | 4 | 40 | 4 | 40 | 2 | 4 | 1 | 2 | 71 | 4
465 | 199 | 116 | 202 | 479 | 626 | 635 | 754 | 985 | 1148 | 1304 | 1418 | 1503 | 1620 | 1706 | 1 | 40 | 71 | 4 | 79 | 4 | 2 | 1 | 79 | 40 | 79 | 79 | 4 | 1 | 71 | 71 | 1 | 2 | 2 | 4 | 71 | 4 | 40 | 4 | 71 | 2 | 79 | 79 | 79 | 40 | 40 | 4 | 2 | 4 | 71 | 79 | 71 | 2 | 1 | 40 | 40 | 1 | 40 | 4 | 71 | 2 | 4 | 40 | 1 | 79 | 2 | 4
466 | 197 | 191 | 272 | 436 | 591 | 674 | 791 | 803 | 848 | 993 | 1073 | 1295 | 1303 | 1455 | 71 | 79 | 1 | 40 | 4 | 2 | 4 | 71 | 4 | 79 | 79 | 2 | 40 | 40 | 4 | 71 | 2 | 1 | 1 | 79 | 2 | 4 | 40 | 71 | 4 | 2 | 2 | 4 | 2 | 1 | 2 | 40 | 2 | 71 | 71 | 1 | 4 | 1 | 71 | 4 | 71 | 1 | 79 | 71 | 4 | 2 | 1 | 1 | 71 | 1 | 79 | 1
467 | 194 | 83 | 199 | 460 | 660 | 751 | 830 | 917 | 1001 | 1047 | 1091 | 1252 | 1335 | 1558 | 2 | 79 | 1 | 1 | 40 | 71 | 4 | 1 | 71 | 71 | 79 | 40 | 40 | 79 | 2 | 79 | 79 | 4 | 4 | 4 | 71 | 2 | 2 | 4 | 2 | 2 | 79 | 4 | 2 | 40 | 2 | 40 | 40 | 1 | 1 | 4 | 1 | 40 | 1 | 2 | 40 | 2 | 40 | 79 | 79 | 1 | 1 | 2 | 71 | 79 | 2 | 71
468 | 123 | 43 | 126 | 284 | 507 | 590 | 773 | 987 | 1209 | 1478 | 1677 | 1868 | 1982 | 2060 | 1 | 1 | 1 | 40 | 1 | 79 | 1 | 2 | 4 | 71 | 79 | 4 | 71 | 2 | 79 | 71 | 1 | 79 | 1 | 2 | 40 | 1 | 71 | 71 | 71 | 71 | 1 | 71 | 71 | 79 | 71 | 1 | 79 | 40 | 71 | 79 | 40 | 40 | 40 | 79 | 71 | 40 | 40 | 40 | 2 | 71 | 40 | 1 | 1 | 71 | 4 | 2
469 | 162 | 156 | 312 | 358 | 480 | 601 | 685 | 801 | 879 | 929 | 1082 | 1230 | 1378 | 1491 | 71 | 79 | 2 | 4 | 4 | 2 | 79 | 71 | 40 | 1 | 1 | 4 | 2 | 40 | 1 | 79 | 1 | 40 | 40 | 40 | 2 | 2 | 40 | 40 | 1 | 4 | 40 | 71 | 2 | 71 | 1 | 4 | 4 | 40 | 2 | 4 | 71 | 1 | 79 | 2 | 4 | 71 | 2 | 71 | 2 | 4 | 71 | 71 | 71 | 40 | 1 | 1
470 | 150 | 144 | 158 | 313 | 428 | 592 | 745 | 947 | 1072 | 1119 | 1194 | 1321 | 1445 | 1609 | 1 | 71 | 1 | 71 | 2 | 4 | 4 | 4 | 71 | 4 | 79 | 1 | 2 | 71 | 40 | 2 | 4 | 79 | 2 | 79 | 1 | 2 | 71 | 79 | 79 | 40 | 4 | 79 | 4 | 79 | 40 | 2 | 4 | 1 | 2 | 40 | 71 | 1 | 1 | 2 | 4 | 4 | 79 | 40 | 40 | 4 | 40 | 40 | 79 | 79 | 2 | 4
471 | 83 | 78 | 124 | 308 | 433 | 577 | 701 | 887 | 937 | 1022 | 1252 | 1297 | 1341 | 1594 | 1 | 4 | 71 | 2 | 1 | 4 | 40 | 1 | 71 | 2 | 40 | 71 | 40 | 4 | 2 | 79 | 1 | 1 | 71 | 71 | 79 | 1 | 4 | 40 | 40 | 71 | 4 | 71 | 40 | 4 | 4 | 2 | 1 | 1 | 79 | 4 | 79 | 79 | 1 | 71 | 1 | 40 | 2 | 2 | 1 | 40 | 2 | 1 | 71 | 71 | 40 | 71
472 | 243 | 160 | 324 | 438 | 593 | 712 | 981 | 1220 | 1306 | 1469 | 1668 | 1744 | 1868 | 2023 | 40 | 40 | 79 | 1 | 79 | 4 | 2 | 79 | 2 | 1 | 71 | 40 | 1 | 4 | 79 | 71 | 40 | 4 | 4 | 71 | 79 | 79 | 40 | 71 | 2 | 79 | 79 | 79 | 40 | 4 | 40 | 2 | 1 | 4 | 79 | 79 | 40 | 40 | 40 | 79 | 2 | 71 | 1 | 2 | 1 | 4 | 79 | 40 | 1 | 71 | 79 | 4
473 | 275 | 231 | 279 | 434 | 588 | 788 | 796 | 959 | 1106 | 1230 | 1316 | 1476 | 1552 | 1668 | 79 | 79 | 71 | 2 | 4 | 40 | 2 | 2 | 1 | 4 | 71 | 79 | 79 | 71 | 2 | 2 | 40 | 79 | 79 | 2 | 2 | 1 | 4 | 1 | 79 | 40 | 4 | 40 | 1 | 71 | 71 | 4 | 79 | 40 | 1 | 4 | 4 | 2 | 40 | 40 | 40 | 40 | 1 | 79 | 2 | 2 | 71 | 1 | 4 | 71 | 40 | 1
474 | 147 | 75 | 152 | 273 | 459 | 698 | 845 | 858 | 982 | 1220 | 1374 | 1459 | 1606 | 1789 | 2 | 1 | 71 | 1 | 1 | 71 | 1 | 4 | 1 | 40 | 40 | 40 | 71 | 4 | 71 | 40 | 2 | 79 | 79 | 79 | 71 | 1 | 4 | 71 | 4 | 4 | 1 | 4 | 40 | 40 | 40 | 4 | 40 | 79 | 79 | 40 | 2 | 79 | 71 | 2 | 4 | 1 | 79 | 1 | 4 | 1 | 71 | 71 | 71 | 40 | 1 | 71
475 | 381 | 308 | 454 | 579 | 740 | 856 | 970 | 1161 | 1245 | 1439 | 1519 | 1674 | 1788 | 1949 | 79 | 79 | 71 | 79 | 2 | 71 | 2 | 71 | 2 | 79 | 4 | 40 | 79 | 79 | 1 | 2 | 4 | 71 | 40 | 1 | 71 | 40 | 2 | 1 | 40 | 71 | 1 | 79 | 1 | 2 | 79 | 2 | 40 | 79 | 4 | 71 | 71 | 4 | 1 | 4 | 4 | 71 | 40 | 40 | 71 | 1 | 40 | 2 | 1 | 79 | 2 | 79
476 | 133 | 14 | 275 | 459 | 645 | 845 | 1075 | 1160 | 1236 | 1420 | 1606 | 1800 | 2030 | 2147 | 4 | 4 | 2 | 4 | 40 | 79 | 71 | 71 | 71 | 2 | 40 | 71 | 4 | 71 | 40 | 71 | 79 | 79 | 2 | 40 | 79 | 1 | 71 | 79 | 2 | 79 | 2 | 2 | 2 | 1 | 71 | 2 | 2 | 71 | 40 | 71 | 40 | 4 | 71 | 71 | 40 | 71 | 79 | 4 | 79 | 71 | 79 | 1 | 4 | 71 | 2 | 40
477 | 127 | 122 | 132 | 288 | 403 | 491 | 652 | 774 | 820 | 975 | 1023 | 1101 | 1254 | 1477 | 1 | 2 | 79 | 40 | 4 | 1 | 4 | 1 | 79 | 71 | 4 | 2 | 40 | 2 | 2 | 71 | 1 | 4 | 79 | 4 | 40 | 2 | 40 | 79 | 2 | 40 | 40 | 40 | 1 | 40 | 1 | 4 | 40 | 40 | 71 | 4 | 40 | 4 | 2 | 2 | 2 | 1 | 4 | 71 | 71 | 79 | 2 | 1 | 71 | 71 | 79 | 2
478 | 203 | 122 | 208 | 289 | 410 | 495 | 581 | 625 | 704 | 820 | 1120 | 1389 | 1464 | 1650 | 40 | 1 | 2 | 79 | 79 | 2 | 1 | 4 | 71 | 2 | 4 | 4 | 40 | 1 | 1 | 79 | 2 | 2 | 2 | 79 | 2 | 1 | 4 | 79 | 1 | 2 | 40 | 1 | 4 | 2 | 71 | 2 | 1 | 4 | 71 | 40 | 79 | 71 | 71 | 79 | 71 | 79 | 40 | 79 | 71 | 1 | 2 | 1 | 71 | 4 | 40 | 71
479 | 205 | 125 | 363 | 547 | 624 | 740 | 856 | 972 | 1158 | 1350 | 1505 | 1667 | 1717 | 1801 | 2 | 40 | 4 | 79 | 1 | 79 | 79 | 79 | 71 | 40 | 2 | 71 | 1 | 1 | 4 | 71 | 4 | 71 | 40 | 1 | 4 | 1 | 71 | 40 | 71 | 1 | 40 | 4 | 4 | 40 | 71 | 71 | 79 | 71 | 40 | 2 | 1 | 4 | 71 | 79 | 2 | 2 | 79 | 79 | 2 | 40 | 4 | 4 | 2 | 1 | 2 | 79
480 | 133 | 127 | 206 | 323 | 409 | 561 | 650 | 805 | 1027 | 1154 | 1239 | 1323 | 1332 | 1480 | 40 | 79 | 4 | 4 | 4 | 2 | 2 | 71 | 40 | 71 | 2 | 4 | 40 | 4 | 2 | 40 | 1 | 40 | 71 | 40 | 4 | 79 | 4 | 2 | 79 | 71 | 1 | 4 | 71 | 79 | 1 | 71 | 4 | 79 | 40 | 4 | 4 | 1 | 40 | 40 | 2 | 79 | 2 | 1 | 1 | 2 | 4 | 2 | 4 | 71 | 71 | 2
481 | 272 | 122 | 347 | 503 | 744 | 985 | 1110 | 1155 | 1318 | 1470 | 1595 | 1833 | 2074 | 2227 | 1 | 2 | 40 | 79 | 79 | 71 | 71 | 4 | 79 | 2 | 4 | 71 | 79 | 79 | 4 | 79 | 79 | 79 | 79 | 4 | 2 | 4 | 40 | 79 | 2 | 1 | 2 | 40 | 79 | 1 | 79 | 4 | 1 | 71 | 1 | 79 | 40 | 4 | 79 | 2 | 40 | 79 | 40 | 79 | 79 | 4 | 79 | 79 | 40 | 71 | 40 | 2
482 | 272 | 153 | 353 | 470 | 547 | 699 | 862 | 1054 | 1176 | 1300 | 1309 | 1390 | 1612 | 1688 | 1 | 2 | 71 | 79 | 79 | 40 | 2 | 79 | 40 | 2 | 71 | 4 | 71 | 4 | 1 | 1 | 71 | 79 | 1 | 1 | 4 | 1 | 79 | 79 | 40 | 2 | 79 | 71 | 2 | 40 | 1 | 79 | 79 | 4 | 1 | 40 | 2 | 4 | 2 | 1 | 2 | 71 | 4 | 4 | 79 | 71 | 71 | 1 | 2 | 71 | 1 | 2
483 | 54 | 12 | 95 | 286 | 480 | 679 | 865 | 942 | 1056 | 1064 | 1114 | 1128 | 1211 | 1293 | 4 | 2 | 4 | 2 | 2 | 40 | 1 | 40 | 71 | 40 | 79 | 1 | 40 | 71 | 79 | 4 | 79 | 40 | 1 | 79 | 40 | 71 | 4 | 71 | 1 | 4 | 1 | 71 | 71 | 1 | 2 | 40 | 2 | 1 | 1 | 4 | 2 | 40 | 4 | 4 | 4 | 4 | 2 | 4 | 2 | 40 | 40 | 1 | 1 | 79 | 1 | 1
484 | 341 | 269 | 413 | 607 | 691 | 849 | 894 | 1047 | 1164 | 1243 | 1401 | 1631 | 1753 | 1978 | 40 | 71 | 79 | 79 | 1 | 71 | 71 | 1 | 71 | 79 | 40 | 4 | 40 | 2 | 40 | 2 | 71 | 4 | 4 | 79 | 1 | 2 | 40 | 2 | 1 | 71 | 2 | 79 | 40 | 4 | 2 | 71 | 4 | 2 | 2 | 71 | 4 | 79 | 4 | 71 | 79 | 40 | 71 | 40 | 40 | 2 | 40 | 40 | 71 | 71 | 4 | 79
485 | 50 | 48 | 130 | 283 | 367 | 515 | 715 | 956 | 1187 | 1381 | 1542 | 1625 | 1781 | 1828 | 2 | 4 | 40 | 2 | 1 | 1 | 1 | 79 | 1 | 71 | 2 | 79 | 40 | 40 | 2 | 2 | 71 | 4 | 71 | 2 | 40 | 79 | 2 | 79 | 4 | 79 | 79 | 79 | 2 | 79 | 71 | 79 | 4 | 79 | 71 | 40 | 2 | 40 | 40 | 79 | 2 | 1 | 79 | 1 | 2 | 79 | 4 | 71 | 2 | 40 | 4 | 1
486 | 89 | 86 | 208 | 332 | 343 | 493 | 637 | 800 | 923 | 1044 | 1352 | 1476 | 1565 | 1645 | 4 | 79 | 1 | 2 | 2 | 1 | 79 | 40 | 1 | 40 | 4 | 79 | 2 | 4 | 1 | 4 | 4 | 71 | 71 | 4 | 71 | 71 | 1 | 1 | 40 | 40 | 4 | 79 | 2 | 2 | 40 | 79 | 40 | 40 | 1 | 40 | 71 | 79 | 79 | 79 | 4 | 40 | 1 | 79 | 4 | 2 | 79 | 4 | 4 | 71 | 1 | 4
487 | 58 | 50 | 63 | 255 | 493 | 649 | 835 | 999 | 1075 | 1087 | 1208 | 1400 | 1485 | 1715 | 2 | 4 | 4 | 40 | 4 | 4 | 4 | 1 | 40 | 71 | 79 | 2 | 40 | 79 | 79 | 40 | 2 | 79 | 4 | 71 | 4 | 40 | 71 | 71 | 79 | 4 | 2 | 79 | 2 | 71 | 2 | 1 | 2 | 4 | 4 | 2 | 1 | 40 | 1 | 79 | 40 | 2 | 79 | 71 | 79 | 4 | 1 | 1 | 71 | 79 | 79 | 1
488 | 94 | 11 | 135 | 291 | 477 | 632 | 678 | 870 | 1025 | 1141 | 1254 | 1268 | 1277 | 1494 | 2 | 4 | 4 | 1 | 4 | 79 | 1 | 40 | 4 | 2 | 79 | 71 | 40 | 4 | 71 | 71 | 4 | 79 | 1 | 71 | 4 | 1 | 40 | 1 | 79 | 71 | 40 | 2 | 4 | 1 | 79 | 71 | 40 | 1 | 4 | 71 | 40 | 71 | 1 | 1 | 2 | 4 | 4 | 4 | 2 | 4 | 2 | 1 | 4 | 71 | 71 | 71
489 | 171 | 88 | 176 | 186 | 342 | 495 | 542 | 625 | 808 | 1008 | 1018 | 1173 | 1333 | 1483 | 4 | 79 | 1 | 4 | 4 | 79 | 1 | 4 | 2 | 2 | 2 | 4 | 79 | 2 | 71 | 4 | 2 | 79 | 71 | 1 | 4 | 1 | 40 | 2 | 40 | 1 | 2 | 40 | 1 | 71 | 40 | 71 | 2 | 79 | 40 | 79 | 2 | 4 | 2 | 2 | 40 | 40 | 4 | 71 | 79 | 1 | 1 | 79 | 71 | 71 | 4 | 4
490 | 190 | 146 | 196 | 352 | 514 | 666 | 789 | 903 | 987 | 1264 | 1383 | 1467 | 1546 | 1706 | 2 | 2 | 71 | 71 | 40 | 4 | 2 | 4 | 79 | 2 | 4 | 71 | 2 | 2 | 79 | 79 | 71 | 40 | 1 | 40 | 79 | 2 | 40 | 2 | 1 | 2 | 40 | 71 | 2 | 40 | 2 | 40 | 79 | 79 | 40 | 79 | 40 | 4 | 4 | 71 | 1 | 2 | 79 | 2 | 4 | 2 | 71 | 2 | 40 | 1 | 79 | 40
491 | 297 | 186 | 380 | 502 | 666 | 888 | 965 | 1040 | 1262 | 1539 | 1692 | 1805 | 1883 | 1930 | 71 | 4 | 71 | 40 | 71 | 40 | 4 | 79 | 79 | 2 | 40 | 1 | 2 | 4 | 79 | 79 | 71 | 71 | 1 | 79 | 2 | 2 | 2 | 71 | 71 | 1 | 2 | 1 | 71 | 71 | 79 | 1 | 79 | 79 | 40 | 79 | 2 | 1 | 71 | 79 | 1 | 1 | 40 | 71 | 1 | 4 | 2 | 71 | 1 | 4 | 40 | 2
492 | 294 | 222 | 336 | 528 | 650 | 777 | 862 | 1054 | 1140 | 1293 | 1459 | 1505 | 1689 | 1763 | 71 | 40 | 40 | 71 | 1 | 71 | 2 | 40 | 79 | 2 | 40 | 71 | 1 | 40 | 79 | 2 | 79 | 4 | 40 | 4 | 40 | 40 | 1 | 4 | 40 | 2 | 79 | 71 | 4 | 40 | 2 | 40 | 2 | 40 | 40 | 71 | 4 | 79 | 4 | 79 | 4 | 40 | 1 | 1 | 2 | 71 | 40 | 71 | 1 | 71 | 1 | 1
493 | 122 | 49 | 195 | 395 | 550 | 597 | 642 | 766 | 891 | 1082 | 1087 | 1161 | 1285 | 1366 | 4 | 40 | 4 | 1 | 2 | 71 | 71 | 2 | 79 | 2 | 40 | 79 | 1 | 4 | 79 | 71 | 2 | 40 | 4 | 1 | 40 | 2 | 2 | 1 | 1 | 40 | 4 | 79 | 40 | 2 | 79 | 4 | 40 | 1 | 79 | 71 | 2 | 1 | 1 | 1 | 1 | 71 | 1 | 1 | 1 | 4 | 79 | 40 | 2 | 4 | 71 | 4
494 | 197 | 194 | 203 | 386 | 500 | 623 | 823 | 1053 | 1353 | 1398 | 1559 | 1712 | 1868 | 1951 | 4 | 71 | 40 | 79 | 2 | 1 | 2 | 4 | 71 | 1 | 71 | 40 | 1 | 71 | 40 | 2 | 79 | 2 | 40 | 2 | 79 | 40 | 2 | 79 | 79 | 79 | 71 | 1 | 71 | 79 | 79 | 71 | 1 | 2 | 2 | 40 | 40 | 2 | 79 | 40 | 1 | 71 | 79 | 2 | 4 | 71 | 79 | 2 | 2 | 1 | 1 | 79
495 | 159 | 86 | 201 | 509 | 631 | 715 | 831 | 955 | 1033 | 1191 | 1316 | 1392 | 1625 | 1840 | 2 | 1 | 4 | 79 | 71 | 2 | 40 | 2 | 79 | 79 | 79 | 71 | 1 | 79 | 40 | 2 | 40 | 2 | 40 | 2 | 1 | 4 | 40 | 71 | 1 | 40 | 79 | 4 | 71 | 1 | 4 | 2 | 79 | 71 | 4 | 4 | 2 | 79 | 40 | 4 | 71 | 2 | 1 | 2 | 79 | 79 | 4 | 71 | 71 | 71 | 71 | 2
496 | 116 | 75 | 160 | 245 | 476 | 595 | 642 | 720 | 731 | 954 | 1068 | 1192 | 1199 | 1313 | 1 | 1 | 71 | 2 | 1 | 40 | 4 | 40 | 4 | 79 | 1 | 1 | 79 | 2 | 79 | 71 | 40 | 4 | 71 | 4 | 40 | 2 | 4 | 1 | 1 | 4 | 71 | 2 | 2 | 4 | 1 | 4 | 2 | 79 | 71 | 71 | 2 | 71 | 40 | 1 | 79 | 4 | 1 | 40 | 1 | 1 | 4 | 1 | 40 | 71 | 1 | 2
497 | 313 | 163 | 316 | 437 | 525 | 748 | 871 | 954 | 1081 | 1244 | 1368 | 1521 | 1723 | 1848 | 79 | 4 | 40 | 40 | 79 | 71 | 2 | 1 | 40 | 1 | 79 | 1 | 1 | 79 | 4 | 4 | 71 | 79 | 71 | 2 | 2 | 79 | 2 | 40 | 1 | 2 | 1 | 79 | 40 | 79 | 4 | 4 | 79 | 40 | 40 | 4 | 79 | 4 | 1 | 40 | 71 | 40 | 2 | 40 | 4 | 79 | 40 | 79 | 2 | 4 | 79 | 40
498 | 263 | 191 | 307 | 314 | 475 | 661 | 852 | 1091 | 1244 | 1467 | 1546 | 1595 | 1787 | 1867 | 79 | 71 | 1 | 40 | 71 | 1 | 40 | 4 | 2 | 1 | 2 | 2 | 2 | 1 | 79 | 79 | 71 | 40 | 4 | 71 | 79 | 71 | 1 | 40 | 2 | 79 | 79 | 79 | 40 | 71 | 2 | 40 | 2 | 79 | 71 | 71 | 2 | 71 | 4 | 2 | 1 | 4 | 4 | 40 | 2 | 71 | 79 | 40 | 4 | 1 | 4 | 71
499 | 127 | 122 | 130 | 213 | 294 | 308 | 468 | 544 | 852 | 1085 | 1315 | 1473 | 1628 | 1780 | 40 | 79 | 2 | 1 | 4 | 1 | 2 | 1 | 1 | 2 | 40 | 40 | 2 | 71 | 4 | 4 | 4 | 2 | 4 | 4 | 40 | 40 | 1 | 79 | 2 | 71 | 1 | 2 | 79 | 71 | 79 | 79 | 4 | 79 | 71 | 79 | 79 | 40 | 40 | 71 | 4 | 71 | 79 | 4 | 1 | 4 | 71 | 79 | 40 | 71 | 40 | 1
500 | 89 | 86 | 208 | 258 | 450 | 673 | 859 | 1074 | 1188 | 1348 | 1542 | 1842 | 2002 | 2051 | 2 | 40 | 4 | 40 | 1 | 2 | 79 | 40 | 40 | 4 | 2 | 4 | 71 | 2 | 40 | 79 | 2 | 79 | 71 | 71 | 71 | 4 | 71 | 40 | 71 | 71 | 71 | 2 | 1 | 40 | 2 | 71 | 40 | 40 | 1 | 79 | 4 | 40 | 79 | 71 | 71 | 79 | 71 | 79 | 40 | 40 | 79 | 1 | 40 | 4 | 4 | 1
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 14.98 | Sum4: 8; Sum8: 57.98; Sum12: 133.95; Sum16: 219.97; Sum20: 311.96; Sum24: 425.99; Sum28: 544; Sum32: 635.92; Sum36: 766.86; Sum40: 898.74; Sum44: 993.48; Sum48: 1108.91; Sum52: 1239.83
2% | 49.98 | Sum4: 9; Sum8: 87.96; Sum12: 165.56; Sum16: 264.94; Sum20: 379.98; Sum24: 475.84; Sum28: 581.92; Sum32: 694; Sum36: 812.96; Sum40: 965.92; Sum44: 1063; Sum48: 1163.98; Sum52: 1280.7
3% | 51 | Sum4: 10.97; Sum8: 93.97; Sum12: 181.76; Sum16: 292.97; Sum20: 406.94; Sum24: 503; Sum28: 622.79; Sum32: 709.94; Sum36: 829.82; Sum40: 978; Sum44: 1083.94; Sum48: 1190.91; Sum52: 1301.97
4% | 53 | Sum4: 11; Sum8: 98.96; Sum12: 207.8; Sum16: 298; Sum20: 415; Sum24: 529.76; Sum28: 629.92; Sum32: 729.88; Sum36: 857.96; Sum40: 993.88; Sum44: 1102.92; Sum48: 1211; Sum52: 1319.72
5% | 55.95 | Sum4: 12; Sum8: 124.95; Sum12: 212.9; Sum16: 321.85; Sum20: 430; Sum24: 538.9; Sum28: 652.9; Sum32: 740.95; Sum36: 871.45; Sum40: 1000.85; Sum44: 1111.8; Sum48: 1223.95; Sum52: 1347.6
6% | 82 | Sum4: 41.38; Sum8: 126; Sum12: 220.7; Sum16: 333.82; Sum20: 439; Sum24: 554; Sum28: 660.94; Sum32: 770.58; Sum36: 888.82; Sum40: 1012; Sum44: 1121.94; Sum48: 1249; Sum52: 1353.88
7% | 83 | Sum4: 44.93; Sum8: 129; Sum12: 240.51; Sum16: 339; Sum20: 448.93; Sum24: 561.65; Sum28: 672.93; Sum32: 790.72; Sum36: 903.93; Sum40: 1022; Sum44: 1127.72; Sum48: 1262.51; Sum52: 1365.58
8% | 84 | Sum4: 46; Sum8: 130; Sum12: 245.92; Sum16: 357.92; Sum20: 452; Sum24: 574.68; Sum28: 687.68; Sum32: 806.52; Sum36: 914.84; Sum40: 1031.76; Sum44: 1138.84; Sum48: 1265; Sum52: 1382
9% | 86.91 | Sum4: 47; Sum8: 134.91; Sum12: 247; Sum16: 361; Sum20: 464; Sum24: 583.73; Sum28: 691.91; Sum32: 813.82; Sum36: 928.91; Sum40: 1040.91; Sum44: 1157.82; Sum48: 1276.82; Sum52: 1395.55
10% | 88 | Sum4: 47; Sum8: 155.9; Sum12: 249.9; Sum16: 364; Sum20: 473.8; Sum24: 595; Sum28: 699.9; Sum32: 820; Sum36: 941.7; Sum40: 1050; Sum44: 1170.5; Sum48: 1296.2; Sum52: 1402.9
11% | 89 | Sum4: 49.89; Sum8: 158.89; Sum12: 254.89; Sum16: 367.89; Sum20: 485; Sum24: 603; Sum28: 707; Sum32: 822.89; Sum36: 952.67; Sum40: 1067.89; Sum44: 1178; Sum48: 1304.89; Sum52: 1414.78
12% | 91 | Sum4: 50; Sum8: 161.76; Sum12: 258; Sum16: 371.88; Sum20: 491; Sum24: 607.76; Sum28: 721.88; Sum32: 840.52; Sum36: 955.88; Sum40: 1075.64; Sum44: 1193.88; Sum48: 1315.16; Sum52: 1426
13% | 93.87 | Sum4: 74; Sum8: 163; Sum12: 276.87; Sum16: 379.61; Sum20: 492; Sum24: 609.87; Sum28: 730; Sum32: 848.87; Sum36: 964; Sum40: 1079; Sum44: 1199.74; Sum48: 1319; Sum52: 1432.48
14% | 117 | Sum4: 75; Sum8: 164.86; Sum12: 282; Sum16: 391.3; Sum20: 495; Sum24: 613; Sum28: 737.86; Sum32: 854.86; Sum36: 975; Sum40: 1086.3; Sum44: 1209.72; Sum48: 1323.86; Sum52: 1446.3
15% | 118.85 | Sum4: 76.85; Sum8: 166; Sum12: 283.85; Sum16: 399.7; Sum20: 497.85; Sum24: 620.55; Sum28: 742.85; Sum32: 864.85; Sum36: 980.85; Sum40: 1098.7; Sum44: 1220.55; Sum48: 1333; Sum52: 1454.85
16% | 121.84 | Sum4: 78; Sum8: 167.84; Sum12: 285.84; Sum16: 403; Sum20: 512; Sum24: 629; Sum28: 750.52; Sum32: 872; Sum36: 986; Sum40: 1107.84; Sum44: 1225.84; Sum48: 1335.84; Sum52: 1468.68
17% | 123 | Sum4: 78.83; Sum8: 171; Sum12: 286.83; Sum16: 404.83; Sum20: 516; Sum24: 634.49; Sum28: 754.83; Sum32: 877.49; Sum36: 990; Sum40: 1114; Sum44: 1230; Sum48: 1340.83; Sum52: 1477.83
18% | 124 | Sum4: 79; Sum8: 173.82; Sum12: 289.82; Sum16: 408; Sum20: 519; Sum24: 637; Sum28: 761.28; Sum32: 888.64; Sum36: 1000.38; Sum40: 1121; Sum44: 1237.46; Sum48: 1351.64; Sum52: 1481.82
19% | 126 | Sum4: 80; Sum8: 191.43; Sum12: 291.81; Sum16: 410; Sum20: 524.81; Sum24: 640; Sum28: 764.81; Sum32: 895.24; Sum36: 1007.62; Sum40: 1124; Sum44: 1247.62; Sum48: 1361.43; Sum52: 1488.86
20% | 127 | Sum4: 81.8; Sum8: 193.8; Sum12: 296; Sum16: 414.8; Sum20: 527.8; Sum24: 642; Sum28: 766.8; Sum32: 902.4; Sum36: 1020.4; Sum40: 1133.2; Sum44: 1259.6; Sum48: 1372.2; Sum52: 1500.8
21% | 127.79 | Sum4: 83; Sum8: 195; Sum12: 307.79; Sum16: 424.37; Sum20: 536.79; Sum24: 647; Sum28: 774; Sum32: 907.79; Sum36: 1023.79; Sum40: 1140.58; Sum44: 1266.79; Sum48: 1381.58; Sum52: 1508.79
22% | 130 | Sum4: 83; Sum8: 197.78; Sum12: 311.78; Sum16: 428; Sum20: 546.12; Sum24: 651.78; Sum28: 779.56; Sum32: 911; Sum36: 1027; Sum40: 1151; Sum44: 1274; Sum48: 1389.56; Sum52: 1516.78
23% | 132.77 | Sum4: 84; Sum8: 198.77; Sum12: 313.77; Sum16: 433; Sum20: 550.77; Sum24: 655; Sum28: 789.85; Sum32: 918.77; Sum36: 1033; Sum40: 1155; Sum44: 1285.62; Sum48: 1397.54; Sum52: 1519.77
24% | 134.52 | Sum4: 84; Sum8: 199.76; Sum12: 317; Sum16: 436.76; Sum20: 554.76; Sum24: 664.28; Sum28: 798.76; Sum32: 922; Sum36: 1039.76; Sum40: 1159.76; Sum44: 1292.76; Sum48: 1402.28; Sum52: 1529.76
25% | 150 | Sum4: 85; Sum8: 201.75; Sum12: 318.75; Sum16: 439; Sum20: 560.25; Sum24: 672.5; Sum28: 801.75; Sum32: 925.75; Sum36: 1043.5; Sum40: 1172; Sum44: 1297.75; Sum48: 1416.75; Sum52: 1531.75
26% | 153 | Sum4: 85; Sum8: 202.74; Sum12: 320; Sum16: 440.74; Sum20: 564.74; Sum24: 678.74; Sum28: 808; Sum32: 930.74; Sum36: 1047; Sum40: 1176.48; Sum44: 1305.74; Sum48: 1425.22; Sum52: 1540.22
27% | 155 | Sum4: 85; Sum8: 205.73; Sum12: 321; Sum16: 442; Sum20: 570; Sum24: 680.73; Sum28: 814.46; Sum32: 935.73; Sum36: 1058.92; Sum40: 1180; Sum44: 1314; Sum48: 1432.46; Sum52: 1547
28% | 156 | Sum4: 86; Sum8: 206; Sum12: 323.72; Sum16: 444; Sum20: 574.16; Sum24: 686.72; Sum28: 818.72; Sum32: 941; Sum36: 1067.16; Sum40: 1192.44; Sum44: 1316.44; Sum48: 1436.72; Sum52: 1557.16
29% | 157 | Sum4: 86; Sum8: 208; Sum12: 325; Sum16: 445; Sum20: 581.71; Sum24: 692.71; Sum28: 822.71; Sum32: 944.42; Sum36: 1074.71; Sum40: 1198; Sum44: 1319.71; Sum48: 1443; Sum52: 1565.71
30% | 158 | Sum4: 86; Sum8: 208; Sum12: 328.7; Sum16: 448.7; Sum20: 586.8; Sum24: 694; Sum28: 827; Sum32: 950.7; Sum36: 1078.7; Sum40: 1207; Sum44: 1322.7; Sum48: 1449.7; Sum52: 1572.1
31% | 158 | Sum4: 86; Sum8: 210; Sum12: 332; Sum16: 452.69; Sum20: 589; Sum24: 702.38; Sum28: 831.69; Sum32: 956; Sum36: 1083.38; Sum40: 1208.69; Sum44: 1325.69; Sum48: 1454; Sum52: 1579.38
32% | 159 | Sum4: 87; Sum8: 212.68; Sum12: 337.04; Sum16: 459; Sum20: 591.68; Sum24: 705.68; Sum28: 834; Sum32: 963.36; Sum36: 1087; Sum40: 1213; Sum44: 1330.72; Sum48: 1460; Sum52: 1586.68
33% | 160 | Sum4: 88; Sum8: 215.01; Sum12: 346; Sum16: 463; Sum20: 593.67; Sum24: 710.67; Sum28: 836.67; Sum32: 966.67; Sum36: 1097.68; Sum40: 1216; Sum44: 1336.34; Sum48: 1467.01; Sum52: 1589.67
34% | 160 | Sum4: 88; Sum8: 230; Sum12: 350.66; Sum16: 468; Sum20: 595.66; Sum24: 714; Sum28: 842.66; Sum32: 977.98; Sum36: 1103.66; Sum40: 1220.66; Sum44: 1342.32; Sum48: 1471.66; Sum52: 1595.66
35% | 161.65 | Sum4: 113; Sum8: 233; Sum12: 353; Sum16: 471; Sum20: 597; Sum24: 715.65; Sum28: 847.95; Sum32: 982.65; Sum36: 1111; Sum40: 1230.65; Sum44: 1351.65; Sum48: 1474.65; Sum52: 1599.65
36% | 165 | Sum4: 114; Sum8: 234; Sum12: 354.64; Sum16: 474; Sum20: 600; Sum24: 720; Sum28: 853.92; Sum32: 987.64; Sum36: 1112; Sum40: 1236.28; Sum44: 1355; Sum48: 1485; Sum52: 1610.28
37% | 166 | Sum4: 114; Sum8: 236; Sum12: 358; Sum16: 475; Sum20: 602; Sum24: 723; Sum28: 857; Sum32: 990.63; Sum36: 1119; Sum40: 1239; Sum44: 1363.15; Sum48: 1494.89; Sum52: 1614.63
38% | 166.62 | Sum4: 114.62; Sum8: 238; Sum12: 360; Sum16: 476; Sum20: 605; Sum24: 727; Sum28: 861.48; Sum32: 995; Sum36: 1125.62; Sum40: 1242.62; Sum44: 1371.24; Sum48: 1500; Sum52: 1619.24
39% | 169 | Sum4: 116; Sum8: 238; Sum12: 361.61; Sum16: 477; Sum20: 607; Sum24: 730; Sum28: 864; Sum32: 1000; Sum36: 1132.22; Sum40: 1246; Sum44: 1377.22; Sum48: 1503.61; Sum52: 1625.61
40% | 169 | Sum4: 117; Sum8: 239; Sum12: 363; Sum16: 480; Sum20: 611.6; Sum24: 734; Sum28: 871.6; Sum32: 1005.6; Sum36: 1134.6; Sum40: 1251.6; Sum44: 1381.6; Sum48: 1507; Sum52: 1634
41% | 172.77 | Sum4: 120.18; Sum8: 241; Sum12: 364; Sum16: 483.18; Sum20: 616.59; Sum24: 740.59; Sum28: 875.77; Sum32: 1009.59; Sum36: 1141; Sum40: 1258.18; Sum44: 1386; Sum48: 1511.59; Sum52: 1639
42% | 188.58 | Sum4: 122; Sum8: 242.58; Sum12: 367; Sum16: 491.16; Sum20: 622; Sum24: 748.58; Sum28: 883.58; Sum32: 1016.32; Sum36: 1144.16; Sum40: 1264; Sum44: 1388.58; Sum48: 1519.9; Sum52: 1644.58
43% | 190 | Sum4: 122; Sum8: 244; Sum12: 368; Sum16: 495.57; Sum20: 626.14; Sum24: 752.57; Sum28: 887; Sum32: 1024.14; Sum36: 1150.57; Sum40: 1270.57; Sum44: 1392; Sum48: 1525.57; Sum52: 1649.14
44% | 193 | Sum4: 123; Sum8: 247.12; Sum12: 371.56; Sum16: 500; Sum20: 632; Sum24: 755.56; Sum28: 894.56; Sum32: 1026; Sum36: 1155; Sum40: 1276; Sum44: 1398.56; Sum48: 1531; Sum52: 1654.56
45% | 194 | Sum4: 124; Sum8: 249; Sum12: 375.55; Sum16: 504; Sum20: 635; Sum24: 762.1; Sum28: 903.55; Sum32: 1028; Sum36: 1158.55; Sum40: 1284; Sum44: 1405.55; Sum48: 1536; Sum52: 1658.1
46% | 196 | Sum4: 124; Sum8: 256.16; Sum12: 386.54; Sum16: 506.54; Sum20: 637.08; Sum24: 767; Sum28: 907.08; Sum32: 1030; Sum36: 1161.54; Sum40: 1289.62; Sum44: 1410.16; Sum48: 1542.62; Sum52: 1664.54
47% | 197 | Sum4: 124.53; Sum8: 266; Sum12: 388.53; Sum16: 512; Sum20: 639; Sum24: 772.53; Sum28: 909.53; Sum32: 1034.53; Sum36: 1164.06; Sum40: 1293.53; Sum44: 1414.53; Sum48: 1548.06; Sum52: 1675
48% | 197 | Sum4: 125; Sum8: 269; Sum12: 390; Sum16: 514; Sum20: 642.52; Sum24: 777.52; Sum28: 912.52; Sum32: 1041; Sum36: 1168; Sum40: 1299; Sum44: 1416; Sum48: 1551.52; Sum52: 1685.6
49% | 198 | Sum4: 127; Sum8: 270; Sum12: 392; Sum16: 519; Sum20: 651.02; Sum24: 781; Sum28: 914; Sum32: 1047.51; Sum36: 1171.51; Sum40: 1303; Sum44: 1424.53; Sum48: 1556; Sum52: 1690.51
50% | 199 | Sum4: 127; Sum8: 272; Sum12: 394; Sum16: 521.5; Sum20: 659; Sum24: 786; Sum28: 917; Sum32: 1049; Sum36: 1175; Sum40: 1307.5; Sum44: 1429.5; Sum48: 1563; Sum52: 1694
51% | 200 | Sum4: 145; Sum8: 274; Sum12: 396; Sum16: 525.49; Sum20: 662.49; Sum24: 790.49; Sum28: 920; Sum32: 1051; Sum36: 1180.49; Sum40: 1313.98; Sum44: 1439.98; Sum48: 1567; Sum52: 1700.49
52% | 202 | Sum4: 147.48; Sum8: 275; Sum12: 397; Sum16: 532; Sum20: 666; Sum24: 794; Sum28: 921.96; Sum32: 1056.48; Sum36: 1184.96; Sum40: 1316; Sum44: 1445; Sum48: 1570; Sum52: 1703.48
53% | 204 | Sum4: 150; Sum8: 276; Sum12: 399; Sum16: 536.47; Sum20: 669; Sum24: 796; Sum28: 932.47; Sum32: 1061.47; Sum36: 1188; Sum40: 1323.41; Sum44: 1454.94; Sum48: 1574.41; Sum52: 1706
54% | 204 | Sum4: 152; Sum8: 276; Sum12: 402.46; Sum16: 540; Sum20: 672.46; Sum24: 799; Sum28: 939.84; Sum32: 1064.46; Sum36: 1191; Sum40: 1331; Sum44: 1463.92; Sum48: 1579.92; Sum52: 1710
55% | 205 | Sum4: 152; Sum8: 277; Sum12: 405.9; Sum16: 544.45; Sum20: 674.45; Sum24: 801.45; Sum28: 943.45; Sum32: 1068.45; Sum36: 1197; Sum40: 1338; Sum44: 1470; Sum48: 1591.45; Sum52: 1715
56% | 207 | Sum4: 153; Sum8: 279; Sum12: 416; Sum16: 546; Sum20: 677.88; Sum24: 806; Sum28: 948.44; Sum32: 1071.44; Sum36: 1201.44; Sum40: 1342.88; Sum44: 1473; Sum48: 1603.44; Sum52: 1722.44
57% | 211.87 | Sum4: 153; Sum8: 280; Sum12: 418; Sum16: 547.43; Sum20: 683; Sum24: 811.43; Sum28: 952.43; Sum32: 1073.43; Sum36: 1204; Sum40: 1351; Sum44: 1476.43; Sum48: 1610.43; Sum52: 1731.29
58% | 225 | Sum4: 153; Sum8: 283.42; Sum12: 422; Sum16: 550; Sum20: 686; Sum24: 819.42; Sum28: 955.42; Sum32: 1077.84; Sum36: 1212.84; Sum40: 1355; Sum44: 1485; Sum48: 1618; Sum52: 1739.42
59% | 226 | Sum4: 154.41; Sum8: 285; Sum12: 424.41; Sum16: 552.41; Sum20: 690; Sum24: 821.41; Sum28: 959; Sum32: 1081.82; Sum36: 1217.82; Sum40: 1362.23; Sum44: 1492.41; Sum48: 1622.82; Sum52: 1746.41
60% | 227 | Sum4: 155; Sum8: 288; Sum12: 427; Sum16: 554.4; Sum20: 694; Sum24: 826; Sum28: 960.8; Sum32: 1091.4; Sum36: 1220.4; Sum40: 1368; Sum44: 1495.4; Sum48: 1627.4; Sum52: 1753.4
61% | 228 | Sum4: 155; Sum8: 293.34; Sum12: 429.39; Sum16: 557.39; Sum20: 699; Sum24: 827; Sum28: 965; Sum32: 1096.39; Sum36: 1226.39; Sum40: 1371; Sum44: 1499.39; Sum48: 1633.39; Sum52: 1760.17
62% | 231.38 | Sum4: 155.38; Sum8: 301; Sum12: 431; Sum16: 560.38; Sum20: 705.38; Sum24: 831; Sum28: 969; Sum32: 1100.38; Sum36: 1229.38; Sum40: 1378.38; Sum44: 1504.38; Sum48: 1639.76; Sum52: 1771
63% | 233 | Sum4: 156; Sum8: 305.37; Sum12: 434; Sum16: 564.37; Sum20: 708.37; Sum24: 835.74; Sum28: 974.74; Sum32: 1107; Sum36: 1233; Sum40: 1381.74; Sum44: 1507; Sum48: 1651.37; Sum52: 1775.48
64% | 233 | Sum4: 158; Sum8: 308; Sum12: 435; Sum16: 568.8; Sum20: 711; Sum24: 841.8; Sum28: 980.36; Sum32: 1112.36; Sum36: 1237.36; Sum40: 1385; Sum44: 1518; Sum48: 1657.36; Sum52: 1783
65% | 234 | Sum4: 160; Sum8: 309; Sum12: 437.35; Sum16: 577.05; Sum20: 713; Sum24: 848.35; Sum28: 982.35; Sum32: 1115.7; Sum36: 1241.35; Sum40: 1388.35; Sum44: 1528.7; Sum48: 1662.4; Sum52: 1792
66% | 235 | Sum4: 160; Sum8: 310.34; Sum12: 440.68; Sum16: 584; Sum20: 715; Sum24: 854.68; Sum28: 990.02; Sum32: 1119.34; Sum36: 1244; Sum40: 1398; Sum44: 1536; Sum48: 1668.68; Sum52: 1797.68
67% | 235 | Sum4: 161; Sum8: 313; Sum12: 444.33; Sum16: 588; Sum20: 718; Sum24: 857; Sum28: 994.33; Sum32: 1126; Sum36: 1249.33; Sum40: 1404; Sum44: 1539.33; Sum48: 1671; Sum52: 1805.33
68% | 236 | Sum4: 161; Sum8: 315; Sum12: 451.64; Sum16: 589.32; Sum20: 727; Sum24: 859.32; Sum28: 999.96; Sum32: 1132.92; Sum36: 1254.32; Sum40: 1407; Sum44: 1547; Sum48: 1680.32; Sum52: 1810.96
69% | 236 | Sum4: 163; Sum8: 316; Sum12: 459.31; Sum16: 591; Sum20: 732.31; Sum24: 862; Sum28: 1004; Sum32: 1140; Sum36: 1263; Sum40: 1413.31; Sum44: 1551; Sum48: 1685.31; Sum52: 1820.31
70% | 238 | Sum4: 163; Sum8: 316.3; Sum12: 461; Sum16: 594.6; Sum20: 738.3; Sum24: 865.3; Sum28: 1012.3; Sum32: 1144.6; Sum36: 1265.3; Sum40: 1419.6; Sum44: 1555.9; Sum48: 1691.6; Sum52: 1826.3
71% | 241.29 | Sum4: 163; Sum8: 319; Sum12: 463; Sum16: 600.29; Sum20: 740.58; Sum24: 869; Sum28: 1018.29; Sum32: 1148; Sum36: 1270.58; Sum40: 1422.87; Sum44: 1564.58; Sum48: 1701.29; Sum52: 1831
72% | 244 | Sum4: 164; Sum8: 321.28; Sum12: 468; Sum16: 605; Sum20: 743.28; Sum24: 872.28; Sum28: 1025.4; Sum32: 1151.56; Sum36: 1284.28; Sum40: 1428.28; Sum44: 1578; Sum48: 1703.28; Sum52: 1846
73% | 255 | Sum4: 164; Sum8: 330.16; Sum12: 469; Sum16: 609.08; Sum20: 747; Sum24: 874.27; Sum28: 1032; Sum32: 1158.27; Sum36: 1293; Sum40: 1432.27; Sum44: 1581.27; Sum48: 1709; Sum52: 1852.62
74% | 263 | Sum4: 183; Sum8: 337; Sum12: 471.26; Sum16: 615.26; Sum20: 750.26; Sum24: 886.26; Sum28: 1034.26; Sum32: 1160.26; Sum36: 1301; Sum40: 1440.3; Sum44: 1586.26; Sum48: 1717.26; Sum52: 1863.26
75% | 264 | Sum4: 183.25; Sum8: 338.25; Sum12: 474.25; Sum16: 619; Sum20: 757.25; Sum24: 888; Sum28: 1042.25; Sum32: 1164; Sum36: 1306.25; Sum40: 1451.5; Sum44: 1590; Sum48: 1727.5; Sum52: 1873
76% | 265 | Sum4: 184; Sum8: 341.48; Sum12: 479; Sum16: 624; Sum20: 760; Sum24: 892.48; Sum28: 1047; Sum32: 1167.24; Sum36: 1312; Sum40: 1461; Sum44: 1593.48; Sum48: 1731.24; Sum52: 1877.48
77% | 269 | Sum4: 186; Sum8: 345.23; Sum12: 482; Sum16: 626.23; Sum20: 762.46; Sum24: 895; Sum28: 1050; Sum32: 1179.23; Sum36: 1320.23; Sum40: 1467.46; Sum44: 1601.46; Sum48: 1739.15; Sum52: 1885.15
78% | 271 | Sum4: 191; Sum8: 346.22; Sum12: 492.22; Sum16: 634.22; Sum20: 767; Sum24: 899.44; Sum28: 1053; Sum32: 1185.44; Sum36: 1330.44; Sum40: 1473.22; Sum44: 1608.22; Sum48: 1747.44; Sum52: 1897.88
79% | 272 | Sum4: 191; Sum8: 347; Sum12: 498.21; Sum16: 640.42; Sum20: 772.21; Sum24: 904.42; Sum28: 1055; Sum32: 1190; Sum36: 1340.42; Sum40: 1486.21; Sum44: 1614.21; Sum48: 1754.21; Sum52: 1903.21
80% | 274 | Sum4: 192; Sum8: 350.2; Sum12: 500.4; Sum16: 645.2; Sum20: 775; Sum24: 912.2; Sum28: 1059.4; Sum32: 1197.2; Sum36: 1348.4; Sum40: 1495; Sum44: 1619.2; Sum48: 1761.2; Sum52: 1915
81% | 275 | Sum4: 194; Sum8: 354; Sum12: 505; Sum16: 654.19; Sum20: 777.38; Sum24: 921.19; Sum28: 1062.19; Sum32: 1204.57; Sum36: 1359; Sum40: 1500.57; Sum44: 1631; Sum48: 1772.57; Sum52: 1921.57
82% | 279.18 | Sum4: 194; Sum8: 355.18; Sum12: 509; Sum16: 659; Sum20: 786; Sum24: 926.18; Sum28: 1067.18; Sum32: 1211.54; Sum36: 1366.18; Sum40: 1510.36; Sum44: 1636.08; Sum48: 1787; Sum52: 1930.36
83% | 283.34 | Sum4: 194; Sum8: 357.17; Sum12: 510.17; Sum16: 660; Sum20: 794; Sum24: 930.17; Sum28: 1074.17; Sum32: 1221.51; Sum36: 1381; Sum40: 1519; Sum44: 1646.17; Sum48: 1797.19; Sum52: 1947
84% | 295.16 | Sum4: 199; Sum8: 360; Sum12: 517.32; Sum16: 662; Sum20: 801.32; Sum24: 935.64; Sum28: 1081.32; Sum32: 1235; Sum36: 1387.32; Sum40: 1528.16; Sum44: 1664.48; Sum48: 1810.32; Sum52: 1955.16
85% | 302 | Sum4: 199; Sum8: 370.6; Sum12: 524.6; Sum16: 665.15; Sum20: 808.15; Sum24: 942; Sum28: 1092.15; Sum32: 1240.6; Sum36: 1394.6; Sum40: 1542; Sum44: 1672; Sum48: 1819.45; Sum52: 1974.15
86% | 305 | Sum4: 202; Sum8: 378.28; Sum12: 530.14; Sum16: 671; Sum20: 811.14; Sum24: 948; Sum28: 1099.42; Sum32: 1246.84; Sum36: 1407; Sum40: 1545.14; Sum44: 1674.7; Sum48: 1830.12; Sum52: 1979.28
87% | 305 | Sum4: 214; Sum8: 382.13; Sum12: 535.13; Sum16: 678.26; Sum20: 816.26; Sum24: 958; Sum28: 1112.3; Sum32: 1262.13; Sum36: 1417.39; Sum40: 1556.26; Sum44: 1703.78; Sum48: 1845.39; Sum52: 1987.39
88% | 306.24 | Sum4: 222; Sum8: 385; Sum12: 540.12; Sum16: 689.12; Sum20: 824.12; Sum24: 965.12; Sum28: 1123; Sum32: 1265.24; Sum36: 1428.12; Sum40: 1577.48; Sum44: 1712.48; Sum48: 1856.36; Sum52: 1995.24
89% | 311.11 | Sum4: 225; Sum8: 386; Sum12: 542; Sum16: 691.11; Sum20: 827; Sum24: 970.22; Sum28: 1131.22; Sum32: 1272.33; Sum36: 1435.22; Sum40: 1590.44; Sum44: 1728.33; Sum48: 1869.11; Sum52: 2003.55
90% | 313 | Sum4: 230; Sum8: 386; Sum12: 545.1; Sum16: 695.1; Sum20: 837.3; Sum24: 981; Sum28: 1144.3; Sum32: 1287.1; Sum36: 1439; Sum40: 1602; Sum44: 1740; Sum48: 1890.8; Sum52: 2023.5
91% | 313.45 | Sum4: 230; Sum8: 391; Sum12: 551.09; Sum16: 699.18; Sum20: 845.27; Sum24: 1003.09; Sum28: 1156.09; Sum32: 1304; Sum36: 1452; Sum40: 1610.27; Sum44: 1753.62; Sum48: 1903.09; Sum52: 2044.09
92% | 333 | Sum4: 231; Sum8: 399; Sum12: 562.08; Sum16: 708; Sum20: 851; Sum24: 1010; Sum28: 1161.08; Sum32: 1311.32; Sum36: 1457.24; Sum40: 1626; Sum44: 1779.24; Sum48: 1912.08; Sum52: 2050.08
93% | 341 | Sum4: 231; Sum8: 407.42; Sum12: 570; Sum16: 717.07; Sum20: 859.42; Sum24: 1030.14; Sum28: 1178.84; Sum32: 1325; Sum36: 1467.14; Sum40: 1643.35; Sum44: 1804.07; Sum48: 1934.07; Sum52: 2056.28
94% | 344 | Sum4: 233; Sum8: 416.06; Sum12: 577.12; Sum16: 730.06; Sum20: 886.12; Sum24: 1043.36; Sum28: 1195.12; Sum32: 1334.54; Sum36: 1478.06; Sum40: 1658.18; Sum44: 1827.36; Sum48: 1959.24; Sum52: 2080.12
95% | 349 | Sum4: 238; Sum8: 427.1; Sum12: 583.05; Sum16: 740; Sum20: 927.1; Sum24: 1067.15; Sum28: 1213.05; Sum32: 1348.1; Sum36: 1503; Sum40: 1671.3; Sum44: 1842.45; Sum48: 1971; Sum52: 2096.5
96% | 350 | Sum4: 241.48; Sum8: 448.16; Sum12: 598.08; Sum16: 744.64; Sum20: 952.04; Sum24: 1077.2; Sum28: 1227.44; Sum32: 1353.12; Sum36: 1523.4; Sum40: 1714.16; Sum44: 1866.08; Sum48: 2002.84; Sum52: 2131.36
97% | 357.21 | Sum4: 261; Sum8: 455; Sum12: 614.09; Sum16: 779.09; Sum20: 959.03; Sum24: 1102.12; Sum28: 1253.06; Sum32: 1399.39; Sum36: 1553.14; Sum40: 1728.3; Sum44: 1876.03; Sum48: 2036.03; Sum52: 2148.33
98% | 375 | Sum4: 269; Sum8: 484.04; Sum12: 624.08; Sum16: 806.18; Sum20: 974.08; Sum24: 1113.5; Sum28: 1299.2; Sum32: 1471.22; Sum36: 1622.24; Sum40: 1762.08; Sum44: 1906.1; Sum48: 2048.04; Sum52: 2204.46
99% | 381.07 | Sum4: 292; Sum8: 491.08; Sum12: 642.03; Sum16: 836.02; Sum20: 1022.01; Sum24: 1205.1; Sum28: 1331.06; Sum32: 1529.23; Sum36: 1702.06; Sum40: 1808.05; Sum44: 1960.12; Sum48: 2158.19; Sum52: 2347.03
100% | 427 | Sum4: 308; Sum8: 508; Sum12: 739; Sum16: 931; Sum20: 1084; Sum24: 1284; Sum28: 1519; Sum32: 1674; Sum36: 1865; Sum40: 2025; Sum44: 2188; Sum48: 2351; Sum52: 2485